## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
a740c83c-6200-4131-b5e5-a040742c9e89 | checklist | ITC&ITP - No.4 Rigid Board - Rev.C |  | Rigid Board
f22dc095-c35b-4974-9d86-2864f19fcb04 | section | ITC&ITP - No.4 Rigid Board - Rev.C
e58b433d-e9b8-4062-986c-c59c7c464bcb | checkpoint | Address Safety
361fd183-64de-5673-b934-7050b6b026d8 | note | Reference Documents - SWMS
2db0fd4b-7b24-5c66-b651-79f814203366 | note | Acceptacne Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
abdf00be-5e51-571b-a3b4-044da8ba1510 | note | Frequency - Each location
8f509a8f-842b-50f2-b25f-74b4066109fe | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
381d9e2e-0f49-5ede-b38c-334b47d8230f | note | Inspection By : Subcontractor - S
91e96409-b44b-5417-8770-70bf911f66ee | note | Inspection By : Georgiou - S
49e8fb69-4328-4d13-ae24-38aacdbcac3c | checkpoint | Set out Rigid Board
16e8021c-9c86-5c3d-8fa5-dde840a283ff | note | Reference Documents - Architect Drawings
2780f503-8483-5b5b-92c9-a382e0fda3d6 | note | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd
84ed84ce-6829-57b7-9370-b772f5f889e2 | note | Frequency - Each location
e8293046-8d00-579f-82f3-b9fac5ffcba6 | note | Verification Records/Comments - Visual Checklist
62447df2-9fee-5bcd-9dc2-54147fb6016f | note | Inspection By : Subcontractor - S
328ae04e-5ec2-5e23-a43b-4a1a12370fa6 | note | Inspection By : Georgiou - S
ce5809eb-d10b-4fd1-b11e-662fd82041dd | checkpoint | Install Rigid Board
485baacb-7730-50c7-b1b3-5c652858d475 | note | Reference Documents - Architect Drawings
51b9d5a6-17c8-5923-a0af-8f4a881695e2 | note | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd, Kingspan Kooltherm K10 Installation guide 2021
45355b64-9973-5b93-9098-d1fb01307ce6 | note | Frequency - Each location
613c95d1-880e-5ef3-a2ca-3de0f299239d | note | Verification Records/Comments - Visual Checklist
cda0a805-ddb0-5bb7-8c03-f0a55d3524d2 | note | Inspection By : Subcontractor - S
ad0679e6-49be-579f-99e6-5742e516f9eb | note | Inspection By : Georgiou - S
ac8cd654-1c78-4bf3-912e-5f0f5fadacc0 | checkpoint | Tape and Seal
8eeff3c9-5338-54ad-ab36-66fa1d1417f0 | note | Reference Documents - N/A
cb745233-e3e3-5ce1-b4a7-09d6f140e910 | note | Acceptacne Criteria - Kingspan Kooltherm K10 Installation guide 2021
fae55304-e508-55b0-b645-a312109231d9 | note | Frequency - Each location
9215eda7-562f-59c5-a44f-3065637d2d71 | note | Verification Records/Comments - Visual Checklist
5f8153f7-4c83-5e43-8837-a94a0a6555c9 | note | Inspection By : Subcontractor - S
9349a9e2-a36a-5497-b134-4ebebbfeb5d0 | note | Inspection By : Georgiou - S
63c749b6-5c64-447f-8076-635035a51d94 | checkpoint | Clean up
d7372ccc-677e-5cd9-8d9b-1228b0f0ffd9 | note | Reference Documents - N/A
fe81e4af-29a7-522b-b381-dc251c0766f0 | note | Acceptacne Criteria - Waste all cleaned. Tools and materials placed well
a0f9d936-71a3-5f6a-bb86-8f7336b1a44d | note | Frequency - Each location
66caf55d-53b6-5483-ae88-08a795faed1d | note | Verification Records/Comments - Visual Checklist
8068bee2-cefb-5848-8dea-64c51d6783ae | note | Inspection By : Subcontractor
1f9667e4-18aa-5f86-8644-20ecbd4ea6a0 | note | Inspection By : Georgiou - R
9ee48150-b917-4f8e-8735-58f2ecfa37af | signoff | Verification Statement