## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
01a8be5c-bf75-58cc-81b7-62408aea5d58 | checklist | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard | itp | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard
94a5765f-4006-5293-a410-4035edbac092 | section | Speedpanel & Pre-hang Fire Rated Plasterboard
5d6edac6-a6b5-529d-95ba-97a9b7802014 | checkpoint | 1 - Set out Speedpanel walls
83a10740-691c-58b7-89ad-ef7253111c63 | note | Reference Documents - HB-AR-00 HB-AR-03 Series
33cdeba8-7f37-50d4-8d1f-0437a426653d | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Speedpanel installation guide revision 1.
d4f12c62-0495-577e-ae4e-c3fd86275d04 | note | Frequency - Each location
f5638591-d97d-57a8-934a-432e7274b169 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
abe79fc9-1303-5652-8c2b-c874ffeedde9 | note | Inspection By: Subcontractor - S
49cb33bb-94ac-5485-8fb4-3a048d2b2598 | note | Inspection By: Built - S
92341123-a47b-5680-b044-392b5f372fee | checkpoint | 2 - Install Speedpanel
bed0332b-005f-56b4-afbe-da9fb938086b | note | Reference Documents - HB-AR-03 HB-AR-08 Series
9c5298fa-546f-5eac-b565-5c74e470b3b1 | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Speedpanel installation guide revision 1.
899c479b-bdc1-527b-9e4e-199c9e39c242 | note | Frequency - Each location
050c0a11-b036-5815-ba04-19916447bf38 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
3f10a54b-250c-56fb-a965-bfd78a8a62af | note | Inspection By: Subcontractor - S
9d2d4734-16a6-5498-90b2-c67112fc7f31 | note | Inspection By: Built - S
125598e5-6239-5c62-b950-c008f677a8a7 | checkpoint | 3 - Caulking
1b5fe35d-f63b-5823-a0c8-99057e4bd7b6 | note | Acceptance Criteria - Speedpanel installation guide revision 1
b7c2ddc9-3bc2-522e-b14b-321430314a69 | note | Frequency - Each location
423fd93b-104e-5a15-a95d-d76656cf1ee5 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
4faf8be2-1d5c-5bfe-94a6-da1c4c473f10 | note | Inspection By: Subcontractor - S
36f33eb0-aae7-56d0-a9e8-b6658ab35838 | note | Inspection By: Built - S
ed37a5aa-f56a-58e1-bfd9-90f24af2a258 | checkpoint | 4 - Clean up
8bf3f2b4-c8e6-5aaa-b820-1ff53bf2224e | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
ced4cf64-28ad-57cb-ae61-176ea554c0bd | note | Frequency - Each location
5f15b97e-d922-52fd-97dd-14ba3b4a9541 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
72e84dd4-9d43-540d-bdc9-ef6db7fe354c | note | Inspection By: Built - R
548fda4b-aac1-5656-a3e5-c814a693c8a2 | checkpoint | 5 - Pre-hang fire rated plasterboard
c68979fe-8184-59bc-ba69-f1d00e94686a | note | Reference Documents - Architect drawings
6687ab59-ffc9-5630-b790-b1907de4095a | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solution Rev. Mar.2024.
d3833a16-c490-5771-9024-198ed0d2a00a | note | Frequency - Each location
7d69b401-afd3-5082-a00a-bf00bfdc6e70 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
33f618bc-4ad3-5e48-ba1c-c3610ad2a288 | note | Inspection By: Subcontractor - S
0dac0344-3b85-5d8d-b724-d767a3fb2a5f | note | Inspection By: Built - S
186e3dcb-6324-52ad-9532-ed253ddbe58a | checkpoint | 6 - Taping and stopping
442784d3-8f65-55a7-8249-2884c645e931 | note | Reference Documents - Architect drawings
eff34cfd-9a54-5650-8941-bce44a6e89d1 | note | Acceptance Criteria - GTEK Ceiling & Wall Solution Rev. Mar.2024
eacd9361-436e-5f6d-b13b-f9cc13b8249e | note | Frequency - Each location
0c399dfa-07b4-56d2-9b85-f07a4a96c007 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
75eaeb73-0a3f-5ad1-ad23-bc83cf9ffb71 | note | Inspection By: Subcontractor - S
fd44e3c9-6275-53f7-ad31-b1328a58e277 | note | Inspection By: Built - S
479168e8-1cdc-5ff3-a5ab-79382d4983a8 | checkpoint | 7 - Clean up
72b6703f-0959-570b-8f83-a7111262d804 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
f28aab86-7dec-5bfe-bdaa-a10af4f27990 | note | Frequency - Each location
872c3d3c-b97d-59e7-9207-434e54354c00 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
aa3e9bf5-03ab-5ff2-bc95-83b6588880d9 | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
5ba316df-6e50-5a31-a57e-7b32e7669da3 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
2064d676-67c4-56c1-afe3-f225c838f3bf | date | Date of Inspection:
f32eac56-4667-5344-a021-3afbeeb0b487 | textbox | Carried out by:
611e74c7-e21f-5156-a0b8-e767b1e7f69d | note | Attachments
43970033-264d-56ed-b25d-209341ccf00f | tickbox | Checklists
48ea4658-9f4c-596f-88d3-406547974a23 | tickbox | Photos
e83eeb88-c9cb-5975-8adf-5304e3ff6861 | tickbox | Dockets
628ee4f3-8c25-5058-9e91-d2144f9ed38f | tickbox | Sample Material
f48b78bf-26cb-5174-9413-ad88422ef530 | tickbox | Drawings
5c27456a-9e70-5c60-869e-26796e1afe46 | tickbox | Calibration Certificates
07019b9e-2634-5313-8cce-6da6d770db37 | tickbox | Test Results / Certificate
5b013dd7-526f-500a-90e9-c7ef938947ca | tickbox | Inspection reports
f3d90842-2e71-5d6c-a21d-ae46aca4f320 | tickbox | Others:
4ba5bf4a-5324-5043-8adf-dce51ae45811 | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed:
aed0609a-7cce-5645-bda9-7912c8d37b5c | checklist | ITC&ITP No.2 - Frame All Walls | itp | ITC&ITP No.2 - Frame All Walls
da50e72b-ebec-58a3-8840-032d08e392a7 | section | Frame All Walls
ced6d4ed-abcd-5c63-8eea-e95b6c351216 | checkpoint | 1 - Set out walls
d6cf43cd-93c6-583f-9c03-2b39db506226 | note | Reference Documents - HB-AR-00 HB-AR-03 HB-AR-06 Series
76879511-95d2-5b68-84ae-d92010b59610 | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
a33f0e0c-26ed-5859-b4d8-d94429fe5278 | textbox | Dwg No:
6b777cd6-dbcb-5ede-8fcd-b617ffac676b | textbox | Rev:
0183db6f-e16c-57b6-be9e-df6537a89f01 | note | Frequency - Each unit
00dcb8e3-c461-54d9-8b46-57f066d00772 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
42c9c532-038b-55f4-9edb-813f5a1f057d | note | Inspection By: Subcontractor - S
96030bbb-3720-5b2c-ada4-818970074628 | note | Inspection By: Built - S
733bf92e-7395-56d4-bb75-1eb009064048 | checkpoint | 2 - Furring channel to walls
9c3859d6-f5b8-5be8-8d12-02ed4b5ae694 | note | Reference Documents - HB-AR-00 HB-AR-03 Series
53d14c92-6033-514c-8b62-cf148d9230dd | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
1afd5ef6-7da8-5f8c-9459-969b050f2100 | note | Frequency - Each unit
6e144dd5-ed1d-5dde-bc62-2072db450298 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
de763718-1a86-5f45-b99e-f3a759e26483 | note | Inspection By: Subcontractor - S
789effc9-759c-50ee-ad9c-c96fb50069a4 | note | Inspection By: Built - S
0a04ef26-1c46-55f1-ae3d-05d1efc01e62 | checkpoint | 3 - Metal stud wall frame
61367dca-4d6d-5cbf-a10f-a61108e6b200 | note | Reference Documents - HB-AR-00 HB-AR-03 Series
33567ee0-0599-500c-bd6d-a3786b4e430c | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
0920d542-a9b5-562b-9c31-b020b9c3ba64 | note | Frequency - Each unit
cd51ca80-97d3-58eb-811b-b275406973be | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
6e149b48-80a7-50a0-af9c-44aa893ca366 | note | Inspection By: Subcontractor - S
e3d95e84-91ff-5c87-8557-8fb64f425fce | note | Inspection By: Built - S
d6cbf426-ea9c-5afd-8fa5-f0e44c74ca59 | checkpoint | 4 - Install and fire rate PMDF
94d3dd82-60d6-5b63-ae6d-2bb0e6511df2 | note | Reference Documents - Architect drawings
e2ad2575-fe1c-55f8-8dce-c191c7f4634c | note | Acceptance Criteria - Architect GA plan & door schedule approved by Built. PMDF installation guide provided by builder
6dc65612-5dff-5115-949e-7eb6631adc21 | note | Frequency - Each location
4ca24154-17de-5ece-ba4e-be03a40dd80e | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
bd9a7127-565b-564b-8f11-138cbb5b00cd | note | Inspection By: Subcontractor - S
51814262-ef67-5ead-9a95-c4d2b6c45f36 | note | Inspection By: Built - S
51f9bc64-91a5-5a88-8e4a-27e8dcf92c37 | checkpoint | 5 - Noggins
d1088b69-fcc6-5fae-9a27-686343c49cd2 | note | Acceptance Criteria - As per scope of work. Studco Wall design & installation manual Volume 3.2
8c9ffe87-d49b-5231-9d7f-2e6e8a694e48 | note | Frequency - Each location
1eae2140-9670-5afe-8cb7-a33c3417c286 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
eae091f0-c4e0-5288-9edc-8640b0cb0d35 | note | Inspection By: Subcontractor - S
ec599d2a-8f70-5d6a-ae83-ba6aa3dd79bd | note | Inspection By: Built - S
683b8024-3e70-532e-8eda-92d0bfa347d3 | checkpoint | 6 - Check no screws in deflection head
3c14d87b-6db4-5d76-8f0a-949be37e9152 | note | Acceptance Criteria - No screws in deflection head
b1675e61-c343-5e7d-b17b-713b676f5638 | note | Frequency - Each location
715e7b49-6cd6-5916-86c6-e0acfb3653c6 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
e5c6ef65-3c05-5735-911f-83fb26c11ae4 | note | Inspection By: Subcontractor - S
c4842dc5-a4a5-54ea-b98a-739574b3b786 | note | Inspection By: Built - S
479168e8-1cdc-5ff3-a5ab-79382d4983a8 | checkpoint | 7 - Clean up
dd60c6ff-5e42-53cf-ac8e-b476e3a71396 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
0ca0b46f-b904-552e-8284-d9ab11beb6e2 | note | Frequency - Each location
5b82f947-204e-593f-ba17-c7f8c53bf6f9 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
3e25ea28-db3a-58ff-a944-36f99a01b194 | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
ba682484-71cf-5f48-81da-b5d7351f8a66 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
db238d54-1fd0-5d25-83a7-f262ccebf0ce | date | Date of Inspection:
1a8c4ce9-c187-5135-aba5-53deecc21aa1 | textbox | Carried out by:
5a085981-fe85-5613-a93b-2bb895be128b | note | Attachments
8b2c99cc-f96f-58bf-a25e-6599b2008aff | tickbox | Checklists
7ae49812-ee42-5a1b-9794-9c273f9b1017 | tickbox | Photos
76686ee6-1997-5095-af94-66c35cb191fd | tickbox | Dockets
1b40c89b-1277-592f-95dd-d2d9f4487ce0 | tickbox | Sample Material
8c11dd84-026e-518b-ad10-8ff44d520102 | tickbox | Drawings
8a5172ca-0310-5ed6-92d4-91e0067a2984 | tickbox | Calibration Certificates
8359929e-bb77-50b2-beba-027200c3b679 | tickbox | Test Results / Certificate
9f3f264a-0825-5b09-b2ba-0f9e15485674 | tickbox | Inspection reports
41633530-f8f9-54f4-bbbc-5eaf1ff0f381 | tickbox | Others:
95815f3b-6518-5135-9b0a-a4476dbe862b | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed:
4d0d08f1-1dd8-567e-9d1a-a47bfac0e337 | checklist | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling | itp | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling
91a8008e-6eaa-508b-99e0-3c4514ce0135 | section | Sheet All Walls & Frame Ceiling
331a5848-8aad-5526-a91a-d2421b4baee1 | checkpoint | 1 - Install insulation
b7e67a29-5cce-5a0b-b295-b80abcb19da3 | note | Reference Documents - Architect drawings
d0e3f739-59fc-5093-bb38-2a0e1e6c671d | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. Ecowool insulation installation guide.
f35b6eae-2979-5413-abb7-848f38f4278d | note | Frequency - Each location
2ab06c81-5b5d-55e5-9604-ef7e4e55f427 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
e5ebcf58-65e6-5fcd-8033-7c7600aeb595 | note | Inspection By: Subcontractor - S
89f1cf16-24e2-56c0-ac35-9ffe3d0fe312 | note | Inspection By: Built - S
6de133d0-3317-552f-92d7-9f0df119eb85 | checkpoint | 2 - Sheet fire walls
d70d7ec7-d3b8-5a8e-87a6-64041f8f7c95 | note | Reference Documents - Architect drawings
d646b90a-8ab1-595e-a410-73361e4f33b2 | note | Acceptance Criteria - Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar 2024.
1fdbdfbf-c414-5106-bee6-0e24ccb5ae9f | note | Frequency - Each unit
74a4ebb0-5386-509a-bf5f-dce208b289dd | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
dbe95680-71d2-55bb-8aa0-bbf69b01aa71 | note | Inspection By: Subcontractor - S
a04988ed-caeb-53b6-a8bb-73ea9a9ba3b5 | note | Inspection By: Built - HP
cc3034cf-34c1-5a65-82e2-6f93ca36a7a4 | signoff | HOLD POINT
81ffd331-a474-51b4-ab17-9b5d20ed45c6 | checkpoint | 3 - Caulking fire walls
47103dfc-338d-5884-85d8-c77d08a62a64 | note | Reference Documents - Architect drawings
ff9731c8-6f1d-5082-80c9-68f7b35fcd7d | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar 2024
828bcff3-514b-551b-a275-a34cfb40b1da | note | Frequency - Each unit
9ac66e5d-96eb-5fb8-a40a-870aeb286911 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
873a491f-8edc-55e3-ab7c-3ab48f1baa90 | note | Inspection By: Subcontractor - S
5472de67-6a9c-5e1f-8362-5723ebfb62ff | note | Inspection By: Built - S
a6efece3-0063-5a39-8278-469682b89c9b | checkpoint | 4 - Sheet remaining walls
992330bd-04d5-5275-a2cd-49fd183c8e1a | note | Reference Documents - Architect drawings
c8263a1a-4f2a-5742-843d-b0275cfb0c0d | note | Acceptance Criteria - Light Weight Wall Plan approved by Built.
7132b987-5da8-56e2-8f72-681747324a08 | note | ○ GTEK Ceiling & Wall Solutions Rev. Mar 2024
f429771d-1379-5573-b31b-8cb6a517bfe5 | note | ○ Class 2-9 Building.
2014e6d2-2404-55f4-ae60-6b5ef73ed2e6 | note | ○ Ecowool insulation installation guide
7868ed49-cbb6-5c1f-9916-f7ff0695bc36 | note | Frequency - Each unit
72505f86-149c-55bc-ac61-5ddb30b6bc6a | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
b391f372-7d0a-5b68-bcc1-7f1cd3c688e0 | note | Inspection By: Subcontractor - S
d2f6fa03-95b8-5b0b-97db-abd4d06353e9 | note | Inspection By: Built - HP
32e51ed0-401c-58ea-baee-22d7678de5c2 | signoff | HOLD POINT
02cd470a-ba37-5b59-a239-263de89c08df | checkpoint | 5 - Frame ceiling
6b546a72-659d-547a-82ae-8a3fcdfbd7b0 | note | Reference Documents - Architect drawings
c0be881a-4969-5001-8537-79a089fd010c | note | Acceptance Criteria - Architect RCP drawings approved by Built. Studco Wall design & installation manual Volume 3.2.
19a01aa2-18c3-5c65-a077-d9f71541113e | note | Frequency - Each unit
7ca09f77-2ab8-5253-ba52-3faf5543bc2a | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
ad316489-564e-59e4-a94c-2c5d851b8e17 | note | Inspection By: Subcontractor - S
d93e656d-73b9-52f1-8e70-e7de673df00c | note | Inspection By: Built - S
d453312d-a437-5187-b48a-8e5698af2c88 | checkpoint | 6 - Trim out access hatches
72cbb9ed-2b1a-507b-aef2-3ff0d9569379 | note | Reference Documents - Architect drawings
107fd9a3-1db9-5569-9ec1-0d748937fc3d | note | Acceptance Criteria - Architect RCP drawings approved by Built.
e7062c69-1e2a-5299-8198-4e4adee2d298 | note | Frequency - Each location
5cdace5f-bfe4-5f0d-92cd-23b213946639 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
37f14f8c-8684-5e6c-bc70-6945c256204f | note | Inspection By: Subcontractor - S
7cf15b86-7140-5695-bce5-91655240ad60 | note | Inspection By: Built - S
479168e8-1cdc-5ff3-a5ab-79382d4983a8 | checkpoint | 7 - Clean up
b9f7cfec-fba5-5834-a1d1-c44a9a92388d | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
8926d212-b3b5-50c8-808b-accee2f6b96f | note | Frequency - Each location
f2ad3443-fc37-509a-a717-740bafd81408 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
fc2fc4c7-f63b-50e7-b292-95a154f8be65 | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
5fd99975-f3cb-5e37-9ace-018accd0e2aa | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
7184dba0-1c79-5028-a3ce-09df728ff42c | date | Date of Inspection:
1e626907-60f1-5a53-9987-29d8436e6096 | textbox | Carried out by:
a1e79f3e-81be-5fb5-a3ac-c512fc32da6a | note | Attachments
a53e0f32-0db3-5dba-862e-78f63ec41a89 | tickbox | Checklists
e0e0dd93-d559-578c-b710-80f28acd42b9 | tickbox | Photos
0e0ef371-20aa-5a5a-9258-26cf48bfe123 | tickbox | Dockets
72eb3bb8-7317-5238-badd-f65c7adc03d8 | tickbox | Sample Material
c6d6d577-99c7-5a4b-9385-6d540e623a10 | tickbox | Drawings
a9844cc5-8e28-5f7e-aa70-de56d16dd761 | tickbox | Calibration Certificates
15bdad7f-a9ef-52dd-9617-fe499bd1fa43 | tickbox | Test Results / Certificate
e2893924-c9cb-5eca-a789-bdf745c2c1fa | tickbox | Inspection reports
0cc11344-7810-5200-9306-6f84acc17332 | tickbox | Others:
1cc16141-b141-5ad0-8c84-e26137761f64 | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed:
75785de6-5235-5784-bc48-8094a4559180 | checklist | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings | itp | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings
93d2ed66-1848-5f5a-b0bb-c9182e7a7a3b | section | Hang Ceilings and Stop, Sand Walls & Ceilings
01d6d831-45a7-5fef-af5f-60e6a6993447 | checkpoint | 1 - Insulation to ceilings
3a675c13-9f4e-5ccd-8d34-02c1f373b887 | note | Reference Documents - Architect drawings
328db4ca-4c61-5bd2-9f30-f63d4c9cd83b | note | Acceptance Criteria - Architect RCP drawings approved by Built. Ecowool insulation installation guide.
08d9f5b2-1bd1-5690-8f46-acc5522d8d5f | note | Frequency - Each unit
1ee6ba69-edc3-55d7-9c0b-fcaf28247c42 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
506b3e03-83c1-55d7-b0f8-23a25db8f7ef | note | Inspection By: Subcontractor - S
e6a04a2b-e1e9-5201-af9c-dd75d2059d96 | note | Inspection By: Built - S
027874c8-e600-5eec-b32e-c5d6c0002425 | checkpoint | 2 - Sheets to ceiling
f223d9da-a015-535f-a74d-06b7bbebc0fb | note | Reference Documents - Architect drawings
e6ccf6f4-aabc-53f7-89c6-02137672d29b | note | Acceptance Criteria - Architect RCP drawings approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar.2024.
9e788404-8f7d-51ee-a54f-7a9d52eefff0 | note | Frequency - Each unit
a9dc33b0-6338-5c62-904d-72c7461ec719 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
894b5266-98d7-5c22-822a-9160b2aac123 | note | Inspection By: Subcontractor - S
83fbaee1-3143-57e5-b761-c426468cf1a5 | note | Inspection By: Built - HP
bbeb95ab-66bd-5179-8428-e278c84af10f | signoff | HOLD POINT
61a3682a-6e39-5452-800f-9b5736377ae7 | checkpoint | 3 - Stopping to walls & ceilings
2f7cf2b7-a198-5acb-8dc5-1d87faa36462 | note | Reference Documents - Architect drawings
945a4e68-c38e-5c1f-b544-10c552f2b94f | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
c50c1a6f-1568-5774-83e0-b1fa76a4efcb | note | Frequency - Each location
4bbc17c2-4f87-50d2-ae85-3fa10a37ad96 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
8ab8cb06-5f95-558c-98fc-3833bc4e47eb | note | Inspection By: Subcontractor - S
d7b7552f-98ae-5a9b-a1f6-469968d3c0a0 | note | Inspection By: Built - S
1297c6de-aaa5-5b45-8158-4e4eb5539d09 | checkpoint | 4 - Sanding to walls & ceilings
c7f82244-8dcc-5291-8090-a202d2ac17ad | note | Reference Documents - Architect drawings
8d694ba5-28bd-5afc-b0a5-11dadeeb67ff | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
186ca99c-0330-5ac0-9359-489cea89d8b2 | note | Frequency - Each location
c741ac04-1679-562d-8922-848b6bcdb2be | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
0fc54559-cf6d-507c-93cd-7b60bb51b83c | note | Inspection By: Subcontractor - S
e6073a30-cfdc-56af-a956-414f3fc70cca | note | Inspection By: Built - S
90221239-74f6-5ad9-a97b-56f3272b746d | checkpoint | 5 - Fit access hatch frame
c81f7847-3fa7-5c4e-a155-2abe4b13665c | note | Reference Documents - Architect drawings
5095db67-43a0-564d-b2f4-96502e468082 | note | Acceptance Criteria - Architect RCP drawings approved by Built.
4af76c5f-b48c-5798-9560-22e70b1d2f53 | note | Frequency - Each location
21583517-013d-58af-b87d-175325c68746 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
531ee757-a312-58f5-8086-72433c964b27 | note | Inspection By: Subcontractor - S
68fe6019-11a8-547e-b686-48220968ba04 | note | Inspection By: Built - S
46761d3c-cad2-5fb1-81e0-fd2a80b540fe | checkpoint | 6 - Cut out for lights
1724b0ad-07c3-5a33-a948-dd720fa779e7 | note | Reference Documents - Architect drawings
3f7f5344-4143-5779-8e9b-f2c9b50c17cf | note | Acceptance Criteria - Architect RCP drawings approved by Built.
1f3916a8-38e9-5984-a06d-6d774708e6e9 | note | Frequency - Each location
e2f51f3d-d6d4-58c8-9c78-1d8b7a1ce664 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
2607d11f-7ecc-55ed-9b0a-f2fa2e78d30f | note | Inspection By: Subcontractor - S
3c8c8904-d1b8-576e-a0dd-c116bc2896bc | note | Inspection By: Built - S
479168e8-1cdc-5ff3-a5ab-79382d4983a8 | checkpoint | 7 - Clean up
9decf326-0c3e-5aed-8c5a-707b114eeb7a | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
ea41648e-f775-5153-aa0f-371926033224 | note | Frequency - Each location
c9f6f415-a87d-52f7-970b-f2ec8c7efb01 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
4af9592d-6a2f-5e3f-a6f0-d67cb8681afa | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
3012003b-8646-58ff-97ba-6032c7e51413 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
4b163976-f5bc-5283-90a2-d44bf47563b3 | date | Date of Inspection:
4757eb2e-3414-50ce-af9f-b3bdae725871 | textbox | Carried out by:
36afca40-85cd-595b-9791-5741510b2e70 | note | Attachments
55412604-78da-56e2-8b7f-d6998b40e7e7 | tickbox | Checklists
a73c4635-46a4-55b3-bb81-ac94c04ac877 | tickbox | Photos
f24b3802-2773-5b39-98fd-4660a1f11759 | tickbox | Dockets
9c0d8122-54ce-5260-994c-b658e7481b38 | tickbox | Sample Material
00209560-9138-56aa-8961-358c37a35999 | tickbox | Drawings
f758cfea-8527-58eb-b358-c1b530e5d0fd | tickbox | Calibration Certificates
e9eebc44-1723-5a1c-9712-99441e395c67 | tickbox | Test Results / Certificate
631dfa4b-7115-5fa7-9b39-0645a5b9f521 | tickbox | Inspection reports
dd19e304-7dc6-50dc-aa33-b808693191dd | tickbox | Others:
87e22488-82d4-5248-89bd-9bbd07c01db5 | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed:
eb9ddd01-d6ee-5eba-9aae-49748c06482a | checklist | ITC&ITP No.5 - Patching | itp | ITC&ITP No.5 - Patching
4b3f4e76-a78e-5b7c-b3c7-0a7a54a2303f | section | Patching
539ae751-a1ab-5e9d-b754-24177c9f50ba | checkpoint | 1 - Check ceilings
3a32a3f2-956e-5617-bd35-3380c7d04b05 | note | Reference Documents - Architect drawings
a0ce27df-130d-57f0-9f28-36f8105cf2cc | note | Acceptance Criteria - Architect RCP drawings approved by Built.
55d0e768-4171-5a21-926e-300e68349aa6 | note | Frequency - Each unit
e3370130-e810-5676-a8c6-d3366e1bce20 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
4e11cb5f-0673-5d0b-b60e-8993ae76559e | note | Inspection By: Subcontractor - S
7c59a333-533e-5a08-a5c5-a97ea6bc6066 | note | Inspection By: Built - S
6233f9fa-2355-5f75-8322-c38eb1a9cd2d | checkpoint | 2 - Check walls
38b56597-3fc6-5e7f-adad-d3dc033ae37b | note | Reference Documents - Architect drawings
b820fa5d-bbfe-5770-b22d-5c10e70b37a3 | note | Acceptance Criteria - Architect GA plan & wall type drawings approved by Built.
7dcf91c9-641e-511c-97c8-1c32906ae1fd | note | Frequency - Each unit
17961d31-e573-5cd6-b50c-59491b6591f6 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
f1bdac65-0821-5ca6-8a4f-147d4aba932f | note | Inspection By: Subcontractor - S
2543b40b-ddfc-53a5-9867-6448f702d415 | note | Inspection By: Built - S
5303f0cc-5a18-56aa-9146-a1729c5254df | checkpoint | 3 - Clean up
8e3088ed-a8a9-5acd-a989-af484b4ff59e | note | Reference Documents - Architect drawings
af21f8fc-b7eb-5c55-81c3-a96feca61fb3 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
75c8b118-225e-5d54-b60d-e879b2fa13a7 | note | Frequency - Each location
4c51ef92-1a3f-5fd7-8b82-9b93531fce28 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
2fa89a91-84f6-59a4-9887-ebf3a45b9f5b | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
0d43f6bf-8b95-51b9-add1-3fcbbf08ecf4 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
9a858b88-16ff-5a94-b661-cc3befb74976 | date | Date of Inspection:
65862ffd-453f-57fc-8330-b3cf7a19d2f1 | textbox | Carried out by:
3db31872-e4ee-5f35-811c-91e74c75b915 | note | Attachments
3593833b-78be-52b5-9dee-1e7b829adc51 | tickbox | Checklists
23db9c14-89fd-55ca-b755-d57352ff54b0 | tickbox | Photos
2dd9a11c-164d-52e1-8c5e-7ff0b1494f53 | tickbox | Dockets
9b643164-3613-5bf9-951e-39390d440a91 | tickbox | Sample Material
25affeef-a8f7-5ad8-a81a-6d9a72e34f2e | tickbox | Drawings
597b0228-35b1-57ab-b24c-d911f136259b | tickbox | Calibration Certificates
bf726c6f-7ba2-5807-96fe-0c5fe8e88fba | tickbox | Test Results / Certificate
008adbee-0bb2-5e68-8659-d73a8d3a928b | tickbox | Inspection reports
3755e9dd-320f-5fa8-956b-c15972ea48cf | tickbox | Others:
5e7c6267-3ab7-57f7-9125-e26ebad76e09 | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed:
96174afd-243e-5175-bc4c-208999d8158e | checklist | ITC&ITP No.6 - Rigid Board | itp | ITC&ITP No.6 - Rigid Board
f5b79ed5-ef23-5c38-bcb3-d70e0c58e3f7 | section | Rigid Board
2f837068-255e-5429-9d86-b19c25b8df1c | checkpoint | 1 - Set out Rigid Board
05ea34c0-ee53-5914-98b8-924bf24aa344 | note | Reference Documents - Architect drawings
87d15287-ad77-5262-82de-5168b745f9e4 | note | Acceptance Criteria - Reflected Ceiling Plan approved by Built
9c85343b-d277-53cd-9112-583c6573d493 | note | Frequency - Each location
f587dd87-5f79-5111-97e3-0f94a39bf5ce | note | Verification Records/Comments - Visual Checklist
33f4fbe7-fe87-51ed-9a02-02cfe34e8895 | note | Inspection By: Subcontractor - S
23e3cfa8-d505-5c80-a512-09bcc1f5325c | note | Inspection By: Built - S
f03de851-df3f-50db-8f69-8fa0cbdf7cea | checkpoint | 2 - Install Rigid Board
53fd34e4-a254-5264-bf54-1b6c9a9cf1b8 | note | Reference Documents - Architect drawings
3f21332b-541e-5a97-8451-4cb6e183bd83 | note | Acceptance Criteria - Reflected Ceiling Plan approved by Built. Kingspan Kooltherm K10 installation guide 2021.
54e422a0-d8c9-5b8d-a90b-5084ef7461d0 | note | Frequency - Each location
8ad03fe2-6812-50e6-81bc-bf7740c448ab | note | Verification Records/Comments - Visual Checklist
cc265441-6f08-5194-9059-b657cdad0eca | note | Inspection By: Subcontractor - S
4c38538f-550b-587b-a5ba-937b71420878 | note | Inspection By: Built - S
745556bb-b3be-5bc5-8c10-9df16a773b57 | checkpoint | 3 - Tape & Seal
f1150430-a7cb-59ca-83c4-c8cd53b79cf4 | note | Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021
7d202566-0508-5c39-b626-ed735548e7db | note | Frequency - Each location
bd418106-511d-59aa-bc04-ca73bb74faaa | note | Verification Records/Comments - Visual Checklist
af5c9b7e-138f-51f1-b464-aea007970f40 | note | Inspection By: Subcontractor - S
c6ba335c-f3da-5be8-85ce-ef0383dca19c | note | Inspection By: Built - S
ed37a5aa-f56a-58e1-bfd9-90f24af2a258 | checkpoint | 4 - Clean up
1c133e24-a0cf-5bca-a0e3-d2b325e984df | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
5add14b9-fef2-5120-81ae-86b221f0c4e7 | note | Frequency - Each location
a6ee7c56-89cc-50ec-b728-0812564a8dae | note | Verification Records/Comments - Visual Checklist
b3cd64b4-c035-5d74-90db-06f6b1e17ecf | note | Inspection By: Built - R
d14cd1fd-e001-5492-a7d5-d08254b725b3 | checkpoint | Verification Statement
786af839-f16a-5117-9fe6-e5bed9094220 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
51688dbd-4c57-5e06-8768-d36eb37f5792 | date | Date of Inspection:
c6eae5f9-19c9-556d-bc3e-800faa625157 | textbox | Carried out by:
11cbc98d-f753-5ed7-9542-f2e4480e9b71 | note | Attachments
0aca7718-170a-526f-9d53-7551bedab014 | tickbox | Checklists
2ed230fa-9885-5a2c-abf5-0574c81a8255 | tickbox | Photos
4fdd7140-2972-546a-89da-c00dee9aa5b9 | tickbox | Dockets
5c234344-e46d-5a2f-96a2-4fd597333809 | tickbox | Sample Material
5105aa72-f7a7-5beb-9d4b-71e8cd844ed4 | tickbox | Drawings
da07ee02-0542-5d2e-9c70-759f41c2c4cf | tickbox | Calibration Certificates
1624c4b1-637a-595a-acd6-1561d2e05344 | tickbox | Test Results / Certificate
398a0bff-3ba0-57c7-94f3-0a368c04c864 | tickbox | Inspection reports
ac1aad4f-5280-5feb-9378-d72b9728af4f | tickbox | Others:
06a17459-256d-55ee-87eb-feb88a881c24 | textbox | Others
d885c681-9521-53f5-a6e8-54beb219ebce | signoff | Signed: