## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a740c83c-6200-4131-b5e5-a040742c9e89 | checklist | ITC&ITP - No.4 Rigid Board - Rev.C |  | ITP - No.04 Rigid Board
f22dc095-c35b-4974-9d86-2864f19fcb04 | section | ITP - No.04 Rigid Board
e58b433d-e9b8-4062-986c-c59c7c464bcb | checkpoint | 1 - Address Safety
361fd183-64de-5673-b934-7050b6b026d8 | note | Reference Documents - SWMS
2db0fd4b-7b24-5c66-b651-79f814203366 | note | Acceptacne Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
abdf00be-5e51-571b-a3b4-044da8ba1510 | note | Frequency - Each location
8f509a8f-842b-50f2-b25f-74b4066109fe | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
381d9e2e-0f49-5ede-b38c-334b47d8230f | note | Inspection By : Subcontractor - S
91e96409-b44b-5417-8770-70bf911f66ee | note | Inspection By : Georgiou - S
49e8fb69-4328-4d13-ae24-38aacdbcac3c | checkpoint | 2 - Set out Rigid Board
16e8021c-9c86-5c3d-8fa5-dde840a283ff | note | Reference Documents - Architect Drawings
2780f503-8483-5b5b-92c9-a382e0fda3d6 | note | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd
84ed84ce-6829-57b7-9370-b772f5f889e2 | note | Frequency - Each location
e8293046-8d00-579f-82f3-b9fac5ffcba6 | note | Verification Records/Comments - Visual Checklist
62447df2-9fee-5bcd-9dc2-54147fb6016f | note | Inspection By : Subcontractor - S
328ae04e-5ec2-5e23-a43b-4a1a12370fa6 | note | Inspection By : Georgiou - S
ce5809eb-d10b-4fd1-b11e-662fd82041dd | checkpoint | 3 - Install Rigid Board
485baacb-7730-50c7-b1b3-5c652858d475 | note | Reference Documents - Architect Drawings
51b9d5a6-17c8-5923-a0af-8f4a881695e2 | note | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd, Kingspan Kooltherm K10 Installation guide 2021
45355b64-9973-5b93-9098-d1fb01307ce6 | note | Frequency - Each location
613c95d1-880e-5ef3-a2ca-3de0f299239d | note | Verification Records/Comments - Visual Checklist
cda0a805-ddb0-5bb7-8c03-f0a55d3524d2 | note | Inspection By : Subcontractor - S
ad0679e6-49be-579f-99e6-5742e516f9eb | note | Inspection By : Georgiou - S
ac8cd654-1c78-4bf3-912e-5f0f5fadacc0 | checkpoint | 4 - Tape and Seal
8eeff3c9-5338-54ad-ab36-66fa1d1417f0 | note | Reference Documents - N/A
cb745233-e3e3-5ce1-b4a7-09d6f140e910 | note | Acceptacne Criteria - Kingspan Kooltherm K10 Installation guide 2021
fae55304-e508-55b0-b645-a312109231d9 | note | Frequency - Each location
9215eda7-562f-59c5-a44f-3065637d2d71 | note | Verification Records/Comments - Visual Checklist
5f8153f7-4c83-5e43-8837-a94a0a6555c9 | note | Inspection By : Subcontractor - S
9349a9e2-a36a-5497-b134-4ebebbfeb5d0 | note | Inspection By : Georgiou - S
63c749b6-5c64-447f-8076-635035a51d94 | checkpoint | 5 - Clean up
d7372ccc-677e-5cd9-8d9b-1228b0f0ffd9 | note | Reference Documents - N/A
fe81e4af-29a7-522b-b381-dc251c0766f0 | note | Acceptacne Criteria - Waste all cleaned. Tools and materials placed well
a0f9d936-71a3-5f6a-bb86-8f7336b1a44d | note | Frequency - Each location
66caf55d-53b6-5483-ae88-08a795faed1d | note | Verification Records/Comments - Visual Checklist
8068bee2-cefb-5848-8dea-64c51d6783ae | note | Inspection By : Subcontractor
1f9667e4-18aa-5f86-8644-20ecbd4ea6a0 | note | Inspection By : Georgiou - R
| checkpoint | Verification Statement
| note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
| date | Date of Inspection:
| textbox | Carried out by:
| note | Attachments
| tickbox | Checklists
| tickbox | Photos
| tickbox | Dockets
| tickbox | Sample Material
| tickbox | Drawings
| tickbox | Calibration Certificates
| tickbox | Test Results / Certificate
| tickbox | Inspection reports
| tickbox | Others:
| textbox | Others
| signoff | Signed: