## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Curtain Wall Facade System Progress L1
| Scope |  |  | L1 | Site QA
Rows
|  | L1 | dynamic | L1 | Site QA
Columns
|  | Pre-Install - 1. Subsill & subhead in postion |  | 1. Subsill and subhead in postion | Pre-Install
|  | Pre-Install - 2. Expansion bolts are fixed & nuts are tightened |  | 2. Expansion bolts are fixed and nuts are tightened | Pre-Install
|  | Pre-Install - 3. Gaps between concrete & subsill subhead sealed properly |  | 3. Gaps between concrete and subsill subhead are sealed properly | Pre-Install
|  | Pre-Install - 4. Gutter plate & sleeve installed |  | 4. Gutter plate and sleeve installed | Pre-Install
|  | Pre-Install - 5. Check panels are correct size/type for planning installed location |  | 5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place. | Pre-Install
|  | Pre-Install - 6. Check façade pane is in good condition |  | 6. Check façade pane is in good condition | Pre-Install
|  | Pre-Install - 7. Check mullion, aluminum panel & steel back-pan cut to right size |  | 7. (For panels that require alteration), check mullion, aluminum panel and steel back-pan cut to right size | Pre-Install
|  | Pre-Install - 8. Check transom is fixed to mullion properly |  | 8. (For panels that require alteration), check transom is fixed to mullion properly | Pre-Install
|  | Pre-Install - 9. Check aluminum panel & back-pan fixed properly |  | 9. (For panels that require alteration), check aluminum panel and back-pan are fixed properly | Pre-Install
|  | Pre-Install - 10. Check all joints are sealed properly |  | 10. (For panels that require alteration), check all joints are sealed properly (photo) | Pre-Install
|  | Pre-Install - 11. Hole is cut as per request |  | 11. (For panels that require penetration), hole is cut as per request | Pre-Install
|  | Pre-Install - 12. Glass cleaned ready for install |  | 12. Glass cleaned ready for install | Pre-Install
|  | Pre-Install - 13. Apply Safety glass stamp where required but missed |  | 13. Apply the Safety glass stamp where is required but missed. | Pre-Install
|  | Install - 1. Panel in good caulking condition |  | 1. Panel in good caulking condition | Install
|  | Install - 2. Protection tape in good condition |  | 2. Protection tape in good condition | Install
|  | Install - 3. No defects/scratch/dents/distortion/crack |  | 3. No defects/scratch/dents/distortion/crack | Install
|  | Install - 4. Panel installed & fixed in position as specified |  | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation) | Install
|  | Install - 5. All Gaskets are installed & caulked neatly |  | 5. All Gaskets are installed and caulked neatly. | Install
|  | Install - 6. Smoke flashing installed & sealed as per design |  | 6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications | Install
|  | Install - 7. Gaps between concrete & subsill subhead are sealed properly |  | 7. Gaps between concrete and subsill subhead are sealed properly | Install
|  | Install - 8. Record panel ID on the floor plans or elevation |  | 8. Record panel ID on the floor plans or elevation | Install
|  | Post-Install - 1. Remove external protection & for gasket caulk only |  | 1. Remove external protection and for gasket caulk only | Post-Install
|  | Post-Install - 2. Check curtain wall in good condition |  | 2. check the curtain wall is in good condition. Address any defect issues and findings | Post-Install
|  | Post-Install - 3. Scratch or Damaged powdercoating surface are repaired |  | 3. Scratch or Damaged powdercoating surface are repaired. | Post-Install
|  | Post-Install - 4. Record defect panel on inspection report including panel ID |  | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel | Post-Install
|  | Post-Install - 5. Record un-installed panel & any un-installed item on report |  | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use. | Post-Install
|  | Post-Install - 6. Hole is sealed properly |  | 6. (For panels that require penetration), hole is sealed properly | Post-Install