## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Curtain Wall Facade System Checklist (L1) |  | Curtain Wall Facade System Checklist
| section | Pre-Install
| checkpoint | 1. Subsill and subhead in postion
| checkpoint | 2. Expansion bolts are fixed and nuts are tightened
| checkpoint | 3. Gaps between concrete and subsill subhead are sealed properly
| checkpoint | 4. Gutter plate and sleeve installed
| checkpoint | 5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
| checkpoint | 6. Check façade pane is in good condition
| checkpoint | 7. (For panels that require alteration), check mullion, aluminum panel and steel back-pan cut to right size
| checkpoint | 8. (For panels that require alteration), check transom is fixed to mullion properly
| checkpoint | 9. (For panels that require alteration), check aluminum panel and back-pan are fixed properly
| checkpoint | 10. (For panels that require alteration), check all joints are sealed properly (photo)
| checkpoint | 11. (For panels that require penetration), hole is cut as per request
| checkpoint | 12. Glass cleaned ready for install
| checkpoint | 13. Apply the Safety glass stamp where is required but missed.
| section | Install
| checkpoint | 1. Panel in good caulking condition
| checkpoint | 2. Protection tape in good condition
| checkpoint | 3. No defects/scratch/dents/distortion/crack
| checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
| checkpoint | 5. All Gaskets are installed and caulked neatly.
| checkpoint | 6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
| checkpoint | 7. Gaps between concrete and subsill subhead are sealed properly
| checkpoint | 8. Record panel ID on the floor plans or elevation
| section | Post-Install
| checkpoint | 1. Remove external protection and for gasket caulk only
| checkpoint | 2. check the curtain wall is in good condition. Address any defect issues and findings
| checkpoint | 3. Scratch or Damaged powdercoating surface are repaired.
| checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
| checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
| checkpoint | 6. (For panels that require penetration), hole is sealed properly