## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-222-CIV-Calder Park Drive-Residential Fencing
ITP Number |  | 222
ITP Description: |  | Calder Park Drive-Residential Fencing
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-11-12
ITP created by: |  | Jason Quan
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | Calder Park Drive
Inspection & Test Plan - Rail Delineation Fencing-Permanent
[9 empty] | Revision: | 0
[9 empty] | Date: | 2024-11-12
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings Manufacture Guidelines Australian Standards | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings/Manufacture guidelines | Min 20 MPa concrete to be used as per Propietry Product Guidelines. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Steel Columns, Cladding etc | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services and post locations Offset checked against the running edge prior to installation of posts. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings Metroll - Colorbond - Metline | Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. | Visual |  | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Fence Post Foundation | IFC Drawings/Manufacture Guidelines | Minimim 20MPa concrete as Per Manufacture Guidelines Typical Footing: Footing dimension 900mm deep, with a 200mm dia | Measure | Each footing | IP | SE/Site Supervisor | Post and concrete dockets
4.4 | Fence Post Installation | IFC Drawings/Manufacture Guidelines | Maximum post spacing 2365mm centres Maximum post heights 2100mm above ground level. Vertical Tolerance (High Risk Areas): ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.6 | Assemble Fence Post | IFC Drawings/Manufacture Guidelines | Assemble posts by screwing them back to back with 7 staggered screws. Use 7 x 10 - 16 x 16mm self-drilling screws. 2 x Screws approxiamiately 60mm from top of post. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.7 | Bracing | IFC Drawings | Powder coated SHS post as a corner for a neater finish. Either 50 x 50mm or 65 x 65mm for ends, corners and junctions. | Visual | Each element | IP | SE/Site Supervisor | This ITP Steel delivery dockts
4.8 | Installation of railing and infill sheets | IFC Drawings Metroll - Colorbond - Metline | Install bottom rail once concrete has fence post foundation has set 24 hours. Slide infill sheets into the bottom rail ensuring a an overlap is allowed for between each sheets. Install top rail once the infill sheets are adjusted correctly. | Visual | Each element | IP | SE/Site Supervisor | This ITP Steel delivery dockts
4.9 | Installation of Lattice Panels | Metroll - Colorbond - Metline | Where a 300mm lattice panel is used, install above top rail and fix it with 6 screws on either side to the top rail. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.1 | Installation of plinths | Metroll - Colorbond - Metline | Where plinths are applicable, insert the plinth into the post at the bottom of the panel. 1 Plinth = 155mm high 2 Plinths = overlapped 265mm high 3 Plinths = overlapped 375mm high 4 Plinths = overlapped 485mm high 5 Plinths = overlapped 595mm high Where more than one plinth is used, a 50 x 50 x 1.6mm SHS post must be used. | Visual | Each post | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | Fence Height Clearance | Metroll - Colorbond - Metline | 50 mm vertical ground clearance from Ground level to bottom of railing. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
5.2 | Asbuilt Survey | IFC Drawings | Asbuilt survey report to be attach for the Residential Fence. | Attach Report | Each Lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /