## Master List Templates
Id | Type | Name | Values | Prompting Name
343c5815-ed91-4044-a130-221c41086702 | checklist | Add Documents & Photos |  | Title:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d14f43e4-490d-48f8-9bed-79da2167ce7e | checkpoint | Please upload the relevant document(s) / photos and press PASS.

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
948300e5-40f8-4657-a838-8f571eff7b3c | checklist | ITP - Mangaheia No.1 Bridge - Tauwhareparae Road RP16.17 | itp | ITP - Mangaheia No.1 Bridge - Tauwhareparae Road RP16.17
a0945eeb-c8e0-43b2-90f0-ad421552a118 | section | 1.0 - DELIVERABLES
d3785d29-d7d8-4d8d-8c1f-0b913b4cbe36 | checkpoint | 1.1 - Prestart handover meeting
13e74fc8-fc2b-5166-928c-34fe99cc21dc | note | Methods or reference - Meeting agender items
a8186a4b-f1bc-5fbd-a707-89cffa8f946f | note | Frequency - Once
eaae33c6-1c17-5c23-a903-44b63e95f948 | note | Acceptance criteria - Prior to commencement of physical works
05365198-64ee-5b0c-bb72-47f187fb2093 | note | Inspection Type - Internal meeting
de3e51fe-8f52-53eb-9340-818446adae31 | note | Assessor - Project Manager
45700e6c-1382-5dc3-a5c8-3629b8ba0e75 | note | Reports to be delivered - Attendance record
9d361a76-051f-5c07-9f38-aaff7916019b | note | Responsible Person - Currie
10cdef25-dcdf-42e0-9960-bc5e933dda02 | checkpoint | 1.2 - Construction Methodology
9c9fd164-b17d-515d-86ec-e56965670734 | note | Specification - Letter of Award
32f04243-6fcb-5cd0-a2b7-c368996eb684 | note | Frequency - Once
3d0621cd-2b54-58a0-ae94-881aa9ea0313 | note | Acceptance criteria - Approved by ER prior to commencement of physical works
22c6a2a3-3eac-5894-9706-66866c900806 | note | Inspection Type - Hold Point
61d1f3b4-4d3d-5a26-858f-754ed1e6be77 | note | Assessor - WSP
56c46e27-1bc3-51e4-8774-2db78533c096 | note | Reports to be delivered - Detailed record
f840d19b-5adf-5680-a101-a40d3bc2e13c | note | Responsible Person - Currie
8ecdc501-6d17-4c44-b533-99845d85926c | signoff | HOLD POINT
60590185-665c-4c8a-aa53-816c5dde67d7 | checkpoint | 1.3 - Construction Programme
bed1a81e-e7ae-5e15-abc1-faec3dcfc6e2 | note | Specification - Special Conditions of Contract cl. 5.10.4 and Letter of Award
e794c0e8-ebc5-57ff-8bf8-b80daeeff2bf | note | Methods or reference - MS Project format
1dcceabb-1584-5273-8c8e-878b3b7c0363 | note | Frequency - Updated weekly
a8c4d674-d157-504d-81e4-acc37f67e632 | note | Acceptance criteria - Conform to contract requirement
f4176422-31d7-5c2d-a72f-c8955207801f | note | Inspection Type - Hold Point
b0c34bab-5d26-5e1f-8671-e5f484cc207c | note | Assessor - WSP
660afef0-0f6b-532d-8995-f0674188da15 | note | Reports to be delivered - Detailed record
76a7f986-9dfc-5556-a205-00874c9afb89 | note | Responsible Person - Currie
f0fc8b54-87ef-4261-8c86-64417d5614f7 | signoff | HOLD POINT
5f82f37d-60dd-4522-9280-4a35a2f1a2ad | checkpoint | 1.4 - Site Specific Risk Assessment
2ec94274-62e9-52dd-be65-c7c0507ddfa5 | note | Specification - Special Conditions of Contract cl. 5.17.1
7607d639-3554-5b96-ad57-3b7d1b4d58b5 | note | Frequency - Once
ff1362f2-f03c-5b8e-938e-f6be9d1fc209 | note | Acceptance criteria - Conform to Contract requirements
ef268089-cc86-5055-84a9-59fbadbb40b5 | note | Inspection Type - Hold Point
804d85dc-cfef-5c83-beb9-9ecdff499289 | note | Assessor - WSP
3bb12d62-6b59-520c-b0f4-7f458b802e00 | note | Reports to be delivered - Detailed record
810ec4d1-4617-5f9a-806e-8403512d9722 | note | Responsible Person - Currie
e445c0b9-17cd-445f-92e0-cda124809231 | signoff | HOLD POINT
be24c9d7-9113-4f2b-8892-467b7d88f6a5 | checkpoint | 1.5 - Health & Safety Management Plan
5b01175b-bcc6-54ef-a00b-19080b8fe0aa | note | Specification - Special Conditions of Contract cl. 5.17.1 and Letter of Award
c88b24a3-ec88-5d3e-b6e9-dfb42a33c9b6 | note | Frequency - Once
7fa47d66-6e3c-5ec5-83f5-7ed37abe1a32 | note | Acceptance criteria - Conform to contract requirement
94a2a363-84e6-5651-a86a-a8534324cddb | note | Inspection Type - Hold Point
a10e7ef7-c753-5858-b135-3527f87d2352 | note | Assessor - WSP
fac228c0-273f-52fe-80b0-6840287ea0c3 | note | Reports to be delivered - Detailed record
4eade64f-9fc0-5a41-b543-08222094890b | note | Responsible Person - Currie
8a085007-c439-44af-a453-2d0ce5da3f1a | signoff | HOLD POINT
27cef8c0-3fd5-4d3a-b396-8253fdb5bedb | checkpoint | 1.6 - Monthly Health & Safety Report
a0043273-8566-5bdd-9f7e-6ae3bd8e5933 | note | Specification - Special Conditions of Contract cl. 5.7.15
c5113604-88ba-5f10-977c-7eb35759c8e7 | note | Frequency - Monthly
16fc26b4-f642-5c75-af16-8c722c726f74 | note | Acceptance criteria - Conform to contract requirement
fdfd6409-f079-53df-a04d-603465b0eb55 | note | Inspection Type - Verification
7cd25b83-bbdf-512e-a82b-fbe0e3249318 | note | Assessor - WSP
bb757d84-4ad3-54de-b743-d60f59241ec1 | note | Reports to be delivered - Detailed record
4def1efa-633b-5032-87c1-49bfe4394385 | note | Responsible Person - Currie
cdb74f3f-52bc-4067-b340-e9bcda6dd2c2 | checkpoint | 1.7 - Quality Management Plan
f2282bcf-ad00-531d-ae73-452ee005d87c | note | Specification - Special Conditions of Contract cl. 5.18.1
60d9763b-d4b9-5212-8002-47cb5e36ae1e | note | Frequency - Once
e66308e1-185e-521d-8c1b-03fdf512afad | note | Acceptance criteria - Deemed as submitted under Panel Agreement
9ae47083-1589-50d1-acf8-97a137ecbc8b | note | Inspection Type - Verification
7821a3bc-379a-5116-856b-6e315215a209 | note | Assessor - WSP
7b125c9f-cd85-549e-aae2-104934f85f96 | note | Reports to be delivered - Detailed record
546e1d43-731e-52f9-97d1-e6534eb60f47 | note | Responsible Person - Currie
8a6caf74-29e1-4771-b367-1fd3220fac58 | checkpoint | 1.8 - Enviromental Management Plan
1198f6ba-951a-5b1b-8332-73e1f86bda57 | note | Specification - Special Conditions of Contract cl. 5.22.1
f6093bc0-e259-5e75-b44a-2cbd7b466608 | note | Frequency - Once
d177ad93-d9a5-56c6-a72c-0a35f54f32fe | note | Acceptance criteria - Deemed as submitted under Panel Agreement
240e2a49-e74d-5e2b-8a38-c024fa81f126 | note | Inspection Type - Verification
0e385177-5435-5adc-b3b4-03304c93a451 | note | Assessor - WSP
4390ccda-e716-5580-8c41-a3af986d32f9 | note | Reports to be delivered - Detailed record
229ba317-09c8-5927-9ad2-90e50cb5aeb4 | note | Responsible Person - Currie
be6b0ca7-45b0-473d-96cc-c34a48f97423 | checkpoint | 1.9 - Erosion & Sediment Control Plan
b77ea4e3-7a9c-5347-9e52-254130f71e84 | note | Specification - Letter of Award
dab960df-8e11-57b9-8562-545bf45d8efc | note | Frequency - Once
b9d576e6-ba92-59a5-9e8d-fb144b9747c6 | note | Acceptance criteria - Conform to Contract requirements
31038f66-4f04-501d-84b4-b53dc606f212 | note | Inspection Type - Hold Point
b5fd927b-43d4-5550-a5d9-f2e1e8eb2ff3 | note | Assessor - WSP
79067d82-cfc9-54ae-980e-c2f8ee731fb9 | note | Reports to be delivered - Detailed record
487bd742-2af4-5ab8-9a2f-97ec84c790f5 | note | Responsible Person - Currie
d55d51c2-546b-4d07-b398-2795ac895c7a | signoff | HOLD POINT
75c8cf9b-ed36-47a7-882b-533cefd90241 | checkpoint | 1.10 - River Based Access
a58b8d3a-50fc-531d-b4ba-405baa67f60b | note | Specification - Technical Specification cl. 1.12
ec887f8d-baa6-5941-96f4-60144feaa39a | note | Methods or reference - Contractor to provide proposed access method
989f85b7-1100-58a9-9e5a-d34a2057e45f | note | Frequency - Once
22c088cd-b0c4-5b4c-a10c-f1e67c2f2ba6 | note | Acceptance criteria - Conform to Contract requirements
94a0e41a-0a6c-541d-813c-32ae9dff01e5 | note | Inspection Type - Hold Point
ff9fb14d-fd31-5593-b9d0-818f2e310224 | note | Assessor - WSP
14962da8-c84c-55ec-9698-ba5d06bc8ba4 | note | Reports to be delivered - Detailed record
73e49658-5edb-5981-848d-43215766eb60 | note | Responsible Person - Currie
eed8aaba-49cb-462c-804c-5266f26e6680 | signoff | HOLD POINT
61b020b5-97f2-4748-83e4-abd507e09842 | checkpoint | 1.11 - Building Consent Expemption
23d72d5b-8283-5c3a-b4a6-973a591a8e33 | note | Specification - Special Conditions of Contract cl. 1.5.1
63f75ec3-500d-5862-82eb-d85a82988ef6 | note | Frequency - Once
a6b8e606-92e7-5078-b943-6b9ff5984ff6 | note | Acceptance criteria - To be provided to the Contractor prior to construction
56649dc2-b844-5c72-bc2c-17b4745e2606 | note | Inspection Type - Hold Point
ce6e39de-1ee0-5471-9c5d-f9ec241373f2 | note | Assessor - WSP
c94363c5-7cae-5e62-950d-2518ba9be446 | note | Reports to be delivered - Detailed record
add81a3e-c75d-5b7c-b8a7-5ec7d39461c0 | note | Responsible Person - GDC
c63183d6-11f5-4e0c-8990-d43843815da1 | signoff | HOLD POINT
8daa0acf-31e7-463c-9333-b16b8ed0dfc4 | checkpoint | 1.12 - Traffic Management Plan
d689d21f-f69b-50c5-9ff7-8218f39d04e6 | note | Specification - Special Conditions of Contract cl. 5.19.1
9eb8fc22-c122-5893-948a-f4767a87635f | note | Methods or reference - GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added
867ce0b3-38a8-5d1e-81fd-6b22a6752209 | note | Frequency - Once
37f4491d-bc81-5e17-87a4-7012584580a2 | note | Acceptance criteria - Conform to Contract requirements
1e4cec63-1053-5850-82cb-5c6b5fe4ad84 | note | Inspection Type - Verification
4c23afb2-9833-5481-b536-1c7d5d4e5e27 | note | Assessor - GDC
e926c846-f96b-500c-b563-fcfad99d3e7a | note | Reports to be delivered - Detailed record
e6002136-47b3-55e1-bcd0-bb4df27eff2d | note | Responsible Person - Currie
404c5188-b068-4545-a758-ad760beefd1a | checkpoint | 1.13 - Bridge Closures
66395c10-4ae2-5398-aff1-460de6b4d4d1 | note | Specification - Technical Specification cl. 1.8
a4262fc1-d1dc-50fa-8516-5207030734e1 | note | Methods or reference - The date and duration of any closures to be agreed with the Engineer
14c103c9-1148-5a18-802e-46962e529f2d | note | Frequency - On-going
3d1ef0da-11e5-5a2d-92d1-9fde50b0850e | note | Acceptance criteria - Conform to Contract requirements
5583b1a0-cdb9-5922-a4b2-a98f2f990902 | note | Inspection Type - Hold Point
eceed653-596e-5fbf-9e30-e53a2bba2a55 | note | Assessor - WSP
8bb53d94-1a0c-59fe-a6cf-d4bf30200927 | note | Reports to be delivered - Detailed record
30bcf783-43bf-5310-a82a-5d464970f5fa | note | Responsible Person - Currie
939dd221-66fd-471a-aa5f-374567222d61 | signoff | HOLD POINT
b8c808e1-8d6c-4298-af4d-c80d7a224983 | checkpoint | 1.14 - Proof of Insurance
fd14b077-a1d3-576e-a722-6c00a8d18a70 | note | Specification - Special Conditions of Contract cl. 8.1.1
aaaaee63-da1e-5f5e-9a8c-a408ac751c95 | note | Verification Activity - Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability
43a3802c-ac4a-564a-a126-4b0bee6041b6 | note | Frequency - Once
0c552f17-e167-50b0-830c-361288917ed9 | note | Acceptance criteria - Conform to Contract requirements
a675de12-7355-5d62-a820-b21e9dea31d9 | note | Inspection Type - Hold Point
48227533-b1cb-51c2-9525-134037cbd8d5 | note | Assessor - WSP
42b0bbb4-dcb7-5aa7-ae7f-2c3a8821996b | note | Reports to be delivered - Detailed record
8f139052-cfde-585e-a40b-390c1ce6134e | note | Responsible Person - Currie
459f1f60-79b8-40ca-b4e4-af2912731d55 | signoff | HOLD POINT
2777420a-3edd-40ed-8e48-e552bf82d047 | checkpoint | 1.15 - Service Locates
04840add-18c3-5b59-a0cc-9e1e613333e0 | note | Specification - Technical Specification cl. 11
90c265e9-c0e1-5ff1-bebd-71bd37275ee0 | note | Verification Activity - Service providers including Before You Dig & close approach agreement
f44ec2ff-19d0-5dcf-89ec-c5f462b9f5e1 | note | Frequency - Once
0b64292d-0434-5196-91f9-be78bb9390cb | note | Acceptance criteria - Prior to commencement of physical works
f6a98636-d540-517e-82ec-992d4e55657e | note | Inspection Type - Verification
31616448-6191-5b57-952e-670e5fe77cb6 | note | Assessor - Foreman
8c213e91-802c-54b1-a5a4-3adff6aceda4 | note | Reports to be delivered - Service details
5322fae9-5ec3-58e7-b6ff-aa99e702888a | note | Responsible Person - Currie
863f3300-92de-4614-b164-344366ea46ae | checkpoint | 1.16 - Dimensions and set-out
f22850df-b09e-5156-aefc-f8e9cfaaec23 | note | Specification - Technical Specification cl. 1.11
75f4ee53-979b-581a-8bdc-47055ce1bf9f | note | Methods or reference - Contractor to confirm set-out and dimensions with the Engineer on-site
1f8fdf1d-ba08-56f2-8b66-c27b60b24017 | note | Frequency - Once
ba5c6357-0c83-5286-9527-257505d5e2de | note | Acceptance criteria - Prior to commencement of physical works
25eb82db-17db-53ad-94c3-1281b5cd4e5c | note | Inspection Type - Hold Point
2127ad6d-cb51-516c-9d70-9ec3257afe62 | note | Assessor - WSP
69846e66-a433-5b1c-b591-9761b42c790a | note | Reports to be delivered - Verification
1a9fb1ad-03cc-526e-81c7-a87c0f3bc187 | note | Responsible Person - Currie
e4cf8498-3271-4335-abf9-f9e7acac069a | signoff | HOLD POINT
2218f327-c5c7-4507-9ce1-72f8e0a3f709 | checkpoint | 1.17 - Clearing of Site
0c3c1711-bc71-5b71-8c8b-79c81ac1e79c | note | Specification - Technical Specification cl. 1.13
f71e52c6-2d24-51cf-89b7-e6a3221cbd90 | note | Methods or reference - Contractor to agree with Engineer the extent of the clearing
021c402d-2efc-5bf1-addb-d980844b97a5 | note | Frequency - Once
0dbb1d68-2a51-53b1-9fe6-19021c86e126 | note | Acceptance criteria - Prior to commencement of physical works
4f4fe493-4d18-5d56-9226-23278a8f91ed | note | Inspection Type - Verification
cd1f0310-9956-5fec-a4c6-6f34484010e4 | note | Assessor - WSP
27ff148a-108e-5bbe-b5d5-b61886e14221 | note | Reports to be delivered - Verification
64a06c39-f7ba-5068-8bcd-904b025ba6f5 | note | Responsible Person - Currie
e284932a-2599-4679-94e2-6264dbac6969 | checkpoint | 1.18 - Earthworks
364e3aed-7567-5f92-a786-29b7d906c805 | note | Specification - Technical Specification cl. 1.10
ae41124c-c606-5f66-afb0-4af54ccc7be4 | note | Verification Activity - Contractor to submit excavation & compaction methodology to the Engineer
9b0e5c9b-f4b2-504c-af42-e92c47756ced | note | Frequency - Once
7adbff42-058e-5514-b024-32c5720e1b8a | note | Acceptance criteria - Conform to Contract requirements
aaf0c293-a362-5249-8d4e-f8e8583f0b26 | note | Inspection Type - Hold Point
836ea00d-ee84-5e89-bb81-7dfce659fc89 | note | Assessor - WSP
8076c24a-1eb7-5abb-bf7e-df1a91134655 | note | Reports to be delivered - Detailed record
672ef6ba-d98a-528c-9d2a-a89e204937f7 | note | Responsible Person - Currie
1164c65f-c2b3-4c95-9fef-b31cdb1b72a7 | signoff | HOLD POINT
59549a4e-ef04-4357-ae85-23e93809d8d2 | section | 2.0 - Materials
ad260e3b-0f69-4e73-af58-4ad86576fb89 | checkpoint | 2.1 - Nuts, bolts and washers
f315b3e6-a1c1-546e-95b8-252339d9fa47 | note | Specification - Technical Specification cl. 2.2
426de1fe-04c0-5f24-b1c9-d5bccc54ae3c | note | Methods or reference - To be Class 8 & HDG
6064a1cd-4253-53c9-a4ed-3a8f439833f9 | note | Frequency - On-going
7deada1d-6ddb-5be9-a175-dc4b9d4d9cc3 | note | Acceptance criteria - Conform to Contract requirements
9a52934f-390d-5a14-9e6d-d6d427bf0dfc | note | Inspection Type - Verification
251a297f-9faf-57b0-9feb-2299d60c8c4d | note | Assessor - WSP
8f29d0ef-6d67-52ab-8059-1173a80e0228 | note | Reports to be delivered - Supplier docket
277d3b9e-4dcd-5314-88fe-f51c43f7ff34 | note | Responsible Person - Currie
e2ea20d0-fc4b-4c54-8b50-f60a5a2de995 | checkpoint | 2.2 - All Steelwork to be Grade 300
218bdd70-661e-5245-827b-13dbdb9a77ae | note | Specification - Technical Specification cl. 2.3
c89a2d7f-e7c5-5010-b167-03292fb5e1e1 | note | Verification Activity - Mill certificate
26f6271b-3f18-5c42-97f9-0dfd1cc228cc | note | Frequency - Once
cbbf9218-d8cd-5a23-b136-63a333db1c98 | note | Acceptance criteria - Conform to Contract requirements
dd322b18-b33e-5d79-8326-2222838857d0 | note | Inspection Type - Verification
b0bf29de-a4ec-58c7-b7f8-4ab281a29b24 | note | Assessor - WSP
b567e9fa-31e7-582b-8606-f38de1ca5863 | note | Reports to be delivered - Detailed record
c8ffe4ea-e37a-5396-bd5d-32c8d40d4b26 | note | Responsible Person - Currie
1eff23c6-344b-4098-beb2-67fc6f99a3bc | checkpoint | 2.3 - Concrete for steel post footings
da7286fd-dbf4-58fb-a9cd-440be958fb74 | note | Specification - Technical Specification cl. 2.4.1
d17d3ea0-9f0c-5dba-b229-1f33aa488147 | note | Verification Activity - Contractor to provide concrete mix design
88cd84eb-bd51-5f04-9e2c-556133737e5f | note | Methods or reference - Concrete to be 30MPa
44d6e518-0c70-5912-b430-93df003bca7d | note | Frequency - Once
89ff5b62-41c4-5b54-b4fc-d83598116788 | note | Acceptance criteria - Conform to Contract requirements
a2b51bc8-1a81-57c8-9b12-063287174d2c | note | Inspection Type - Hold Point
8b8a6b08-d96f-5c15-966f-bd820ee49a21 | note | Assessor - WSP
0f544129-522b-55bd-9804-48cb80835d34 | note | Reports to be delivered - Detailed record
97502147-f805-5dbf-9604-f94398788e38 | note | Responsible Person - Currie
65fc2d44-7efc-4597-a2c3-3bca90969795 | signoff | HOLD POINT
87252f73-ad5e-47cf-b298-65979cd590c2 | checkpoint | 2.4 - No-fines concrete
7d6d3b7f-6980-52b4-b0c8-73a79e5b986a | note | Specification - Technical Specification cl. 2.4.2
6c19a1eb-bbe3-5e99-a620-ea1f061dc876 | note | Verification Activity - Contractor to provide concrete mix design
90eb97a2-b19d-5261-a947-cea751a957a0 | note | Methods or reference - Concrete to be 7.5MPa
48cb4c71-4c02-5a25-93a8-79b1de6d4cdd | note | Frequency - Once
843c9afd-2b7a-5992-aac2-0c2f918b4173 | note | Acceptance criteria - Conform to Contract requirements
fb7d2ba6-14cd-55c8-820a-b495ffa3dde9 | note | Inspection Type - Hold Point
65af0170-1924-5125-a55e-94e883e1d489 | note | Assessor - WSP
ec156475-7bde-5122-8d3c-f4505a3a8945 | note | Reports to be delivered - Detailed record
50e8d629-8c6b-5746-8c5e-204a9d7cd883 | note | Responsible Person - Currie
7821d49d-6706-4079-ae94-eb174d0e986c | signoff | HOLD POINT
56d0fbdc-b3eb-438b-898d-1be06f165144 | checkpoint | 2.5 - Timber lagging
b91a228d-ef4c-59dd-a06b-9aff5df8dfae | note | Specification - Technical Specification cl. 2.5.1
f6ead6fe-0a6b-57a6-aae2-0958edf894c2 | note | Verification Activity - Visual
0a114e56-9f70-56fe-bf49-3912c310a1c1 | note | Methods or reference - To be SG8 H4 with cut surfaces treated with Metalex
9de9b2f8-6a97-502e-919d-bcbe5d3b918d | note | Frequency - On-going
8273c460-58d2-5399-8466-f57069b42ec1 | note | Acceptance criteria - Conform to Contract requirements
e6896919-c8ba-5631-ad0c-42de4ef5a42a | note | Inspection Type - Verification
acf7dfa2-f4cd-5d26-9b63-4df2965ee153 | note | Assessor - WSP
dfbf5d5f-f8fe-592b-ba16-064c7989199e | note | Reports to be delivered - Supplier docket
d36ebcf1-b5f1-5c66-95c3-19ad4bf7d95b | note | Responsible Person - Currie
455523e9-88e5-4190-a255-1b4aee4e6f37 | checkpoint | 2.6 - Timber lagging fixings
790f26e2-6f71-5067-b8e1-42ed78f912c8 | note | Specification - Technical Specification cl. 2.5.1
2c3c83ac-15ad-5d58-8595-89dab3fe70ae | note | Methods or reference - All fixings to be stainless steel
1df9027a-d8f1-5479-8e18-fe2e6b3b1021 | note | Frequency - On-going
5fc3b485-c902-569e-bd85-eff5136af59d | note | Acceptance criteria - Conform to Contract requirements
36504838-da20-5762-8488-1ce3cb7ae23f | note | Inspection Type - Verification
13b50a9b-df34-5c7e-b1b1-a501193e87bd | note | Assessor - WSP
91df5027-8b3a-5bda-820d-b749d34e1192 | note | Reports to be delivered - Supplier docket
8589890f-4367-5f96-900c-0baafcf7b85f | note | Responsible Person - Currie
8f8105ab-a2d8-44eb-88d4-4cb293f6bb8a | checkpoint | 2.7 - Lagging thickness
03d587ec-9446-5ef6-b98a-c3e06e6cbc01 | note | Specification - Drawings C03 & C04
e58eb334-480b-5d84-b6ec-ee729700fb39 | note | Verification Activity - Visual
b1f26289-a857-53ea-964c-75b54b177d18 | note | Methods or reference - Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick
cdd7b70d-b372-5569-9516-628f234c500e | note | Frequency - On-going
a2afb114-a49a-512f-9b8f-c8d0b0ebde6a | note | Acceptance criteria - Conform to Contract requirements
8ec20637-8bc5-510d-9ad5-1cdf56b222de | note | Inspection Type - Verification
370c2737-274b-5547-8bdc-6dcb648cdfd9 | note | Assessor - WSP
9d367c31-f7d4-5d9f-b332-44e80fddfd15 | note | Reports to be delivered - Verification
c8226b97-03df-586c-9f3f-7d09085488ba | note | Responsible Person - Currie
b01cb061-a900-4a61-bd6b-ca05bc15c1e6 | checkpoint | 2.8 - Geo-textile
75230231-ef06-566d-9b2b-f19343dfcd14 | note | Specification - Technical Specification cl. 2.6
3980a2a6-d041-596e-b242-7c8129515a87 | note | Methods or reference - A29 required behind timber lagging & around sub-soil drain
4cde4702-bff1-5176-9644-af531dcc8bfa | note | Frequency - On-going
c940cccd-29e7-528b-8e0f-957e4a5c12f3 | note | Acceptance criteria - Conform to Contract requirements
440d0ca9-947a-509e-89d0-e6f113d5d363 | note | Inspection Type - Verification
d54fe4cd-c019-58b7-b3f2-201c1611315f | note | Assessor - WSP
4c08c5a3-7f4c-5c0d-9942-b2a95e328daa | note | Reports to be delivered - Supplier docket
206fd9da-a7d8-533c-bb9b-44035e6e2319 | note | Responsible Person - Currie
d022895e-3ff2-4165-bfd0-33478f6dffcb | checkpoint | 2.9 - Drainage composite
03188be3-7156-511e-9567-40f5d4f11b29 | note | Specification - Technical Specification cl. 2.7
df59493e-87fc-53cb-a9d0-51423d3632bf | note | Methods or reference - Filtration Class 1 & Strength Class C - laid over batter slopes
87e2821f-b1d6-5050-9175-0644ee1bdaf3 | note | Frequency - On-going
c17eab8b-7961-5300-b396-283b4620b237 | note | Acceptance criteria - Conform to Contract requirements
f684987d-51d9-554c-9319-f0133fdcd629 | note | Inspection Type - Verification
dad13647-c305-5504-bd43-12655b5cdd7a | note | Assessor - WSP
ba7187bd-479f-54be-a62c-7a1cd966f739 | note | Reports to be delivered - Supplier docket
bf6e4b2e-09fa-5860-816d-7405f3b413c7 | note | Responsible Person - Currie
a0748e69-4a28-4f22-905a-e56e10316485 | checkpoint | 2.10 - Drainage aggregate
db6d08ea-29b4-5dfa-8d4e-e894e92702b6 | note | Specification - Technical Specification cl. 2.8
bf9a6b27-5061-58d1-962f-3bdceb44f5dd | note | Methods or reference - Free draining clean aggregate with 100% passing 19mm sieve
d2b11389-d91a-5007-a543-f004cbf70536 | note | Frequency - On-going
287ac58f-e2f7-5271-aca6-dff96472a162 | note | Acceptance criteria - Conform to Contract requirements
7435e86d-21e3-585a-94fc-6d0dfbb96e58 | note | Inspection Type - Verification
5cb917c6-301a-5efe-9996-c563511101f8 | note | Assessor - WSP
3e78db9a-3cc1-539e-ad88-1260c7e3284f | note | Reports to be delivered - Supplier docket
ad8a3c7a-3a0a-56e7-82e3-b1f09af8ae91 | note | Responsible Person - Currie
02057dad-87e1-4db7-a937-1eee107bc84c | checkpoint | 2.11 - Retaining wall backfill
b5b4da86-6ed3-5ef9-9eba-cf4ed7447ccb | note | Specification - Technical Specification cl. 2.9
252e142a-c592-51bd-b953-1314896c5c20 | note | Verification Activity - Contractor to provide concrete mix design
860bdafb-7252-5fa3-9e0d-02d6a59772d7 | note | Methods or reference - Sand & cement mix with strength of 1MPa & slump of 350 - 500mm
fb2f524e-97c7-501e-8be1-dc5af7327dae | note | Frequency - Once
b8dde2db-5e0b-5ffe-be0c-b3918cb4b3a0 | note | Acceptance criteria - Conform to Contract requirements
7a5e8f0c-baac-56a4-b9b7-72b8af775e80 | note | Inspection Type - Hold Point
19dfba76-3bff-50db-abeb-08b4cf8e981e | note | Assessor - WSP
e7e4f319-2fad-5214-9605-2a1dc2a99b76 | note | Reports to be delivered - Detailed record
b68bde6b-c87d-50a3-84d6-e93226aef897 | note | Responsible Person - Currie
2193332f-3c6b-4e03-8ebb-4de9bc109ca9 | signoff | HOLD POINT
974bb206-e251-4379-838e-ac9b3c5ff720 | checkpoint | 2.12 - Sub-soil drain
2eafaea5-4d38-588e-be56-88da272a894a | note | Specification - Technical Specification cl. 2.10
dc330c64-4602-5748-a36f-1bb23dddc75e | note | Methods or reference - 150mm Punched HDPe sub-soil pipe
c38277d1-70fd-55f5-8141-4c58ff6de326 | note | Frequency - Once
66e8fcce-4779-5ccf-87ec-447fe74714c9 | note | Acceptance criteria - Conform to Contract requirements
467ffb8f-7c39-5bad-b07c-e05138fc5d5f | note | Inspection Type - Verification
7e9510fb-7f82-54a6-91e6-6d6a6517a565 | note | Assessor - WSP
47a24ec3-6704-5fd2-8973-4985ac1dc6de | note | Reports to be delivered - Supplier docket
890365e2-8ca9-53ee-ba5f-6dc21d68dd66 | note | Responsible Person - Currie
fd7892c1-0904-4083-a20b-4d280a089320 | checkpoint | 2.13 - Inspection of sub-soil drain
9c549c91-fb2e-5761-99c1-d99cf1987e72 | note | Specification - Technical Specification cl. 14
e5c16bfe-4bf2-5290-bb1d-b4eb5f5b56d9 | note | Verification Activity - Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling
53fa4abf-842b-5515-b347-0612e3e5941c | note | Frequency - Once
e2f016ab-b76a-5030-a7a7-49d95aeddd5c | note | Acceptance criteria - Conform to Contract requirements
99dc128f-5282-53f6-a413-5bcb4a87a0b4 | note | Inspection Type - Hold Point
6e4dd87d-85d9-57f3-9834-8d2ec7aedc29 | note | Assessor - WSP
39986f01-f86c-5da8-a4d0-5bb565362fb5 | note | Reports to be delivered - Site check
af42d082-b713-5739-b636-f384ff56c4bb | note | Responsible Person - Currie
cb694e68-6bd2-482e-8245-da24ca4c35f5 | signoff | HOLD POINT
91f0327d-4278-44bd-92b6-f4aef688b63f | checkpoint | 2.14 - Topsoil
b7686277-8a60-5277-b88e-755741ab98b2 | note | Specification - Technical Specification cl. 2.11
28240cfd-6982-5f10-a3f1-40bd34d26f57 | note | Verification Activity - Visual
19783cd7-4ec8-5436-8255-acead72ec3da | note | Methods or reference - Re-use existing topsoil
6557a849-edcf-5f3a-8a2e-ffec4bde02e5 | note | Frequency - Once
c8575df3-c4dc-593f-8dd8-baa991482bb7 | note | Acceptance criteria - Conform to Contract requirements
9b80d91f-5971-5664-b051-481a6ebb8c11 | note | Inspection Type - Verification
e13d500d-459a-5f66-ad22-7d96d8530e90 | note | Assessor - WSP
9dd02529-e5c0-502c-8727-cf88eab54d2c | note | Reports to be delivered - Verification
d1f766d5-8260-5dd6-907f-3cc9aa266e6f | note | Responsible Person - Currie
3478e49e-1eb5-49f4-a7ef-c742817fcae0 | checkpoint | 2.15 - Testing of materials
85e4490f-8ba2-52de-8776-bca2d6a6f387 | note | Specification - Technical Specification cl. 2.13
2a637987-7bbb-57b0-9d49-de7aa1c4a4e3 | note | Verification Activity - Supplied by the Contractor to the Engineer with 3 days of the activity occurring
cfdd38ba-4c5b-52d9-8bc0-5ff91c695ca1 | note | Frequency - On-going
bbff1456-8446-5716-b607-f04f162650db | note | Acceptance criteria - Conform to Contract requirements
afc2811b-aec1-51d1-ae0b-67f206fee57b | note | Inspection Type - Verification
69b534a6-6e65-581b-af77-546c96241d6d | note | Assessor - WSP
e2cfba28-084b-5291-b6e2-3e1336ebc72c | note | Reports to be delivered - Detailed record
660c3fb1-c366-5bfb-9005-e672527ee641 | note | Responsible Person - Currie
d230dc9c-eeb3-4119-9844-48727490277f | section | 3.0 - Steelwork Fabrication
1d9a4e14-9155-434d-89d9-3c06a829b36f | checkpoint | 3.1 - Shop drawings
f58fcfa9-fe40-5246-88bb-30f233d1a6e5 | note | Specification - Technical Specification cl. 3.2
7c171d17-7060-5008-a33b-3434207b870b | note | Verification Activity - To be supplied to the Engineer
b4be04f2-f53b-5b25-b18c-9cbdceb06746 | note | Frequency - Once
cec97fe3-0404-5135-acf9-afdcaef7f985 | note | Acceptance criteria - Conform to Contract requirements
566e4712-ee47-5dd8-978c-03e109c2dcc5 | note | Inspection Type - Verification
2ddc5dcc-2d80-5422-b985-bb46d9494d59 | note | Assessor - WSP
3205ab38-cf24-5188-b934-60659dd681a8 | note | Reports to be delivered - Detailed drawing
8348f06e-036f-5248-88b9-421f58297646 | note | Responsible Person - Currie
8e183840-b723-4dc4-92b2-ac74a05d102b | checkpoint | 3.2 - All piles, walers & accessories
054741d7-4ef7-578a-99ce-f77052290c67 | note | Specification - Technical Specification cl. 3.2
e53f0252-49b7-5d23-8a33-d824b3603999 | note | Verification Activity - To be inspected by the Engineer before installation
b4f012e4-757e-55b4-90e7-c1da791e263b | note | Frequency - Once
101adc2b-7e1d-5b97-b84d-ab47276bb89c | note | Acceptance criteria - Conform to Contract requirements
e0d4b4de-ca68-52a9-94f1-c6120df38a76 | note | Inspection Type - Hold Point
8eaf091c-20b4-5387-96b0-96c3699fe734 | note | Assessor - WSP
95022d2c-bd73-5793-af75-f902bd638de8 | note | Reports to be delivered - Verification
1ffce8e0-5876-5907-b139-329c790bb293 | note | Responsible Person - Currie
a5f70aa7-fdd5-4152-8622-ffb2ded10470 | signoff | HOLD POINT
cb3b6bb9-b130-4ff5-8b40-ffa43f94051f | checkpoint | 4.1 - Pile holes
1bd3224b-248e-5eb2-8f78-ac716ddef1c2 | note | Specification - Technical Specification cl. 4.1 drg C03 & C04
ad2224cf-5b68-5770-a02c-1ed2c41b3379 | note | Verification Activity - 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket
a9b3c242-68fe-5bd2-a6bc-1af6060b9cd0 | note | Methods or reference - Engineer to inspect pile holes before pouring
9868da48-c5f0-5211-8cfc-9d7cebf2075d | note | Frequency - On-going
3870f418-80c3-5a66-bf31-f87ff14a185b | note | Acceptance criteria - Conform to Contract requirements
d940252a-1b2d-5a50-a04e-e8c5c5a473ba | note | Inspection Type - Hold Point
311fb839-a12c-5834-8969-18d43d383d83 | note | Assessor - WSP
577290b8-586f-5de6-a6ce-93dc95fa30e7 | note | Reports to be delivered - Site check
0bae632e-2ef8-5c6f-83c8-f6c7d4eac0f6 | note | Responsible Person - Currie
131d5f59-0297-42d3-b868-64b6c36418c2 | signoff | HOLD POINT
7a9a9f99-a02e-4612-aaff-13db883b2bb6 | checkpoint | 4.2 - Pile spacing
94e5415e-b978-5ce2-9c4b-cedb52bde50d | note | Specification - Technical Specification cl. 4.1 drg C03 & C04
ad8ba7da-68a4-5798-9ab4-9320cc7792ee | note | Verification Activity - Abutment A: Spacing varies between 1.2m & 1.5m ; Abutment C: Spacing at 1.2m centres
c4eaadda-6762-5389-9b69-64cea0c79e93 | note | Frequency - On-going
eb0afd68-a158-5d44-b3a4-d35d52bbe4d7 | note | Acceptance criteria - Conform to Contract requirements
add3f788-9ca4-5009-941e-29e1746219ae | note | Inspection Type - Verification
460396e2-6835-5e5c-9f08-f17b35a10270 | note | Assessor - WSP
6da60294-ffba-5a80-b9e2-d637b2ff578f | note | Reports to be delivered - Site check
3c91ae86-a68d-5fd6-bae4-03d2113abc7d | note | Responsible Person - Currie
01cf689a-829c-434b-8a9c-f1725c8455b9 | checkpoint | 4.3 - Maximum retained height
870d45f4-5d62-5d3f-9c68-c63c9f6aae46 | note | Specification - Technical Specification cl. 4.1 drg C03 & C04
2c66c8d9-1868-52b7-a30b-76c8797f2684 | note | Verification Activity - Abutment A: 3.5m ; Abutment C: 1.9m
2fcb1109-6310-55f2-9d42-81849ae550a0 | note | Frequency - On-going
4d1ec38a-9de4-52b8-a835-491c81873698 | note | Acceptance criteria - Conform to Contract requirements
a91cd146-98ce-53ab-b59b-9d129d1897b4 | note | Inspection Type - Verification
95bd2fe4-5257-5009-a887-b5cd3aedb9e7 | note | Assessor - WSP
77cff676-9c34-5d35-85c9-b3830f468f76 | note | Reports to be delivered - Site check
edd82982-2141-55c8-9979-e8db45e8c121 | note | Responsible Person - Currie
18cb03d9-4ed0-475b-8a1e-da91e52ee1d2 | checkpoint | 4.4 - Pile hole augering methodology
37c51c94-782b-589d-97bb-13c7a5e5310b | note | Specification - Technical Specification cl. 4.1
0681edf1-4c5a-5c1d-8a3c-2abecaeb2a17 | note | Verification Activity - Visual check
9e714d16-3090-5a96-a5a8-e41fa4e5c0bd | note | Methods or reference - Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes.
08b0b68f-26cb-502f-9efc-006267360daa | note | Frequency - Once
ba1eeda4-6d2f-51fb-ae03-ad9e03752cd6 | note | Acceptance criteria - Conform to Contract requirements
28451b63-901e-5a80-8211-f0afa7ffef0a | note | Inspection Type - Verification
80c13514-1290-5431-9a13-729919326515 | note | Assessor - Foreman
12879890-3a42-5dbb-b19b-5bbc5abb18bc | note | Reports to be delivered - Site check
9677095a-8a60-54be-937a-b11d4eea469e | note | Responsible Person - Currie
e9e2deff-0c1a-47e6-b177-7f7285e2c1f4 | checkpoint | 4.5 - Augered pile holes
8cbc9705-d548-54c8-ac54-b800d1ce2c1e | note | Specification - Technical Specification cl. 4.2
f5d253d4-7109-569e-833c-bfa110e336ba | note | Verification Activity - Pile logs submitted to engineer by the next day after augering
0fa0886a-a4c2-5c1c-b9a6-dcd3849178b4 | note | Frequency - On-going
cd4702e0-2567-5766-8335-4f8de18fdc5d | note | Acceptance criteria - Conform to Contract requirements
04552692-5680-53da-9a6e-57885bcfcfdd | note | Inspection Type - Verification
c7af8809-7e93-5525-9f82-df19b50dc139 | note | Assessor - WSP
11f337bb-ad6c-5d83-b2fd-05f65eebda9d | note | Reports to be delivered - Detailed record
ad58270c-2453-505a-be06-ccaf75f8563e | note | Responsible Person - Currie
a16031ee-63df-49b5-b50f-4c8df7619036 | checkpoint | 4.6 - Pile hole tolerances
701082fb-f2d5-5484-b839-87d89ac547ed | note | Specification - Technical Specification cl. 4.3
21c000f7-c447-518b-933a-450a93ad7768 | note | Verification Activity - Pole dia. +50mm/0mm, hole plan position +/-20mm.
a00cf80d-4858-5a0d-9c40-884d27be4ead | note | Methods or reference - Tape measure
b59c962c-5b68-5b79-924f-b25daf8462d7 | note | Frequency - Once
1e758a66-8224-5ac4-893c-32bd1f0e5d11 | note | Acceptance criteria - Conform to Contract requirements
738f9d32-d3ed-5a73-8059-f4c0a5c333ef | note | Inspection Type - Verification
a58836a7-c06a-5c10-b554-264afd5e73e9 | note | Assessor - WSP
32f68c4e-38d3-551f-8d2a-37578c2cb617 | note | Reports to be delivered - Site check
77af4410-3a10-5e6a-83e5-1349b1522b40 | note | Responsible Person - Currie
f267dd46-430c-460c-b10e-1acfde0a760c | checkpoint | 4.7 - UC post tolerances
918de358-4d54-50b7-936f-d80bd4e0df99 | note | Specification - Technical Specification cl. 4.3
7cd41a5c-ba95-5811-a37d-b0a521635e9a | note | Verification Activity - Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm
f7e06bf5-384a-5db1-9c23-c512a3c14cd7 | note | Methods or reference - String lines and tape measures
dc75c852-f2c9-5fe4-a695-00e4ea86bb7e | note | Frequency - Once
80b2b2f7-e7c8-5f04-82aa-5aa490e4e259 | note | Acceptance criteria - Conform to Contract requirements
aef6356e-0b8b-5184-bd86-cb4ff34dad98 | note | Inspection Type - Verification
a6ac9f5f-2df9-55e0-a787-5e8242318ffd | note | Assessor - WSP
cc65c97b-9064-5a0a-a419-db9e1117f75c | note | Reports to be delivered - Site check
cd08e17b-bcb0-5c80-8d34-488b49ba406b | note | Responsible Person - Currie
7c397ee9-b57b-4771-8147-07ebc5f10d17 | checkpoint | 4.8 - UC post size & treatment
737fa7ec-6219-515b-9cc7-2caa2d7b3b63 | note | Specification - Drg C03 & C04
9b86f17c-39a9-546c-a366-efb73fcaa28a | note | Verification Activity - 150UC30 ungalvanized
42f9fbcf-0597-5ac9-8237-90b4d873a67f | note | Frequency - Once
1b4542c1-7e7d-52b9-8628-791359f9656d | note | Acceptance criteria - Conform to Contract requirements
a1da670c-e76f-5001-a4ed-206664b5b2e7 | note | Inspection Type - Verification
6188521b-e5a7-57a3-aa5a-daa8f089f561 | note | Assessor - WSP
32d14921-04ac-5423-b006-15b573416a98 | note | Reports to be delivered - Delivery docket
fbb2c340-3f5b-5d52-8ada-e8ae0383c6ee | note | Responsible Person - Currie
f3ee79e7-d3d3-4edc-b7c3-273d4ed72b22 | checkpoint | 4.9 - Concreting UC posts
13d6ddf5-af32-55bb-a2e7-5133a01d538a | note | Specification - Technical Specification cl. 2.4.1 & 4.3
dcb5ba43-f261-5c2f-b5c2-f41afd43d1e6 | note | Verification Activity - 30MPa concrete
726c1da5-2ae4-55e6-b59b-fcaa211b2d9a | note | Methods or reference - Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer
d36472da-2d11-56a0-be69-e3e8cf0b5c44 | note | Frequency - On-going
03b1b936-152b-5733-9a2f-72efc526b316 | note | Acceptance criteria - Conform to Contract requirements
b0a4f0de-5c45-5808-99d1-acddfb778f5d | note | Inspection Type - Verification
081fd85f-ed3c-5c33-8a10-c8da885eb7a9 | note | Assessor - WSP
1fc32c26-2d91-57ad-bef0-42095e034cad | note | Reports to be delivered - Detailed records
bcdc415d-762b-5971-ac18-07682d28c849 | note | Responsible Person - Currie
fe716642-e532-46a7-8349-ecf86cc150ee | section | 5.0 - Welding
01845225-0881-4dea-9c60-279f94db4cf7 | checkpoint | 5.1 - Welds
4c3dc57f-ee25-5e11-8d6c-73b8b3377124 | note | Specification - Technical Specification cl. 6.1
eada4d92-33ba-5ec5-b986-20ba7ee676be | note | Verification Activity - All welds to be category SP
c02b4542-2b74-5589-b2a7-883510ea9a10 | note | Frequency - On-going
b400bc8e-19b2-5c5f-8b0e-725c170bbf93 | note | Acceptance criteria - Conform to Contract requirements
8610cea2-af0f-548e-b342-24148829f9d8 | note | Inspection Type - Verification
96b8cc6a-8dbc-5b2b-9fb0-4038acf2ec97 | note | Assessor - WSP
3154e399-12af-5611-ac08-8e5ef79999bd | note | Reports to be delivered - Site check
2046017c-364f-573f-823a-e36fc16316dc | note | Responsible Person - Currie
c79a1881-d339-488e-adc1-a3d6c52e7c55 | checkpoint | 5.2 - Welder qualifications
dd25f08d-bdd1-5480-a55b-a79c784c920e | note | Specification - Technical Specification cl. 6.1
a7c18287-034e-58f1-99f8-34c3fa859ce3 | note | Verification Activity - Welder qualifications to be submitted to the Engineer for approval
72ceb817-0284-5c79-9691-f1475f9b804f | note | Frequency - Once
7c8da4b5-39af-51fe-b89c-c91ef362d8e9 | note | Acceptance criteria - Conform to Contract requirements
81a01df2-632a-5517-8c46-e35acd856f12 | note | Inspection Type - Hold Point
19b3ef9b-cad7-532f-95b9-a769e274b4d5 | note | Assessor - WSP
f2a6f1cc-8a32-54e3-a655-783800bedb67 | note | Reports to be delivered - Detailed records
882efba5-3c07-5384-bb0a-e6f383932fd5 | note | Responsible Person - Currie
3e044696-86a3-42c0-8883-a51bea5da11a | signoff | HOLD POINT
2043a7f4-345c-4ced-9e77-d3945ee4d6a2 | section | 6.0 - Concreting
13761e57-9c84-46f3-93fd-c6bee9adaecc | checkpoint | 6.1 - Formwork
59ed0dd5-6284-5bd0-9dc6-bbeb569a914e | note | Specification - Technical Specification cl. 7.1
a77a65ef-f0be-5be9-9683-069b509cabd0 | note | Verification Activity - Formwork to remain in place for 48hrs after pouring
17beaae3-eb5f-509b-a113-9e70a95e6830 | note | Frequency - On-going
03919e70-4a1d-5b05-b89e-a1ce1bd5f3ab | note | Acceptance criteria - Conform to Contract requirements
95b6ef77-c12a-5463-8aaf-84ede958a8d5 | note | Inspection Type - Verification
acd5e8c9-7ed2-500f-b13d-b510f833d8bf | note | Assessor - WSP
c5278e18-7475-5c5a-99ea-9aa8196b38bf | note | Reports to be delivered - Site check
6836e0dd-cfc9-5082-b6ea-2e103826697d | note | Responsible Person - Currie
5eccad2f-95d0-47c5-bbb1-d7074f812025 | checkpoint | 6.2 - Concrete workmanship
526368a5-ffb4-5d17-b317-ba973005b6cc | note | Specification - Technical Specification cl. 7.2
9315e34e-5975-5747-906f-6dacaf7e2d85 | note | Verification Activity - Concrete to be placed in dry conditions
070d57af-3776-5802-825c-7c105162dd11 | note | Frequency - On-going
dc040489-ed30-579b-9b55-90481c31a732 | note | Acceptance criteria - Conform to Contract requirements
7b354d1d-752b-53c0-8dd6-04e6118980d5 | note | Inspection Type - Verification
416e3757-acd6-5445-8146-483e6c546e1a | note | Assessor - WSP
9d871ef9-081e-5174-9d52-0a33b9983b53 | note | Reports to be delivered - Site check
fff03142-7ce4-54f9-823c-b0150718168d | note | Responsible Person - Currie
ecf2c692-81e1-47d2-a830-2ec36c5ed85f | checkpoint | 6.3 - Concrete testing
de8f1d60-e297-54f7-8925-95b5395b274e | note | Specification - Technical Specification cl. 7.4
0a95aee2-4cc0-5c70-b941-476117b62eaa | note | Verification Activity - Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d
4e6d172a-59b6-5116-8e7a-9e23ad298c74 | note | Frequency - On-going
e905f1b5-483f-58d7-9244-a0f00f12ba8e | note | Acceptance criteria - Conform to Contract requirements
ab1210b9-1081-58c9-9cce-718340c7dbc2 | note | Inspection Type - Verification
706119fc-511c-5644-a513-98c848b32cb6 | note | Assessor - WSP
9646bbc7-9b64-5800-b243-dd4633988dd4 | note | Reports to be delivered - Detailed records
5371a256-2a4b-59f6-8e57-4c2a4d71d42b | note | Responsible Person - Currie
196af8f1-3e1f-432e-bca1-8196042aab49 | section | 7.0 - Crib Wall
b7f18a48-90d5-49f7-a958-39681684e5f9 | checkpoint | 7.1 - Pouring no-fines concrete
9a806238-3abd-5e03-80c1-24cc563b3adb | note | Specification - Technical Specification cl. 8.2
7cab88aa-429b-505a-87e7-0b43116fd933 | note | Verification Activity - No-fines to be poured up to the front face of the crib wall
ff28033b-7133-5e2d-a14e-c99d7f755137 | note | Frequency - On-going
6b6e61a0-3935-5e3f-a693-20e44c1e7464 | note | Acceptance criteria - Conform to Contract requirements
f25800f2-4aa4-5e67-99dd-567e077b793e | note | Inspection Type - Verification
59d96a7d-cb1c-5842-940f-c23ad9e68821 | note | Assessor - WSP
37aad82d-8f99-5202-9b02-56e2f4f05153 | note | Reports to be delivered - Site check
0f4f14d6-e892-5b05-b543-adf3d305ce7f | note | Responsible Person - Currie
f8482024-68e1-4580-84db-ac410c1600a5 | section | 8.0 - Ground Anchors
9fe50804-5b3a-4840-9596-69ff4ded9d64 | checkpoint | 8.1 - Anchor installation
7292a686-e8c7-5fb0-adae-4dc63f8fea1e | note | Specification - Technical Specification cl. 9.1
47d57686-bee1-5f23-ae3e-711c279d44c7 | note | Verification Activity - Contractor to notify Engineer at least 2 days prior to installation & testing
cf425310-a967-582e-9863-f602400f5752 | note | Frequency - On-going
251f1efb-3501-5676-8060-bb5b5f5280f8 | note | Acceptance criteria - Conform to Contract requirements
a3429d89-01ba-5269-98df-b5a3486e98a9 | note | Inspection Type - Verification
ea72ce22-e800-51b7-b997-beb5086920ba | note | Assessor - Project manager
d9a89ea3-c450-590b-b2c2-25e755e623a7 | note | Reports to be delivered - Verification
a9248fdd-ee0c-55ba-90c8-a9b06d9425d8 | note | Responsible Person - Currie
9203e036-9db1-4627-89c1-22c214736f40 | checkpoint | 8.2 - Anchor grout volume
c7e51a27-5ff2-50c3-a3d5-a304ced6790d | note | Specification - Technical Specification cl. 9.1
a753eba2-5200-502e-838d-0bd7684c8321 | note | Verification Activity - Supply grout volume records for each anchor & submit to engineer
65c58901-d6bc-5706-98f0-f19433545dbf | note | Frequency - On-going
55a81550-e3b3-5dc9-aaff-645bd5020293 | note | Acceptance criteria - Conform to Contract requirements
6c2e4b55-c3bb-5bd1-b037-9cbc04307c74 | note | Inspection Type - Verification
40d7f74e-5943-5fe1-9323-26626eaa33dd | note | Assessor - WSP
b229a4d5-58aa-5540-a8a8-79e720698db8 | note | Reports to be delivered - Grout Log Record
2917d270-9a9a-5e18-977b-8728da871d74 | note | Responsible Person - Currie
977e04e7-a26b-4d2e-86f4-fa0f35140ecc | checkpoint | 8.3 - Anchor installation
01cc2c58-da69-503c-8838-b2b03279f7ff | note | Specification - Technical Specification cl. 9.1
cad09c83-b78d-52a2-b90b-9353757d9fe1 | note | Verification Activity - Hollow bars not to be installed at a rate exceeding 1m per minute
37910e94-7750-5c45-9b47-4ee2b28fd179 | note | Frequency - On-going
15bdb846-5ec5-530d-a51d-d848e4f0d674 | note | Acceptance criteria - Conform to Contract requirements
57fbbaef-8f7d-5408-98fb-821c4303a998 | note | Inspection Type - Verification
799bfd53-b34c-58e3-9efc-12e38fa2b03d | note | Assessor - WSP
9f013ea7-a93c-528b-967a-b2ee0f2f94b7 | note | Reports to be delivered - Site check
278174d3-9192-5e96-b5b1-7534fa92f20d | note | Responsible Person - Currie
e313cccd-a455-4847-83e3-2a29c8607e29 | checkpoint | 8.4 - Loading of anchors
931465a7-7828-5d38-b432-01ea25b49be7 | note | Specification - Technical Specification cl. 9.1
fc432940-544d-5e97-885f-f1ae68bcb12f | note | Verification Activity - Anchors shall not be loaded for at least 7 days following grouting
24cd5a73-ca4e-5b5e-8a1d-e2063d86c175 | note | Frequency - On-going
539081d2-2675-534e-ba58-a9773e95ed60 | note | Acceptance criteria - Conform to Contract requirements
b68693d9-2b9e-5e85-8e17-6c0d2efafb32 | note | Inspection Type - Verification
7b0f50d5-f9e5-5b7c-97f2-914158fa53d8 | note | Assessor - WSP
7d4e917e-e999-50cf-ae48-9b8f21343d3b | note | Reports to be delivered - Verification
0cf142d3-4879-5ee0-990b-5e95d972f5ca | note | Responsible Person - Currie
c0becf33-27a1-4aa2-a6e6-7f759b07bb13 | checkpoint | 8.5 - Anchor testing equipment
a56f2274-9a06-59a4-b320-23d9034b5547 | note | Specification - Technical Specification cl. 9.2
2171473c-097e-5021-867d-62bc6237dfc7 | note | Verification Activity - Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing
6a78da11-f683-53b7-a254-163d476efa54 | note | Frequency - Once
d94a51be-a3a4-58ba-88ab-17eed6ebe265 | note | Acceptance criteria - Conform to Contract requirements
167077f1-a150-5eba-854e-09d88b93d2fb | note | Inspection Type - Verification
680f8155-59f8-507e-8dcb-a37e244cb466 | note | Assessor - Project manager
d47be8b3-4d4a-5356-ae96-3a1f58ca358e | note | Reports to be delivered - Detailed records
66c556de-dbee-5970-bea7-015b78b1147f | note | Responsible Person - Currie
2057dbf0-fe35-4280-a9e1-1a9b75223202 | checkpoint | 8.6 - Anchor test results
a67bf083-7c47-51ee-9871-881f349aa290 | note | Specification - Technical Specification cl. 9.2
0b358c10-627c-5899-9b0f-555f263d7ebd | note | Verification Activity - Contractor to provide the Engineer with test results within 2 days of testing
dde21965-dfde-53f4-a772-f89c87f1b00f | note | Frequency - On-going
fede5beb-2521-580a-ae38-28ecc671e1fd | note | Acceptance criteria - Conform to Contract requirements
c84eb87d-815b-51cf-9140-f9e718cf7a70 | note | Inspection Type - Verification
0f88ac63-058a-50a1-9e11-ece93945e95e | note | Assessor - Project manager
7c8555a3-3eef-5895-9b7d-2ed2bd9dd66a | note | Reports to be delivered - Detailed records
5bf1dc20-c441-5103-8fd3-51abcdc79428 | note | Responsible Person - Currie
65c73299-704c-4689-aa6f-f9ebb2590f26 | checkpoint | 8.7 - Sacrificial tests
4d89952c-9b0c-5264-9304-34ed91fa1a68 | note | Specification - Technical Specification cl. 9.3
f96de698-684e-517d-8621-3be0fdd7c5e8 | note | Verification Activity - Abutment A: 1 x sacrificial test : Abutment C: 1 x sacrificial test
f6f3a38b-51d9-5683-8b9f-ee8b91271d67 | note | Methods or reference - Positions to be agreed with the Engineer & outside of the work area
798f34cb-b907-5f13-9b4d-46fc1ec0fec6 | note | Frequency - Once
6425bad9-22e5-542b-ab6a-97b880d344b5 | note | Acceptance criteria - Conform to Contract requirements
c24d09e0-c6c4-5aee-8d0b-f7fdb10f55ae | note | Inspection Type - Verification
96a23231-35a4-5b6a-aa71-30d52f59a3c3 | note | Assessor - WSP/Currie
fa2f832b-106c-5aa0-a28d-6f53b05babfb | note | Reports to be delivered - Verification
62013b5a-f040-50da-a36c-e6418e1ac78e | note | Responsible Person - Currie
40f57938-2e0b-478d-89d6-b5673e620a57 | checkpoint | 8.8 - Production anchors
8e5d6f2a-abe0-5c7f-b414-5bd487acbd2a | note | Specification - Technical Specification cl. 9.2 & 9.4
8b29f876-c376-52bc-a068-6ecf8645b9e0 | note | Verification Activity - All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test
04722277-08e2-5057-a47a-605f61bd7f23 | note | Frequency - On-going
71f766a8-e6a0-5742-9651-6a9bb7e00df5 | note | Acceptance criteria - Conform to Contract requirements
ffe56907-8ca9-562e-b9f6-820a299ff78d | note | Inspection Type - Verification
d7a4e9ee-e1b3-5177-a582-4befb33c249b | note | Assessor - WSP
7f4991b5-7306-594e-a5ad-5a7dd67f3f6e | note | Reports to be delivered - Anchor Load Test Record
6d3d3f4c-3ac0-5bda-aaec-0cc9434b94d6 | note | Responsible Person - Currie
1f837e41-3774-491c-8f96-ba69f2402261 | checkpoint | 8.9 - Sacrificial & production anchors
918ec531-81cb-5a4d-b596-d3fd14430b2a | note | Specification - Technical Specification cl. 9.3
c829d5af-4e61-547c-bd87-a0906cca3714 | note | Verification Activity - Engineer to witness testing and shall be given at least 2 days notice of testing
c8799220-261f-5dd1-80c5-0de872e27eef | note | Frequency - On-going
2ec21b3f-e974-5da4-945d-4e5aeea73ba1 | note | Acceptance criteria - Conform to Contract requirements
b647b262-e6b9-5fe3-8367-7f9068786b90 | note | Inspection Type - Hold Point
8c067473-a5de-5bc2-8a97-e028ec7ed982 | note | Assessor - WSP
fbf676a6-8e57-507c-9ab1-81007e89b5b8 | note | Reports to be delivered - Verification
bcef7b38-90eb-5a8a-8bf2-92d2ba5ec2bb | note | Responsible Person - Currie
9fd7e4ea-bf56-495e-b48a-d42ff8119764 | signoff | HOLD POINT
e2a0afdd-f3c1-4400-8108-2836584918ee | checkpoint | 8.10 - Grout mix design
6e41c91c-9fad-5648-8380-34a75ee68dc8 | note | Specification - Technical Specification cl. 9.7
3394d178-2cf4-5199-a12c-7f329f6d18dc | note | Verification Activity - Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting
6dc205d2-b4eb-5bc8-876f-f01d3055252b | note | Frequency - Once
e9f1f46a-58d6-5c86-929f-32c837bcb183 | note | Acceptance criteria - Conform to Contract requirements
160e08ca-9412-578c-a8ea-dd4d9e4f9323 | note | Inspection Type - Verification
a4f509fc-41e1-5f85-ad82-c1ee1e68b320 | note | Assessor - Project manager
630b55ac-345b-501a-b595-cc8edab03e72 | note | Reports to be delivered - Detailed records
ab7790a0-5b04-5845-ae62-cf0127cd1740 | note | Responsible Person - Currie
bb3b3d31-c51e-461f-b5e8-7d6228e73e17 | checkpoint | 8.11 - Anchor grout
98d646f3-aa23-5c7a-960b-aebe35edf98c | note | Specification - Technical Specification cl. 9.3, 9.4 & 9.7
41f1cf92-5ab5-596a-a516-16b2e1bfd859 | note | Verification Activity - 30MPa required at 28 days and 30MPa before testing
a347ac80-a5d8-5551-b2fd-eeb80e2fc908 | note | Methods or reference - 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d
492f5af6-8e9e-56b8-97e1-46c4bbd7bdd3 | note | Frequency - Once
a901d877-5720-5aa7-baf2-75f7a7a3e96b | note | Acceptance criteria - 30MPa before testing & proven with cube test results prior to testing
45fe221c-3e09-57c6-827e-88654d1696c6 | note | Inspection Type - Hold Point
73ad63da-2e06-50a6-b59e-d93fc54a56be | note | Assessor - WSP/Project manager
2f862e2b-c819-5889-9ab1-daf73164237f | note | Reports to be delivered - Detailed report
96813fd8-20c1-5d77-a383-6e2d251d49ee | note | Responsible Person - Currie
0008e9fe-78b5-4393-8648-bebd157d8709 | signoff | HOLD POINT
40af9a48-0ff9-4845-a498-3d54405731bd | checkpoint | 8.12 - Anchor tolerences
ccfc6a90-c9fe-5edb-a885-66790071e83a | note | Specification - Technical Specification cl. 9.6
52bc1a5d-9949-5ed5-968f-0e9183314da1 | note | Verification Activity - Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees
6b01951a-075e-5276-a7fe-c6d9a6c82084 | note | Methods or reference - Tape measure & digital spirit level
e95ee299-4798-5f0c-b439-5d1a90f24135 | note | Frequency - Once
4e25f2f2-453b-5931-a8fe-22fd2cc7b6b1 | note | Acceptance criteria - Conform to Contract requirements
1b483ce8-ac56-5b88-803f-05f7d6e35620 | note | Inspection Type - Verification
6b8fdd34-ec12-5f2a-8e60-ca9604b58bb6 | note | Assessor - WSP
9ea54045-c016-5bbd-8d11-8711a39c529f | note | Reports to be delivered - Site check
b36cae98-5f45-51ad-86bc-5fb42819feb1 | note | Responsible Person - Currie
1a3c1ddf-f846-456d-ab8f-7e1bd89e75f6 | checkpoint | 8.13 - Anchor testing
dcecdd1d-fd28-54fb-9f4b-c7486026aece | note | Specification - Drg C11 Table 2
f510a07f-11f6-52ed-b33d-06b71ad20d70 | note | Verification Activity - Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN & 40/20 bar = 430kN ; Abutment C: 30/14 bar = 220 kN
91dbef35-6064-5649-b671-d413a397ae8b | note | Methods or reference - Hydraulic test jack
7772fb26-aded-5477-b31c-88e7c28bba0a | note | Frequency - Every anchor
18f57f8f-022b-524f-b276-75399d427ee2 | note | Acceptance criteria - Conform to Contract requirements
64eb92e5-c18c-5159-8da9-aa1a5bac1150 | note | Inspection Type - Verification
cc1718a8-7188-51b6-aab1-3b7bc5e1e760 | note | Assessor - WSP
e9f390ea-dfd4-55e3-b137-bb6f1acb6f33 | note | Reports to be delivered - Detailed record
04c89592-b169-5f97-8313-f39ba0bc5d1c | note | Responsible Person - Currie
e8e55f57-4f2f-41ce-bddf-190061ece78b | checkpoint | 8.14 - Anchor bar lengths
4244183f-cac1-5b0f-8006-314987c53d77 | note | Specification - Drg C11 Table 2
6d35c1c2-e3a8-5c7b-b053-a3268ce4308f | note | Verification Activity - Abutment A: GA1 - GA5 = 3.0m unbonded & min. 3.0m rock socket ; GA6 - GA7 = 3.0m unbonded & min. 5.0m rock socket ; Abutment C: GA8 - GA13 = 3.0m unbonded & min. 3.0m rock socket
a149c38d-cd10-5d2a-9e1c-d6f563626509 | note | Methods or reference - Abutment A: GA1 - GA5 = 30/14 anchor at 1.2 - 1.5m centres ; GA6 - GA7 = 40/20 anchor at 1.35m centres ; Abutment C: GA8 - GA13 = 30/14 anchor at 1.2m centres
bd79dac2-5380-57a6-bd10-e168a0860e00 | note | Frequency - On-going
56bae5b8-5b93-5d83-992f-ae4a0ba131a9 | note | Acceptance criteria - Conform to Contract requirements
4d18eb9b-fb6e-55f0-990f-b33c4b84d485 | note | Inspection Type - Verification
a95f1cfa-088c-54f8-953d-5f7448c4b11a | note | Assessor - WSP
4bfccfa9-e1c7-5fdb-9136-2dba675d2b93 | note | Reports to be delivered - Anchor Log Record
55319d00-f7d1-5eca-b9b9-b60d84de237f | note | Responsible Person - Currie
738c47c4-4d6f-43d0-bc2c-4903e79f71af | checkpoint | 8.15 - Anchor bar couplers, nuts & washers
d8cc1912-2830-5485-93b3-3d8e0d67527e | note | Specification - All hot dip galvanized
1093e37c-6e0a-5b25-8ea1-cd32db238034 | note | Frequency - Once
1168f87e-acff-596d-ba2c-88990d012bec | note | Acceptance criteria - Conform to Contract requirements
d815a8ee-f5db-5784-83ca-46679b7da42c | note | Inspection Type - Verification
3529494e-a4b5-5eae-a80e-3e81eccd8afb | note | Assessor - WSP
f21d0a44-6d18-5681-aff1-561af50df0fd | note | Reports to be delivered - Site check
5be72818-56aa-544a-84d2-e12079588639 | note | Responsible Person - Currie
1e230f7d-12ab-48b8-bf8c-b384d6cef3f3 | section | 9.0 - Earthworks
1e21f1ab-e312-4a8c-86ba-b15f2fdb67f9 | checkpoint | 9.1 - Site sourced material
1e8ef7f5-1102-5292-92e9-c0e1165c1bf0 | note | Specification - Technical Specification cl. 10.3
152ff844-88c1-5c67-99f4-92224302c988 | note | Verification Activity - Site sourced to be used for all backfilling EXCEPT for behind the retaining walls
35a073f2-2229-58de-b27a-331b10c18c1d | note | Frequency - On-going
651cce11-831e-5d9c-868b-09e6a9208a0c | note | Acceptance criteria - Conform to Contract requirements
5fa3ff24-d932-5e4e-8a6f-4e6cf08f8529 | note | Inspection Type - Verification
1ff58722-d8b7-5cc5-a2d9-535d3c4292dc | note | Assessor - WSP
118a9cd8-e5ee-5787-9860-00000792aaa6 | note | Reports to be delivered - Visual
45aaf96e-39c6-56f3-ac86-09e232e1b5f9 | note | Responsible Person - Currie
aa72444d-cd81-4343-a9d1-f73bfa17f3d3 | checkpoint | 9.2 - Compaction layer thickness
c910f8b8-2263-5d00-8228-2c34826fb745 | note | Specification - Technical Specification cl. 10.3
45aa27e3-0b43-5d29-884c-a7394a059a8e | note | Verification Activity - Compaction to be in loose layers not exceeding 300mm
26f50ba2-c221-5c7a-a6d5-e9a414ba118f | note | Frequency - On-going
818ec94b-b127-52c3-b1b4-e087084ed672 | note | Acceptance criteria - Conform to Contract requirements
54d1b281-398e-513f-afac-b31e65a34611 | note | Inspection Type - Verification
8ef1ce03-0dc7-54a9-81c6-3b53604f7409 | note | Assessor - WSP
03b842fc-c250-5031-b220-05719406fc5f | note | Reports to be delivered - Site check
dbd7fa7a-8efd-5983-9c01-598992aa137b | note | Responsible Person - Currie
771e72df-06d4-49f1-aef3-5c4bdaedc8a8 | checkpoint | 9.3 - Centre pier rip rap protection
5cf4d222-0bf2-5333-8488-c1dda7874f08 | note | Specification - Drg C01
996d3ae3-c8a3-5321-b259-9a5a430548d7 | note | Verification Activity - Rip rap to be site won
29be5ca1-8bb5-55ac-b279-2f5eeacd9fef | note | Frequency - On-going
7c621035-1822-513e-9d94-840629b39aa3 | note | Acceptance criteria - Conform to Contract requirements
4b6447e6-8961-5536-b5f7-d527c37bebb3 | note | Inspection Type - Verification
1fbe6dfa-c8b5-571b-95a1-186016eb1ea8 | note | Assessor - WSP
022298be-9b5c-56f8-ba85-893b80e12566 | note | Reports to be delivered - Site check
38a98aca-9cf6-5659-a68a-bbf85acccfa1 | note | Responsible Person - Currie
bc4f2fe5-2324-4a86-92ed-9c6e98d671ba | section | 10.0 - COMPLETION
1745dd6b-914f-42ea-8afd-ef7312a68104 | checkpoint | 10.1 - Remove erosion and sediment control measures
a995c141-9ced-5cf4-a41d-c6355ca1d270 | note | Specification - Remove once planting has taken
156756f6-060b-52ad-ba13-6d523cc9221e | note | Frequency - Once
5916697c-3b23-5901-b2bc-ca53a03e1759 | note | Acceptance criteria - According to Environmental Management Plan
994187a1-1556-5402-84c7-ee07a7fc1738 | note | Inspection Type - Verification
68f007f4-ee65-501e-ae3a-a271d492f20f | note | Assessor - Foreman
2b649df6-8d43-5810-8974-59c471915e17 | note | Reports to be delivered - Photo
5a414766-9cb6-527c-90be-f29c4eb12ac2 | note | Responsible Person - Currie
e4051018-a105-4af7-9f8c-6bde6721bf89 | checkpoint | 10.2 - Remove Traffic Control
045e8a80-e6f0-56a7-9f80-403f870cffa5 | note | Specification - Safety
307880bb-a96c-5ed7-b94c-1d9f921746f3 | note | Frequency - Once
7bfc9565-be17-5a2d-a3be-a41921a144d3 | note | Acceptance criteria - According to TMP
3b941baf-9dc6-5f89-b35d-6969a08562cc | note | Inspection Type - Verification
cb897190-5fab-571d-9fbf-61843d6c7456 | note | Assessor - Supervisor
dfb1e8f2-7e01-56de-975f-9faa2befa9a3 | note | Reports to be delivered - Photo
3139bdbe-5456-5fab-9772-388e010b154c | note | Responsible Person - Currie
e451a268-6498-4316-a3ed-278076d761ca | checkpoint | 10.3 - Site maintained in a tidy state during construction
c59cc96d-4f08-52b6-98da-93989d44eccd | note | Specification - Best as is reasonably practicable
b6a2d97c-c071-5699-ad2c-02f37f7c7124 | note | Frequency - Daily
4dafdf82-db08-54ca-aff6-a358144357a3 | note | Inspection Type - Verification
adf621b3-c797-50f1-99c0-17d4d3136014 | note | Assessor - Supervisor
c1e2b72f-149a-50c8-945a-25612bc3e943 | note | Reports to be delivered - Photo
645827e5-bcca-5f4f-af62-806ed3622127 | note | Responsible Person - Currie
e423c3cc-3b00-4347-9b37-f193da589f08 | checkpoint | 10.4 - Practical Completion Inspection
915e4ff5-259c-5b3a-a49d-44f60c23daed | note | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a)
aa810b51-2314-5073-92ab-a73af05bb353 | note | Verification Activity - Engineer to inspect site on completion of physical works
79f990ea-e0d9-5d5a-972d-bcb5de606505 | note | Frequency - Once
ad08b103-2bc1-5551-b984-43af8659e2a5 | note | Acceptance criteria - Supply as-built drawings & PS3
a6e97442-2003-53a5-b1ab-25c9ada141bc | note | Inspection Type - Hold Point
5f772f2c-0130-54cb-86a7-39b0403e4935 | note | Assessor - WSP
e57829b1-b4af-558f-b909-4feafdda4c63 | note | Reports to be delivered - Inspection record
7a7bbb89-2d39-59ed-a428-d553d0a95c1b | note | Responsible Person - Currie/WSP
7176c6bf-4b19-4f7a-aa43-804c03e23c4a | signoff | HOLD POINT
bafa6704-852f-4e2f-b74f-e2d248d5cae7 | checkpoint | 10.5 - Inspect site 12 months after completion
e2f8d8b8-c781-5166-99f1-754fd08c0c09 | note | Specification - Remedy agreed defects
bb7712e9-28a4-5693-b74f-c288006ce768 | note | Frequency - Once
278ce9e8-695c-5d64-a152-0e76bc308a86 | note | Inspection Type - Verification
04d43f1e-9e65-510b-8253-83f5e81b576d | note | Assessor - WSP
6973925c-2fc3-5c7c-94c4-58dd671aa09a | note | Reports to be delivered - Site Inspection
b35742d1-6f1b-5006-9c75-533531cc737d | note | Responsible Person - Currie/WSP
fcb57c0f-818e-48d4-8b57-3f2f4c0e6e59 | checklist | ITP - Mangaheia No.3 Bridge - Tauwhareparae Road RP17.7 | itp | ITP - Mangaheia No.3 Bridge - Tauwhareparae Road RP17.7
0a843131-5f5b-4925-8525-d22e8a15b61a | section | 1.0 - DELIVERABLES
4ad3ac4e-2977-4e24-950d-aeb305e05f06 | checkpoint | 1.1 - Prestart handover meeting
aa09a869-fb61-5ebe-bd94-018d445dad20 | note | Methods or reference - Meeting agender items
86f36228-0e0f-5cfd-8305-94f770654e15 | note | Frequency - Once
e626e1c7-a89e-521d-a51a-27374e1f6710 | note | Acceptance criteria - Prior to commencement of physical works
0b50ab37-8e1e-5fb9-978d-806dde65b512 | note | Inspection Type - Internal meeting
4d99e9ee-5f08-53a6-bbd3-99399fc0a299 | note | Assessor - Project Manager
36cf8e8f-6671-52f1-bbab-860e9c1d6b88 | note | Reports to be delivered - Attendance record
14b89fa7-90e0-5b0e-8684-5baf75a8e683 | note | Responsible Person - Currie
c6d73862-5426-47c1-b0b6-09140d21f4ec | checkpoint | 1.2 - Construction Methodology
e1b7f2a2-42ce-517c-97bd-b01e7ec9f152 | note | Specification - Letter of Award
042ebbd8-cf35-5950-9c3e-2df1fd1aff03 | note | Frequency - Once
1eeed441-7642-553c-ad29-a671fc7e0824 | note | Acceptance criteria - Approved by ER prior to commencement of physical works
bc58334a-19f7-574a-a903-b3170e753d52 | note | Inspection Type - Hold Point
8ef98bfe-c112-522a-939a-b18042543cba | note | Assessor - WSP
9bb576b7-d5da-5d76-8573-8d4c9db49e76 | note | Reports to be delivered - Detailed record
bb175afb-6fa6-5283-8618-622b3fbc87e2 | note | Responsible Person - Currie
5f9c00cb-4ded-456e-81e7-e21b1e3d00ac | signoff | HOLD POINT
c9960c29-78e5-42b0-937c-395b475c9bc2 | checkpoint | 1.3 - Construction Programme
621e238e-5d4a-512e-927e-0f245d5ce4b3 | note | Specification - Special Conditions of Contract cl. 5.10.4 and Letter of Award
a473a317-22b3-503d-a723-9c7dc0eeb1e2 | note | Methods or reference - MS Project format
432af225-7c62-5825-949a-d4995bac41dc | note | Frequency - Updated weekly
e66cbadf-e2cd-52f8-8595-7e65d956e87c | note | Acceptance criteria - Conform to contract requirement
452476b7-2682-5d8e-8e8e-372d4ba01f97 | note | Inspection Type - Hold Point
324c636f-8d1e-539a-9ac4-aacbaa0f8d03 | note | Assessor - WSP
f32fc6e1-e193-58e4-991d-73579cfcfb23 | note | Reports to be delivered - Detailed record
7c8731fd-ecd6-5405-a77e-c07b07675481 | note | Responsible Person - Currie
29ca043e-c439-4abd-8bd0-a65a47a75bc0 | signoff | HOLD POINT
413ec2df-298e-4890-91aa-0609f4f149f0 | checkpoint | 1.4 - Site Specific Risk Assessment
efed5063-2502-52b2-bdbd-f49ef0efedf2 | note | Specification - Special Conditions of Contract cl. 5.17.1
640c9ee2-7b22-5f20-8ba3-a8814273ca7c | note | Frequency - Once
d6eee4e5-5452-55ab-9830-dc03f546df47 | note | Acceptance criteria - Conform to Contract requirements
697f1e2b-a0fd-597c-a16c-149741ae3148 | note | Inspection Type - Hold Point
39ec572b-361e-51f2-85d7-e6947258b434 | note | Assessor - WSP
5acbd339-ccca-5013-ade5-89f17740ebe1 | note | Reports to be delivered - Detailed record
253de00b-4691-5bce-a65c-afa7ed851d92 | note | Responsible Person - Currie
b156cf73-ee4c-4ee1-a637-15a44908e679 | signoff | HOLD POINT
e49dbf8f-8dd9-46e9-b837-856d34eabb4f | checkpoint | 1.5 - Health & Safety Management Plan
5a6df5a6-dc96-5240-8011-b7b19acd78bc | note | Specification - Special Conditions of Contract cl. 5.17.1 and Letter of Award
d727c3e8-7935-5d39-b4ae-2a2b4058b313 | note | Frequency - Once
1c1d1d8d-b3e6-50f3-a286-16379aa6042d | note | Acceptance criteria - Conform to contract requirement
29b47202-d940-52d7-896b-6b07bd356699 | note | Inspection Type - Hold Point
420857f7-0a83-5f70-882a-d6e393288a71 | note | Assessor - WSP
d7b502f3-db90-57f5-92e1-c280ac61fe92 | note | Reports to be delivered - Detailed record
7daab2db-4fc0-5ace-8474-630ddcb96bc4 | note | Responsible Person - Currie
d425ad78-19d1-44a8-92f1-52f11b3c184a | signoff | HOLD POINT
7007eea8-22b6-4512-a410-0dbb4cc1d3af | checkpoint | 1.6 - Monthly Health & Safety Report
a210853f-3749-5d81-93a5-c6cfa4b941ac | note | Specification - Special Conditions of Contract cl. 5.7.15
01bef1f8-fbde-5909-ac35-c10d36af4436 | note | Frequency - Monthly
03b481b4-9b3b-5e18-a246-5de099f5b809 | note | Acceptance criteria - Conform to contract requirement
50c58a20-ccf3-56ea-b756-f0e554e03510 | note | Inspection Type - Verification
5520d2fc-77ce-5c54-8c69-f6e9f47c611a | note | Assessor - WSP
12f33cca-6560-567b-9a0e-0c2d6150039e | note | Reports to be delivered - Detailed record
de06713e-0350-55e2-9add-953d4c408237 | note | Responsible Person - Currie
8abe8d8a-5934-42ee-af7d-2e15dbac5f36 | checkpoint | 1.7 - Quality Management Plan
3dc30e85-2e46-5afe-92bd-344966b87ae2 | note | Specification - Special Conditions of Contract cl. 5.18.1
ced19035-12ef-5902-b426-f5b6dc10b403 | note | Frequency - Once
8805049f-e0b2-5b50-b874-a10598d4bc35 | note | Acceptance criteria - Deemed as submitted under Panel Agreement
21fad457-3ef3-5d96-af31-1ff2e5a62b83 | note | Inspection Type - Verification
098d93f0-12d2-56ac-84e9-ec7939953c8e | note | Assessor - WSP
b40232fa-8a2d-5c8e-a488-65a8469c70e4 | note | Reports to be delivered - Detailed record
9f9c6d08-47d6-58aa-bb42-fdfe3ba3b002 | note | Responsible Person - Currie
9e48e2de-3245-4afc-a6a3-c6b2410c0cae | checkpoint | 1.8 - Enviromental Management Plan
ab293b8e-f48d-51e7-ab84-f2f11e269d5c | note | Specification - Special Conditions of Contract cl. 5.22.1
e389a39e-0890-5f14-8306-412d03123b64 | note | Frequency - Once
cb68ea31-6dff-5636-96f6-3bd659ccf1ba | note | Acceptance criteria - Deemed as submitted under Panel Agreement
f0818415-5f61-557e-b066-4e2b2b9c7830 | note | Inspection Type - Verification
f5f68d71-40fe-520b-8e59-938926ce1328 | note | Assessor - WSP
5d7723a1-f47f-5213-9797-016dc202fdfa | note | Reports to be delivered - Detailed record
0390597d-2bf9-5a0a-9a0d-f39c5307d8ca | note | Responsible Person - Currie
c49027eb-3299-449d-8f43-fe1cab33f9c8 | checkpoint | 1.9 - Erosion & Sediment Control Plan
c6f969a9-5208-524b-9067-badca154e4c9 | note | Specification - Letter of Award
7de3c6ef-4e23-557d-bb47-4e25bf84a7ab | note | Frequency - Once
3fe6b5b1-357b-51b2-9159-625fadcce56d | note | Acceptance criteria - Conform to Contract requirements
c5bad726-c8a6-5ca4-94b0-dbbf51a24ede | note | Inspection Type - Hold Point
8d25cc8b-29f1-5a66-bac1-ccdfc07947fe | note | Assessor - WSP
e4660c09-c464-566b-b0bb-f69c25c5a1aa | note | Reports to be delivered - Detailed record
cb265d40-873a-5cd2-8237-ca45d0b88010 | note | Responsible Person - Currie
91383a36-a2f7-47ec-9ccc-1ce4675755c1 | signoff | HOLD POINT
c889a407-3ef8-4e0f-8ed2-1e27943fd983 | checkpoint | 1.10 - River Based Access
c09fd8d7-dbdb-5b2f-b179-be645dda701b | note | Specification - Technical Specification cl. 1.12
900ae209-be18-5b83-ba8e-2bb021238196 | note | Methods or reference - Contractor to provide proposed access method
ad99f82d-7c09-53e8-895a-ef41ea85ffec | note | Frequency - Once
d15591ee-df11-5f48-a3ec-b056abd264eb | note | Acceptance criteria - Conform to Contract requirements
ee3d7248-ac18-5ea7-a8b9-53a10454f27a | note | Inspection Type - Hold Point
da45a072-5c0e-5124-a23d-f89809b9cef6 | note | Assessor - WSP
e26792a5-97b1-57fa-933a-cb0d211b210a | note | Reports to be delivered - Detailed record
4a1ffbde-1ab4-5a55-b3c0-887637443da9 | note | Responsible Person - Currie
34b103f8-920d-4953-97ae-bfda781d8899 | signoff | HOLD POINT
59ef0f81-efd6-4b4e-a62b-f24c3d74bb1f | checkpoint | 1.11 - Building Consent Expemption
b60b650a-c397-5c66-aa68-a183dfb852ca | note | Specification - Special Conditions of Contract cl. 1.5.1
230a03ad-5142-5c84-ad6b-42fc5e57737b | note | Frequency - Once
6e1f7ef2-d0e9-5fc3-86ee-2fde28f954ba | note | Acceptance criteria - To be provided to the Contractor prior to construction
3d8eb6d7-2d73-59fa-996c-f203a2952ffc | note | Inspection Type - Hold Point
ce7b071e-4c97-5034-8c73-aecffad75955 | note | Assessor - WSP
0cc968a2-d4a8-5925-98b8-eb7605da7009 | note | Reports to be delivered - Detailed record
9b58bc9f-fb60-5b72-bb8f-7142b2025c07 | note | Responsible Person - GDC
5b1ac868-f88a-4588-af86-beaa458858c3 | signoff | HOLD POINT
519064b4-c06b-4f37-9609-56d66b109d30 | checkpoint | 1.12 - Traffic Management Plan
82a93370-eb3b-584b-91a8-0963cea01889 | note | Specification - Special Conditions of Contract cl. 5.19.1
1e9223c5-3a22-5beb-aad9-b90c00bb9265 | note | Methods or reference - GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added
90b1bcd9-1d74-54ee-8610-0cbdb5ec9bb5 | note | Frequency - Once
3d7fc008-7a2a-594d-b70d-df1fa95665a0 | note | Acceptance criteria - Conform to Contract requirements
4225b443-2666-5733-98e7-9c1ef4827849 | note | Inspection Type - Verification
54ab141f-3228-5e94-8b3f-cc968d4c0e78 | note | Assessor - GDC
2fb61330-28d0-547f-8053-e70d0f6f7cbb | note | Reports to be delivered - Detailed record
6964fe97-ee46-5bbb-907b-ab667a93fb1d | note | Responsible Person - Currie
73972674-6570-4d91-83ac-3d03c539394a | checkpoint | 1.13 - Bridge Closures
9e69aa77-49f6-53db-a22d-883563e468fe | note | Specification - Technical Specification cl. 1.8
a38b4efc-8515-51ee-802b-862ec2780f70 | note | Methods or reference - The date and duration of any closures to be agreed with the Engineer
2d5fc350-c71d-51a4-a85f-525005fb56c2 | note | Frequency - On-going
d2cd991b-b2ab-5ea5-9308-47de27fd55ce | note | Acceptance criteria - Conform to Contract requirements
ab3be8a8-7d50-5d73-aa3f-5812f469db47 | note | Inspection Type - Hold Point
4f53d883-ffda-50ba-be2d-2c6040e86add | note | Assessor - WSP
c04abae5-769c-535b-9e41-dccf21c2b148 | note | Reports to be delivered - Detailed record
b8b776f9-c116-5563-bb48-c412b1052ac1 | note | Responsible Person - Currie
408e64cd-1545-4a7e-8c22-4c1efa64d900 | signoff | HOLD POINT
4c22684f-6e9d-4086-806e-70baa7d81b81 | checkpoint | 1.14 - Proof of Insurance
ffb661e9-6a1c-51e1-9999-00da55da1443 | note | Specification - Special Conditions of Contract cl. 8.1.1
856352ea-60f9-5194-bdb2-9863fc5628db | note | Verification Activity - Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability
5eec29d8-5bc5-52e4-98df-626cfca92d9a | note | Frequency - Once
358f52d1-8611-565e-9962-121f47c5b5f5 | note | Acceptance criteria - Conform to Contract requirements
a535bb3f-1b9c-5858-8c24-a721d97717cf | note | Inspection Type - Hold Point
665c2bd7-cf07-5aa1-a3f7-682784c3b6b5 | note | Assessor - WSP
11452a81-3777-529b-8b8f-d0e79d5a73bd | note | Reports to be delivered - Detailed record
d0abcc04-38bc-5705-a7b8-62f8c702d457 | note | Responsible Person - Currie
39a07374-f734-410f-b716-7148886a8455 | signoff | HOLD POINT
63bdba46-4aba-469b-aa19-9628344ba880 | checkpoint | 1.15 - Service Locates
4fbccfce-264d-5273-95f3-71cd263422cb | note | Specification - Technical Specification cl. 11
7a4a21de-0d4f-5ca8-8fb2-245231df4f52 | note | Verification Activity - Service providers including Before You Dig & close approach agreement
5e3e3d3f-b287-5c08-8e13-731523a6b413 | note | Frequency - Once
1bd82364-2298-53eb-8b44-55d54cb346fb | note | Acceptance criteria - Prior to commencement of physical works
df5de724-a893-560d-aeb2-8bafe69d3cd0 | note | Inspection Type - Verification
3b809b32-a148-5eed-a42b-869f489d43ac | note | Assessor - Foreman
fb0ebf52-fa6b-5b59-b34b-e59a7a87be88 | note | Reports to be delivered - Service details
a3d893d3-5804-5cab-8968-6f6fa10ddc6f | note | Responsible Person - Currie
eecdb8bf-51fe-470d-b208-2f7d748ae8ea | checkpoint | 1.16 - Dimensions and set-out
17cd7ef8-8897-57d0-a631-9a9a354c7c69 | note | Specification - Technical Specification cl. 1.11
7fb29879-f237-50b2-b8f4-67d61b17b8ab | note | Methods or reference - Contractor to confirm set-out and dimensions with the Engineer on-site
a9541a2c-2021-566d-99c2-c85024569335 | note | Frequency - Once
0087b81a-a5f7-550a-a4c6-fb126ab52845 | note | Acceptance criteria - Prior to commencement of physical works
471bc7a7-b1cc-5575-8f09-ebce9e0daf1a | note | Inspection Type - Hold Point
035d89ae-b9c6-5a5d-936a-4062cfd61748 | note | Assessor - WSP
6a8a7229-6c45-50df-88c8-b2ffbf1d909f | note | Reports to be delivered - Verification
9d823142-aa5d-502a-b406-a1e79a9f58bf | note | Responsible Person - Currie
16f03540-b032-4614-be81-2d71d64684ce | signoff | HOLD POINT
4dd5698f-7443-4290-a4fd-45b86c901f21 | checkpoint | 1.17 - Clearing of Site
d1ba513d-999e-513d-b2a2-e48ac6b0c514 | note | Specification - Technical Specification cl. 1.13
4ba1ca3d-945c-5d6c-939e-9f2beda60dd9 | note | Methods or reference - Contractor to agree with Engineer the extent of the clearing
ed6f2fe6-0666-540e-91bf-fe0b84a14850 | note | Frequency - Once
bd3e9b42-f586-583e-969c-4b6cac1498c3 | note | Acceptance criteria - Prior to commencement of physical works
910094a1-274b-57b1-a41e-c1d3fbd16ce3 | note | Inspection Type - Verification
2802b4eb-0ee3-585d-bc6a-c2443bbc4b20 | note | Assessor - WSP
9d522a19-dedb-5250-992e-708f7f71765c | note | Reports to be delivered - Verification
bd12be0b-78ad-5088-87a1-f0d6b80e19d7 | note | Responsible Person - Currie
3894a2da-30f6-4ba1-9cac-15ac26032c34 | checkpoint | 1.18 - Earthworks
98c48eda-c41c-539d-b4ba-43f3c523c425 | note | Specification - Technical Specification cl. 1.10
47778576-3da8-54cd-9b9f-63fd6c33c83a | note | Verification Activity - Contractor to submit excavation & compaction methodology to the Engineer
256f77e0-08b7-58d1-a916-709ce9cb5502 | note | Frequency - Once
c79fae8d-40fa-5799-b815-99fe173e8079 | note | Acceptance criteria - Conform to Contract requirements
dd73d1fd-b4a6-57b2-adc9-4c48b4f0d769 | note | Inspection Type - Hold Point
43d0423f-8f29-5082-9358-ae866ef3bd2d | note | Assessor - WSP
4518dfd9-0386-5a99-83f1-3b85e6646110 | note | Reports to be delivered - Detailed record
949bdc34-db01-5c31-aed9-ed5bde989046 | note | Responsible Person - Currie
62ece9f8-decf-471a-98d5-dde467aea213 | signoff | HOLD POINT
fbb7bb4b-5de9-4eaa-98e9-b27b54770c74 | section | 2.0 - Materials
4822be96-8875-4951-a5d8-95e44b6b3bcb | checkpoint | 2.1 - Nuts, bolts and washers
e737834e-76fe-5cba-b08d-b96e56671981 | note | Specification - Technical Specification cl. 2.2
54a32d15-5a84-50e3-8d38-53ab24110019 | note | Methods or reference - To be Class 8 & HDG
5a6e91f7-ac3e-57fa-b786-bf45d326e255 | note | Frequency - On-going
94b5f55b-c4db-5bf9-be2e-f29a7fc4d100 | note | Acceptance criteria - Conform to Contract requirements
dcfd9825-fef2-5ebf-87e7-de95c7624253 | note | Inspection Type - Verification
f61ac75e-066f-5464-93ca-b99e1d408fdf | note | Assessor - WSP
4d9652e7-b7f5-5a3f-9318-93719c84e958 | note | Reports to be delivered - Supplier docket
04bc06d9-bca1-59eb-897a-1e14a7140358 | note | Responsible Person - Currie
d73219ea-f7a4-430c-b304-dab390dba277 | checkpoint | 2.2 - All Steelwork to be Grade 300
410fda1f-98c6-516d-8a48-9bb04ae28b9d | note | Specification - Technical Specification cl. 2.3
dab28e8d-617d-59d2-831b-6856b6e2800f | note | Verification Activity - Mill certificate
22239a52-3106-5197-b60a-9605ce4481f5 | note | Frequency - Once
621a04c7-4205-58d1-9007-1654722e9f49 | note | Acceptance criteria - Conform to Contract requirements
46a1cd4a-8aff-5aba-8e27-a536522c2c63 | note | Inspection Type - Verification
5900460c-3d21-5280-82e1-fcbfa1e0c009 | note | Assessor - WSP
0dcc45b3-26b7-5ea4-a481-82bc7cdf3a08 | note | Reports to be delivered - Detailed record
3d2b48d6-43ac-5c64-82c9-e8e1c90f1088 | note | Responsible Person - Currie
d17b7ff6-07a4-4e64-9871-cee17a2600dc | checkpoint | 2.3 - Concrete for steel post footings
d6dad406-dd1e-5ffc-9faa-920c16c15a8b | note | Specification - Technical Specification cl. 2.4.1
48c110fe-9b88-56ab-ad59-c9ee602c0502 | note | Verification Activity - Contractor to provide concrete mix design
a6255300-7376-5cf2-8dab-afde6db76281 | note | Methods or reference - Concrete to be 30MPa
31a707c9-b81b-5344-97a6-fffc0ca04730 | note | Frequency - Once
e7d413f1-a985-5eb1-bfca-7a513d79d2ee | note | Acceptance criteria - Conform to Contract requirements
c09d668e-f137-5eef-a07b-5af2e2242c51 | note | Inspection Type - Hold Point
65f58530-ae80-519a-a99a-af393a42eb71 | note | Assessor - WSP
d1cd22ef-fbb4-58bd-9667-46891cf65c70 | note | Reports to be delivered - Detailed record
cfc6dd8b-b677-5a0b-83f3-717d2e3be67b | note | Responsible Person - Currie
f8dd4430-af11-4816-8e08-741926bf3cf7 | signoff | HOLD POINT
251fff20-5527-4726-b21d-2a267219c5b0 | checkpoint | 2.4 - No-fines concrete
04a4e8df-da0e-5bae-ac32-3a54a21af4aa | note | Specification - Technical Specification cl. 2.4.2
aee10832-8be3-518d-ae25-e184124034ca | note | Verification Activity - Contractor to provide concrete mix design
440b6efe-3d05-5d7c-a918-20b718ebd59d | note | Methods or reference - Concrete to be 7.5MPa
dfecb626-e752-5ffc-a519-7f2be084cbd6 | note | Frequency - Once
25fcd8c3-44f4-5008-ba0a-6322aafe436b | note | Acceptance criteria - Conform to Contract requirements
f47dc4d5-c836-5c49-ac7f-637cc26a4483 | note | Inspection Type - Hold Point
9c623b13-b348-571d-8e17-7ae312436a41 | note | Assessor - WSP
5b977a93-358a-5e83-a3bd-197c1e3a3ff6 | note | Reports to be delivered - Detailed record
1c46f099-3a82-56a1-b8a1-5106e9b365d1 | note | Responsible Person - Currie
636d9dd1-f362-4604-acb9-e094153b19c1 | signoff | HOLD POINT
500cff2b-ed7e-4212-beb8-19a6ca244082 | checkpoint | 2.5 - Timber lagging
9b06e571-6412-5069-8381-0aa9fd65b33c | note | Specification - Technical Specification cl. 2.5.1
c31df741-b2dc-5edb-a576-f4fa89581a45 | note | Verification Activity - Visual
a3d1c80f-10ac-57b4-a798-b2818bf56019 | note | Methods or reference - To be SG8 H4 with cut surfaces treated with Metalex
7b4670a4-8f5a-58a7-8f47-ab977bef76bd | note | Frequency - On-going
45bdc781-99a3-5039-861a-37d8d82c567b | note | Acceptance criteria - Conform to Contract requirements
a58aa7bb-5dde-5687-acc2-bd2bb190e288 | note | Inspection Type - Verification
dc476ba9-f8ed-5c08-82a8-6a778f627dd0 | note | Assessor - WSP
a35d7861-c017-5b3b-bd4f-c9c0456a7e29 | note | Reports to be delivered - Supplier docket
1079b2b8-4bcf-5630-b216-01ea90c3cfcd | note | Responsible Person - Currie
513feef1-e44d-42ef-88ae-38b7e204cc2d | checkpoint | 2.6 - Timber lagging fixings
7451408b-b974-599b-8fc7-1e743bba288e | note | Specification - Technical Specification cl. 2.5.1
a778e890-207b-5e6b-a9d3-32927dee8e07 | note | Methods or reference - All fixings to be stainless steel
d3cb28ea-6928-5b1d-9dc6-b1327457c46f | note | Frequency - On-going
26f88d34-d263-5dbe-ab87-936379d98986 | note | Acceptance criteria - Conform to Contract requirements
c874c632-a5d3-5ed4-b98b-e5391f903eba | note | Inspection Type - Verification
5d709e5c-8147-5991-8262-c6f23a70d7ed | note | Assessor - WSP
7efe7354-d3aa-5d23-80f9-2f89fe3ca851 | note | Reports to be delivered - Supplier docket
638fb374-d9be-56ce-bef9-42028e3f755c | note | Responsible Person - Currie
9919d93d-873a-404f-a888-848cb462748a | checkpoint | 2.7 - Lagging thickness
16b37005-c42e-5b55-bb9b-98256ca53bf7 | note | Specification - Drawings C03 & C04
6382540b-08f1-53f7-a89c-b7fc4b607322 | note | Verification Activity - Visual
3f08071b-08e2-5a57-8199-58e983a21b5b | note | Methods or reference - Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick
3f52858c-2053-5417-8d6a-a076d4b6f27a | note | Frequency - On-going
76c2edc7-5c2b-5c9d-a163-083d9bff0947 | note | Acceptance criteria - Conform to Contract requirements
7f01edaa-d9f0-5fa9-bbca-963119e80208 | note | Inspection Type - Verification
c44cc0d8-2555-5962-b7a1-ad38d5a1161f | note | Assessor - WSP
ca76754a-c5ca-5bd3-8137-8790a433fdce | note | Reports to be delivered - Verification
d3a95710-f0bf-5c80-a629-58f3697e863d | note | Responsible Person - Currie
f5699130-4c15-43a0-ba23-a4f2da8db093 | checkpoint | 2.8 - Geo-textile
e2f6bf8e-4083-5013-ad86-965249e96bfd | note | Specification - Technical Specification cl. 2.6
6f7e490d-6bb4-5405-b261-1fd4ab759e0f | note | Methods or reference - A29 required behind timber lagging & around sub-soil drain
3a332848-b5be-5d38-be48-78869bf8b805 | note | Frequency - On-going
1252515c-45eb-5c3f-ae45-b35212076940 | note | Acceptance criteria - Conform to Contract requirements
54ec9001-cb03-592a-89cc-15feb2867919 | note | Inspection Type - Verification
ffff7019-644d-58c8-b807-8145dfdb6a4a | note | Assessor - WSP
56889723-aa1b-5770-9b27-234a8b75e7cf | note | Reports to be delivered - Supplier docket
eb17e02c-a67d-5ae7-9c0f-203af513a2b9 | note | Responsible Person - Currie
8148a7ef-f998-436c-bbc0-c8433b9c7199 | checkpoint | 2.9 - Drainage composite
8e3cb073-0091-5a16-9ab8-e1693ec68245 | note | Specification - Technical Specification cl. 2.7
377cf554-f381-5b7c-baac-5486d0313214 | note | Methods or reference - Filtration Class 1 & Strength Class C - laid over batter slopes
211dc450-7655-5a1f-bce2-f405ab42515c | note | Frequency - On-going
8b3cfc77-7036-52bf-ba55-ae79d999d563 | note | Acceptance criteria - Conform to Contract requirements
1d5dcc09-b422-5a85-b4ac-855e389f7582 | note | Inspection Type - Verification
64ea23f4-a95e-58f8-8b5e-777c2eb08828 | note | Assessor - WSP
aff305c8-c80e-5d03-abfc-d21aa90b21a1 | note | Reports to be delivered - Supplier docket
87b6f9fc-c1a4-5a35-bdb9-74d38f1a092d | note | Responsible Person - Currie
980d0ee4-a1c3-41f6-a98c-5f498254f243 | checkpoint | 2.10 - Drainage aggregate
647ea514-d57c-54ad-b90f-c0fcaa7b1c86 | note | Specification - Technical Specification cl. 2.8
631e6f47-0d32-50a7-a284-2384320479bc | note | Methods or reference - Free draining clean aggregate with 100% passing 19mm sieve
3da5ad8d-a1b6-5ebe-80e6-b2ca8e2bce9a | note | Frequency - On-going
0e85afc2-0db8-5df6-a42a-04f71697f1e8 | note | Acceptance criteria - Conform to Contract requirements
f8593696-5bc5-537e-bb04-d151904afc82 | note | Inspection Type - Verification
45789efb-ef24-577b-98b7-4e08a238bcfd | note | Assessor - WSP
8a15956d-5611-54a0-ae18-5bd1a0e971b5 | note | Reports to be delivered - Supplier docket
99d1cade-8309-5436-8add-5a18775d346b | note | Responsible Person - Currie
9eb0efe3-eead-46fc-94be-eecd34d07048 | checkpoint | 2.11 - Retaining wall backfill
7a12f9cc-ce05-58f4-9d58-84bdf61f50d2 | note | Specification - Technical Specification cl. 2.9
7151412d-783f-563b-9a02-8e811f09067e | note | Verification Activity - Contractor to provide concrete mix design
6aa6a47f-a0b1-5324-91d1-ea7bcab0bfc5 | note | Methods or reference - Sand & cement mix with strength of 1MPa & slump of 350 - 500mm
74944f02-348f-5b21-ab42-31b068144de2 | note | Frequency - Once
baa80046-8898-5f88-8fe3-e99e6e2fb001 | note | Acceptance criteria - Conform to Contract requirements
6aae6c69-5ab1-5728-ba8b-0a702b5aacd7 | note | Inspection Type - Hold Point
7e1c8c18-ace7-5a63-91a0-3d5f6667e294 | note | Assessor - WSP
7fb90201-46b5-5f0e-8a3a-1518ebf5bf5b | note | Reports to be delivered - Detailed record
3c14e314-1474-5ec9-b409-f3c6492cbdd0 | note | Responsible Person - Currie
b2a2f062-d9a6-4649-a662-8bc089447b87 | signoff | HOLD POINT
778acd6e-fa0a-4650-a47c-8c9284c5ec2f | checkpoint | 2.12 - Sub-soil drain
f496b644-fd0a-59cd-9423-e55ea5558913 | note | Specification - Technical Specification cl. 2.10
dabd4aaa-0d28-5d03-a2df-bede229daaeb | note | Methods or reference - 150mm Punched HDPe sub-soil pipe
96878fa9-5376-598e-be41-5cf4a258eaa8 | note | Frequency - Once
c83cc751-ee27-53fe-979d-1728fcb43e24 | note | Acceptance criteria - Conform to Contract requirements
2764d412-0d83-5b1c-8f7d-6aec307fc50e | note | Inspection Type - Verification
1c05606c-5c3d-5f3c-a456-9add6eed08e2 | note | Assessor - WSP
87436515-c647-5fcf-82ec-c461c21a5e88 | note | Reports to be delivered - Supplier docket
3e47f2a2-69bd-5ffb-8a04-69151f411bc4 | note | Responsible Person - Currie
7cfd9155-1935-48c1-a49d-df48b0dd32d2 | checkpoint | 2.13 - Inspection of sub-soil drain
18ed530c-7c83-5251-b73e-1523dfb266d4 | note | Specification - Technical Specification cl. 14
65f73e26-bd29-571a-8976-23f4653d7a88 | note | Verification Activity - Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling
e3f979d2-772a-5145-a813-997d7e43a341 | note | Frequency - Once
748ea78a-5034-5b93-b933-ce31dd9a9382 | note | Acceptance criteria - Conform to Contract requirements
018972bc-d81a-536e-9ce4-b03133829229 | note | Inspection Type - Hold Point
d637d8be-2bf0-53a2-9a63-e669a222d439 | note | Assessor - WSP
d8a65544-9393-5472-9382-1a863598918c | note | Reports to be delivered - Site check
ed679c2e-e86a-5862-a082-faccccecb69c | note | Responsible Person - Currie
64f50c87-7a69-4260-8ae9-7e925cfc77d0 | signoff | HOLD POINT
717293dc-84f6-42dd-a9e3-7f8f5302c2bb | checkpoint | 2.14 - Topsoil
ce8c0f5a-6a1c-565c-8f64-db75cb07c828 | note | Specification - Technical Specification cl. 2.11
de608738-e79f-524a-a187-7e58aae317fb | note | Verification Activity - Visual
e172c518-6c9e-57ed-b87c-11ab1594fd24 | note | Methods or reference - Re-use existing topsoil
7b83096a-1370-5271-aeba-21709a80acfd | note | Frequency - Once
958efa9d-b251-5b42-b48e-5bd613b5fb38 | note | Acceptance criteria - Conform to Contract requirements
3927b7a5-8952-55b3-a6ca-c268d91464b5 | note | Inspection Type - Verification
f07a8dc4-8e86-504a-bf24-32a0f02ebd62 | note | Assessor - WSP
2c2940a6-030b-5379-92d0-d1d9fc4c27d7 | note | Reports to be delivered - Verification
e6e8c66c-aee4-5688-8e9f-aa97aba0d5ee | note | Responsible Person - Currie
bd6a7b19-09f0-47fe-9c39-c048963f5928 | checkpoint | 2.15 - Testing of materials
ca2dd43e-3757-5c10-87c8-26eb6a0d01e2 | note | Specification - Technical Specification cl. 2.13
312c7931-7103-5f23-b24d-f4a04da15c6d | note | Verification Activity - Supplied by the Contractor to the Engineer with 3 days of the activity occurring
c91f00a6-a763-5834-a676-6977a8c969c2 | note | Frequency - On-going
33d21882-3e10-567f-aa57-70da3316af0e | note | Acceptance criteria - Conform to Contract requirements
445efd1a-f03c-5dbc-9ba1-1ace26dd13d9 | note | Inspection Type - Verification
bd52a95c-f55d-57ed-83cb-e6dd4f77fabd | note | Assessor - WSP
721965d3-844d-5e3c-8213-ed19df90c0a3 | note | Reports to be delivered - Detailed record
138ac283-72ec-54f9-9fd6-49b251c73740 | note | Responsible Person - Currie
8d257b66-16c1-402f-bb56-ce9c9ae9bd12 | section | 3.0 - Steelwork Fabrication
7cd2e03e-454b-466c-8b44-ff03a4261c1b | checkpoint | 3.1 - Shop drawings
e8d6a2dc-b2d9-5165-bc76-b051ca32c7ce | note | Specification - Technical Specification cl. 3.2
8eaf70e9-22e2-5613-aa02-ae301950cf34 | note | Verification Activity - To be supplied to the Engineer
1abe00fd-258a-5f18-85dc-4da1669daba5 | note | Frequency - Once
b4d27681-82ec-59a4-814c-24990790dbe0 | note | Acceptance criteria - Conform to Contract requirements
cb391147-f5cd-5add-a3df-c4203d90a8e0 | note | Inspection Type - Verification
66aaea22-26b8-5094-af5a-6b5cb2171d95 | note | Assessor - WSP
1f3beb7d-ba06-5584-b86c-1e46d40a71b4 | note | Reports to be delivered - Detailed drawing
7226ff07-677b-539f-af72-8f84fb76d1c3 | note | Responsible Person - Currie
2fdcba33-63ec-4d18-a15e-375ba5e5aabb | checkpoint | 3.2 - All piles, walers & accessories
6bb87cd9-0d24-5b74-9dc9-39d79f4a174d | note | Specification - Technical Specification cl. 3.2
642e9265-450e-5f3d-8909-7f2fb469f1d9 | note | Verification Activity - To be inspected by the Engineer before installation
b6e81358-8fac-545c-a2f2-29c6ca18d568 | note | Frequency - Once
14b081d3-3438-536d-b34f-1ca7b3467933 | note | Acceptance criteria - Conform to Contract requirements
df437f01-0007-555b-9d03-304d64a49f3d | note | Inspection Type - Hold Point
c588dafa-0772-5b71-8527-67f70bd4e078 | note | Assessor - WSP
df217788-9607-513f-a642-c24aa4a5357a | note | Reports to be delivered - Verification
4af9497e-85ff-50a2-b8a8-0edab4bee732 | note | Responsible Person - Currie
f90f102a-63ea-4736-8a63-fce891a7eeac | signoff | HOLD POINT
ea101681-a038-42c7-83c1-fdeca59e947d | section | 4.0 - Piling
f3c104c6-ae06-4a2e-ba8f-7eb511e7909a | checkpoint | 4.1 - Pile holes
13d13003-a4f7-59ce-b6c0-e78b472bdbb6 | note | Specification - Technical Specification cl. 4.1 drg C04
b6454aad-d7a2-55b3-975b-0563e10f2978 | note | Verification Activity - 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket
7972fb1f-def7-5468-9cd7-c6b3c93b3d34 | note | Methods or reference - Engineer to inspect pile holes before pouring
61496370-7fc8-57f4-bf71-920e7b29934f | note | Frequency - On-going
a2202c43-2426-54aa-9f50-e51959f8735b | note | Acceptance criteria - Conform to Contract requirements
8d4459c8-8a94-5378-9f8b-0fe558ec1232 | note | Inspection Type - Hold Point
fac78cdb-ff9b-5c69-b8fb-4e42cede5084 | note | Assessor - WSP
ba8926c1-18ae-5871-9a6b-acb8113e801c | note | Reports to be delivered - Site check
43ec62d6-d9c3-5626-80fa-a8bc3a813a8c | note | Responsible Person - Currie
da16c1c3-25c4-452a-9837-22f53533ed84 | signoff | HOLD POINT
779cc70d-8f05-42bb-bf36-b80e63e84902 | checkpoint | 4.2 - Pile spacing
a1dabaaf-a0b1-5794-9ba9-b6c728b20d28 | note | Specification - Technical Specification cl. 4.1 drg C03
286fca16-b3dc-54d3-8211-f1df3afa4ecd | note | Verification Activity - Abutment A: Spacing 1.2m centres
cf15ebab-a281-5db8-8898-d4133e92da63 | note | Frequency - On-going
0ba0fd7b-6e92-5b1f-aa39-f45636de1ba7 | note | Acceptance criteria - Conform to Contract requirements
a51beac6-2b39-5225-8dba-eb0df80d04d3 | note | Inspection Type - Verification
8886adbc-f0f5-5fb3-b944-3b6c72edcca1 | note | Assessor - WSP
888c3ff3-4174-53d3-9af4-0dd8dbb7c21d | note | Reports to be delivered - Site check
24a75a58-455a-56c0-a95a-b9461bfc4473 | note | Responsible Person - Currie
b8420d1d-3175-4b81-b06c-0976a1a28219 | checkpoint | 4.3 - Maximum retained height
b756b151-d055-5ae8-b1b2-4fa7190ef636 | note | Specification - Technical Specification cl. 4.1 drg C03 & C11
626dc039-6342-5f8a-a6da-4129c4d32d1c | note | Verification Activity - Abutment A: 2.3m
ee2d51b1-c79d-5764-825e-b470c61956a7 | note | Frequency - On-going
e2edc10e-2907-5e2e-b53e-39f657bf1412 | note | Acceptance criteria - Conform to Contract requirements
962af73f-0a8e-5da7-9eb2-32b486fd7970 | note | Inspection Type - Verification
0c157fae-e18b-5343-b85d-d2d5095d6a72 | note | Assessor - WSP
a66d8ae4-f96e-57af-8434-14acc840b275 | note | Reports to be delivered - Site check
ff82f452-d812-5fdd-9e78-958d25b8c94a | note | Responsible Person - Currie
de9909d7-5fdd-4b6b-8c75-bbdf01a22117 | checkpoint | 4.4 - Pile hole augering methodology
f51d8d7c-47aa-5e4c-b391-0c38e4172217 | note | Specification - Technical Specification cl. 4.1
a09a1a74-3cb6-5720-9ad6-124d74f5d251 | note | Verification Activity - Visual check
6f2a5b3a-3d4c-5b95-ba28-9792d6ecf104 | note | Methods or reference - Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes.
98f47b76-1aa6-53c1-b016-090fa953e438 | note | Frequency - Once
89f809f7-0920-5419-80ae-238b96b521b5 | note | Acceptance criteria - Conform to Contract requirements
f986b9d5-8198-5777-a46c-5aab2096f8a6 | note | Inspection Type - Verification
840668d3-8a04-5d4f-a376-923810b1549f | note | Assessor - Foreman
f4e42bc5-1adf-5bd6-97b8-6f6fd3f5c5d2 | note | Reports to be delivered - Site check
82150d0e-9a07-5104-8dde-8301fc87bedd | note | Responsible Person - Currie
fbab75e3-1527-4181-9894-a644bcde6ad1 | checkpoint | 4.5 - Augered pile holes
51c87b01-0254-5992-b297-002efffe5f6f | note | Specification - Technical Specification cl. 4.2
ba431f46-897e-50f9-a9dd-c8314a9248ab | note | Verification Activity - Pile logs submitted to engineer by the next day after augering
2ae44cf7-c7c8-56b2-a409-56adc68965fd | note | Frequency - On-going
5e9a5507-0572-59f9-9a3c-e38e7a5c29c9 | note | Acceptance criteria - Conform to Contract requirements
0fe77e89-ea10-5575-808e-ec5829385bfe | note | Inspection Type - Verification
6b1b2202-6b69-5ef3-a46d-c7d535de5e83 | note | Assessor - WSP
8b8678c4-de6f-5dc4-8895-fb2eed0d0a21 | note | Reports to be delivered - Detailed record
e09d8fad-cee4-5e03-aab3-d574be8130e6 | note | Responsible Person - Currie
bfd06f47-fa1b-4dd6-9674-632af3b37b6a | checkpoint | 4.6 - Pile hole tolerances
2e510f2f-2160-55e6-b7ee-396a15d74601 | note | Specification - Technical Specification cl. 4.3
d5049972-69de-5a67-b022-30519d1a2021 | note | Verification Activity - Pole dia. +50mm/0mm, hole plan position +/-20mm.
f0de0fe6-b816-5b1b-8609-cd0c10cb2c27 | note | Methods or reference - Tape measure
95597442-ae5c-5eec-81ac-655cedb7345c | note | Frequency - Once
79476870-3186-52b3-8010-3e478af83229 | note | Acceptance criteria - Conform to Contract requirements
31458bb6-c926-58c0-8730-7e50373e7eac | note | Inspection Type - Verification
02de8182-8440-5754-ac0b-24a748c92351 | note | Assessor - WSP
14c113da-7de3-5042-b103-4d36b924710e | note | Reports to be delivered - Site check
d5b42508-fb4f-5d68-b224-b1541c2f25d0 | note | Responsible Person - Currie
a7d2692f-09a1-410c-a561-f3431a245bd6 | checkpoint | 4.7 - UC post tolerances
9a221870-fa6b-5181-9284-6646fa009305 | note | Specification - Technical Specification cl. 4.3
058f4741-3a66-59e7-8b01-a4132c0286f2 | note | Verification Activity - Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm
0ae03af2-5ea5-52bb-852c-db32e020fc93 | note | Methods or reference - String lines and tape measures
34103ff9-dc06-58bc-835d-af8b6d0a4053 | note | Frequency - Once
6351a2a3-3a13-5983-8b7f-a7ebf1a8122d | note | Acceptance criteria - Conform to Contract requirements
2a411abc-3e6c-5551-819a-927172ffb0d4 | note | Inspection Type - Verification
c3cfc246-4795-55c9-b87e-4a49bbe3c608 | note | Assessor - WSP
ab815d56-6910-52eb-acc9-db70930e81e4 | note | Reports to be delivered - Site check
c55c1f78-b3e3-5138-8430-993983438eef | note | Responsible Person - Currie
855076db-8c5d-44dd-a376-37fd6a299567 | checkpoint | 4.8 - UC post size & treatment
f5a458e8-9d5e-563a-a1b1-08906ee3cf0f | note | Specification - Drg C03 & C04
66cdd400-4733-5e9c-ac03-3bce497df709 | note | Verification Activity - 150UC30 ungalvanized
8aa42045-438d-5ea2-92a0-3c5d35da72a6 | note | Frequency - Once
92a73bfc-5264-5aa8-ae1d-bdfe99201d82 | note | Acceptance criteria - Conform to Contract requirements
9da51925-0c7d-58d1-bd75-a278592a5309 | note | Inspection Type - Verification
88a0e584-d8a8-59c8-9035-89f622b116d1 | note | Assessor - WSP
504e692d-6453-5877-9fdb-1989b13c87ea | note | Reports to be delivered - Delivery docket
0cb2eebd-6b50-50e5-b20d-b590be734213 | note | Responsible Person - Currie
f8be2908-653a-4730-a0fb-fbb640fca2c6 | checkpoint | 4.9 - Concreting UC posts
3b56e8c6-3f5f-569f-b529-d4f498f03e77 | note | Specification - Technical Specification cl. 2.4.1 & 4.3
374ee008-81ee-5cbe-8743-d95468df423c | note | Verification Activity - 30MPa concrete
e4a045df-b2b3-5e44-9838-35fdfec91082 | note | Methods or reference - Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer
c2845ef2-d413-57fa-a636-50c801be0d23 | note | Frequency - On-going
d8211e49-df01-59f4-af52-40bddd1b4e83 | note | Acceptance criteria - Conform to Contract requirements
c267be37-5e15-5e5f-8cb0-249a8c7ed196 | note | Inspection Type - Verification
9a874b31-0b32-5b41-a2c2-bbb2d08c80cb | note | Assessor - WSP
f79c763a-14d8-50c2-8880-cb238e2a7dd1 | note | Reports to be delivered - Detailed records
e91a504b-5d97-5c36-8018-965517ed3c91 | note | Responsible Person - Currie
fd1b82de-8b20-40cc-8e54-92ed000b5c96 | section | 5.0 - Welding
c407f628-85db-4997-9165-3a375f4598de | checkpoint | 5.1 - Welds
1cb8bbcb-dd75-5a42-902c-4634432925d5 | note | Specification - Technical Specification cl. 6.1
8466ba2b-b957-5d44-9d67-352b297197ed | note | Verification Activity - All welds to be category SP
c9c1e461-cbd3-530e-9731-711ad2483b4b | note | Frequency - On-going
50bae4b5-447d-5108-85d4-f05b9950bb1b | note | Acceptance criteria - Conform to Contract requirements
0fc672fa-7b5f-56fa-a392-499c0aabb5e1 | note | Inspection Type - Verification
990cf6a3-f134-50ff-9ee2-b1f8a44fe007 | note | Assessor - WSP
e1e7942f-37a8-5587-8bd6-a4b41e377d7a | note | Reports to be delivered - Site check
b63c61d2-52ff-5526-8469-df0504de92cb | note | Responsible Person - Currie
758798a8-ae49-490f-8018-03149cf011b9 | checkpoint | 5.2 - Welder qualifications
5262e86f-be14-5e56-a8a3-c13902089626 | note | Specification - Technical Specification cl. 6.1
af379f29-c809-58cc-9b06-0c4614ba357f | note | Verification Activity - Welder qualifications to be submitted to the Engineer for approval
953a25ef-7504-5646-8f72-795735861e96 | note | Frequency - Once
1e35688b-a09a-502f-b8dd-5e565a58d659 | note | Acceptance criteria - Conform to Contract requirements
cb4e9c3b-cd3f-5c94-b037-d297042a6ca4 | note | Inspection Type - Hold Point
b8bde779-b24d-54f0-be93-c4664c5bd14a | note | Assessor - WSP
9288ab3c-3f40-52e9-95d2-56facbfa48f2 | note | Reports to be delivered - Detailed records
ecac1946-5a7f-546e-9989-800e0329b397 | note | Responsible Person - Currie
d1919310-024d-4a10-8d7c-b22a89695573 | signoff | HOLD POINT
9b3e705e-3761-4a36-a213-3ecba2b59f96 | section | 6.0 - Concreting
7fc9d8c6-50b7-4885-8712-06284d7eedef | checkpoint | 6.1 - Formwork
34742353-5e70-5a39-b84a-0b8baf3d0435 | note | Specification - Technical Specification cl. 7.1
3e893632-49d7-5c16-9ed9-0b057808367b | note | Verification Activity - Formwork to remain in place for 48hrs after pouring
bb02bfa9-f1a7-5f0a-ac90-3ddb95e172c0 | note | Frequency - On-going
477301ad-3a33-5684-bbb7-db75be39e436 | note | Acceptance criteria - Conform to Contract requirements
56f2b282-6d98-5509-85d9-32031392d231 | note | Inspection Type - Verification
6c7b29d3-23a1-524a-a88b-119f93fd4dd4 | note | Assessor - WSP
7d997fa6-986a-5554-b33b-436f01a5509e | note | Reports to be delivered - Site check
bd7d8fa2-74f8-5d61-a819-3ed53e3ce076 | note | Responsible Person - Currie
4a712085-725a-4e01-ac70-29f6c89bdefd | checkpoint | 6.2 - Concrete workmanship
643dbd57-1fe9-5653-8c8d-6d08b786ba3a | note | Specification - Technical Specification cl. 7.2
7d9baf90-79a8-5fb5-ba8b-aecd81187915 | note | Verification Activity - Concrete to be placed in dry conditions
e1a316b0-5aa4-5f79-a023-dbdf70b75da3 | note | Frequency - On-going
67fa6ca8-e9c0-5006-baf4-ce3ae3fc3d63 | note | Acceptance criteria - Conform to Contract requirements
bb8e8c38-db0e-542f-a1c4-fe819eb6f9e2 | note | Inspection Type - Verification
cadab5ad-fe4c-5911-812e-193d794e0358 | note | Assessor - WSP
5e17c148-7a75-5537-8bbd-34eb28c6a9b8 | note | Reports to be delivered - Site check
3ae29bbb-66ef-5ad9-8858-3a68e0ca2107 | note | Responsible Person - Currie
c2816074-15e1-4e0e-8618-001531c17117 | checkpoint | 6.3 - Concrete testing
f9dcf2bc-c6d8-552f-be77-ca31b8797a67 | note | Specification - Technical Specification cl. 7.4
c5af4148-800a-5889-aefa-4f6fac5c6585 | note | Verification Activity - Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d
99c35dae-e4b2-5df8-a486-e2f878998a36 | note | Frequency - On-going
52c1b881-e0c4-5afa-9f7b-bd6b6719efa1 | note | Acceptance criteria - Conform to Contract requirements
aaa115ab-9173-5fe9-a726-d03db5313555 | note | Inspection Type - Verification
b60964d2-d69b-573a-b507-f50b16981bab | note | Assessor - WSP
a43344f5-d8fe-5fd2-949e-ae4fafe9b903 | note | Reports to be delivered - Detailed records
59e6e3bd-e462-5a40-9030-2fa7966257a5 | note | Responsible Person - Currie
bf14721b-6219-47a2-8684-c72f3b2bbaad | section | 7.0 - Crib Wall
b76669db-9bc6-4f45-b96d-1c9d7bcab851 | checkpoint | 7.1 - Pouring no-fines concrete
fff85333-98a5-5bbd-8abe-5eb122a9628d | note | Specification - Technical Specification cl. 8.2
797f4053-5cf2-5cd2-b0fe-578877b004f5 | note | Verification Activity - No-fines to be poured up to the front face of the crib wall
9ae27acc-7914-514c-89b7-def6ebedaf08 | note | Frequency - On-going
dca6adf4-4036-5810-8832-ec89294cb08c | note | Acceptance criteria - Conform to Contract requirements
652457e0-4ab4-5042-95da-eff35c472f23 | note | Inspection Type - Verification
6a4ae428-ef1e-51b6-abe4-1f493d9fdc60 | note | Assessor - WSP
61b9d3b0-0c5d-5db6-a273-925f0694451b | note | Reports to be delivered - Site check
78dcc751-2f91-5836-94e5-05532f4327fe | note | Responsible Person - Currie
a49e3193-2262-4785-93fa-67532b4bda57 | section | 8.0 - Ground Anchors
8072bb6f-b7e9-4436-acc8-7f15f8352278 | checkpoint | 8.1 - Anchor installation
9abdbaa2-0152-56d1-95a2-2127942ae6bf | note | Specification - Technical Specification cl. 9.1
0f31930d-06b9-5a53-be19-1cdabd043e02 | note | Verification Activity - Contractor to notify Engineer at least 2 days prior to installation & testing
21f70793-6bb6-5c22-9cb5-2a780ddc4b58 | note | Frequency - On-going
4fbcc71e-a85a-57f4-857a-bc77f23962eb | note | Acceptance criteria - Conform to Contract requirements
dff048e5-38e2-56d1-aaa3-378fed158e2c | note | Inspection Type - Verification
3c7353d2-0d67-5dd9-9bd6-5dd0c11f9478 | note | Assessor - Project manager
9a53d4fc-b4d7-5d67-a849-e3f5316b0b88 | note | Reports to be delivered - Verification
c943d5a1-e676-5d48-af18-7ae2525e2313 | note | Responsible Person - Currie
165f13c9-3634-449b-b783-6a42523a9d57 | checkpoint | 8.2 - Anchor grout volume
ea62e789-e7e2-537b-a3fc-9ff44f85d856 | note | Specification - Technical Specification cl. 9.1
1c6f7c9f-a3ac-5dbe-8759-e822aebb406a | note | Verification Activity - Supply grout volume records for each anchor & submit to engineer
77f8c89a-a427-5855-a6e9-00bb7b589cee | note | Frequency - On-going
d4d7f425-ed52-5924-b069-ffa41a4938b9 | note | Acceptance criteria - Conform to Contract requirements
5e5ad2a5-db6f-5201-8503-5c5bcafbee18 | note | Inspection Type - Verification
e126294e-3f1a-594b-98ac-f25541254ae4 | note | Assessor - WSP
22529d90-82ba-5b54-b0b4-0d2453fe88da | note | Reports to be delivered - Grout Log Record
bd8560ea-b15a-5a9a-9c9d-19e24b186881 | note | Responsible Person - Currie
f5cdeb92-9343-4f2b-a81f-24f0626aa03f | checkpoint | 8.3 - Anchor installation
a2bbf5e2-f105-5005-9ad6-b760777648c7 | note | Specification - Technical Specification cl. 9.1
4382c605-280e-5296-a207-ee5f20da9932 | note | Verification Activity - Hollow bars not to be installed at a rate exceeding 1m per minute
61897032-f1f9-520d-be0c-51fef33ffba0 | note | Frequency - On-going
fbcdc380-5008-5358-9388-5cc9b60f40fa | note | Acceptance criteria - Conform to Contract requirements
2673f9b5-455b-5d5a-a3ff-b734d47cc57d | note | Inspection Type - Verification
1a113d9a-e935-562b-8df2-39e47a8c933e | note | Assessor - WSP
5fd3aff4-d896-57d1-a21c-f73320f377b5 | note | Reports to be delivered - Site check
fdd1c699-67b9-527f-b091-66c6a1f6264e | note | Responsible Person - Currie
d54e0396-9e6b-47f6-837e-af014eef4e40 | checkpoint | 8.4 - Loading of anchors
94f12784-6e3e-5b12-9234-9033916775f9 | note | Specification - Technical Specification cl. 9.1
9bef79ce-3d4d-5e02-9de0-603d781b80bb | note | Verification Activity - Anchors shall not be loaded for at least 7 days following grouting
8b90efaa-8ee7-5ae4-93b0-7ba29005636b | note | Frequency - On-going
216fc024-669b-5932-88fb-e8251c4021b8 | note | Acceptance criteria - Conform to Contract requirements
658b66de-48e8-5459-b740-6dba0dec2da4 | note | Inspection Type - Verification
68ccff6d-7607-539d-b884-7e4f1b8a889f | note | Assessor - WSP
730a6be3-a2e9-5eba-83d2-fed8c5af43d1 | note | Reports to be delivered - Verification
c1070295-2e03-5bd8-9ce8-0bf526cd3c85 | note | Responsible Person - Currie
8e3df3c6-bbee-49a7-a155-3e514809deed | checkpoint | 8.5 - Anchor testing equipment
547cd961-0b6e-531b-b0f6-2f088c36ea52 | note | Specification - Technical Specification cl. 9.2
67fd64b9-719b-5e18-b329-09948d6ac0b2 | note | Verification Activity - Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing
f8c489ed-a434-5d2a-a391-d6a74016d9a0 | note | Frequency - Once
9a39bfd4-d721-5482-84d1-74f7774d8c81 | note | Acceptance criteria - Conform to Contract requirements
bd660125-c880-5f83-9cef-592cbbba179d | note | Inspection Type - Verification
dc3a72b4-acdd-544c-b3f7-bb025d8ac1f6 | note | Assessor - Project manager
65c8b406-c658-583c-9c2d-17fd2e9d8ce7 | note | Reports to be delivered - Detailed records
6ed56084-0f3a-57c6-b0c4-5055470ac240 | note | Responsible Person - Currie
b2a16095-f401-4b63-8bbd-b59f6091af20 | checkpoint | 8.6 - Anchor test results
a56fcfec-1d08-5060-bb7c-569bba738e06 | note | Specification - Technical Specification cl. 9.2
797cb5e5-2eb8-5759-b851-c359aa9e2a8d | note | Verification Activity - Contractor to provide the Engineer with test results within 2 days of testing
4a7da559-bd4e-5aa7-b1d7-22999b2abc5b | note | Frequency - On-going
feda0211-5d1b-5c64-a2a1-ccb9dee2054f | note | Acceptance criteria - Conform to Contract requirements
afbbadb5-0943-504d-941e-3ae74e964f34 | note | Inspection Type - Verification
4835268f-677a-5909-b5c9-7a1c1ae6c205 | note | Assessor - Project manager
1e8bc048-ce77-541a-a2b2-58bd91c852cd | note | Reports to be delivered - Detailed records
97a7db83-f54b-5d51-95d8-1d717f7648b3 | note | Responsible Person - Currie
fddb9706-073a-4a62-9760-bd69df805641 | checkpoint | 8.7 - Sacrificial tests
2010386c-25d5-5b60-8345-8be0b1a52d3c | note | Specification - Technical Specification cl. 9.3
017a9f40-e6e9-5dd1-853c-17f83101348d | note | Verification Activity - Abutment A: 1 x sacrificial test
bc4d628c-3da0-516f-bcb7-9ede0614f305 | note | Methods or reference - Positions to be agreed with the Engineer & outside of the work area
a7d8dec1-62b4-5af9-864b-96ad3c739a1f | note | Frequency - Once
e2efa754-9642-551d-bae3-69ad92016c5e | note | Acceptance criteria - Conform to Contract requirements
66a26e26-57f8-5168-9819-4e0ffb1e5564 | note | Inspection Type - Verification
cca45846-156c-5bff-a31d-42ca2442240e | note | Assessor - WSP/Currie
a1c48788-4f3f-55f9-a129-3ae4f9a42fc4 | note | Reports to be delivered - Verification
35dd2f9d-7f71-52c9-8a73-311cb4a3a17a | note | Responsible Person - Currie
a3744347-c1a6-476a-a641-c7e1344b5428 | checkpoint | 8.8 - Production anchors
58e03345-6939-5bf8-a784-3676115127a8 | note | Specification - Technical Specification cl. 9.2 & 9.4
14c54899-c36f-5e78-b7f8-1dcfb8caadd8 | note | Verification Activity - All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test
2e198d30-8bf3-5c0d-8856-07d15f14c73b | note | Frequency - On-going
2df6d90e-2999-5779-acc5-05d67cec0a16 | note | Acceptance criteria - Conform to Contract requirements
49d5b634-a2b4-5b98-9243-cabce3131c41 | note | Inspection Type - Verification
740a0e47-68eb-5c3d-a0f6-6984d9feca58 | note | Assessor - WSP
44f1d7a3-552f-567c-896e-03676489c875 | note | Reports to be delivered - Anchor Load Test Record
07f2313c-954b-5ad3-b977-6afb5792ef6c | note | Responsible Person - Currie
478092c6-e922-42b1-aa1e-b9f6be3144e0 | checkpoint | 8.9 - Sacrificial & production anchors
4493f8bc-db0b-52ae-a534-c67c52c8116e | note | Specification - Technical Specification cl. 9.3
f681f8ab-d6a8-546e-8431-d5cd467e740d | note | Verification Activity - Engineer to witness testing and shall be given at least 2 days notice of testing
6d08000a-4b76-5702-88b0-1f71706bbcc5 | note | Frequency - On-going
ddd02147-5dda-5fe3-a018-0d46113e766b | note | Acceptance criteria - Conform to Contract requirements
1bc26de4-d7c5-5ed0-ba39-c08288051e52 | note | Inspection Type - Hold Point
098e73c5-7731-5e21-b766-a12d167867ea | note | Assessor - WSP
f4d8af8e-fbf0-5c3d-b5c8-aa460ea1cb7c | note | Reports to be delivered - Verification
bb662366-2102-57c0-a355-41affb305a4c | note | Responsible Person - Currie
9a609bf4-1983-410d-8dc2-02d77180c361 | signoff | HOLD POINT
bf845577-83db-4ad4-8798-af06cd9d39c9 | checkpoint | 8.10 - Grout mix design
6fc972f2-1661-5a65-8a31-bca6db700641 | note | Specification - Technical Specification cl. 9.7
0cc18728-ef71-5400-9f31-a9346d49e1f7 | note | Verification Activity - Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting
e1918ad1-47e1-552b-b1cb-8a6daedf70b6 | note | Frequency - Once
af30628e-95d5-5f2b-b4e0-867acb05a5f1 | note | Acceptance criteria - Conform to Contract requirements
19b0e9b6-98b8-596c-9fa3-d942181ddf30 | note | Inspection Type - Verification
2db91593-ddae-5f4a-a3cf-e905350547d0 | note | Assessor - Project manager
3025fd9a-183b-5575-8d3b-86411caa51e6 | note | Reports to be delivered - Detailed records
283d87ab-742b-5ef8-9122-bc086309d006 | note | Responsible Person - Currie
65fbb38c-5941-4874-8c9b-3a02d51fb47f | checkpoint | 8.11 - Anchor grout
6cfcc611-ec24-5660-84f8-d242da850de9 | note | Specification - Technical Specification cl. 9.3, 9.4 & 9.7
92f73618-66aa-50d3-9a11-142a75dfc059 | note | Verification Activity - 30MPa required at 28 days and 30MPa before testing
3c52cd83-fa86-5575-9bc2-620de9ef4b1c | note | Methods or reference - 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d
66b0b7eb-360c-5df6-8d75-db37f0e4373c | note | Frequency - Once
45ff8bfa-0316-5e46-ad25-271906a7ddbe | note | Acceptance criteria - 30MPa before testing & proven with cube test results prior to testing
dd620b3b-66ee-52d1-94d8-bf14ee7b0908 | note | Inspection Type - Hold Point
d16443d2-37e5-533c-a11a-f5a246336b33 | note | Assessor - WSP/Project manager
829f5d8d-f792-5e86-933d-8a78bc72461c | note | Reports to be delivered - Detailed report
ce5ea76b-dfbc-544d-8d16-81e7b9158044 | note | Responsible Person - Currie
d3e2af7d-aba5-494a-837b-4ce99279371f | signoff | HOLD POINT
b59ead18-549e-4a1b-9f82-06ca13586d11 | checkpoint | 8.12 - Anchor tolerences
d49e8e17-d5bc-53c2-b1cb-28671d832a9a | note | Specification - Technical Specification cl. 9.6
782c73ee-bcc4-5f6e-af27-5c1c4ef2a957 | note | Verification Activity - Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees
aeb13a7d-8850-5848-8f81-423558bb68bf | note | Methods or reference - Tape measure & digital spirit level
71d7cfd0-df34-5774-9fb7-2a81a198d7b0 | note | Frequency - Once
04e8c3fb-62b2-52c5-98b9-03d3cd5d91d4 | note | Acceptance criteria - Conform to Contract requirements
abc0ab53-7856-50db-946d-7907b99c7e2c | note | Inspection Type - Verification
a70892bb-e703-5180-b09a-c2a904856374 | note | Assessor - WSP
f78f9b2a-4b31-5380-b8fd-0d0a55f70bb8 | note | Reports to be delivered - Site check
a2da2570-1654-5cc6-94c8-9c0c8b7d586f | note | Responsible Person - Currie
655a1f5f-e134-4483-b254-952e2fc136ea | checkpoint | 8.13 - Anchor testing
99cfe0cc-a6ac-5eff-a967-4f449e1790f9 | note | Specification - Drg C11 Table 2
8e9ad532-825d-504f-bb63-bc0a7107b000 | note | Verification Activity - Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN
224fe710-3e73-535d-af11-3d6c8a929573 | note | Methods or reference - Hydraulic test jack
b382be05-822f-5b84-a1a3-e11417b410af | note | Frequency - Every anchor
cf719e3b-51d9-549d-adf2-290614bf6945 | note | Acceptance criteria - Conform to Contract requirements
b5003d5f-d8f4-5eb0-8190-f950fe7e7a7e | note | Inspection Type - Verification
439c82ae-d09c-5f5b-a8db-a91b502797f3 | note | Assessor - WSP
1478610e-57ab-5a68-8c8a-6024cc562276 | note | Reports to be delivered - Detailed record
27ccb3b4-cf5d-5365-a56d-b62a1292fd2d | note | Responsible Person - Currie
e2810a20-1d4a-47e8-84dc-b6240ebad806 | checkpoint | 8.14 - Anchor bar lengths
a4212868-53ff-5652-88c1-fb2fed031bdb | note | Specification - Drg C11 Table 2
fbf2dce4-bdf0-5377-aef0-ddbc77fd4937 | note | Verification Activity - Abutment A: GA1 - GA6 = 3.0m unbonded & min. 3.0m rock socket
fd6b78f7-8d4a-5587-898f-17ba523b30b2 | note | Methods or reference - Abutment A: GA1 - GA6 = 30/14 anchor at 1.2m centres
21eac777-2af5-566a-a3a1-b3d194200ef6 | note | Frequency - On-going
f156ce85-4f17-5781-ab0b-bd12d97274c4 | note | Acceptance criteria - Conform to Contract requirements
2ea79f7d-c3b7-52d1-bab2-b50293940ae9 | note | Inspection Type - Verification
ea2a8e6c-7ebb-50a5-9ebe-5609deed8114 | note | Assessor - WSP
05dd1360-26ae-5cb5-9bad-a8e90000f164 | note | Reports to be delivered - Anchor Log Record
931985e3-dd24-5cd1-9f3b-07de5da07259 | note | Responsible Person - Currie
bd720e60-5ad3-45e9-8137-5110564de97f | checkpoint | 8.15 - Anchor bar couplers, nuts & washers
44261962-0ff1-5625-a589-6f2715b6784c | note | Specification - All hot dip galvanized
30a65d44-5c01-5aca-8a10-f6cf6b570671 | note | Frequency - Once
7584d110-e921-56db-9f45-ce2bf0385ebb | note | Acceptance criteria - Conform to Contract requirements
e001ff61-0996-5f63-9868-8e3733d13463 | note | Inspection Type - Verification
9e216eaf-4fc9-5bb2-886f-0ad977839220 | note | Assessor - WSP
6d038d40-7e78-525d-9e75-1c1ebfd07349 | note | Reports to be delivered - Site check
489a6cb0-1f46-5c88-9107-3593604ffe48 | note | Responsible Person - Currie
140712be-fbfe-45c7-adcf-123e825173ec | section | 9.0 - Earthworks
762e8945-f9f8-479e-b3d7-7cfc34d8da59 | checkpoint | 9.1 - Site sourced material
b521497a-079a-5d1e-8c87-dbcb3a3d27d5 | note | Specification - Technical Specification cl. 10.3
abe1628c-17a1-58ef-8124-842e0a860ca5 | note | Verification Activity - Site sourced to be used for all backfilling EXCEPT for behind the retaining walls
6a545760-f651-5501-bd4a-8fea1b31d722 | note | Frequency - On-going
8d07f85b-32f7-54d0-93fb-23937858e3c1 | note | Acceptance criteria - Conform to Contract requirements
93d7e5e7-3932-5d5d-a853-a2f582a88992 | note | Inspection Type - Verification
97619f2c-6025-5c89-8ff0-fda96d26f1b1 | note | Assessor - WSP
425027f3-ace5-51f5-b8e1-e79de34cad26 | note | Reports to be delivered - Visual
b5e03d02-fda2-5326-818d-2a1da30bc5f6 | note | Responsible Person - Currie
c5325fb7-f18c-43d8-b3ce-eef918e10043 | checkpoint | 9.2 - Compaction layer thickness
db5222c2-2c81-59c0-a821-2a96be046595 | note | Specification - Technical Specification cl. 10.3
1509dc63-9b8b-53ac-ace1-943c66cf787c | note | Verification Activity - Compaction to be in loose layers not exceeding 300mm
375bc6e0-9617-5f02-8e1e-61057936ecbd | note | Frequency - On-going
caba2c92-7ea0-5ed8-b853-0e21472408ae | note | Acceptance criteria - Conform to Contract requirements
c06e1b47-3769-5ec5-b6f2-97f495bf1011 | note | Inspection Type - Verification
59cfd313-9e6d-51ff-bb66-c55b9b66822c | note | Assessor - WSP
de193ac7-30af-5f16-aff9-597f622acd4f | note | Reports to be delivered - Site check
0ad275e5-3536-5c62-9cd9-34163089a829 | note | Responsible Person - Currie
2e9c5fd7-8c4f-4c64-b645-4ccef5cd2aa8 | checkpoint | 9.3 - Rip rap top-up in front of existing bridge piles & new retaining wall
de583b3a-ff83-5233-bcc4-b23c8a6897f6 | note | Specification - Drg C01
67de2129-8e4e-568b-866d-e90400f66a13 | note | Verification Activity - Rip rap to be site won
909922b2-54bf-57b3-b92d-048c06defe72 | note | Frequency - On-going
3365541c-a473-5743-b7a5-063788262746 | note | Acceptance criteria - Conform to Contract requirements
0f9ddd76-3e81-52b1-b4ba-cd5d7e009d3f | note | Inspection Type - Verification
08fc2bb5-0e55-5e24-9cba-d9732d4b5f2b | note | Assessor - WSP
dbc96b16-9e93-56e5-9c15-c1d7fd041778 | note | Reports to be delivered - Site check
5ffd5887-c5b6-5e80-8ec6-cbe21617ddc6 | note | Responsible Person - Currie
50ea11ef-737b-4366-8d36-f999abddc7b6 | checkpoint | 9.4 - Centre pier rip rap protection
41aa173c-5885-5b61-a422-a2d529af92da | note | Specification - Drg C01
4a85bbb5-2df6-54ab-8d4e-9caff8b0ce2b | note | Verification Activity - Rip rap to be site won
20566c2e-b0de-5164-9c4f-8037d1f711b6 | note | Frequency - On-going
87607f49-8d14-5920-bcf2-c9d61cb55c49 | note | Acceptance criteria - Conform to Contract requirements
12db3a91-277b-5bab-bdcc-e6d776e5d5fd | note | Inspection Type - Verification
4be76cd6-e418-5368-abe3-90e27a98debf | note | Assessor - WSP
ea86f2a6-7687-5d97-85f2-bfc05c68dd67 | note | Reports to be delivered - Site check
0176db6c-3245-51e6-8dc6-ea35279fd0ce | note | Responsible Person - Currie
949b2cf6-4a99-49ae-9019-76c1eb8023b3 | section | 10.0 - COMPLETION
e7ac1b6e-63fb-492b-b9e3-daae710dc883 | checkpoint | 10.1 - Remove erosion and sediment control measures
293bebbf-a632-53fe-88df-b122d1d48aea | note | Specification - Remove once planting has taken
f927df5b-3439-554f-9762-3565003c3727 | note | Frequency - Once
eceb82e8-e343-5d30-8b56-34ee1532ae09 | note | Acceptance criteria - According to Environmental Management Plan
53a2510d-994b-5d44-b360-49d34b301078 | note | Inspection Type - Verification
d5c086d8-ad02-5bc0-afc8-2e90babc1a8c | note | Assessor - Foreman
35faf9cb-aa3a-57d5-969d-a2c71901abf4 | note | Reports to be delivered - Photo
d03b3e4d-6edd-550e-bf61-09ede6526b72 | note | Responsible Person - Currie
94a14ea2-d5f5-4b71-bc1f-57e4434f9830 | checkpoint | 10.2 - Remove Traffic Control
5cfa713d-6f54-5198-8fc9-d07b420a8d75 | note | Specification - Safety
6007662f-2568-5828-9b41-da347232bc39 | note | Frequency - Once
8c89d18b-216d-5ce5-8896-ea16c6bda7a6 | note | Acceptance criteria - According to TMP
6da1fb48-36d6-5349-afee-804c7dedaac8 | note | Inspection Type - Verification
3f264b3e-00eb-56b4-8649-af32e5c01989 | note | Assessor - Supervisor
9c9e2b3b-bf92-591a-8b61-dedc98b19100 | note | Reports to be delivered - Photo
e2dd3718-9a7f-5d42-9801-844f0ea1613c | note | Responsible Person - Currie
519418b4-7c4a-4010-8a45-869e8e792246 | checkpoint | 10.3 - Site maintained in a tidy state during construction
b6563a08-abe4-5430-bb3b-23edea4feff2 | note | Specification - Best as is reasonably practicable
0a2d8163-6153-5ccf-a42f-2f00c8cce791 | note | Frequency - Daily
e4a0d757-af92-5b56-bb6d-49a74cb390f7 | note | Inspection Type - Verification
c58a9a75-7983-5c1d-a0ee-499766164f38 | note | Assessor - Supervisor
2fe1188e-c152-5f18-8a5c-f1854e1120a8 | note | Reports to be delivered - Photo
c7ad49d3-cdfb-56e9-ab42-e3fc6436331a | note | Responsible Person - Currie
a7c0bc67-bed7-417d-ac81-ca987d2877f5 | checkpoint | 10.4 - Practical Completion Inspection
abf6597c-b1c9-53e0-9d6a-a843e1a0902f | note | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a)
bfd86bee-c687-5bdd-91d3-d39bef82b37a | note | Verification Activity - Engineer to inspect site on completion of physical works
86a942be-1d37-5a35-a506-5d2cb25a4061 | note | Frequency - Once
cae98ff0-9e24-5aa1-9dd8-e83ad5bb64c4 | note | Acceptance criteria - Supply as-built drawings & PS3
45961b47-6723-5405-bac9-4f44f8600eaf | note | Inspection Type - Hold Point
753a4539-ab2d-5d02-bb3f-e7e536349a09 | note | Assessor - WSP
6e6f57f4-a941-59b0-81aa-c48d4465649a | note | Reports to be delivered - Inspection record
adb9dd02-6d49-5fe7-aa1e-3779807357f4 | note | Responsible Person - Currie/WSP
d7835c23-69ee-4e2a-b84a-20e7d91a8e0f | signoff | HOLD POINT
d68e6a02-1b5d-43dc-a4f7-e8b3e6153beb | checkpoint | 10.5 - Inspect site 12 months after completion
eca21282-16a0-584d-9b4a-c3f5f1772fe5 | note | Specification - Remedy agreed defects
1dc64e7a-45cf-5c6e-b891-20eefabc86d4 | note | Frequency - Once
29d028ef-4a39-5473-94d7-3b28ce5646f2 | note | Inspection Type - Verification
89274f11-230c-573a-8b8d-e188ef0f46c1 | note | Assessor - WSP
67e15e31-346c-5443-978b-37174a6ffe80 | note | Reports to be delivered - Site Inspection
23bb6507-d90c-5621-a46f-1c3e4b54dbb6 | note | Responsible Person - Currie/WSP