## Table 1
Activity Description | Spec | Verification Activity | Methods or reference | Frequency | Acceptance criteria | Inspection Type | Assessor | Reports to be delivered | Responsible Person | Records/ Remarks Sign and date if appropriate
Pre commencement
Submit pre commencement docs | Updated Works Programme Quality Plan Health and Safety Plan Traffic Management Plan Environmental Management Plan including Erosion and Sediment Control | Engineers approval | In line with supplied specifications | Once | Compliant with lead contractors requirements | Hold Point | GHD | Copy of documents | CC
Implementation of site specific safety plans | Compliance to document monitored | daily checks | Supplied SSSP | Daily | In line with supplied document | Verification | CC | Document | CC
Implementation of environmental management plan | Compliance with all requirements of approved EMP including RC conditions | daily checks | Supplied EMP | Daily | In line with supplied document | Verification | CC | Document | CC
Implementation of traffic management plan | Meets requirements of approved traffic management plan | weekly monitoring reports | Supplied TMP | Weekly | In line with supplied document | Verification | CC | Document | CC
Setting out | Setout survey controls in line with supplied co-ordinates | Survey control report | Supplied plans | Once | Within tolerance of specification - +/- 50mm horiz, +/- 5mm vert | Verification | CC | Document | CC
Submit progress reports | - | Visual Check | - | Weekly | - | Verification | GHD | Copy of documents | CC
Materials
Pre characterisation testing of borrow pit materials to establish target density | Undertake lab testing of borrow pit material to establish required compaction criteria for site won structural fill | Lab testing | - | Once | Meets engineers approval | Verification | GHD | Lab report | CC
Submission of shop drawings | - | Engineers review approval of submitted shop drawings | - | Once | As per design | Verification | GHD | Document | CC
Submit concrete mix design | Capping beam 40MPa - concrete approach slab - 20MPa | Approval of submitted mix design | Structural specification | Once | Meets design specification - 40MPa capping beams, 20MPa slab | Hold Point | GHD | Document | CC
Submit steel / reinforcing manufacturers certs for approval | mill certificates and test sheets, showing the chemical properties and results of tensile tests, shall be provided by the Contractor to the Engineer prior to commencing the Works. | Email | NZS4671 and 4672 | Once | Reinforcing in line with NZA4671 and 4672 | Verification | GHD | Copy of documents | CC
Sheet pile mill cert | - | Submit Mill cert | - | Once | Properties in line with steel specification | Verification | GHD | Copy of documents | CC
Cycleway barrier | - | Submit manufacturers warranty / guaruntee | General spec item 607 | Once | In line with specification | Verification | GHD | Copy of documents | CC
FRP panels | - | Submit manufacturers warranty / guaruntee | - | Once | In line with specification | Verification | GHD | Copy of documents | CC
Weld testing | Non-destructive testing shall be performed in accordance with ISO 3452, AS 2177 and AS 2207. Materials rejected as a result of non- destructive testing, shall be replaced or repaired and re-tested in accordance with this specification. The quantity of pile welds tested shall be subject to a minimum of:  100 Visual 20 Ultrasonic testing | Engineers approval | AS2177 and 2207 | Once | In line with AS2177 and AS2207 | Verification | GHD | Copy of documents | CC
Construction
Subgrade testing | the contractor will arrange and complete Scala penetrometer testing to confirm the suitability of the ground for all areas where concern exists. The Engineer will consider all results prior to confirming for the Contractor to either proceed with general filling or to undertake undercut to waste. Removal of unsuitable material shall only be undertaken with approval of the Engineer. | NDM results - visual inspection of subgrade formation level prior to | Supplied specification | Once | In line with engineers specification | Hold Point | GHD | Copy of documents / testing results | CC
Subgrade inspection | After stripping and prior to placement of fill engineer will inspect formation level - this will be done prior to any excavation of unsuitable material which will be defined based on soil testing and site visit information | Inspection request visual inspection of subgrade formation level prior to | Supplied specification section 300-4 | Once | In line with engineers specification | Hold Point | GHD | Site Visit | CC
FIRST LIFT Site won structural fill compaction | Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | NDM, MDD, OPC testing results | Supplied specification section 300-4 | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Hold Point | GHD | Submit compaction results | CC
Site won structural fill compaction | The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Inspection request NDM, MDD, OPC testing results | Supplied specification | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Hold Point | GHD | Site Visit / compaction results | CC
Imported fill compaction - basecourse | The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Inspection request NDM, MDD, OPC testing results | Supplied specification | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - | Hold Point | GHD | Site visit / compaction results | CC
Pile driving | The following records shall be kept where appropriate, and shall be submitted to the Engineer for review no later than 24 hours after each days’ driving:  Pile reference number or location  Pile type and grade of steel  Pile length  Type of hammer and details (energy, blow per minute, etc.)  Details of any packing or cushioning at the pile head  Date of driving  Commencing surface level  Depth driven  Length of offcuts  Length of pile extensions  The measurement of driving resistance at appropriate depths (number of blows per 250 mm penetration over the length of the pile and number of blows every 100 mm penetration in the founding stratum)  The recorded level of top of founding stratum of increased driving resistance  The termination toe level and depth of embedment in the founding stratum and  The final position of the driven sheet pile and any deviation from specified location  All information regarding interruptions, unexpected changes in driving characteristics, obstructions and times taken in overcoming them. Document pre augered holes and bentonite slurry if required | Fill in pile log / engineers approval | Pile sets and depth supplied | Once | Meets construction tolerances and in line with supplied documents | Verification | GHD | Pile logs | CC
Pre pour inspection | Check covers - dimensions in line with supplied documents check reinforcing bar size, spacing / quantity and arrangement | Inspection request Engineers approval | Supplied drawings and specifications | Once | In line with supplied documents and NZS3101 | Hold Point | GHD | Site Visit | CC
Post pour inspection | The engineer shall be afforded the opportunity to inspect the concrete finish after formwork has been removed - based on this inspection and the nature of any defects, a remedial proposal will be made by the contractor including submittal of any proposed concrete repair materials | Inspection request Approval from engineer | Supplied drawings and specifications | Once | In line with supplied drawings and specifications | Hold Point | GHD | Site Visit | CC
Concrete testing | Carry out sampling and concrete acceptance tests during construction to NZS 3109.9. Concrete acceptance tests during construction. Conduct 7 day and 28 day strength tests. Include slump test documentation. | Approval from Engineer / engineers representative | Supplied specifications | Once | In line with specifications in engineers documentation and NZS3109, 3112 and 3104 | Verification | GHD | Copy of documents | CC
Welder qualifications | Only qualified welders shall be employed on the Works. Proof of any welder’s proficiency shall be made available on request. | Approval from Engineer / engineers representative | - | Once | - | Verification | GHD | Relevant documents | CC
Notify commencement of fabrication | Give notice so that inspection may be made of the following materials including welding consumables before fabrication submission of proposed welding procedure to prevent distortion and non- ductile welds in tension zones testing of welding procedures and welder qualification tests commencement of shop fabrication commencement of welding before placement of root runs of complete penetration butt welds completion of fabrication before surface preparation surface preparation before shop painting completion of protective coating before delivery to site | Email | - | Once | - | Verification | GHD | Email | CC
Completion
As Built drawings | Supply of as built drawings | Approval from Engineer / engineers representative | Supplied specification | Once | Meets requirements in section 107 of contract specification +/- 50mm horiz +/- 5mm vert | Hold Point | GHD | Copy of documents | CC
Complete works inspection | As per drawings, technical specs and amendments | On site inspection | As per drawings, technical specs and amendments | Once | As agreed | Hold Point | GHD | Site Visit | CC/GHD