## Sheet1
Submit pre commencement docs | Updated Works Programme Quality Plan Health and Safety Plan Traffic Management Plan Environmental Management Plan including Erosion and Sediment Control | Engineers approval | In line with supplied specifications | Once | Compliant with lead contractors requirements | Hold Point | GHD | Copy of documents | CC | Submit pre commencement docs | Spec - Updated Works Programme Quality Plan Health and Safety Plan Traffic Management Plan Environmental Management Plan including Erosion and Sediment Control | Verification Activity - Engineers approval | Methods or reference - In line with supplied specifications | Frequency - Once | Acceptance criteria - Compliant with lead contractors requirements | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Submit pre commencement docs
Implementation of site specific safety plans | Compliance to document monitored | daily checks | Supplied SSSP | Daily | In line with supplied document | Verification | CC | Document | CC | Implementation of site specific safety plans | Spec - Compliance to document monitored | Verification Activity - daily checks | Methods or reference - Supplied SSSP | Frequency - Daily | Acceptance criteria - In line with supplied document | Inspection Type - Verification | Assessor - CC | Reports to be delivered - Document | Responsible Person - CC | Spec - Updated Works Programme Quality Plan Health and Safety Plan Traffic Management Plan Environmental Management Plan including Erosion and Sediment Control
Implementation of environmental management plan | Compliance with all requirements of approved EMP including RC conditions | daily checks | Supplied EMP | Daily | In line with supplied document | Verification | CC | Document | CC | Implementation of environmental management plan | Spec - Compliance with all requirements of approved EMP including RC conditions | Verification Activity - daily checks | Methods or reference - Supplied EMP | Frequency - Daily | Acceptance criteria - In line with supplied document | Inspection Type - Verification | Assessor - CC | Reports to be delivered - Document | Responsible Person - CC | Verification Activity - Engineers approval
Implementation of traffic management plan | Meets requirements of approved traffic management plan | weekly monitoring reports | Supplied TMP | Weekly | In line with supplied document | Verification | CC | Document | CC | Implementation of traffic management plan | Spec - Meets requirements of approved traffic management plan | Verification Activity - weekly monitoring reports | Methods or reference - Supplied TMP | Frequency - Weekly | Acceptance criteria - In line with supplied document | Inspection Type - Verification | Assessor - CC | Reports to be delivered - Document | Responsible Person - CC | Methods or reference - In line with supplied specifications
Setting out | Setout survey controls in line with supplied co-ordinates | Survey control report | Supplied plans | Once | Within tolerance of specification - +/- 50mm horiz, +/- 5mm vert | Verification | CC | Document | CC | Setting out | Spec - Setout survey controls in line with supplied co-ordinates | Verification Activity - Survey control report | Methods or reference - Supplied plans | Frequency - Once | Acceptance criteria - Within tolerance of specification - +/- 50mm horiz, +/- 5mm vert | Inspection Type - Verification | Assessor - CC | Reports to be delivered - Document | Responsible Person - CC | Frequency - Once
Submit progress reports | - | Visual Check | - | Weekly | - | Verification | GHD | Copy of documents | CC | Submit progress reports | Spec - - | Verification Activity - Visual Check | Methods or reference - - | Frequency - Weekly | Acceptance criteria - - | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Acceptance criteria - Compliant with lead contractors requirements
Pre characterisation testing of borrow pit materials to establish target density | Undertake lab testing of borrow pit material to establish required compaction criteria for site won structural fill | Lab testing | - | Once | Meets engineers approval | Verification | GHD | Lab report | CC | Pre characterisation testing of borrow pit materials to establish target density | Spec - Undertake lab testing of borrow pit material to establish required compaction criteria for site won structural fill | Verification Activity - Lab testing | Methods or reference - - | Frequency - Once | Acceptance criteria - Meets engineers approval | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Lab report | Responsible Person - CC | Inspection Type - Hold Point
Submission of shop drawings | - | Engineers review approval of submitted shop drawings | - | Once | As per design | Verification | GHD | Document | CC | Submission of shop drawings | Spec - - | Verification Activity - Engineers review approval of submitted shop drawings | Methods or reference - - | Frequency - Once | Acceptance criteria - As per design | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Document | Responsible Person - CC | Assessor - GHD
Submit concrete mix design | Capping beam 40MPa - concrete approach slab - 20MPa | Approval of submitted mix design | Structural specification | Once | Meets design specification - 40MPa capping beams, 20MPa slab | Hold Point | GHD | Document | CC | Submit concrete mix design | Spec - Capping beam 40MPa - concrete approach slab - 20MPa | Verification Activity - Approval of submitted mix design | Methods or reference - Structural specification | Frequency - Once | Acceptance criteria - Meets design specification - 40MPa capping beams, 20MPa slab | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Document | Responsible Person - CC | Reports to be delivered - Copy of documents
Submit steel / reinforcing manufacturers certs for approval | mill certificates and test sheets, showing the chemical properties and results of tensile tests, shall be provided by the Contractor to the Engineer prior to commencing the Works. | Email | NZS4671 and 4672 | Once | Reinforcing in line with NZA4671 and 4672 | Verification | GHD | Copy of documents | CC | Submit steel / reinforcing manufacturers certs for approval | Spec - mill certificates and test sheets, showing the chemical properties and results of tensile tests, shall be provided by the Contractor to the Engineer prior to commencing the Works. | Verification Activity - Email | Methods or reference - NZS4671 and 4672 | Frequency - Once | Acceptance criteria - Reinforcing in line with NZA4671 and 4672 | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Responsible Person - CC
Sheet pile mill cert | - | Submit Mill cert | - | Once | Properties in line with steel specification | Verification | GHD | Copy of documents | CC | Sheet pile mill cert | Spec - - | Verification Activity - Submit Mill cert | Methods or reference - - | Frequency - Once | Acceptance criteria - Properties in line with steel specification | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Implementation of site specific safety plans
Cycleway barrier | - | Submit manufacturers warranty / guaruntee | General spec item 607 | Once | In line with specification | Verification | GHD | Copy of documents | CC | Cycleway barrier | Spec - - | Verification Activity - Submit manufacturers warranty / guaruntee | Methods or reference - General spec item 607 | Frequency - Once | Acceptance criteria - In line with specification | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Spec - Compliance to document monitored
FRP panels | - | Submit manufacturers warranty / guaruntee | - | Once | In line with specification | Verification | GHD | Copy of documents | CC | FRP panels | Spec - - | Verification Activity - Submit manufacturers warranty / guaruntee | Methods or reference - - | Frequency - Once | Acceptance criteria - In line with specification | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Verification Activity - daily checks
Weld testing | Non-destructive testing shall be performed in accordance with ISO 3452, AS 2177 and AS 2207. Materials rejected as a result of non- destructive testing, shall be replaced or repaired and re-tested in accordance with this specification. The quantity of pile welds tested shall be subject to a minimum of:  100 Visual 20 Ultrasonic testing | Engineers approval | AS2177 and 2207 | Once | In line with AS2177 and AS2207 | Verification | GHD | Copy of documents | CC | Weld testing | Spec - Non-destructive testing shall be performed in accordance with ISO 3452, AS 2177 and AS 2207. Materials rejected as a result of non- destructive testing, shall be replaced or repaired and re-tested in accordance with this specification. The quantity of pile welds tested shall be subject to a minimum of:  100 Visual 20 Ultrasonic testing | Verification Activity - Engineers approval | Methods or reference - AS2177 and 2207 | Frequency - Once | Acceptance criteria - In line with AS2177 and AS2207 | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Methods or reference - Supplied SSSP
Subgrade testing | the contractor will arrange and complete Scala penetrometer testing to confirm the suitability of the ground for all areas where concern exists. The Engineer will consider all results prior to confirming for the Contractor to either proceed with general filling or to undertake undercut to waste. Removal of unsuitable material shall only be undertaken with approval of the Engineer. | NDM results - visual inspection of subgrade formation level prior to | Supplied specification | Once | In line with engineers specification | Hold Point | GHD | Copy of documents / testing results | CC | Subgrade testing | Spec - the contractor will arrange and complete Scala penetrometer testing to confirm the suitability of the ground for all areas where concern exists. The Engineer will consider all results prior to confirming for the Contractor to either proceed with general filling or to undertake undercut to waste. Removal of unsuitable material shall only be undertaken with approval of the Engineer. | Verification Activity - NDM results - visual inspection of subgrade formation level prior to | Methods or reference - Supplied specification | Frequency - Once | Acceptance criteria - In line with engineers specification | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Copy of documents / testing results | Responsible Person - CC | Frequency - Daily
Subgrade inspection | After stripping and prior to placement of fill engineer will inspect formation level - this will be done prior to any excavation of unsuitable material which will be defined based on soil testing and site visit information | Inspection request visual inspection of subgrade formation level prior to | Supplied specification section 300-4 | Once | In line with engineers specification | Hold Point | GHD | Site Visit | CC | Subgrade inspection | Spec - After stripping and prior to placement of fill engineer will inspect formation level - this will be done prior to any excavation of unsuitable material which will be defined based on soil testing and site visit information | Verification Activity - Inspection request visual inspection of subgrade formation level prior to | Methods or reference - Supplied specification section 300-4 | Frequency - Once | Acceptance criteria - In line with engineers specification | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site Visit | Responsible Person - CC | Acceptance criteria - In line with supplied document
FIRST LIFT Site won structural fill compaction | Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | NDM, MDD, OPC testing results | Supplied specification section 300-4 | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Hold Point | GHD | Submit compaction results | CC | FIRST LIFT Site won structural fill compaction | Spec - Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Verification Activity - NDM, MDD, OPC testing results | Methods or reference - Supplied specification section 300-4 | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Submit compaction results | Responsible Person - CC | Inspection Type - Verification
Site won structural fill compaction | The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Inspection request NDM, MDD, OPC testing results | Supplied specification | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Hold Point | GHD | Site Visit / compaction results | CC | Site won structural fill compaction | Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Verification Activity - Inspection request NDM, MDD, OPC testing results | Methods or reference - Supplied specification | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site Visit / compaction results | Responsible Person - CC | Assessor - CC
Imported fill compaction - basecourse | The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Inspection request NDM, MDD, OPC testing results | Supplied specification | each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | MDD ave 95 (min 92 ) max 12 air voids - | Hold Point | GHD | Site visit / compaction results | CC | Imported fill compaction - basecourse | Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method. | Verification Activity - Inspection request NDM, MDD, OPC testing results | Methods or reference - Supplied specification | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged. | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site visit / compaction results | Responsible Person - CC | Reports to be delivered - Document
Pile driving | The following records shall be kept where appropriate, and shall be submitted to the Engineer for review no later than 24 hours after each days’ driving:  Pile reference number or location  Pile type and grade of steel  Pile length  Type of hammer and details (energy, blow per minute, etc.)  Details of any packing or cushioning at the pile head  Date of driving  Commencing surface level  Depth driven  Length of offcuts  Length of pile extensions  The measurement of driving resistance at appropriate depths (number of blows per 250 mm penetration over the length of the pile and number of blows every 100 mm penetration in the founding stratum)  The recorded level of top of founding stratum of increased driving resistance  The termination toe level and depth of embedment in the founding stratum and  The final position of the driven sheet pile and any deviation from specified location  All information regarding interruptions, unexpected changes in driving characteristics, obstructions and times taken in overcoming them. Document pre augered holes and bentonite slurry if required | Fill in pile log / engineers approval | Pile sets and depth supplied | Once | Meets construction tolerances and in line with supplied documents | Verification | GHD | Pile logs | CC | Pile driving | Spec - The following records shall be kept where appropriate, and shall be submitted to the Engineer for review no later than 24 hours after each days’ driving:  Pile reference number or location  Pile type and grade of steel  Pile length  Type of hammer and details (energy, blow per minute, etc.)  Details of any packing or cushioning at the pile head  Date of driving  Commencing surface level  Depth driven  Length of offcuts  Length of pile extensions  The measurement of driving resistance at appropriate depths (number of blows per 250 mm penetration over the length of the pile and number of blows every 100 mm penetration in the founding stratum)  The recorded level of top of founding stratum of increased driving resistance  The termination toe level and depth of embedment in the founding stratum and  The final position of the driven sheet pile and any deviation from specified location  All information regarding interruptions, unexpected changes in driving characteristics, obstructions and times taken in overcoming them. Document pre augered holes and bentonite slurry if required | Verification Activity - Fill in pile log / engineers approval | Methods or reference - Pile sets and depth supplied | Frequency - Once | Acceptance criteria - Meets construction tolerances and in line with supplied documents | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Pile logs | Responsible Person - CC | Responsible Person - CC
Pre pour inspection | Check covers - dimensions in line with supplied documents check reinforcing bar size, spacing / quantity and arrangement | Inspection request Engineers approval | Supplied drawings and specifications | Once | In line with supplied documents and NZS3101 | Hold Point | GHD | Site Visit | CC | Pre pour inspection | Spec - Check covers - dimensions in line with supplied documents check reinforcing bar size, spacing / quantity and arrangement | Verification Activity - Inspection request Engineers approval | Methods or reference - Supplied drawings and specifications | Frequency - Once | Acceptance criteria - In line with supplied documents and NZS3101 | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site Visit | Responsible Person - CC | Implementation of environmental management plan
Post pour inspection | The engineer shall be afforded the opportunity to inspect the concrete finish after formwork has been removed - based on this inspection and the nature of any defects, a remedial proposal will be made by the contractor including submittal of any proposed concrete repair materials | Inspection request Approval from engineer | Supplied drawings and specifications | Once | In line with supplied drawings and specifications | Hold Point | GHD | Site Visit | CC | Post pour inspection | Spec - The engineer shall be afforded the opportunity to inspect the concrete finish after formwork has been removed - based on this inspection and the nature of any defects, a remedial proposal will be made by the contractor including submittal of any proposed concrete repair materials | Verification Activity - Inspection request Approval from engineer | Methods or reference - Supplied drawings and specifications | Frequency - Once | Acceptance criteria - In line with supplied drawings and specifications | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site Visit | Responsible Person - CC | Spec - Compliance with all requirements of approved EMP including RC conditions
Concrete testing | Carry out sampling and concrete acceptance tests during construction to NZS 3109.9. Concrete acceptance tests during construction. Conduct 7 day and 28 day strength tests. Include slump test documentation. | Approval from Engineer / engineers representative | Supplied specifications | Once | In line with specifications in engineers documentation and NZS3109, 3112 and 3104 | Verification | GHD | Copy of documents | CC | Concrete testing | Spec - Carry out sampling and concrete acceptance tests during construction to NZS 3109.9. Concrete acceptance tests during construction. Conduct 7 day and 28 day strength tests. Include slump test documentation. | Verification Activity - Approval from Engineer / engineers representative | Methods or reference - Supplied specifications | Frequency - Once | Acceptance criteria - In line with specifications in engineers documentation and NZS3109, 3112 and 3104 | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Verification Activity - daily checks
Welder qualifications | Only qualified welders shall be employed on the Works. Proof of any welder’s proficiency shall be made available on request. | Approval from Engineer / engineers representative | - | Once | - | Verification | GHD | Relevant documents | CC | Welder qualifications | Spec - Only qualified welders shall be employed on the Works. Proof of any welder’s proficiency shall be made available on request. | Verification Activity - Approval from Engineer / engineers representative | Methods or reference - - | Frequency - Once | Acceptance criteria - - | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Relevant documents | Responsible Person - CC | Methods or reference - Supplied EMP
Notify commencement of fabrication | Give notice so that inspection may be made of the following materials including welding consumables before fabrication submission of proposed welding procedure to prevent distortion and non- ductile welds in tension zones testing of welding procedures and welder qualification tests commencement of shop fabrication commencement of welding before placement of root runs of complete penetration butt welds completion of fabrication before surface preparation surface preparation before shop painting completion of protective coating before delivery to site | Email | - | Once | - | Verification | GHD | Email | CC | Notify commencement of fabrication | Spec - Give notice so that inspection may be made of the following materials including welding consumables before fabrication submission of proposed welding procedure to prevent distortion and non- ductile welds in tension zones testing of welding procedures and welder qualification tests commencement of shop fabrication commencement of welding before placement of root runs of complete penetration butt welds completion of fabrication before surface preparation surface preparation before shop painting completion of protective coating before delivery to site | Verification Activity - Email | Methods or reference - - | Frequency - Once | Acceptance criteria - - | Inspection Type - Verification | Assessor - GHD | Reports to be delivered - Email | Responsible Person - CC | Frequency - Daily
As Built drawings | Supply of as built drawings | Approval from Engineer / engineers representative | Supplied specification | Once | Meets requirements in section 107 of contract specification +/- 50mm horiz +/- 5mm vert | Hold Point | GHD | Copy of documents | CC | As Built drawings | Spec - Supply of as built drawings | Verification Activity - Approval from Engineer / engineers representative | Methods or reference - Supplied specification | Frequency - Once | Acceptance criteria - Meets requirements in section 107 of contract specification +/- 50mm horiz +/- 5mm vert | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Copy of documents | Responsible Person - CC | Acceptance criteria - In line with supplied document
Complete works inspection | As per drawings, technical specs and amendments | On site inspection | As per drawings, technical specs and amendments | Once | As agreed | Hold Point | GHD | Site Visit | CC/GHD | Complete works inspection | Spec - As per drawings, technical specs and amendments | Verification Activity - On site inspection | Methods or reference - As per drawings, technical specs and amendments | Frequency - Once | Acceptance criteria - As agreed | Inspection Type - Hold Point | Assessor - GHD | Reports to be delivered - Site Visit | Responsible Person - CC/GHD | Inspection Type - Verification
Assessor - CC
Reports to be delivered - Document
Responsible Person - CC
Implementation of traffic management plan
Spec - Meets requirements of approved traffic management plan
Verification Activity - weekly monitoring reports
Methods or reference - Supplied TMP
Frequency - Weekly
Acceptance criteria - In line with supplied document
Inspection Type - Verification
Assessor - CC
Reports to be delivered - Document
Responsible Person - CC
Setting out
Spec - Setout survey controls in line with supplied co-ordinates
Verification Activity - Survey control report
Methods or reference - Supplied plans
Frequency - Once
Acceptance criteria - Within tolerance of specification - +/- 50mm horiz, +/- 5mm vert
Inspection Type - Verification
Assessor - CC
Reports to be delivered - Document
Responsible Person - CC
Submit progress reports
Spec - -
Verification Activity - Visual Check
Methods or reference - -
Frequency - Weekly
Acceptance criteria - -
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Pre characterisation testing of borrow pit materials to establish target density
Spec - Undertake lab testing of borrow pit material to establish required compaction criteria for site won structural fill
Verification Activity - Lab testing
Methods or reference - -
Frequency - Once
Acceptance criteria - Meets engineers approval
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Lab report
Responsible Person - CC
Submission of shop drawings
Spec - -
Verification Activity - Engineers review approval of submitted shop drawings
Methods or reference - -
Frequency - Once
Acceptance criteria - As per design
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Document
Responsible Person - CC
Submit concrete mix design
Spec - Capping beam 40MPa - concrete approach slab - 20MPa
Verification Activity - Approval of submitted mix design
Methods or reference - Structural specification
Frequency - Once
Acceptance criteria - Meets design specification - 40MPa capping beams, 20MPa slab
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Document
Responsible Person - CC
Submit steel / reinforcing manufacturers certs for approval
Spec - mill certificates and test sheets, showing the chemical properties and results of tensile tests, shall be provided by the Contractor to the Engineer prior to commencing the Works.
Verification Activity - Email
Methods or reference - NZS4671 and 4672
Frequency - Once
Acceptance criteria - Reinforcing in line with NZA4671 and 4672
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Sheet pile mill cert
Spec - -
Verification Activity - Submit Mill cert
Methods or reference - -
Frequency - Once
Acceptance criteria - Properties in line with steel specification
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Cycleway barrier
Spec - -
Verification Activity - Submit manufacturers warranty / guaruntee
Methods or reference - General spec item 607
Frequency - Once
Acceptance criteria - In line with specification
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
FRP panels
Spec - -
Verification Activity - Submit manufacturers warranty / guaruntee
Methods or reference - -
Frequency - Once
Acceptance criteria - In line with specification
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Weld testing
Spec - Non-destructive testing shall be performed in accordance with ISO 3452, AS 2177 and AS 2207. Materials rejected as a result of non- destructive testing, shall be replaced or repaired and re-tested in accordance with this specification. The quantity of pile welds tested shall be subject to a minimum of:  100 Visual 20 Ultrasonic testing
Verification Activity - Engineers approval
Methods or reference - AS2177 and 2207
Frequency - Once
Acceptance criteria - In line with AS2177 and AS2207
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Subgrade testing
Spec - the contractor will arrange and complete Scala penetrometer testing to confirm the suitability of the ground for all areas where concern exists. The Engineer will consider all results prior to confirming for the Contractor to either proceed with general filling or to undertake undercut to waste. Removal of unsuitable material shall only be undertaken with approval of the Engineer.
Verification Activity - NDM results - visual inspection of subgrade formation level prior to
Methods or reference - Supplied specification
Frequency - Once
Acceptance criteria - In line with engineers specification
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Copy of documents / testing results
Responsible Person - CC
Subgrade inspection
Spec - After stripping and prior to placement of fill engineer will inspect formation level - this will be done prior to any excavation of unsuitable material which will be defined based on soil testing and site visit information
Verification Activity - Inspection request visual inspection of subgrade formation level prior to
Methods or reference - Supplied specification section 300-4
Frequency - Once
Acceptance criteria - In line with engineers specification
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site Visit
Responsible Person - CC
FIRST LIFT Site won structural fill compaction
Spec - Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
Verification Activity - NDM, MDD, OPC testing results
Methods or reference - Supplied specification section 300-4
Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Submit compaction results
Responsible Person - CC
Site won structural fill compaction
Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
Verification Activity - Inspection request NDM, MDD, OPC testing results
Methods or reference - Supplied specification
Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site Visit / compaction results
Responsible Person - CC
Imported fill compaction - basecourse
Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out. Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
Verification Activity - Inspection request NDM, MDD, OPC testing results
Methods or reference - Supplied specification
Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids -
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site visit / compaction results
Responsible Person - CC
Pile driving
Spec - The following records shall be kept where appropriate, and shall be submitted to the Engineer for review no later than 24 hours after each days’ driving:  Pile reference number or location  Pile type and grade of steel  Pile length  Type of hammer and details (energy, blow per minute, etc.)  Details of any packing or cushioning at the pile head  Date of driving  Commencing surface level  Depth driven  Length of offcuts  Length of pile extensions  The measurement of driving resistance at appropriate depths (number of blows per 250 mm penetration over the length of the pile and number of blows every 100 mm penetration in the founding stratum)  The recorded level of top of founding stratum of increased driving resistance  The termination toe level and depth of embedment in the founding stratum and  The final position of the driven sheet pile and any deviation from specified location  All information regarding interruptions, unexpected changes in driving characteristics, obstructions and times taken in overcoming them. Document pre augered holes and bentonite slurry if required
Verification Activity - Fill in pile log / engineers approval
Methods or reference - Pile sets and depth supplied
Frequency - Once
Acceptance criteria - Meets construction tolerances and in line with supplied documents
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Pile logs
Responsible Person - CC
Pre pour inspection
Spec - Check covers - dimensions in line with supplied documents check reinforcing bar size, spacing / quantity and arrangement
Verification Activity - Inspection request Engineers approval
Methods or reference - Supplied drawings and specifications
Frequency - Once
Acceptance criteria - In line with supplied documents and NZS3101
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site Visit
Responsible Person - CC
Post pour inspection
Spec - The engineer shall be afforded the opportunity to inspect the concrete finish after formwork has been removed - based on this inspection and the nature of any defects, a remedial proposal will be made by the contractor including submittal of any proposed concrete repair materials
Verification Activity - Inspection request Approval from engineer
Methods or reference - Supplied drawings and specifications
Frequency - Once
Acceptance criteria - In line with supplied drawings and specifications
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site Visit
Responsible Person - CC
Concrete testing
Spec - Carry out sampling and concrete acceptance tests during construction to NZS 3109.9. Concrete acceptance tests during construction. Conduct 7 day and 28 day strength tests. Include slump test documentation.
Verification Activity - Approval from Engineer / engineers representative
Methods or reference - Supplied specifications
Frequency - Once
Acceptance criteria - In line with specifications in engineers documentation and NZS3109, 3112 and 3104
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Welder qualifications
Spec - Only qualified welders shall be employed on the Works. Proof of any welder’s proficiency shall be made available on request.
Verification Activity - Approval from Engineer / engineers representative
Methods or reference - -
Frequency - Once
Acceptance criteria - -
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Relevant documents
Responsible Person - CC
Notify commencement of fabrication
Spec - Give notice so that inspection may be made of the following materials including welding consumables before fabrication submission of proposed welding procedure to prevent distortion and non- ductile welds in tension zones testing of welding procedures and welder qualification tests commencement of shop fabrication commencement of welding before placement of root runs of complete penetration butt welds completion of fabrication before surface preparation surface preparation before shop painting completion of protective coating before delivery to site
Verification Activity - Email
Methods or reference - -
Frequency - Once
Acceptance criteria - -
Inspection Type - Verification
Assessor - GHD
Reports to be delivered - Email
Responsible Person - CC
As Built drawings
Spec - Supply of as built drawings
Verification Activity - Approval from Engineer / engineers representative
Methods or reference - Supplied specification
Frequency - Once
Acceptance criteria - Meets requirements in section 107 of contract specification +/- 50mm horiz +/- 5mm vert
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Copy of documents
Responsible Person - CC
Complete works inspection
Spec - As per drawings, technical specs and amendments
Verification Activity - On site inspection
Methods or reference - As per drawings, technical specs and amendments
Frequency - Once
Acceptance criteria - As agreed
Inspection Type - Hold Point
Assessor - GHD
Reports to be delivered - Site Visit
Responsible Person - CC/GHD