## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Whatatuna | itp
section | Pre commencement
checkpoint | Submit pre commencement docs
label | Spec - Updated Works Programme Quality Plan
label | ○ Health and Safety Plan Traffic Management Plan
label | ○ Environmental Management Plan including Erosion and Sediment Control
label | Verification Activity - Engineers approval
label | Methods or reference - In line with supplied specifications
label | Frequency - Once
label | Acceptance criteria - Compliant with lead contractors requirements
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Implementation of site specific safety plans
label | Spec - Compliance to document monitored
label | Verification Activity - daily checks
label | Methods or reference - Supplied SSSP
label | Frequency - Daily
label | Acceptance criteria - In line with supplied document
label | Inspection Type - Verification
label | Assessor - CC
label | Reports to be delivered - Document
label | Responsible Person - CC
checkpoint | Implementation of environmental management plan
label | Spec - Compliance with all requirements of approved EMP including RC conditions
label | Verification Activity - daily checks
label | Methods or reference - Supplied EMP
label | Frequency - Daily
label | Acceptance criteria - In line with supplied document
label | Inspection Type - Verification
label | Assessor - CC
label | Reports to be delivered - Document
label | Responsible Person - CC
checkpoint | Implementation of traffic management plan
label | Spec - Meets requirements of approved traffic management plan
label | Verification Activity - weekly monitoring reports
label | Methods or reference - Supplied TMP
label | Frequency - Weekly
label | Acceptance criteria - In line with supplied document
label | Inspection Type - Verification
label | Assessor - CC
label | Reports to be delivered - Document
label | Responsible Person - CC
checkpoint | Setting out
label | Spec - Setout survey controls in line with supplied co-ordinates
label | Verification Activity - Survey control report
label | Methods or reference - Supplied plans
label | Frequency - Once
label | Acceptance criteria - Within tolerance of specification - +/- 50mm horiz, +/- 5mm vert
label | Inspection Type - Verification
label | Assessor - CC
label | Reports to be delivered - Document
label | Responsible Person - CC
checkpoint | Submit progress reports
label | Verification Activity - Visual Check
label | Frequency - Weekly
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
section | Materials
checkpoint | Pre characterisation testing of borrow pit materials to establish target density
label | Spec - Undertake lab testing of borrow pit material to establish required compaction criteria for site won structural fill
label | Verification Activity - Lab testing
label | Frequency - Once
label | Acceptance criteria - Meets engineers approval
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Lab report
label | Responsible Person - CC
checkpoint | Submission of shop drawings
label | Verification Activity - Engineers review approval of submitted shop drawings
label | Frequency - Once
label | Acceptance criteria - As per design
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Document
label | Responsible Person - CC
checkpoint | Submit concrete mix design
label | Spec - Capping beam 40MPa - concrete approach slab - 20MPa
label | Verification Activity - Approval of submitted mix design
label | Methods or reference - Structural specification
label | Frequency - Once
label | Acceptance criteria - Meets design specification - 40MPa capping beams, 20MPa slab
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Document
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Submit steel / reinforcing manufacturers certs for approval
label | Spec - mill certificates and test sheets, showing the chemical properties and results of tensile tests, shall be provided by the Contractor to the Engineer prior to commencing the Works.
label | Verification Activity - Email
label | Methods or reference - NZS4671 and 4672
label | Frequency - Once
label | Acceptance criteria - Reinforcing in line with NZA4671 and 4672
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
checkpoint | Sheet pile mill cert
label | Verification Activity - Submit Mill cert
label | Frequency - Once
label | Acceptance criteria - Properties in line with steel specification
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
checkpoint | Cycleway barrier
label | Verification Activity - Submit manufacturers warranty / guaruntee
label | Methods or reference - General spec item 607
label | Frequency - Once
label | Acceptance criteria - In line with specification
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
checkpoint | FRP panels
label | Verification Activity - Submit manufacturers warranty / guaruntee
label | Frequency - Once
label | Acceptance criteria - In line with specification
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
checkpoint | Weld testing
label | Spec - Non-destructive testing shall be performed in accordance with ISO 3452, AS 2177 and AS 2207. Materials rejected as a result of non- destructive testing, shall be replaced or repaired and re-tested in accordance with this specification. The quantity of pile welds tested shall be subject to a minimum of:
label | ○ 100 Visual
label | ○ 20 Ultrasonic testing
label | Verification Activity - Engineers approval
label | Methods or reference - AS2177 and 2207
label | Frequency - Once
label | Acceptance criteria - In line with AS2177 and AS2207
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
section | Construction
checkpoint | Subgrade testing
label | Spec - the contractor will arrange and complete Scala penetrometer testing to confirm the suitability of the ground for all areas where concern exists.
label | ○ The Engineer will consider all results prior to confirming for the Contractor to either proceed with general filling or to undertake undercut to waste. Removal of unsuitable material shall only be undertaken with approval of the Engineer.
label | Verification Activity - NDM results - visual inspection of subgrade formation level prior to
label | Methods or reference - Supplied specification
label | Frequency - Once
label | Acceptance criteria - In line with engineers specification
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Copy of documents / testing results
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Subgrade inspection
label | Spec - After stripping and prior to placement of fill engineer will inspect formation level - this will be done prior to any excavation of unsuitable material which will be defined based on soil testing and site visit information
label | Verification Activity - Inspection request visual inspection of subgrade formation level prior to
label | Methods or reference - Supplied specification section 300-4
label | Frequency - Once
label | Acceptance criteria - In line with engineers specification
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site Visit
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | FIRST LIFT Site won structural fill compaction
label | Spec - Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material.
label | ○ The contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
label | Verification Activity - NDM, MDD, OPC testing results
label | Methods or reference - Supplied specification section 300-4
label | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
label | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Submit compaction results
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Site won structural fill compaction
label | Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out.
label | ○ Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material. the contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
label | Verification Activity - Inspection request NDM, MDD, OPC testing results
label | Methods or reference - Supplied specification
label | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
label | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids - shear vane - within 5 of established shear strength coorelation
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site Visit / compaction results
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Imported fill compaction - basecourse
label | Spec - The Engineer may carry out density tests of compaction at any time. The Contractor shall stop or divert his machines as required by the Engineer to allow the tests to be safely carried out.
label | ○ Where field tests indicate that the specified standard of compaction has not been achieved, corrective action shall be taken to bring the fill to the required standard and as required by the Engineer. This may require excavation and removal of the failed fill material.
label | ○ The contractor shall supply the engineer the test results to demonstrate compaction compliance after placement of first lift and prior to next lift - NDM or other approved method.
label | Verification Activity - Inspection request NDM, MDD, OPC testing results
label | Methods or reference - Supplied specification
label | Frequency - each lift, testing every 10m linear length of stop bank - 3x tests to be taken at each location and averaged.
label | Acceptance criteria - MDD ave 95 (min 92 ) max 12 air voids -
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site visit / compaction results
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Pile driving
label | Spec - The following records shall be kept where appropriate, and shall be submitted to the Engineer for review no later than 24 hours after each days’ driving:
label | ○ Pile reference number or location
label | ○ Pile type and grade of steel
label | ○ Pile length
label | ○ Type of hammer and details (energy, blow per minute, etc.)
label | ○ Details of any packing or cushioning at the pile head
label | ○ Date of driving
label | ○ Commencing surface level
label | ○ Depth driven
label | ○ Length of offcuts
label | ○ Length of pile extensions
label | ○ The measurement of driving resistance at appropriate depths (number of blows per 250 mm penetration over the length of the pile and number of blows every 100 mm penetration in the founding stratum)
label | ○ The recorded level of top of founding stratum of increased driving resistance
label | ○ The termination toe level and depth of embedment in the founding stratum and
label | ○ The final position of the driven sheet pile and any deviation from specified location
label | ○ All information regarding interruptions, unexpected changes in driving characteristics, obstructions and times taken in overcoming them.
label | ○ Document pre augered holes and bentonite slurry if required
label | Verification Activity - Fill in pile log / engineers approval
label | Methods or reference - Pile sets and depth supplied
label | Frequency - Once
label | Acceptance criteria - Meets construction tolerances and in line with supplied documents
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Pile logs
label | Responsible Person - CC
checkpoint | Pre pour inspection
label | Spec - Check covers - dimensions in line with supplied documents check reinforcing bar size, spacing / quantity and arrangement
label | Verification Activity - Inspection request Engineers approval
label | Methods or reference - Supplied drawings and specifications
label | Frequency - Once
label | Acceptance criteria - In line with supplied documents and NZS3101
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site Visit
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Post pour inspection
label | Spec - The engineer shall be afforded the opportunity to inspect the concrete finish after formwork has been removed - based on this inspection and the nature of any defects, a remedial proposal will be made by the contractor including submittal of any proposed concrete repair materials
label | Verification Activity - Inspection request, Approval from engineer
label | Methods or reference - Supplied drawings and specifications
label | Frequency - Once
label | Acceptance criteria - In line with supplied drawings and specifications
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site Visit
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Concrete testing
label | Spec - Carry out sampling and concrete acceptance tests during construction to NZS 3109.9. Concrete acceptance tests during construction.
label | ○ Conduct 7 day and 28 day strength tests. Include slump test documentation.
label | Verification Activity - Approval from Engineer / engineers representative
label | Methods or reference - Supplied specifications
label | Frequency - Once
label | Acceptance criteria - In line with specifications in engineers documentation and NZS3109, 3112 and 3104
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
checkpoint | Welder qualifications
label | Spec - Only qualified welders shall be employed on the Works. Proof of any welder’s proficiency shall be made available on request.
label | Verification Activity - Approval from Engineer / engineers representative
label | Frequency - Once
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Relevant documents
label | Responsible Person - CC
checkpoint | Notify commencement of fabrication
label | Spec - Give notice so that inspection may be made of the following materials including welding consumables before fabrication submission of proposed welding procedure to prevent distortion and non- ductile welds in tension zones testing of welding procedures and welder qualification tests commencement of shop fabrication commencement of welding before placement of root runs of complete penetration butt welds completion of fabrication before surface preparation surface preparation before shop painting completion of protective coating before delivery to site
label | Verification Activity - Email
label | Frequency - Once
label | Inspection Type - Verification
label | Assessor - GHD
label | Reports to be delivered - Email
label | Responsible Person - CC
section | Completion
checkpoint | As Built drawings
label | Spec - Supply of as built drawings
label | Verification Activity - Approval from Engineer / engineers representative
label | Methods or reference - Supplied specification
label | Frequency - Once
label | Acceptance criteria - Meets requirements in section 107 of contract specification
label | ○ +/- 50mm horiz
label | ○ +/- 5mm vert
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Copy of documents
label | Responsible Person - CC
holdpoint | HOLD POINT
checkpoint | Complete works inspection
label | Spec - As per drawings, technical specs and amendments
label | Verification Activity - On site inspection
label | Methods or reference - As per drawings, technical specs and amendments
label | Frequency - Once
label | Acceptance criteria - As agreed
label | Inspection Type - Hold Point
label | Assessor - GHD
label | Reports to be delivered - Site Visit
label | Responsible Person - CC/GHD
holdpoint | HOLD POINT