## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-033 ITP Cycle Way | itp |  |  |  |  | DN1210-033 ITP Cycle Way Rev 1
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >80%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA,AB,AC,BA,BB,CA or CB
label | Standard / Specification - NZS4407:2015 Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve ¦¦ Percentage Passing
label | 63.0 ¦¦ 100%
label | 37.5 ¦¦ 68-90%
label | 19 ¦¦ 42-76%
label | 9.5 ¦¦ 26-58%
label | 4.75 ¦¦ 16-44%
label | 2.36 ¦¦ 10-33%
label | 1.18 ¦¦ 6-24%
label | 0.425 ¦¦ 3-14%
label | 0.075 ¦¦ 1-6%
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - <8
label | Standard / Specification - NZS4407:2015 Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >130KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >80%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA,AB,AC,BA,BB ,CA or CB
label | Standard / Specification - NZS4407:2015 Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ Percentage Passing
label | 37.5 ¦¦ 100%
label | 19.0 ¦¦ 62-81%
label | 9.5 ¦¦ 38-60%
label | 4.75 ¦¦ 24-45%
label | 2.36 ¦¦ 15-35 %
label | 1.18 ¦¦ 8-27%
label | 0.600 ¦¦ 4-21%
label | 0.300 ¦¦ 1-16%
label | 0.150 ¦¦ 1-12%
label | 0.075 ¦¦ 0-9%
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - <8
label | ○ If SE is <35
label | Standard / Specification - NZS4407:2015 Test 3.2
label | ○ NZS4407:2015 Test 3.3
label | ○ NZS4407:2015 Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >35
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - <5
label | ○ If SE is <35
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2- CONSTRUCTION - PREP GENERAL
checkpoint | 2.1 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 2 blows per 100mm penetration (Minimum CBR of 3)
label | Standard / Specification - Appendix XVIII Drawing
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2 - Proof roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection of Proof Roll
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - Across Whole are
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
section | SECTION 3 - Subbase Layer AP65-2 (Only If CBR is less than 3)
checkpoint | 3.1.1 - Subbase - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface.
label | Acceptance / Conformance Criteria - (-25+5mm)
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Subbase - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 - Basecourse Layer (AP40-3)
checkpoint | 4.1.1 - Basecourse - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface.
label | Acceptance / Conformance Criteria - (-15mm+0mm)
label | Standard / Specification -
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Basecourse Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification -
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - As-Builts Red Pen markup
label | Detail - Final inspection of All Work
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | ○ Record Any Undercuts or change in Design.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records, Red Pen Mark up
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature