## Catchpit
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | A | B | C | 0 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications: Regional Infrastructure Technical Specification (RITS) Activity: Uplift/Repair of existing Catchpit |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved by: Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Director |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Designer | Eng. Rep / NZTA | Contractor | Date
1.0. CONSTUCTION
1.01 | Removal of Catchpit Cast Iron Frame and Grate | Removal of frame and grate and insitu riser | M | Each catchpit to uplift/repair | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | I | I | A | dd/mm/yy
1.02 | Installation of Riser | Installation and grouting of riser using epoxy/sealant. | M | Each catchpit to uplift/repair | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | I | I | A | dd/mm/yy
1.03 | Backfill Inspection | Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit. | H | Each catchpit to uplift/repair | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | I | I | A | dd/mm/yy
1.04 | Concreting | Concreting of Catchpit apron | M | Each catchpit to uplift/repair | Visual / Photo | Site Engineers Approval | Concrete Docket | Contractor |  | I | I | A | dd/mm/yy
1.05 | Installation Cast Iron Frame & Grate | Concreting of frame and grate | M | Each catchpit to uplift/repair | Visual / Photo | Catchpit s grate and frames shall be cast iron and certified under AS3996:2019 | Data Sheet | Contractor |  | I | I | A | dd/mm/yy
1.06 | Final Inspection | Cleaning/Removal of debris from inside catchpit | M | For every catchpit to uplift/repair | Visual / Photo | Visual Inspection | Photo | Contractor |  | I | I | A | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Sheet1
1. Pre-Construction Design Approval: Confirm approved drawings and specifications. Product Acceptance: Ensure all materials (precast units, pipes, grates) are on the Acceptable Products List. 2. Excavation & Base Preparation Excavation: Check excavation is to correct line, level, and dimensions. Foundation: Inspect for suitable subgrade; if unsuitable, ensure remedial works are completed. Base: Confirm correct bedding material and compaction. 3. Catchpit Installation Placement: Ensure catchpit is placed at correct location, orientation, and level. Alignment: Check inlet/outlet pipe connections for correct alignment and seal. Jointing: Inspect all joints for watertightness. 4. Backfilling Material: Use approved backfill material. Compaction: Backfill in layers and compact to specified density. Protection: Protect catchpit from damage during backfilling. 5. Surface Works Grate & Frame: Install to correct level (flush with finished surface or as specified). Surround: Ensure concrete surround (if required) is to specification. 6. Final Inspection Cleaning: Remove debris from inside catchpit. Functionality: Confirm free flow of water through catchpit and pipes. Finish: Check for damage, correct installation, and compliance with drawings. 7. Documentation As-Built Records: Submit as-built plans and inspection records. Checklist: Complete and sign the RITS Stormwater Catchpit Checklist.