## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Uplift or Repair Catchpit | itp |  |  |  |  | ITP - Uplift or Repair Catchpit Rev A
section | 1.0. CONSTUCTION
checkpoint | 1.01 - Removal of Catchpit Cast Iron Frame and Grate
label | Detail of Activity / Test - Removal of frame and grate and insitu riser
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
checkpoint | 1.02 - Installation of Riser
label | Detail of Activity / Test - Installation and grouting of riser using epoxy/sealant.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
checkpoint | 1.03 - Backfill Inspection
label | Detail of Activity / Test - Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit.
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Concreting
label | Detail of Activity / Test - Concreting of Catchpit apron
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Concrete Docket
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
checkpoint | 1.05 - Installation Cast Iron Frame & Grate
label | Detail of Activity / Test - Concreting of frame and grate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Catchpit s grate and frames shall be cast iron and certified under AS3996:2019
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
checkpoint | 1.06 - Final Inspection
label | Detail of Activity / Test - Cleaning/Removal of debris from inside catchpit
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For every catchpit to uplift/repair
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Visual Inspection
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature