## Sheet1
INSPECTION & TEST PLAN
|  | Contract Name: 7069- Ngawha- Reinjection Line | [6 empty] | Rev: | Originator | Date | Approved | Date
[5 empty] | Hold Point (H) | Verify (V) |  |  | 0 | Cameron | 24/04/2025
Hinge
|  |  | Contractual Obligations |  | Submit (S) | Review (R) |  |  | 1
ITP001- Whainui Matari- Remediation Works |  |  |  |  | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Client | UCCL | Client | DATE |  | COMMENTS
Signature
Materials
Concrete | All concrete to be 30 mpa Grade |  |  | Prior to Placement |  |  |  | R, S | R, W, A
Backfill Material | Geotechnical Spec (Site Material) | Visual Check |  | Prior to Placement | Free from Organic Material, Meets Grading |  |  | R, S | R, W, A
Compact |  |  |  | Prior to Placement |  |  |  | R, S | R, W, A
Pre Construction Site works
Layer Placement | Project Specification | Visual Check | UCCL | Each Layer | Max 200-300 Loose Layer |  |  | R, S | R, W, A
Compaction Testing | NZS 4431/ ASTM D1557 | Visual Check, Scala test | UCCL | Once desired layer is Achived | 100 kpa Compaction Grade |  |  | R, S | R, W, A
Backfill Around Structures | Drawings | Visual Check | UCCL | During Works | No voids, Hand compact Near structures |  |  | R, S | R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-M-005 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-M-006 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-S-021 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
PS: Concrete - Procurement | 22-30-S-021 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
PS: Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-M-005 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-M-006 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-S-021 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
PS: Concrete - Procurement | 22-30-S-021 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
PS: Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-M-002 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-M-003 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-C-020 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
PG: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
PG: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Pipe support Foundations: PGL-04, 06, 07 | 22-30-M-002 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PGL-04, 06, 07 | 22-30-M-003 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
Pipe support Foundations: PGL-04, 06, 07 | 22-30-C-020 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval |  |  | R, S | R, W, A
PGL: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
PGL: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Brine Pump | 22-30-C-020 (Dimentions and Location) | Visual Check | UCCL | Prior to works Comencing | Engineers Approval |  |  | R, S | R, W, A
BP: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
BP: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Seal Water | 22-30-M-007 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, W, A
Seal Water | RFI-CEC Ref: 18830 (Spec) | Visual Check | UCCL | Prior to works Comencing | Engineers Approval |  |  | R, S | R, W, A
Seal: Concrete - Procurement | RFI-CEC Ref: 18830 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval |  |  | W | R, A
Seal: Reinforcing - Placement | RFI-CEC Ref: 18830 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval |  |  | R, S | R, A, V
Excavation and installation
Post Construction
As builts and Redline Markup |  | Asbuilt file | UCCL | Following completion of construction | As built drawings, redline markups and RAMM sheets |  |  | S | A