## Sheet1
Concrete | All concrete to be 30 mpa Grade | — | — | Prior to Placement | — | R, S | R, W, A | Concrete | SPECIFICATION REFERENCE: All concrete to be 30 mpa Grade | TEST REQUIRED: — | INSPECTION BY: — | TASK TIMING OR TASK FREQUENCY: Prior to Placement | ACCEPTANCE CRITERIA: — | UCCL: R, S | Client: R, W, A | Concrete
Backfill Material | Geotechnical Spec (Site Material) | Visual Check | — | Prior to Placement | Free from Organic Material, Meets Grading | R, S | R, W, A | Backfill Material | SPECIFICATION REFERENCE: Geotechnical Spec (Site Material) | TEST REQUIRED: Visual Check | INSPECTION BY: — | TASK TIMING OR TASK FREQUENCY: Prior to Placement | ACCEPTANCE CRITERIA: Free from Organic Material, Meets Grading | UCCL: R, S | Client: R, W, A | SPECIFICATION REFERENCE: All concrete to be 30 mpa Grade
Compact | — | — | — | Prior to Placement | — | R, S | R, W, A | Compact | SPECIFICATION REFERENCE: — | TEST REQUIRED: — | INSPECTION BY: — | TASK TIMING OR TASK FREQUENCY: Prior to Placement | ACCEPTANCE CRITERIA: — | UCCL: R, S | Client: R, W, A | TEST REQUIRED: —
Layer Placement | Project Specification | Visual Check | UCCL | Each Layer | Max 200-300 Loose Layer | R, S | R, W, A | Layer Placement | SPECIFICATION REFERENCE: Project Specification | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Each Layer | ACCEPTANCE CRITERIA: Max 200-300 Loose Layer | UCCL: R, S | Client: R, W, A | INSPECTION BY: —
Compaction Testing | NZS 4431/ ASTM D1557 | Visual Check, Scala test | UCCL | Once desired layer is Achived | 100 kpa Compaction Grade | R, S | R, W, A | Compaction Testing | SPECIFICATION REFERENCE: NZS 4431/ ASTM D1557 | TEST REQUIRED: Visual Check, Scala test | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Once desired layer is Achived | ACCEPTANCE CRITERIA: 100 kpa Compaction Grade | UCCL: R, S | Client: R, W, A | TASK TIMING OR TASK FREQUENCY: Prior to Placement
Backfill Around Structures | Drawings | Visual Check | UCCL | During Works | No voids, Hand compact Near structures | R, S | R, W, A | Backfill Around Structures | SPECIFICATION REFERENCE: Drawings | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: During Works | ACCEPTANCE CRITERIA: No voids, Hand compact Near structures | UCCL: R, S | Client: R, W, A | ACCEPTANCE CRITERIA: —
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-M-005 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | SPECIFICATION REFERENCE: 22-30-M-005 (Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | UCCL: R, S
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-M-006 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | SPECIFICATION REFERENCE: 22-30-M-006 (Description) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | Client: R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | 22-30-S-021 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24 | SPECIFICATION REFERENCE: 22-30-S-021 (Spec) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | Backfill Material
PS: Concrete - Procurement | 22-30-S-021 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | PS: Concrete - Procurement | SPECIFICATION REFERENCE: 22-30-S-021 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | SPECIFICATION REFERENCE: Geotechnical Spec (Site Material)
PS: Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | PS: Reinforcing - Placement | SPECIFICATION REFERENCE: DRW No. SPEC 02. | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | TEST REQUIRED: Visual Check
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-M-005 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-18, 19, 20, 21 | SPECIFICATION REFERENCE: 22-30-M-005 (Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | INSPECTION BY: —
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-M-006 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-18, 19, 20, 21 | SPECIFICATION REFERENCE: 22-30-M-006 (Description) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | TASK TIMING OR TASK FREQUENCY: Prior to Placement
Pipe support Foundations: PS-18, 19, 20, 21 | 22-30-S-021 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PS-18, 19, 20, 21 | SPECIFICATION REFERENCE: 22-30-S-021 (Spec) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | ACCEPTANCE CRITERIA: Free from Organic Material, Meets Grading
PS: Concrete - Procurement | 22-30-S-021 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | PS: Concrete - Procurement | SPECIFICATION REFERENCE: 22-30-S-021 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | UCCL: R, S
PS: Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | PS: Reinforcing - Placement | SPECIFICATION REFERENCE: DRW No. SPEC 02. | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | Client: R, W, A
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-M-002 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PG-01, 02, 03, 05, 06 | SPECIFICATION REFERENCE: 22-30-M-002 (Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | Compact
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-M-003 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PG-01, 02, 03, 05, 06 | SPECIFICATION REFERENCE: 22-30-M-003 (Description) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | SPECIFICATION REFERENCE: —
Pipe support Foundations: PG-01, 02, 03, 05, 06 | 22-30-C-020 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PG-01, 02, 03, 05, 06 | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | TEST REQUIRED: —
PG: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | PG: Concrete - Procurement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | INSPECTION BY: —
PG: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | PG: Reinforcing - Placement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | TASK TIMING OR TASK FREQUENCY: Prior to Placement
Pipe support Foundations: PGL-04, 06, 07 | 22-30-M-002 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PGL-04, 06, 07 | SPECIFICATION REFERENCE: 22-30-M-002 (Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | ACCEPTANCE CRITERIA: —
Pipe support Foundations: PGL-04, 06, 07 | 22-30-M-003 (Description) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PGL-04, 06, 07 | SPECIFICATION REFERENCE: 22-30-M-003 (Description) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | UCCL: R, S
Pipe support Foundations: PGL-04, 06, 07 | 22-30-C-020 (Spec) | Visual Check | UCCL | Prior to works Comencing, Each Support | Engineers Approval | R, S | R, W, A | Pipe support Foundations: PGL-04, 06, 07 | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | Client: R, W, A
PGL: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | PGL: Concrete - Procurement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | Layer Placement
PGL: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | PGL: Reinforcing - Placement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | SPECIFICATION REFERENCE: Project Specification
Brine Pump | 22-30-C-020 (Dimentions and Location) | Visual Check | UCCL | Prior to works Comencing | Engineers Approval | R, S | R, W, A | Brine Pump | SPECIFICATION REFERENCE: 22-30-C-020 (Dimentions and Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | TEST REQUIRED: Visual Check
BP: Concrete - Procurement | 22-30-C-020 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | BP: Concrete - Procurement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | INSPECTION BY: UCCL
BP: Reinforcing - Placement | 22-30-C-020 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | BP: Reinforcing - Placement | SPECIFICATION REFERENCE: 22-30-C-020 (Spec) | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | TASK TIMING OR TASK FREQUENCY: Each Layer
Seal Water | 22-30-M-007 (Location) | Visual Check | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, W, A | Seal Water | SPECIFICATION REFERENCE: 22-30-M-007 (Location) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | ACCEPTANCE CRITERIA: Max 200-300 Loose Layer
Seal Water | RFI-CEC Ref: 18830 (Spec) | Visual Check | UCCL | Prior to works Comencing | Engineers Approval | R, S | R, W, A | Seal Water | SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec) | TEST REQUIRED: Visual Check | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to works Comencing | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, W, A | UCCL: R, S
Seal: Concrete - Procurement | RFI-CEC Ref: 18830 (Spec) | Concrete mix design | UCCL | Following Award | Engineers Approval | W | R, A | Seal: Concrete - Procurement | SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec) | TEST REQUIRED: Concrete mix design | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following Award | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: W | Client: R, A | Client: R, W, A
Seal: Reinforcing - Placement | RFI-CEC Ref: 18830 (Spec) | Engineers inspection | UCCL | Prior to Concrete Placement | Engineers Approval | R, S | R, A, V | Seal: Reinforcing - Placement | SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec) | TEST REQUIRED: Engineers inspection | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement | ACCEPTANCE CRITERIA: Engineers Approval | UCCL: R, S | Client: R, A, V | Compaction Testing
As builts and Redline Markup | — | Asbuilt file | UCCL | Following completion of construction | As built drawings, redline markups and RAMM sheets | S | A | As builts and Redline Markup | SPECIFICATION REFERENCE: — | TEST REQUIRED: Asbuilt file | INSPECTION BY: UCCL | TASK TIMING OR TASK FREQUENCY: Following completion of construction | ACCEPTANCE CRITERIA: As built drawings, redline markups and RAMM sheets | UCCL: S | Client: A | SPECIFICATION REFERENCE: NZS 4431/ ASTM D1557
TEST REQUIRED: Visual Check, Scala test
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Once desired layer is Achived
ACCEPTANCE CRITERIA: 100 kpa Compaction Grade
UCCL: R, S
Client: R, W, A
Backfill Around Structures
SPECIFICATION REFERENCE: Drawings
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: During Works
ACCEPTANCE CRITERIA: No voids, Hand compact Near structures
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24
SPECIFICATION REFERENCE: 22-30-M-005 (Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24
SPECIFICATION REFERENCE: 22-30-M-006 (Description)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PS-02, 03, 04, 07, 08, 10, 11, 17, 22, 24
SPECIFICATION REFERENCE: 22-30-S-021 (Spec)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
PS: Concrete - Procurement
SPECIFICATION REFERENCE: 22-30-S-021 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
PS: Reinforcing - Placement
SPECIFICATION REFERENCE: DRW No. SPEC 02.
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
Pipe support Foundations: PS-18, 19, 20, 21
SPECIFICATION REFERENCE: 22-30-M-005 (Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PS-18, 19, 20, 21
SPECIFICATION REFERENCE: 22-30-M-006 (Description)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PS-18, 19, 20, 21
SPECIFICATION REFERENCE: 22-30-S-021 (Spec)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
PS: Concrete - Procurement
SPECIFICATION REFERENCE: 22-30-S-021 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
PS: Reinforcing - Placement
SPECIFICATION REFERENCE: DRW No. SPEC 02.
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
Pipe support Foundations: PG-01, 02, 03, 05, 06
SPECIFICATION REFERENCE: 22-30-M-002 (Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PG-01, 02, 03, 05, 06
SPECIFICATION REFERENCE: 22-30-M-003 (Description)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PG-01, 02, 03, 05, 06
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
PG: Concrete - Procurement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
PG: Reinforcing - Placement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
Pipe support Foundations: PGL-04, 06, 07
SPECIFICATION REFERENCE: 22-30-M-002 (Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PGL-04, 06, 07
SPECIFICATION REFERENCE: 22-30-M-003 (Description)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Pipe support Foundations: PGL-04, 06, 07
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing, Each Support
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
PGL: Concrete - Procurement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
PGL: Reinforcing - Placement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
Brine Pump
SPECIFICATION REFERENCE: 22-30-C-020 (Dimentions and Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
BP: Concrete - Procurement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
BP: Reinforcing - Placement
SPECIFICATION REFERENCE: 22-30-C-020 (Spec)
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
Seal Water
SPECIFICATION REFERENCE: 22-30-M-007 (Location)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Seal Water
SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec)
TEST REQUIRED: Visual Check
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to works Comencing
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, W, A
Seal: Concrete - Procurement
SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec)
TEST REQUIRED: Concrete mix design
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following Award
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: W
Client: R, A
Seal: Reinforcing - Placement
SPECIFICATION REFERENCE: RFI-CEC Ref: 18830 (Spec)
TEST REQUIRED: Engineers inspection
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Prior to Concrete Placement
ACCEPTANCE CRITERIA: Engineers Approval
UCCL: R, S
Client: R, A, V
As builts and Redline Markup
SPECIFICATION REFERENCE: —
TEST REQUIRED: Asbuilt file
INSPECTION BY: UCCL
TASK TIMING OR TASK FREQUENCY: Following completion of construction
ACCEPTANCE CRITERIA: As built drawings, redline markups and RAMM sheets
UCCL: S
Client: A