## ITP-003
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # M3RNAR-FUL-QAC-ITP-003
[11 empty] | Revision : 2 | Date : 30/01/2025
Client: |  | APAM |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Northern Access Road |  | Preparation of Subgrade |  | Name: Leo Watson |  | Name: Jack Wood |  |  | Name: Damon Bromwich
Job No: |  | 7436000 |  | Specifications: Department of Transport Standard Specification Section 204 as outlined in M3R-BECA-001-SPC-00001[C04]
|  |  |  | Structure / Component: Earthworks |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: NAR & Sunbury Road |  | Date : 09/07/25 |  | Date : 08/08/2025 |  |  | Date : 08/08/25
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Survey Set-Out |  | Prior to commencement of excavation | Area has been set out in accordance with the drawings | Drawings, Work Procedure | Verify | This ITP signed | IP | Site Engineer/ Surveyor | N/A |  | N/A
2.2 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2.3 | Subgrade Material Properties |  | Each Lot | Material at cut floor level to have CBR > 2% as per drawing 12001. | Drawings | Test Point | Test Reports | TP | Site Engineer | N/A |  | N/A
2.4 | Inspection of Subgrade Material |  | Each lot | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on suitability in accordance with 204.04. | 204.06 (c) | Verify | This ITP Signed Off | HP | Site Engineer/ Superintendent |  |  | N/A
2.5 | Unsuitable Material |  | Each Lot | Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review. | 204.07 (d) | Visual Inspection | This ITP Signed Off | HP | Site Engineer/ Superintendent |  |  | N/A
2.6 | Groundwater |  | Each Lot | Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater | 204.06 (h) | Visual inspection | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
2.7 | Trimming and Level conformity (Scale B for NAR) |  | Each Lot | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2. Level tolerances: Range x = +5, -25mm Max S = 15 mm 40 measurements per lot (Scale B) | 204.03(g) | Survey Report | Survey Record | SCP | Site Engineer/ Surveyor | N/a |  | N/A
2.8 | Trimming and Level conformity (Scale A for Sunbury Rd) |  | Each Lot | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2. Level tolerances: Range x = +5, -15mm Max S = 12 mm 80 measurements per lot (Scale A) | 204.03(g) | Survey Report | Survey Record | SCP | Site Engineer/ Surveyor | N/a |  | N/A
3 | Testing
3.1 | Proof Rolling |  | Each Lot | Proof rolls to be conducted in accordance with Section 173 of the Department of Transports Standard Specification | Section 173 | Visual Inspection | This ITP signed off | HP* WP | Site Engineer/ Superintendent |  |  | N/A
3.2 | Minimum Testing |  | Each Lot | Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142 | 204.14 c | Test Point | This ITP signed off | HP* WP | Site Engineer/ Superintendent |  |  | N/A
3.3 | Compaction Testing (Scale B for NAR) |  | Each Lot | All Type A Material = minimum compaction 98% MDD Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% MDD. Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% MDD. Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% MDD. | Table 204.131 | Test Point | Test Records Lot Register | TP | Site Engineer | N/A |  | N/A
3.4 | Compaction Testing (Scale A for Sunbury Rd) |  | Each Lot | All Type A Material = minimum compaction 99% MDD Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD. Type B Material placed within 400 mm of top of Type B Material = minimum compaction 97% MDD. Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD. | Table 204.131 | Test Point | Test Records Lot Register | TP | Site Engineer | N/A |  | N/A
3.5 | Compaction Testing (Small Lots) |  | Each Lot | Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% MDD. | 173.04 d | Test Point | Test Records Lot Register | TP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a class C there is no scale C so does it revert to scale B? Reply: Section 204.031 and table 204.16
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale C? Table 204.131
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale C? Table 204.131