## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | M3RNAR-FUL-QAC-ITP-001 - Clearing & Grubbing | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-001 - Clearing & Grubbing Rev3
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP,CSEMP, ERA, QMP, CHMP, SWMS, Hume Council Permit No: P25490
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, CSEMP, ERA, QMP, CHMP, SWMS, Permit No: P25490
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Flora & Fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | REFERENCE DOCUMENTS: CEMP, ECP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.4 Permit to distrurb flora & fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Obtain Part 13 Permit & PP010l permit from APAM prior to tree removal. Obtain all other permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | REFERENCE DOCUMENTS: CEMP, ECP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
section | Clear & Grub
checkpoint | 2.1 Lot start date
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Insert lot start date:
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Define work area
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | REFERENCE DOCUMENTS: 201.03
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 2.3 Identify No-go Zones
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing. Signage shall be erected outside the limit of the of the vegetation or the habitat site.
label | REFERENCE DOCUMENTS: Drawings 201.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.4 Clear felling distances of trees are adequate.
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Clear and grub trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
label | ○ Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
label | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.7 Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works or otherwise transported to the APAM mulch laydown area.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials shall be sent to APAM site recycling facilities.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-002 - Profiling | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-002 - Profiling Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Profiling Works
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
label | REFERENCE DOCUMENTS: 402.02
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | Date Completed:
checkpoint | 2.2 Depth check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
label | REFERENCE DOCUMENTS: 402.02
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | Date Completed:
checkpoint | 2.3 Temporary ramping (longitudinal)
label | FREQUENCY: Longitudinal edges
label | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
label | REFERENCE DOCUMENTS: 402.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | Date Completed:
checkpoint | 2.4 Temporary ramping (transverse)
label | FREQUENCY: Transverse Edges
label | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
label | REFERENCE DOCUMENTS: 402.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-003 - Subgrade Preparation | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-003 - Subgrade Preparation Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Drawings, Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.2 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Subgrade Material Properties
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Material at cut floor level to have CBR > 2% as per drawing 12001.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Inspection of Subgrade Material
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on suitability in accordance with 204.04.
label | REFERENCE DOCUMENTS: 204.06 (c)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Unsuitable Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
label | REFERENCE DOCUMENTS: 204.07 (d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 Groundwater
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | REFERENCE DOCUMENTS: 204.06 (h)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 Trimming and Level conformity (Scale B for NAR)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
label | ○ Level tolerances:
label | — Range x = +5, -25mm
label | — Max S = 15 mm
label | — 40 measurements per lot (Scale B)
label | REFERENCE DOCUMENTS: 204.03(g)
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.8 Trimming and Level conformity (Scale A for Sunbury Rd)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
label | ○ Level tolerances:
label | — Range x = +5, -15mm
label | — Max S = 12 mm
label | — 80 measurements per lot (Scale A)
label | REFERENCE DOCUMENTS: 204.03(g)
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Proof Rolling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the Department of Transports Standard Specification
label | REFERENCE DOCUMENTS: Section 173
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*, WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 3.2 Minimum Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
label | REFERENCE DOCUMENTS: 204.14 c
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*, WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 3.3 Compaction Testing (Scale B for NAR)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All Type A Material = minimum compaction 98% MDD
label | ○ Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% MDD.
label | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% MDD.
label | REFERENCE DOCUMENTS: Table 204.131
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.4 Compaction Testing (Scale A for Sunbury Rd)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All Type A Material = minimum compaction 99% MDD
label | ○ Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
label | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 97% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
label | REFERENCE DOCUMENTS: Table 204.131
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.5 Compaction Testing (Small Lots)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% MDD.
label | REFERENCE DOCUMENTS: 173.04 d
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-004 - Type A Fill Placement | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-004 - Type A Fill Placement Rev2
section | Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Placement/ Each Lot
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Material Approval
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
label | ○ Assigned CBR to be greater than 10%, swell is to equal or less than 1.5%, unless approved as expansive.
label | ○ Permeability of less than 5X10^-9 for capping and verge material
label | REFERENCE DOCUMENTS: Table 204.041
label | INSPECTION/TEST METHOD: Verfiy
label | RECORD OF CONFORMITY: Aconex Acceptance
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Verify Material
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent
label | REFERENCE DOCUMENTS: Cl. 204.04(b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Record (If silt is proposed for Type A material)
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.2 Inspection of fill area
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: 204.10 (b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Layer Thickness
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.10(d)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Maximum Lot Size
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
label | REFERENCE DOCUMENTS: DTPs Spec. Table 204.142
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Proof Roll
label | FREQUENCY: Prior to placement
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the Department of Transports Standard Specification
label | REFERENCE DOCUMENTS: 173.03, 204.12, 204.10 (b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Site Foreman/ Superintendent
textbox | Date Completed:
checkpoint | 2.5 Type A Placement
label | FREQUENCY: Prior to Placement/ Each Lot
label | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather
label | ○ Any rocky material present must be uniform throughout the layer
label | ○ Each layer shall be kept generally parallel to the surface of subgrade
label | REFERENCE DOCUMENTS: 204.10 (d) (i). 204.10 (d) (ii).
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Reduced Test Frequency
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
label | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
label | INSPECTION/TEST METHOD: Test Record
label | RECORD OF CONFORMITY: Test Records
label | AP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 3.2 Compaction Testing (Scale B for NAR)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
label | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Compaction Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 Compaction Testing (Scale A for Sunbury Rd)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Type A material should be compacted to 99% Characteristic Value of Density Ratio (Scale A).
label | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Compaction Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.4 Compaction Testing (Small Lots)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
label | REFERENCE DOCUMENTS: 173.04 d
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.5 Maximum Particle Size
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
label | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.6 CBR/Swell
label | FREQUENCY: First lot only
label | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
label | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(i) Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: CBR/Swell Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.7 Atterberg Limit Tests
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
label | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: PI Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.8 Permeability
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
label | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Permeability Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.9 Material Property Testing (Scale B for NAR)
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
label | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: NATA test report
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.10 Material Property Testing (Scale A for Sunbury Rd)
label | FREQUENCY: Each lot, unless reduced frequency has been approved
label | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
label | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: NATA test report
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.11 Survey Conformance (Scale B for NAR)
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
label | ○ Scale B:
label | — Range x = +5,-25
label | — Max S = 15mm
label | — 40 measurements per lot
label | REFERENCE DOCUMENTS: 204.03
label | INSPECTION/TEST METHOD: Survey conformance point
label | RECORD OF CONFORMITY: Survey report, Lot Register
label | WP, SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
textbox | Date Completed:
checkpoint | 3.12 Survey Conformance (Scale A for Sunbury Rd)
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
label | ○ Scale A:
label | — Range x = +5,-15
label | — Max S = 12mm
label | — 80 measurements per lot
label | REFERENCE DOCUMENTS: 204.03
label | INSPECTION/TEST METHOD: Survey conformance point
label | RECORD OF CONFORMITY: Survey report, Lot Register
label | WP, SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: