## Table 1
No. |  | Description Inspection / test |  | Frequency | Spec/standard | Acceptance Criteria |  | Measuring Devices |  | Reporting Format | Inspected by* |  |  | Hold Points Sign off | Remarks
[11 empty] | HCL | SC | Consult
1 |  | Material Compliance
1.1 |  | Fill Materials
1.1.1 |  | Bedding and Backfill GAP65 or AP40 |  | Per Batch | CIV Spec - S12.3.5 DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject |  | N/A |  | Dockets / Material Data Sheets | R | SUB | R | Hold Point | —
1.2 |  | Pits/Chamber
1.2.1 |  | PCC Risers/Chambers With HN-HO-72 Load Bearing Capacity |  | Each Unit | CIV Spec - S12.3.3 | Accept/Reject |  | N/A |  | Dockets / Material Data Sheets | R | SUB | R | Hold Point | —
1.2.2 |  | Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G |  | Each unit | CIV Spec - S9.3.8 | Shop drawings, Dockets/ Visual Checks |  | N/A |  | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | —
1.3 |  | Concrete Mix
1.3.1 |  | Standard Concrete Mix |  | Each Structure | CIV Spec - S13.3.1.1 | Accept/Reject |  | N/A |  | Design Mix | R | SUB | R | Hold Point | —
1.4 |  | Reinforcement
1.4.1 |  | Reinforcement Bending Schedules |  | Each Structure | CIV Spec - S14.3.1 | Accept/Reject |  | N/A |  | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | —
1.4.2 |  | Bending Schedules |  | Each Structure | CIV Spec - S14.4.6 | Accept/Reject |  | N/A |  | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | —
1.5 |  | Waterproofing
1.5.1 |  | Pipe & Pit Waterproofing – Hydrotite CJ 0725 3K or Similar |  | Each Pipe and Structure | DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject |  | N/A |  | Dockets/ Technical Data Sheets | R | SUB | R | — | —
2 |  | Construction
2.1 |  | Pre-Condition Assessments
2.1.1 |  | Survey Setout Chambers/Pits Position and Heights |  | Each Manhole | N/A | Survey Setout records and Setout pegs, Plans |  | GPS, Total Station |  | Setout CSV file, QC Checklist | — | — | — | — | Coordinates mentioned in plans
2.2 |  | Cast In-Situ Chamber Construction
2.2.1 |  | Excavation Extents |  | Each element installed | CIV Spec - S13.4.1 CIV Spec - S4.5.9 (earthworks section) | N/A |  | Rotating level and GPS |  | N/A | M | — | — | — | —
2.2.2 |  | Chambers/Pits subgrade testing |  | Utility Access Chambers: 2 tests at the base of excavation | CIV Spec - S4.6.2.2 (earthworks section) | Bearing Capacity as mentioned in the drawings For cohesive soil Shear Vane Test at EGL (0.0m), 0.5m and 1.0m depths For non-cohesive soil scala test to 1m depth. Inspection required by engineer for acceptance |  | Shear Vane Scala Penetrometer |  | QC Checklist, Visual Checks, Excel & pdf | M | SUB | W | Witness Point | If ground failing, Engineer to advise MM will attend all witness points
2.2.3 |  | 200mm thick 20MPa concrete bedding |  | Each structure | DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject, 20MPa Concrete |  | N/A |  | QC Checklist, Dockets | M | SUB | R | — | —
2.2.4 |  | Formwork |  | Each Structure | CIV Spec - S13.4.2 | Accept/Reject Dimension Accuracy, Alignment and position |  | GPS/ Total Station/ Rotating Laser |  | QC Checklist, As-Built drawings to confirm the tolerances | M | SUB | I | — | Engineer inspection will be done along with the reinforcement
2.2.5 |  | Reinforcement Laps |  | Each unit | CIV Spec - S14.4.7 DP001-MMD-DRW- CS-B-Z-3013 | Accept/Reject |  | N/A |  | QC Checklist, Visual Checks | M/I | SUB | — | — | Reinforcement Laps to be followed as shown in the plans
2.2.6 |  | Reinforcement fixing and spacing |  | Each Structure | CIV Spec - S14.4.8 | Accept/Reject |  | N/A |  | QC Checklist, Visual Checks | M/I | SUB | I | — | —
2.2.7 |  | Concrete Cover/Spacer blocks |  | Each Structure | CIV Spec - S14.4.8 CIV Spec - S14.4.11 Shop Drawings | Min 50mm unless noted on plans |  | N/A |  | QC Checklist, Visual Checks | M/I | SUB | I | — | —
2.2.8 |  | Duct Penetrations and Water proofing |  | Each Duct | Plans and Shop Drawings | Penetration reinforcement installed as shown on the drawings, Hydrotite CJ 0725 3K wrapped around the duct |  | N/A |  | Pre-Pour QC Checklist | M/I | SUB | R | — | Refer to drawings, shop drawings and plans
2.2.9 |  | Inspection of Reinforcement steel and Formwork |  | Each Structure | CIV Spec - S13.4.2 | Accept/Reject Hydrotite CJ 0725 3K installed in construction joints as per drawings |  | N/A |  | QC Checklist, Visual Checks | R | SUB | I | Hold point | Back formwork shall not be placed until the Engineer Inspection is completed.
2010-02-02 |  | Concrete Placement |  | Each Structure | CIV Spec - S13.4.3.1 | Mix Design Docket |  | N/A |  | Dockets, Pre- Pour QC Checklist | M | SUB | R | — | Pumping concrete to be done with prior approval.
2011-02-02 |  | Concrete Finish |  | Each Structure | CIV Spec - S13.4.5 | Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 |  | N/A |  | QC Checklist, Visual Checks | M | SUB | R | — | —
2012-02-02 |  | Concrete Testing Slump Test 4x Concrete Cylinder tests |  | Each Batch | CIV Spec - S13.5.3.2 | 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour |  | N/A |  | Test Results, QC Checklist | R/M | SUB | R | — | —
2013-02-02 |  | Grout Testing |  | Each Batch | CIV Spec - S13.5.3.3 | Test at 28 days |  | N/A |  | Test Results | R/M | SUB | R | — | —
2.3 |  | Mass Concrete Chambers
2.3.1 |  | Formwork |  | Each Structure | CIV Spec - S13.4.2 CIV Spec - S13.4.3.2 | Accept/Reject Dimension Accuracy, Alignment and position |  | GPS/ Total Station/ Rotating Laser |  | QC Checklist, Visual Checks | M | SUB | I | Hold Point | —
2.3.2 |  | Concrete Placement |  | Each Structure | CIV Spec - S13.4.3.2 | 20MPa Concrete |  | N/A |  | Dockets, Pre- Pour QA Checklist | M | SUB | R | — | —
2.3.3 |  | Duct Penetrations and Water proofing |  | Each Duct | Plans and Shop Drawings | As shown on the drawings, Hydrotite CJ 0725 3K wrapped around the pipe |  | N/A |  | Pre-Pour QA Checklist | M/I | SUB | R | — | Refer to Shop drawings and Plans
2.3.4 |  | Curing |  | Each structure | CIV Spec - S13.4.3.6 | A1/A2 Environment: 3 Days B1/B2 Environment: 7 Days |  | N/A |  | QC Checklist | M | SUB | R | — | —
2.3.5 |  | Grouting of Ducts and Voids |  | Each Duct and Each Structure | CIV Spec - S13.4.3.7 | All voids, and gaps of duct penetrations |  | N/A |  | QC Checklist | M | SUB | I | — | —
2.3.6 |  | Backfilling GAP65 or AP40 |  | Each Structure | CIV Spec - S13.4.4 Table 4.3 (Earthworks Section) | CIV > 25 Clegg Test corelated to an NDM |  | Clegg Hammer |  | QC Checklist, QVC, Clegg Sheets | M | SUB | R | Witness Point | Engineer to inspect before backfilling
2.3.7 |  | Concrete Finish |  | Each Structure | CIV Spec - S13.4.5 | Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 |  | N/A |  | QC Checklist, Visual Checks | M | SUB | R | — | —
2.3.8 |  | Concrete Testing Slump Test 4x Concrete Cylinder tests |  | Each Batch | CIV Spec - S13.5.3.2 | 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour |  | N/A |  | Test Results, QC Checklist | R/M | SUB | R | — | —
2.3.9 |  | Grout Testing |  | Each Batch | CIV Spec - S13.5.3.3 | Test at 28 days |  | N/A |  | Test Results | R/M | SUB | R | — | —
3 |  | Post Construction
3.1 |  | As built Works |  | Each Chamber | CIV Spec - S12.4.10 CIV Spec - S13.4.7 | Position tolerance +/- 20mm Level Tolerance 0mm to +3mm |  | Surveyor Equipment, Total Station |  | Certified As- built PDF and DWG file | R | SUB | R | — | —
5. Document Deliverables (The documents listed below shall be completed and compiled during the course of the construction)
Results of Compactions | [8 empty] | EPD Certificate if applicable
Material Certificates | [8 empty] | As Built
QC records
6. Distribution Records
| Name |  | Position |  |  |  | Company | [8 empty] | Date
| TBA | [5 empty] | Mott McDonalds
| TBA | [5 empty] | BECA
| TBA | [5 empty] | AIAL
 Inspect (I) – To visually examine or measure an item or contracted work operation to verify its conformance to predetermined quality requirements  Review (R) – To examine any form of documentation to establish its acceptability against specified requirements  Surveillance (S) – To observe in-process activities to the degree necessary to be assured that they comply with the established criteria  Test (T) – To subject a component, structure, or system to a controlled set of physical, chemical, environmental or operational conditions to determine or verify its capability to meet specified requirements  Witness (W) – To watch over, observe or visually examine a specific work operation or test performed by others under Contractor supervision  Monitor (M) – General oversight of work in progress with no need to document formally.  Submission (Sub) – Submission of a document
Note: The Engineer shall be provided a minimum of two (2) working days’ notice ahead of a requested inspection.