## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-318-CIV-SSO - Handrails (Supply & Install)
ITP Description: |  | SSO - Handrails (Supply & Install)
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-08-22
ITP created by: |  | Sandy Escalona/ Derek Collins
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for SSO Project
Inspection & Test Plan - SSO - Handrails (Supply & Install)
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-08-22
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings VicRoads Section 610 & 630 AS 1252 AS 5100.6 AS 5131:216 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Concrete Mix Design | VR Clause 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on IFC drawings (32MPa) Enter: Teambinder Material Approval number | Verify Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA/ TB Hold Point Release
2.2 | Drawings | VR Clause 630.05 | Subcontractor is responsible for preparation and verification of shop drawings. Prior fabrication, shop drawings are to be verified by a competent Structural Steel Engineer. Evidence of this review and competency of the reviewer shall be submitted to Nominated Authority. | Verify Document Review | Prior fabrication | HP | Nominated Authority | ConQA/ TB Hold Point Release
2.3 | Material Certification | VR Clause 630.07 | The Subcontractor shall submit to the Nominated Authority the steel manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate. The test certificates shall be related to the steel by trademarks and heat number. | Verify Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA/ TB Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Check for correct documentation | IFC Drawings Manufacture's Installation Guideline | Ensure that all employees and sub contractors are: - Using the correct and complete set of IFC drawings (latest revision as per TeamBinder) - Using approved shop drawings - Follow Manufacturer's recommendations | Document Review | Once, prior to the commencement of activities | HP* | SE/PE/SPE | This ITP
4 | Pre-construction Activities
4.1 | Setting out | IFC Drawings | Set out work in accordance with IFC Drawings. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings Attach: Lot Map-marked up drawing to indicate the location of the Lot | Verify | Prior to starting Works | HP* | Surveyor/ Nominated Authority | This ITP
5 | Construction Activities
5.1 | Footing Installation | IFC Drawings Manufacturer's Installation Guideline | Footings to be constructed by Superintendent following IFC Drawings and Manufacturer's Installation Guidelines. Attach: subcontractors ITP signed off | Visual Site Survey | Each lot | IP | Surveyor/ SE/PE/SPE | This ITP
5.2 | Installing Structures on site snug-tight Condition or tensioned using the Part-turn method if required | IFC Drawings AS 1252 AS 5100.6 Manufacturer's Installation Guideline | Bolts shall be installed as per AS 1252 & AS5100.6. All bolts to be supplied complete with nut, locknut (where specified) & washer. Attach: subcontractors ITP signed off | Visual Site Survey | Each lot | IP | SE/PE/SPE | This ITP
5.3 | Grouting of Base Plate Posts | IFC Drawings AS 1252 AS 5100.6 Manufacturer's Installation Guideline | Superintendent to survey posts and confirm it is within tolerances prior to grouting base plates. Grout as per Engineering specifications. Attach: subcontractors ITP signed off | Check level and alignments | Each lot | IP | SE/PE/SPE | This ITP
5.4 | Completion of Works | IFC Drawings Approved shop drawings | Ensure that works were constructed as per IFC & approved shop drawings. Subcontractor and Superintendent must inspect works for damages and rectification of defects, including but not limited to protective coating and painting touch ups. Attach: subcontractors ITP signed off | Visual | Each lot | IP | SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | DDA audit compliance | IFC Drawings AS 1428.1 AGRD 6A | Ensure compliance for railing heights and offsets from pathways Attach: DDA compliance report | Document Review | Completion of each lot | WP | Surveyor/ SE/PE/SPE | DDA compliance report
6.2 | Compressive Strength Test Results | IFC Drawings Table VR Table 610.051 VR Clause 610.16 | 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | IP | SE/PE | This ITP
6.3 | NCR Close out (if applicable) | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot/ element/ work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /