## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
3bcc8c6a-e0b5-445a-9c48-7acbda6c092f | checklist | CHK-015-CIV-SSO-Stormwater Drainage Pipes installation Rev 0 | itp | CHK-015-CIV-SSO-Stormwater Drainage Pipes installation | 72eb5c0d-fa92-4fab-9d96-44b8c997e86e
99e1804e-4e45-43ab-b127-4fe223d46112 | section | Referenced Documentation
28c64c5e-4a4a-4b7b-a373-e70cf6977ed4 | checkpoint | Referenced Documentation
56471230-9e36-5235-824a-701381e1e23a | note | Document Title: CHK-CIV-SSO-Stormwater Drainage Pipes Installation
87fa11af-ddee-5878-bb74-f1a83c53bb02 | note | Checklist Description: SSO-Stormwater Drainage Pipes Installation
f6745745-f89f-5f68-acaf-06e1d9f2d10e | note | Discipline (e.g. CIV/STR/RAIL): CIV
9bc4022f-6e21-59d2-9114-0a493720dba5 | note | Revision Number: 0
932b7d1d-ac16-5bcc-9649-84b3573ebbfa | note | Revision Date: 22/10/2024
7d3f6a6d-3219-525e-92a5-0be9a71305e6 | note | ITP created by: Sandy Escalona
b81576e0-a7b6-5b5c-a456-93885e3ac70f | note | ITP approved for use by: Sandy Escalona
124dde14-52bc-57ef-9605-66ff657cbfab | note | 1.1 Non Dependent
be61466e-dc03-59fd-a24d-83353b913fd1 | note | Reference: VicRoads, Sec 701
f99c33de-7b67-580e-aed7-bce9ddc64bcc | note | 1.2 Main ITP
37fcee65-3b1c-54b8-a4cb-68b1cc624834 | note | Reference: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
798d4f91-541d-5ae4-a20a-4abcbda2aad1 | note | Acceptance Criteria: This checklist should be used in Conjunction with ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
a82e017a-03a0-5f34-bd2c-d740b2231726 | textbox | Enter: Lot Number
cd259ab8-c745-417b-8b46-f448f2e2b74d | section | Preliminaries - Materials
03c5bae1-27e4-4f2c-8be8-0df09a97db0c | checkpoint | 2.1 Bedding
235c92a4-bc34-55b2-8732-6b89e1139a71 | note | REFERENCE: VicRoads, Sec 701
3ab0f05e-fb4a-5994-8577-fff850ef7a70 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
14692ad1-5a58-5344-9ca8-35b4f724a39b | note | ○ ATTACH: Bedding Material Delivery Docket
1dffcdac-03e3-53d6-ba9a-a5b5e7c61835 | note | METHOD: Document Review
e45df636-7078-5dbe-ba7f-d21c8488f74e | note | FREQUENCY: Each Lot
fc196a72-c7d8-5c58-96dc-839e5e08ba58 | note | CATEGORY: HP*
a7b0ac02-7945-5704-a4e2-770fff4578e5 | note | RESPONSIBILITY: SE
c307264b-34fc-593d-972b-757651326f44 | note | VERIFYING DOCUMENTS: Material Delivery Docket
ee0ecb7c-4009-5643-b17a-67d7e344ba52 | date | Date Completed:
7e4901c2-d546-45ec-96f8-aab58e5ca6d3 | checkpoint | 2.2 Backfill Material
12e42028-026b-54c6-aeb7-080d517e082e | note | REFERENCE: VicRoads, Sec 701
0b285af8-d505-59f8-97c6-0e2a7900f495 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
f8f31ccc-f68c-57b7-a64e-08f8efd7a526 | note | ○ ATTACH: Backfill Material Delivery Docket
4433e1a1-ce93-501b-a5db-ad9b1ef6b9bf | note | METHOD: Document Review
41c946a0-bfd0-5f6c-8f9c-c2b4ad9e9b4a | note | FREQUENCY: Each Lot
593c5d7d-07ba-5465-b0b9-ddf0a0958549 | note | CATEGORY: HP*
d7329c28-7232-5aa9-850a-31491aa828c1 | note | RESPONSIBILITY: SE
f8c0ace5-0d60-5ed2-ae56-a104ab40df2d | note | VERIFYING DOCUMENTS: Material Delivery Docket
b7812e2c-9f82-5e7f-add7-b82f33213e74 | date | Date Completed:
3a382366-3f54-49d5-8823-0f7231e54f10 | checkpoint | 2.3 Stabilized Sand
42215a86-0f23-5c63-bc41-e787863a0be3 | note | REFERENCE: VicRoads, Sec 701
3ca504e1-15e3-5838-b25c-a786fda215a2 | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
81a3c3d8-7edb-50d1-978d-6e1da42aa1aa | note | ○ ATTACH: Selected Backfill Material Delivery Docket
c143a04a-aef6-54bf-901b-ea0173bd49ec | note | METHOD: Document Review
ba281def-3858-5455-b4d0-3d0d4817672f | note | FREQUENCY: Each Lot
aec06b35-ba6c-52d2-8ec7-ae9790814074 | note | CATEGORY: HP*
e2bf5d46-573c-555d-a8d5-bbc736e950b6 | note | RESPONSIBILITY: SE
53385695-36fc-5e67-a667-6733f9ba7d41 | note | VERIFYING DOCUMENTS: Material Delivery Docket
614c7a82-fe01-5d29-820b-25390b95f196 | date | Date Completed:
2f614215-dfa1-46c5-8682-3def2091ac34 | section | Preliminaries - Procedures & Documentation
f5689fa0-0a12-4ba1-abc8-ab4fe9df298f | checkpoint | 3.1 Subcontractor QA Submissions and ITP
7c18befd-a584-5d97-9b7b-68b7b4d10aad | note | REFERENCE: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
f1da693c-fc27-5ff0-9fbf-8b251bc915e7 | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
a7afa351-39dc-5fde-a865-a4c7ccfe014b | note | ○ ATTACH: Subcontractor Signed ITP
f6eaf0fe-d06c-5a9a-be07-11c945e32d29 | note | METHOD: Document Review
c7557291-9b7b-59fa-ae0e-5c8481d840c3 | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
fc43e65b-82b0-5e9b-a44d-7b9953dc8f84 | note | CATEGORY: HP*
5bf13725-515e-57d2-97c8-5d586f3f5096 | note | RESPONSIBILITY: SE
933414b8-f594-5631-beee-28a8e6ad5f44 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
77eadaa9-49ad-57af-bfde-93874c02ca7d | date | Date Completed:
58bfd7fd-4ee2-4c8f-8df3-f8fcfc0e4bf1 | section | Pre-construction Activities
c680acd4-18db-435d-b0c3-27ff83557475 | checkpoint | 4.1 Survey Set-Out
36cecf75-974e-5557-b258-d0d010b032f7 | note | REFERENCE: VicRoads, Cl 710.10
0e42efa9-aa10-51a3-9d8e-81f0ebdd11d5 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
f25cfae8-d646-510b-b440-3ee31c1d1241 | note | ○ The culverts constructed shall be constructed true to line and level.
603a6cc6-f1db-5060-b1ec-df9ff4beffec | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
3a64ce7a-c731-549e-b165-535fa862c8ac | note | METHOD: Survey, Measure
fe4309a1-da1a-5da6-a4ac-55c86041399f | note | FREQUENCY: Each Lot
548d6030-0b15-50e5-a59c-9765a84f99ec | note | CATEGORY: HP*
bf8bebca-3bfb-5d7e-b124-6dff6f71af81 | note | RESPONSIBILITY: SE
23b4a729-5513-5501-81a3-452e1c3c5412 | note | VERIFYING DOCUMENTS: This ITP, Main Lot Map
9606cd2c-9a80-5acc-b613-8b4d1d32c589 | date | Date Completed:
89f8dc8b-cdaf-483e-8217-fbcb6a49688c | section | Construction Activities
4ae4e286-b9f9-4c08-9d83-7513fc7eec94 | checkpoint | 5.1 Trench Excavation
01638902-3bb8-5ddf-a49d-e677a80bccb8 | note | REFERENCE: VicRoads, Cl 701.15
1b029a58-6a19-53f4-9e94-61cf7ca55ffc | note | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
8ff41b3f-f401-5264-9354-e5871a85cbdc | note | ○ Horizontal Clearance from the outside of pipe to the wall of trench to be within the limits:
3523e4f0-c9e8-5429-8bce-fbdd63bfa01e | note | – Corrugated metal culvert: >300mm to <1000mm
317c711e-e8f0-54b7-ada5-90774e6e2e94 | note | – Other pipe culverts: >300mm to <600mm
a285ba7d-982b-578b-b425-f9a1b02b0180 | note | ○ Box Culverts: clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
da9c2c7b-9361-5e78-936f-be47fc1ec909 | note | METHOD: Measure
b792486c-214e-5b06-9078-d8d2db5a5b2e | note | FREQUENCY: Each Lot
9d982791-52a1-58da-ad5e-4aff3ed7b8cc | note | CATEGORY: IP
d49db2f8-ecd6-5877-b3c4-ee35e972ac22 | note | RESPONSIBILITY: SE
6a4dd6d1-9ab1-57f7-96c1-609369b9d505 | note | VERIFYING DOCUMENTS: This ITP
6d3ecbb0-a0ee-542f-8aef-6f5c7a2518ce | date | Date Completed:
baa2f9f9-be7a-4497-83a6-965d61b6678a | checkpoint | 5.2 Trench Base
0d507508-9b22-51de-9578-d38eb963ba94 | note | REFERENCE: VicRoads, Cl 701.16
ff44895a-e625-561f-83e3-baf737479a9b | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
d99f0524-7700-52e5-8832-da81e7f0a6c3 | note | METHOD: Visual
24253746-40af-5b78-9dee-1d2481d3bc65 | note | FREQUENCY: Each Lot
308f6276-f0f3-5229-b394-b7b8a43fff4a | note | CATEGORY: SP
285b6e9e-415c-5b23-8d73-645ff9ae3b79 | note | RESPONSIBILITY: SE
8fd10d97-bf31-5587-adb8-69cd45d4fd95 | note | VERIFYING DOCUMENTS: This ITP
77023f3f-016a-5ae5-8ae9-c4715a7d9c63 | date | Date Completed:
723537d2-1256-4c48-bb82-15b4f2b82ab8 | checkpoint | 5.3 Bedding-Placement and compaction
14959f55-eadd-5c6b-b6f7-2d5847e35925 | note | REFERENCE: VicRoads, Cl 701.16 & 701.20 (a)
4622c73a-9755-57f9-9e3e-5bb8f851badc | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
fb3e2926-67ec-5275-97a1-0b2293038939 | note | – 100 mm where D < 1500 mm
14c237bd-c334-505a-8ace-f0bc252e70ff | note | – 200 mm where D ≥ 1500 mm
8ec2ab5d-58a9-57f1-a644-3456a5c30735 | note | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
f92d31b5-104d-58f3-942d-c081c5087409 | note | METHOD: Visual, Measure
91bc0105-f5fc-5b55-917b-34c12aa36928 | note | FREQUENCY: Each Lot
b215e91f-51bc-5eb4-98b8-02b9436f6c89 | note | CATEGORY: SP
17742daa-8644-56d2-9ab7-7decde1e0ac8 | note | RESPONSIBILITY: SE
a000cdcc-c0d8-5139-810d-03eebe0c8414 | note | VERIFYING DOCUMENTS: This ITP
881880f5-16b2-5d94-93ea-b91e1890fd90 | date | Date Completed:
f5fdc5c4-30f2-448d-a092-e7e7f4b78c15 | checkpoint | 5.4 Laying pipes-Bedding conformity
1b96610e-aea8-52f4-84da-6eab8cfe95c0 | note | REFERENCE: VicRoads, Cl 701.17
dc2c7dca-ff66-571c-89b6-c65b402ae727 | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
3cf263a2-42ae-5303-a7e7-c970c6906bc3 | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
c7a9ecda-2b1e-5d9c-9ff4-33d6e6ee7526 | note | METHOD: Visual
1cd11e2c-0dff-507f-b056-4b7c5217a1ad | note | FREQUENCY: Each Lot
96ff6ba4-5520-5021-a9dc-027cf9f5d102 | note | CATEGORY: HP*
f35a34bf-5bcb-5d9a-b5bd-00749d24e8f3 | note | RESPONSIBILITY: SE
26120fb6-242e-53dc-ac0d-cba0f662fc5a | note | VERIFYING DOCUMENTS: This ITP
f98e620f-5fd0-5688-a6c8-5f7ae9dcb17f | date | Date Completed:
3e6198a5-41e5-4d1b-bb6f-cab81bbb23b8 | checkpoint | 5.5 Pipe Laying
6e45e330-113b-54a1-bdf4-6b1120a6f2eb | note | REFERENCE: VicRoads, Cl 701.16 & 701.17
431620fd-bc2f-5e98-9884-2e4b0028781d | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
7c8bb506-97e4-5fc4-85b9-4c022a4f6b7e | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
10119ab4-1d48-5186-93a4-5d836230856c | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
b71e42c5-cb21-5037-b928-4822d46db5ee | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
e576a221-fa7c-5baa-be0e-7e3133022d77 | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
04d28980-97ce-50d5-85e1-8b0fc5d7f472 | note | METHOD: Visual
5512b086-3adf-5631-996d-e0880aba3b30 | note | FREQUENCY: Each Pipe
44355d1f-6f90-55a4-8b28-efd7f0dea9ce | note | CATEGORY: SP
b1117685-9e89-5504-b0e3-05fe430a9db6 | note | RESPONSIBILITY: SE
cabde53b-54f3-56ab-9f47-4a57f1ec15ea | note | VERIFYING DOCUMENTS: This ITP
75ffb881-67cd-5c93-8c5b-625642a8487c | date | Date Completed:
de22b749-28e7-4460-9ad1-8d15a693f767 | checkpoint | 5.6 Pipe Joints and rotation
fec88bac-40d7-58b2-90ef-c75a7edf37c6 | note | REFERENCE: VicRoads, Cl 701.18
d75300b7-ea95-5fa4-9201-e93d84b098f9 | note | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
f59b518d-cf18-5ea8-a4c8-3521c038f5ec | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
a1f31c35-9d84-542c-a000-d55f414b0fdb | note | METHOD: Visual
0e696e70-1561-5443-aff2-366c41471a55 | note | FREQUENCY: Each Pipe
ad3b116e-4862-524a-9332-4d0944cddd17 | note | CATEGORY: SP
f0db273b-8175-54f2-98ee-7b77628456e4 | note | RESPONSIBILITY: SE
54e52997-2d5c-5c01-96cd-235fe1311e98 | note | VERIFYING DOCUMENTS: This ITP
ce3a5560-56d3-55e7-9b06-643a71ac4c91 | date | Date Completed:
b1243c03-4a24-4162-9a09-c53feb8147b4 | checkpoint | 5.7 Conformity with drawings
41e7499a-33d6-56a3-b56b-1d7baa4bee1d | note | REFERENCE: VicRoads, Cl 701.10
348d1403-4b13-5598-8e1c-9dec07696fb8 | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
84d93c0b-e829-5668-b987-54b27f0d6847 | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
6e6a7f77-caa5-53e4-b189-0e8c43d969f3 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
2a462577-d697-56d6-8bc2-0397aa4d8836 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
9f40fc8e-4ee6-5a51-b471-133af11bf673 | note | (c) invert level of pipes at pits ±50 mm
d0e18f0c-0878-5475-9937-23c87a4f98de | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
1b58f186-f005-52d4-9936-41ac53435663 | note | ○ ATTACH: Survey Report
0eb4498b-7a3f-55c7-9d61-6c330cf03a5c | note | METHOD: Measure
5f350d4d-79f7-55b5-8f13-834603f6d8b6 | note | FREQUENCY: Each Lot
362d98b6-55d6-5432-9940-398e1463d59b | note | CATEGORY: HP*
08460496-4793-5d88-8b62-fb18275c87a0 | note | RESPONSIBILITY: SE
d2c18451-f10c-5a68-a0ae-4df90d20571e | note | VERIFYING DOCUMENTS: Survey Report
43f58d00-4687-56a2-a2c5-b8e30f0d3196 | date | Date Completed:
e2747a35-a326-4997-aebe-c8e76b4b08bd | checkpoint | 5.8 Backfill-Under area to be paved
48d47669-8ba2-58ef-bdc1-57de0b0035a5 | note | REFERENCE: VicRoads, Cl 701.19 (a) i
0613653e-93aa-5681-a91d-9620ab8b7fc9 | note | ACCEPTANCE CRITERIA: Culvert under area to be paved
b44cd530-e86b-5eae-b311-2c28372592f9 | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
053585ac-dc4f-52af-9e3a-5f11958f1986 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
f92d22b9-2b79-54b8-a0a4-c5b145c15e08 | note | METHOD: Visual
08603fb7-a74c-531c-a11a-6c18374c0cc9 | note | FREQUENCY: Each Lot
43a47a30-0d52-5684-afc8-0e4fd3a88a1e | note | CATEGORY: SP
fb80b1f2-c9e5-5377-82c6-a74b0440bf72 | note | RESPONSIBILITY: SE
936b1157-3915-593f-b4cc-5dbff5d9e3fd | note | VERIFYING DOCUMENTS: This ITP
a2a5ed26-66db-5494-b594-4705e664b7cb | date | Date Completed:
94cc2062-cbd4-4dd2-9764-70cf85387c1b | checkpoint | 5.9 Backfill-Under area not to be paved
b51c2d39-b6cc-5ef0-98b3-4828f9ddd962 | note | REFERENCE: VicRoads, Cl 701.19 (a) ii
04e08b22-d600-51b8-85fb-6a57712bb56c | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
e5978db2-e2e9-5936-aba0-626f4a591eae | note | METHOD: Visual
2bac883f-1986-52b3-8d09-878726c6fb59 | note | FREQUENCY: Each Lot
4efa5606-01d5-53d0-8d9b-f031ff54dfdc | note | CATEGORY: SP
287763b0-0c2c-55c4-8cc3-57f74c401892 | note | RESPONSIBILITY: SE
5d9fd264-3653-580b-ad0d-d9d70f4fffd9 | note | VERIFYING DOCUMENTS: This ITP
99067dd6-a1ee-5863-b763-1a1376f05b4f | date | Date Completed:
4d841008-1e90-42e7-b345-ae55df14d8f5 | checkpoint | 5.10 Backfilling with cement stabilised sand
ba7c7b77-8a95-5332-aca9-b365f9d92fc2 | note | REFERENCE: VicRoads, Cl 701.19 (c)
e5285fe7-cc05-5efc-bd0c-7fb3f3d8786f | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
6e6589af-4ef3-583f-91b7-44baaeba4f5a | note | ○ ATTACH: Selected Backfill Material Delivery Docket
8caba614-ffba-5883-a9dc-44cae26b6b2b | note | METHOD: Visual
07fe673b-3c0a-550f-8eac-e973c909011e | note | FREQUENCY: Each Lot
7755e448-d11a-57b9-9e7f-92b9c96ba96e | note | CATEGORY: SP
400ef724-b6ed-5822-8ac4-22d530a433ef | note | RESPONSIBILITY: SE
5e1e3425-cb68-5ea4-821b-22cd17d48698 | note | VERIFYING DOCUMENTS: Material Delivery Docket
5a631b21-c93d-5be6-b07e-ed7b2e4b1799 | date | Date Completed:
003dde94-0e3b-4a0d-9267-851061ba4783 | checkpoint | 5.11 Backfill Placement
5ad7b07d-4c30-5aef-983b-c21fe20cb092 | note | REFERENCE: VicRoads, Cl 701.20
9625e741-14f0-59ca-8497-a5e6adf475d5 | note | ACCEPTANCE CRITERIA: backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
14d29300-cebc-5ca2-8e1f-04664ca67f7c | note | METHOD: Visual
947b1b7d-bf59-59d2-850e-8129ead0f3a8 | note | FREQUENCY: Each Lot
dd5f3e3b-77bc-5fa8-ab56-fe719c7ae264 | note | CATEGORY: SP
bc280a50-fb1d-51a1-9ff5-94486212c552 | note | RESPONSIBILITY: SE
24e04c30-5d3c-55cd-8e4d-99c37d37c5c1 | note | VERIFYING DOCUMENTS: This ITP
cbffc7ff-e425-54a8-95e5-1032ac2cdd3e | date | Date Completed:
273d3a97-5e0c-48ae-bf3e-e0de4913bdaa | checkpoint | 5.12 Backfill Compaction
aa229ea2-ec7a-5ea3-8756-940c83c953e5 | note | REFERENCE: VicRoads, Cl 701.20 (b) (i)
bbb6f316-0cfe-5fbf-b3d9-183731821137 | note | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
5a333a09-a2ad-561a-8d23-f9a97374eccf | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
3ae0ddf6-24d8-590e-a717-6fd830c34c84 | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
01fc1818-45ad-5ddb-8d34-18f4b772ba95 | note | METHOD: Test
224be9fd-7051-530d-aaa1-2307569f9b3f | note | FREQUENCY: Each Lot
77836f4e-3b87-5686-a6c7-da01999b2e67 | note | CATEGORY: HP*
55c40dcb-900b-5309-b428-f093482ac559 | note | RESPONSIBILITY: PE
2a2146ec-f16e-5894-9a45-74f975afe193 | note | VERIFYING DOCUMENTS: This ITP
e5826c8d-eb3b-545c-8fe4-95f68a36d2a5 | date | Date Completed:
9937b774-4a36-409f-998e-240d6fa1ec5a | section | Post-construction Activities
9feb7ed6-ebfb-47aa-94cb-c0542055a774 | checkpoint | 6.1 Compaction and Moisture content tests
003813b5-c405-5289-b277-996c4f39b98b | note | REFERENCE: VicRoads, Cl 701.20
5cd872e2-2123-5305-82f1-fe54a8c13f56 | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
5d938d5d-aae5-5b17-b4fa-5a7592812b9c | note | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
78b5ed81-c26a-5934-aee6-79db1ae2e2a2 | note | ○ ATTACH: Compaction and Moisture content test results
bbfa31a3-bc9c-5b77-94f7-9e930834deee | note | METHOD: Document Review
ffd5a36a-7b1f-53d2-9392-800eaeb84e6a | note | FREQUENCY: Each Lot
eb2ae1fe-d60f-5124-b489-bbe2c8bf5e95 | note | CATEGORY: IP
a80c6c2d-49e4-5ec5-b4fa-71e040bdb130 | note | RESPONSIBILITY: SE/PE
47d67995-a218-5bac-87bb-56d803fee8f5 | note | VERIFYING DOCUMENTS: Test Results
5587677d-bdbb-5b3a-896f-3ac017a5f825 | date | Date Completed:
d39ffdd0-a315-4909-8496-c3e9aa54084d | checkpoint | Final Inspection
eb4baea2-9d76-5d6a-bf0a-2adf57355aca | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9784e178-494b-50cd-9db5-76ecf89f0e29 | textbox | Name:
c29e6b7d-411c-511b-b9f0-5b7c18f04a54 | textbox | Position:
2d9ad4b0-bc7d-51a2-8379-d857127c1318 | date | Date Completed:
a4e037bf-1f2c-4cfe-9322-0287c1ace89b | signoff | Sign ITP
455afee7-eef4-4696-b9e6-39e5c7dc7d4a | checklist | CHK-016-CIV-SSO-Stormwater Drainage Pits Installation Rev 0 | itp | CHK-016-CIV-SSO-Stormwater Drainage Pits Installation | 8e089dbf-3341-4bca-ae38-ef3356f4b1a4
a8c1c694-ba5a-490e-a826-74aabe8ed295 | section | Referenced Documentation
391f973a-2bad-4931-83be-d17f9791acd0 | checkpoint | Referenced Documentation
d93391bc-da9e-56ec-bcfa-e22cdfa15811 | note | Document Title: CHK-CIV-SSO-Stormwater Drainage Pipes Installation
65427a5a-ba2f-5702-ac32-167cd18cb86a | note | Checklist Description: SSO-Stormwater Drainage Pipes Installation
afcf51f9-f05d-53ee-a64f-7022b69b6632 | note | Discipline (e.g. CIV/STR/RAIL): CIV
ef38bd47-7132-5d5f-9d87-f987c8ed8169 | note | Revision Number: 0
69cf9cd9-ab31-5fb3-82fd-81722307ede6 | note | Revision Date: 22/10/2024
f40068e1-bb0f-537e-934a-276220c16059 | note | ITP created by: Sandy Escalona
a99b82f1-2cf6-5f8e-ad9c-af2731549b51 | note | ITP approved for use by: Sandy Escalona
6629630b-b70d-5be6-974d-8a078217c539 | note | 1.1 Non Dependent
155a6e1f-bb52-53a6-a29a-3ddacddb2546 | note | Reference: VicRoads, Section 701
069623cf-ad0e-5789-afc9-0bcfacc37552 | note | 1.2 Main ITP
0b8cd348-0d4b-5c0c-92de-1779d02377ab | note | Reference: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
465b03f5-c069-5edc-990f-7c70689cd5b7 | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
03e5fea5-7d7a-5b26-833f-3d7c669ad895 | textbox | Enter: Lot Number
b62a228c-a3d6-47b7-9c01-b10bbbe794a5 | section | Preliminaries - Materials
3fc44c57-b9f8-4e7d-93ef-a1eb51aefa4b | checkpoint | 2.1 Bedding
6a30ece8-e2a0-51d9-88cc-60936457cdc4 | note | REFERENCE: VicRoads: Cl 701.09 (d)
34ff2d7d-0646-5a45-ae3e-390d89491d12 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
024fa1e7-3ae9-5dfc-a49e-8987354d1c36 | note | METHOD: Document Review
80558a69-7852-57aa-be84-2050c00605c2 | note | FREQUENCY: Each Lot
d0396600-f87f-5a29-ae6a-4cac66303ed4 | note | CATEGORY: HP*
c14afd3e-df44-5fd4-b36d-2bc0f0a0dcbb | note | RESPONSIBILITY: SE
b5bd4392-68a7-5600-851b-40570fc2b047 | note | VERIFYING DOCUMENTS: Material Delivery Docket
b390b99c-79fa-5397-b5ba-96d2c3e5cf8b | date | Date Completed:
08d95df8-e9bc-4af6-bd52-883d6bb06b75 | checkpoint | 2.2 Backfill Material
c8e16543-75d4-5171-a714-271d5c2a6c91 | note | REFERENCE: VicRoads: Cl 701.09 (d)
1584e9a9-5e6b-567d-99b1-d45391af0426 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
bbd3d1df-52b5-5a8d-9370-c735a85047db | note | ○ ATTACH: Backfill Material Delivery Docket
bc056053-1e80-51c1-81b9-0a1167e6e31f | note | METHOD: Document Review
c69bfbf2-57ab-5624-86c3-8667f0ed2d3d | note | FREQUENCY: Each Lot
487df645-e64e-521b-bd1f-36e823a168cd | note | CATEGORY: HP*
a3201a88-00f7-539a-8911-145ffa5ba0ad | note | RESPONSIBILITY: SE
b3e8638a-1b5b-54ba-be31-afa4029c28ca | note | VERIFYING DOCUMENTS: Material Delivery Docket
dc284baa-836e-5265-8356-37f1b9f08d55 | date | Date Completed:
fd0a2560-259e-4b26-9baa-0b8a7343d432 | section | Preliminaries - Procedures & Documentation
da9f0b8c-643d-4be4-bf1a-ef95785583e9 | checkpoint | 3.1 Subcontractor QA Submissions and ITP
d31b8178-b982-5a3b-b8df-a3a8222c87ec | note | REFERENCE: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
cd0432e2-581f-5566-8c6a-c5b8484d7e8f | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
f8efea5a-fc59-5a07-9b35-365b73a0261a | note | ○ ATTACH: Subcontractor Signed ITP
9483e1d7-6785-5cc7-9b52-fb5727bee9b8 | note | METHOD: Document Review
86147f1c-cc7b-5d15-98b4-893584638f11 | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
49f8b011-9db5-57f6-a369-d8ad7b38a0c8 | note | CATEGORY: HP*
cb12d8be-77d8-5f73-ae57-2928826d5fd7 | note | RESPONSIBILITY: SE
4f780d98-057a-52a9-a543-09c5dc2d70c0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
edcf5483-fc82-5d6f-8dcf-3f03d7bb89ad | date | Date Completed:
ddb95f51-61ae-4bb9-ad4f-b07ae07989bb | section | Pre-Construction Activities
d79b2044-c9fe-4969-94a8-ee8870f3d7f9 | checkpoint | 4.1 Survey Set Out
3924545f-6a82-53f3-8de1-3e1a61835e1c | note | REFERENCE: VicRoads, Cl 710.10
ddf3bfd9-c874-5e9d-b6a0-b6a4e5cb7b15 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
c75666e2-fb10-5f6d-aee5-1401ead91c00 | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
76895f1b-7f49-51a7-bed6-01e4d590751a | note | METHOD: Visual inspection
d0607da2-a914-5e41-a5f2-5e9fcfac6ffb | note | FREQUENCY: Each Lot
04f925e2-3f55-54fd-a7ab-d33adb4835e6 | note | CATEGORY: HP*
0ff229da-bd46-59e4-8585-d302e806112b | note | RESPONSIBILITY: SE
8bffb94e-5afa-5f13-9c83-d2201557df0d | note | VERIFYING DOCUMENTS: This ITP
bb30630d-3959-548d-8cf4-fc60428fc648 | date | Date Completed:
20fbb51b-1b57-47e2-a0e8-4612fd06bb2e | section | Construction Activities
1a119f34-b550-4cce-9523-5c36645250e3 | checkpoint | 5.1 Pit Excavation
da968399-15e2-5e39-993e-5c79ad3817dd | note | REFERENCE: VicRoads, Cl 705.05
08e554c4-e92b-54f5-8caf-1cfab9560c12 | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
573b27e3-207d-5141-a26d-c338a7742fb3 | note | METHOD: Visual inspection
684fcead-55bc-55fe-bc2a-cc61c7d06d54 | note | FREQUENCY: Each Lot
1bea1ece-3684-579b-aab6-c665f1d73cb3 | note | CATEGORY: IP
15d3550c-49f6-5fa5-95f1-1ab5437f0ba6 | note | RESPONSIBILITY: SE
fe333c21-b82a-5cb6-ab53-248e9ecc607e | note | VERIFYING DOCUMENTS: This ITP
c7510d87-6c4f-5900-981f-fd94356af3fe | date | Date Completed:
4db20bab-6eef-4a83-8577-dc596bf2c00d | checkpoint | 5.2 Excavation Foundation
ad7cb34a-6b8b-5d29-ba28-8eabb5e2ee6d | note | REFERENCE: VicRoads, Cl 705.05
6c452ab4-231e-578e-8910-cb21fae691a3 | note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness:
22e6edde-873f-5931-a8b9-0be41232fcb6 | note | ○ > 80mm for clay foundations
c954e8d6-7c7a-5ad8-ba6e-6ed2ae8e9651 | note | ○ > 150mm for rock foundations
31e74ba3-2b0b-56aa-8971-95c63ffd9f42 | note | METHOD: Visual inspection
5a7a6080-99fb-5588-ae52-569e0fb38952 | note | FREQUENCY: Each Lot
b706268f-99ca-5dae-aec0-01a2995e9619 | note | CATEGORY: IP
5f10c749-af51-5be5-912f-c62d08ca1602 | note | RESPONSIBILITY: SE
7eef7f85-6f2f-5b9e-aae3-a44c424b0e40 | note | VERIFYING DOCUMENTS: This ITP
476c079b-0852-540f-b98a-1a99457cdaa3 | date | Date Completed:
f6105e09-cdb7-4b18-9909-85a62ce011de | checkpoint | 5.3 Placement of Pit-Conformity with drawings
abb61580-271c-5ed7-a216-b9f500b7c1fe | note | REFERENCE: VicRoads, Cl 701.10
0b3eb9cd-6bbc-5af6-a511-9f34a0e030d8 | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
ec844d64-194b-5fa9-a435-f4e1d13d5f70 | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
cb2a4896-5430-574d-9ae1-dea5342a92b4 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
b7bbf577-1a06-5638-bbee-b64e5ac53662 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
03f9abb5-4cd9-59dd-b86c-f5f3e0176c1e | note | (c) invert level of pipes at pits ±50 mm
7d39e06e-b8a2-5eed-9365-0bcffb2033fc | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
b342ab2f-4873-58a0-9d88-3ee47f84efc4 | note | ○ ATTACH: Survey Report
c05f2239-c663-5fae-b1f1-5b3db92d94aa | note | METHOD: Measure
c1f2a96e-3504-5e54-b4db-4a63e6d04cc6 | note | FREQUENCY: Each Lot
36eda661-9670-5dc2-aebc-6330ab383cfd | note | CATEGORY: HP*
7554b0c9-2399-5cd4-b54c-16d42f58ee18 | note | RESPONSIBILITY: SE
9aec8449-5246-5c57-a47e-50d2e3c76ed4 | note | VERIFYING DOCUMENTS: Survey Report
4055e1c4-46fa-50c7-b6b1-8fa85532cce4 | date | Date Completed:
bb34565b-17c4-4afa-b6f7-f0148f3f6df2 | checkpoint | 5.4 Jointing
fae02156-2cee-57a3-a37a-86359df79ac4 | note | REFERENCE: VicRoads, Cl 705.11 & 705.15
fbae456c-c997-5201-83f2-bb7ce9d02d86 | note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
cac7ac41-4963-58dd-a4d3-399de0cd5cf0 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
772e62ff-3caa-5ea4-8b13-73e6c1b57299 | note | METHOD: Visual inspection
03b5b315-5b56-5486-a21c-8b20b6160ab3 | note | FREQUENCY: Each Lot
3092eadd-1f2e-5ec6-b095-a76158bc2adc | note | CATEGORY: IP
fc69a341-387a-567b-b5d9-20f2aba94ee7 | note | RESPONSIBILITY: SE
4f2c75c5-d9b1-55bb-b3cd-95bb54eed8e9 | note | VERIFYING DOCUMENTS: This ITP
aa3fc116-ba56-5c4e-8b65-4e7fb15d1bbc | date | Date Completed:
453bbf2a-d2da-45c5-b2d5-95ed97a71d25 | checkpoint | 5.5 Shaping of Floor
16d60355-aa0e-5453-9a31-a485e4e17f22 | note | REFERENCE: VicRoads, Cl 705.13
21f7b730-66c9-57b7-84d0-6ec0556d0440 | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe with cementitious mortar, which shall comply with requirements of Clause 610.33
d7a63951-1bb5-585c-924f-8024f17af20c | note | METHOD: Visual inspection
497693e2-ca37-51e6-9eea-f3358e8a31b2 | note | FREQUENCY: Each Lot
d39ec890-c0ed-507a-8023-a48efa31da6e | note | CATEGORY: IP
223ba233-2a02-5868-818f-9a1cd06cf4eb | note | RESPONSIBILITY: SE
38250cd5-81f7-508f-a46c-bbf542323b84 | note | VERIFYING DOCUMENTS: This ITP
dfbba840-4cf6-52e9-87fe-233de0392d66 | date | Date Completed:
dc94c35d-d304-4451-8532-6337b8b0d7a0 | checkpoint | 5.6 Step Irons
037c9d80-7fda-5b3d-a6ea-26eba2753af1 | note | REFERENCE: VicRoads, Cl 705.12
92589653-b20a-5dc5-9404-023c3fe27c33 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder shall not obstruct openings and that water does not discharge on them. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or across a corner of the pit.
e64b36c1-5899-5c76-8c64-a6b41bbbde7d | note | METHOD: Visual inspection
ed69c4a9-691c-5578-8640-614a87115090 | note | FREQUENCY: Each Lot
eefd1582-73c2-58a5-a2f7-466d67526b8f | note | CATEGORY: IP
fbb6c7f2-5fb3-58b6-8d88-5f8bf4799071 | note | RESPONSIBILITY: SE
64856692-79ea-5f3a-b95b-df57fcb52b7a | note | VERIFYING DOCUMENTS: This ITP
db27055e-bbb0-5886-933c-5791330dcbb6 | date | Date Completed:
a0283426-86da-4187-922c-160f828df9a2 | checkpoint | 5.7 Fitting of Covers
8ed197fc-1069-5603-b730-708c7256d982 | note | REFERENCE: VicRoads, Cl 705.17
abf57361-cd3a-54c1-b027-0d213f245e7f | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
bd331345-8be3-5e98-87a3-5cd442e2f79a | note | ○ The level at every point of the perimeter shall be within 10 mm of the design level for that point, and the line of the cover shall be within 10 mm of the design kerb line.
2c494dcf-70f5-5d57-b3dd-d2602843360a | note | METHOD: Visual inspection
06da6996-884a-5f47-a527-fb58bdd28e2f | note | FREQUENCY: Each Lot
d01f06bf-e86a-50ce-95ac-cc1f7ea15e32 | note | CATEGORY: IP
0d3b0ad9-361f-5487-b8db-54cc8c0df631 | note | RESPONSIBILITY: SE
f7c464ff-ddec-51f9-a1c0-49c951552c6f | note | VERIFYING DOCUMENTS: This ITP
3bfa8185-5a9d-5488-b216-ffff11b52806 | date | Date Completed:
4ddf08f6-bb62-40a3-b0a9-5e7c8d668086 | checkpoint | 5.8 Backfilling Around Drainage Pits
43e8b59e-b857-5724-bc86-35c961ea48e0 | note | REFERENCE: VicRoads, Cl 705.18
6fc0f74a-686b-5f81-adc7-c3b439cdf42a | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment
90b0857e-3212-56d3-be10-b70eb8dd9c56 | note | METHOD: Visual inspection
c0c490e0-6e2b-5893-a162-643285394e04 | note | FREQUENCY: Each Lot
3a64e4fc-b73a-5b36-8eff-a22d9b23e755 | note | CATEGORY: IP
ee06b23c-2afe-5c3d-8c12-050e4fba57ff | note | RESPONSIBILITY: SE
4b777db3-d54a-5823-a5ca-c6fe848a015c | note | VERIFYING DOCUMENTS: This ITP
3a2140ef-487a-5f68-bc71-d2fa9d3c64ce | date | Date Completed:
7166cdea-0934-45d4-81bb-4bb9587f207d | section | Post-construction Activities
3f5c94f9-1390-44d8-b6fe-c3968dd299cf | checkpoint | 6.1 Compaction and Moisture content tests
3ff7c2c7-4ab5-5c5b-86c7-0b8a559c2d96 | note | REFERENCE: VicRoads, Cl 701.20
72a860d6-7cea-509f-8e8c-5566b34e8a25 | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
89f66424-4266-5e1a-a3c0-c427bd6dcd88 | note | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
efab15f3-1b68-573b-902d-97e6b8958d83 | note | ○ ATTACH: Compaction and Moisture content test results:
1a7371d5-02e3-5b1e-b9cf-474561b3a052 | note | METHOD: Document Review
919d61c6-6d38-59af-895b-4cefd888f0f3 | note | FREQUENCY: Each Lot
1d0003f8-1f15-55e7-b5c8-25a64ba371c8 | note | CATEGORY: IP
6e020628-784a-5a06-b03f-37795199869d | note | RESPONSIBILITY: SE/PE
b5c2b57e-653a-5735-9752-81ced145e02a | note | VERIFYING DOCUMENTS: Test Results
84624430-4186-52b8-9cc6-ad23f9334ae9 | date | Date Completed:
fdf6ee69-0fbb-4cf5-b969-61879548019e | checkpoint | 6.2 CCTV Inspection
45656097-defd-5d41-a4a5-e301d337eade | note | REFERENCE: VicRoads, Cl 701.30
1d698863-327d-5253-916e-303f0e9f419d | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
6fd47b62-59b1-561b-8034-f0a894cc694d | note | ○ ATTACH: CCTV Report (PDF)
6832c559-685a-55c7-bec5-162b1b31f7b5 | note | METHOD: Document Review
1d6d9662-347a-5f19-b854-564abff0e437 | note | FREQUENCY: Each Lot
776b677f-111f-561e-88c3-b0de9f9e8aeb | note | CATEGORY: HP
56164202-4fa0-5cc3-b675-3c64df0d977f | note | RESPONSIBILITY: Nominated Authority
083124f9-ec9f-5f91-a799-923726cb7a33 | note | VERIFYING DOCUMENTS: CCTV Reports
86e92b63-8739-51fb-88aa-24f4ef8bc706 | date | Date Completed:
e8fbc45f-ed62-4cf8-b4d8-7b88d2fdf54f | signoff | AUTHORITY HOLDPOINT
3c40cf5a-e4b1-43cd-819f-92c89a09c014 | checkpoint | Final Inspection
9272c476-342b-5ab9-9cdd-d7815b1d90f7 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f8f4a644-818d-53d3-8056-0af6327d473d | textbox | Name:
fbf22616-d302-5039-86a3-0728bad8e981 | textbox | Position:
b1d7d0cd-b5d2-58af-ab5a-d6c7dfb01854 | date | Date Completed:
451f22e8-b1a4-4350-bedf-be2e489700c8 | signoff | Sign ITP
| checklist | ITP-209-STR-SSO-SUP Widening Rev 0 | itp | ITP-209-STR-SSO-SUP Widening | 292a57d8-9900-4e70-935b-1e1f4b262101
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d497ddbb-690a-5ce5-9769-5ba4868397d4 | note | Document Title: ITP-209-STR-SSO-SUP Widening
e929758b-a6e1-5710-bad4-a25e190b5970 | note | ITP Description: SSO-SUP Widening
d99d9ddb-b695-578e-a9e6-c5cd1b9698e7 | note | Discipline (e.g. CIV/STR/RAIL): STR
1236ec97-42f0-539b-8ba3-d658883c77e2 | note | Revision Number: 0
713514b7-7f73-5dad-92d0-2151efc37579 | note | Revision Date: 23/10/2024
3468dbb0-971e-56da-92fb-a03e9f4fccac | note | ITP created by: Dimitri Santoreneos
27fa28d4-9dda-5a59-a7bb-dc79f59e425d | note | ITP approved for use by: Sandy Escalona
29d6f386-d9fb-5874-a213-fce82447d1c5 | note | 1.1 Non Dependent
b907d638-0790-5855-b267-8e6028e9370f | note | Reference: VicRoads Section 602 June 2007
4586ffce-e547-5184-b1b9-8249e70f7184 | note | 1.2 Non Dependent
f07f57c3-9f6b-5585-a42c-1bc598bdac1a | note | Reference: VicRoads Section 610 February 2020
563362ad-43ae-5ecf-bf11-353958490915 | note | 1.3 Non Dependent
3f555d7c-5e79-5ea3-8eee-17c9183d9145 | note | Reference: VicRoads Section 611 November 2018
749b6390-6762-5391-96cf-5ff62705774a | note | 1.4 Non Dependent
7bd68e0c-cf5a-5722-a7ee-2238619b4aa5 | note | Reference: VicRoads Section 614 June 2017
0d3520a2-0ca4-58c1-b64a-fb6c3f20fb9f | note | 1.5 Non Dependent
3b779244-e0e2-5627-8db3-9b4f556c281d | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
720360ff-8449-55df-8695-ffe8b37985fe | note | REFERENCE: IFC Drawings VicRoads: Cl 610.07 Table 610.071
a504c7db-134e-5fd6-9ab8-e0e516dba17a | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
5605beed-efa5-5784-a35b-46a782b8f61c | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
40fd7b35-7d27-59d9-8f75-a17cec3f3ef3 | textbox | Enter: Teambinder Material Approval number
fdefc9ac-2970-5682-b705-0d88bf98ccf5 | note | METHOD: Document Review
aae37aac-fada-509b-940f-938f70dccfb1 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
094571ab-94a8-5de1-9007-ab7a046178e4 | note | CATEGORY: HP
66db58fc-21d0-5d0f-902e-8d4a41019a39 | note | RESPONSIBILITY: Nominated Authority
d05d1c5a-1e1c-5fcb-b2a0-4ed5888d5cf1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
44ecb179-ee2c-5379-ab0b-082f848918bd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
91cb5827-8d63-5f53-96b2-f7879bd2f377 | note | REFERENCE: VicRoads: Cl 611.05 (a)
90f008b1-33a3-538a-bb72-a2b0245920c5 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
b8420b05-d3e9-50a3-824d-a9dbb239e638 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
ab4999e6-fd57-59e2-90a9-9296c8ece6ca | textbox | Enter: Teambinder Material Approval number
6f87ba14-aa1a-558e-9f8c-51a330c7ef1b | note | METHOD: Document Review
5b359197-b1ea-5b73-829e-ed76b83e4e81 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
9ab1d161-9404-5cc6-8212-b65c748c2eb8 | note | CATEGORY: HP
aa583fbb-e264-5ce9-bd8e-735466583571 | note | RESPONSIBILITY: Nominated Authority
4ff6cd60-7b7e-5882-a686-b154857c2f95 | note | VERIFYING DOCUMENTS: This ITP
d4a951c0-485d-5fea-b3cc-98b09336ed8d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
2900917c-5e77-5b8d-b43b-a0ee3e3e4df1 | note | REFERENCE: VicRoads: Cl 610.26 (a)
86a1c71e-29c8-52bf-b526-059b6389cddf | note | ACCEPTANCE CRITERIA: Plastic Bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
a1cd24ce-ee38-52f3-9cd0-c44acc57d715 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing (chloride ion and sulphate ion content) in accordance with AS 1012.20.1 on a 12 monthly basis or earlier if the mix design changes to demonstrate compliance with the requirements of clause 610.07(k) for soluble salts.
917dc959-8157-5ef7-811d-d45e511dedd2 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
a72e89a8-9103-5eb8-9a74-0eacec100772 | textbox | Enter: Teambinder Material Approval number
c39d4f78-c401-5118-8e70-0fc9292206e5 | note | METHOD: Document Review
5693b316-214a-547f-89fe-3018e76da251 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
348557cc-858a-592f-b2d1-214ff1ce1415 | note | CATEGORY: HP
a89038f9-4088-5250-ac1d-541e8daa0543 | note | RESPONSIBILITY: Nominated Authority
cb9d8a55-ac28-5572-8f3a-03a6688d20d2 | note | VERIFYING DOCUMENTS: This ITP
e169123c-7d9a-584c-b6e1-144d3b26f356 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
936d9233-6271-56e0-b036-8efdac250c3c | note | REFERENCE: VicRoads: Cl 610.17 (f)
851c525f-8a44-5fd7-a6aa-305274411e5b | note | ACCEPTANCE CRITERIA: Details of evaporative retardant and application procedure (including application rates) to be submitted for review to the Nominated Authority.
00547f32-0e3f-579c-8e53-a41a0f4c22a5 | textbox | Enter: Teambinder Material Approval number
a55c394e-d086-5570-ac4a-0f29d23ea5a3 | note | METHOD: Document Review
52813a7e-1393-565d-89a9-11b734c59759 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
dfb551a9-8822-5de8-9ca2-0c8a165d804e | note | CATEGORY: HP
7b4a2f99-b972-59ea-a18f-f39a22864732 | note | RESPONSIBILITY: Nominated Authority
0f6cfc03-d519-5044-a4f4-abdb20c9f559 | note | VERIFYING DOCUMENTS: This ITP
d7d9686c-2983-5fef-b1c6-3d13dec4a8d6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
feb66a43-9624-5e95-916a-22702f7531ab | note | REFERENCE: VicRoads: Cl 610.23 (d)
42037d5c-4585-5acd-baae-cef2f5d8aebc | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 (non-volatile content and density in accordance with Cl 3.2, and for viscosity in accordance with Cl 3.1.5). Tests shall be vaild for not more than 3 years from issue, to be submitted for review to the Nominated Authority.
74c59f82-5bc5-58a6-a9e6-4ba70315f2d0 | textbox | Enter: Teambinder Material Approval number
149af261-b4e5-5652-8ac8-a13bd1cc12f7 | note | METHOD: Document Review
03990b73-b236-5d9c-89bb-802f8af2da7e | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
2d3838ff-e1e6-5c2c-b269-eb4fa2a117e1 | note | CATEGORY: HP
9fcfcc00-9aa9-54bc-b4fc-66216687c00f | note | RESPONSIBILITY: Nominated Authority
d28fd50a-cc9f-5fcd-987f-5b1ff968693a | note | VERIFYING DOCUMENTS: This ITP
4ba246f7-845e-5786-9800-2b59271a7f50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
7449b2b9-3e41-5aac-bd06-e983afc1d32d | note | REFERENCE: VicRoads: Cl 610.18 (a) (i)
f585a8e4-e00c-55a1-8164-9b67e485d19d | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
7741cbcd-bc15-5587-ae85-ce484b944653 | textbox | Enter: Teambinder Approval number
5da1b2fb-08b6-54f8-adba-20854480becc | note | METHOD: Document Review
397b9d47-3c18-567e-bedd-3f89daa3a3e4 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
7297f814-ce09-58c8-9778-fcc2dcdc6fc7 | note | CATEGORY: HP
db0fb64e-c5d2-50cf-8a2e-64ebd4d0a278 | note | RESPONSIBILITY: Nominated Authority
c6ad1783-fda9-53da-a0fa-4ed7abeae2f0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
949de399-16e1-5403-823a-5fc352c391f9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
ca9f491e-c451-5b5b-b4d8-836146f21805 | note | REFERENCE: VicRoads: Cl 610.18 (a) (v)
e2e2fa27-303c-5a91-a745-efb9a34c2995 | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
9631df6e-fdf6-522f-bbb8-bb6cca399b48 | textbox | Enter: Teambinder Approval number
a25bfb63-aca8-5bb4-bce2-7188a4ab2ca0 | note | METHOD: Document Review
241c38b0-24d6-5318-a20d-4d8e296c74f8 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
af50e579-4f75-5e61-b72b-54fe15a58855 | note | CATEGORY: HP
ae6fd791-d00a-5066-9f28-5a774fcef1e1 | note | RESPONSIBILITY: Nominated Authority
830bf8aa-bb15-5d92-a6ba-0b5396f45fc5 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
dacdfac5-8aba-5f02-b57c-8cfd0295e2c7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
e9a88f57-0c35-5034-a3a6-2e738334d2a2 | note | REFERENCE: VicRoads: Cl 610.18 (a) (iv)
dd2bb7b6-961a-5b7f-a227-871787eadfaa | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
c7d84b0a-8c7c-55e6-9deb-f8cbfb9a72d1 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
8c52ae13-f596-50d9-8776-6f96660745ab | textbox | Enter: Teambinder Approval number
2a2766b4-86a8-5f56-90c6-12815e64c78c | note | METHOD: Document Review
75e86407-ded0-598f-951b-4bbdb6e3173d | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
87d85416-f330-5703-832e-9423b5f58779 | note | CATEGORY: HP
6020d406-4739-5e80-9b44-d06682e0206d | note | RESPONSIBILITY: Nominated Authority
fa9f9804-2734-5dad-8d5f-337f0067521a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d0fd43ea-65bf-52ee-9f98-9972e35b7d20 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
8677f654-cd8d-545b-a1e4-ecdd7cf49767 | note | REFERENCE: VicRoads: Cl 610.17 (a)
814a6577-de32-538c-a603-947ea3b7521f | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
ba75f13e-5fe8-5e87-8f75-29e74b35eb69 | textbox | Enter: Teambinder Approval number
9203624d-1548-5279-a918-c022d6595d57 | note | METHOD: Document Review
3a472631-2342-572b-a805-7a5ecde8a52a | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
7ec9eef0-4730-5d6c-bb38-6d7e28e7a630 | note | CATEGORY: HP
bd27a1ac-ab6e-5017-b739-9617bf2d6442 | note | RESPONSIBILITY: Nominated Authority
7f043d08-4680-5b2e-94ac-ed851d74ee4c | note | VERIFYING DOCUMENTS: This ITP
6b90ec1b-c8a4-5c8d-a031-7dd02503ab9c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
28791f03-99f1-5830-87d9-9317945ef7e5 | note | REFERENCE: VicRoads: Cl 610.23 (a)
8c93d10a-a572-5270-8cd3-7ee27f396057 | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
da9da9ee-15f7-54f9-8755-b90ddaf25fe4 | textbox | Enter: Teambinder Approval number
3b564c68-e685-5962-839f-e2459f299e29 | note | METHOD: Document Review
c8ec80a5-4e2b-5653-b36b-db87017ec127 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
768af07b-9a88-5f4d-a195-16bc8d9b9a21 | note | CATEGORY: HP
4f6b1828-0253-5b60-8e52-bf7e5533aba9 | note | RESPONSIBILITY: Nominated Authority
ce264d3f-ca1e-5e71-bbd4-dcae0d9a0b46 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
b7a94c5b-7650-581c-93d5-6740ff346b1e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Concrete Drilling Procedure
23226384-a508-523e-981c-aacd71d6654f | note | REFERENCE: VicRoads: Cl 610.46
a2908dce-6eca-5012-a8f2-1d2b46e62f53 | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
5bd551a3-a520-5fd0-a39c-f420c6ca670a | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
587a72b6-a5dc-5f5f-a190-e012acd7afc6 | textbox | Enter: Teambinder Approval number
54bb2c9c-ca78-593a-91ab-63445bf76659 | note | METHOD: Document Review
d1075f57-d8fd-58b0-8f22-ca300e83bdf4 | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
91cf2407-c1a5-57b8-b675-9fb23b5a5c64 | note | CATEGORY: HP
b3e2913c-32f9-5483-ab9e-1108c30602bb | note | RESPONSIBILITY: Nominated Authority
efc2a77e-39b2-544e-80d8-ec32eb3add6c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
98d15744-85c1-507d-b0a8-f1e21c3efdd0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Temperature difference measuring-Calibration & Cover meter-calibration
b9d3ac02-02cf-5de0-a1ae-7d43cce56ffc | note | REFERENCE: MRPA Quality Management Plan VicRoads: Cl 610.34
f253cf01-c0a2-5b5a-ba4a-a729cdc389b0 | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
4e2d7e49-b904-550f-8d28-970457d58e3d | note | ○ Attach: Calibration certificate
d8adea66-3eea-5ef4-826b-e7dbef9d1836 | note | METHOD: Document review
28a03a6e-7749-556b-972c-4d69e7fd2dfd | note | FREQUENCY: Where applicable
3a254c15-1257-5f14-9141-a1067ab0e60c | note | CATEGORY: HP*
1b987f5f-6180-58e6-828c-8957c93430e6 | note | RESPONSIBILITY: PE
b251af90-7c9d-5fcb-b994-eb4c43997d2c | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
6f155a10-a9d4-5823-abf9-fe11c2455085 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
a36ccab0-0458-52e3-8bc6-149254d963ad | note | REFERENCE: MRPA Quality Management Plan
4d9b3106-2d00-55a8-8a56-d9795b6ebcb1 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
53dcbd7d-fe11-599c-b81f-ca42b2a2eeb9 | note | METHOD: Document Review
83ffd646-828f-538b-80cd-2d6dc094d648 | note | FREQUENCY: Prior to starting Works and at regular intervals
138daedd-9b94-5ded-afe1-754bdca2c82f | note | CATEGORY: HP*
6b704585-f98f-5794-abfe-26e3687a2ff6 | note | RESPONSIBILITY: All
0811db4a-b79c-5cc1-bae8-b629ced46e24 | note | VERIFYING DOCUMENTS: This ITP
5316b0dd-6495-5a72-b186-85a4120ac0d6 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
97d60521-226d-57e1-98bf-d1b95c1cc04e | note | REFERENCE: IFC Drawings VicRoads: Cl 610.47 (a) Table 610.472
3ca9aa3d-f668-5ae7-ab97-5ba447b205cd | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
4588f8b5-97cf-589d-aa89-f7c112ec2af9 | note | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
6d4fa62e-eb41-5bfe-ba65-2eadb65a31e0 | note | METHOD: Measure, Visual
7d5462ba-1ba6-5f0c-8c55-434cddf8de85 | note | FREQUENCY: Each element
c19593d7-b5d2-577f-a165-9e0b7627c2bb | note | CATEGORY: IP
5c4cf054-4a45-53e4-8e24-bc623b9f6a0b | note | RESPONSIBILITY: Surveyor, SE/PE
6a2c1711-592a-5c6d-bc94-70c6c13e1ff1 | note | VERIFYING DOCUMENTS: This ITP
b43d56ff-0b8c-5bae-a31d-86df27de21f6 | date | Date Completed:
| checkpoint | 4.3 Excavation support
682602e0-a44f-5a06-bd9c-e488f993354c | note | REFERENCE: VicRoads: Cl 602.02
f93b9020-c669-50a2-83fd-dcf5eafae904 | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
3121dd92-9c27-58de-b825-2d7ff5087811 | textbox | Enter: Teambinder Approval number
0d3dff14-a76c-591a-b76a-b4365bd7d51c | note | METHOD: Document Review
230eee08-8c24-5ae6-b41a-aeff155af1f0 | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
1d69c9dc-5c09-5af5-a3ee-fa504d99114f | note | CATEGORY: WP
ce5180df-f96e-516c-bcd4-58228ef39d79 | note | RESPONSIBILITY: SE/PE/SPE
2fc3c019-4808-5b30-8642-53acda4a6233 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
6421b82a-9947-5e2e-bf6a-59934a2ed982 | date | Date Completed:
| checkpoint | 4.4 Excavation Inspection
e971998a-5d3b-59e0-a220-d8c0448d9e29 | note | REFERENCE: VicRoads: Cl 602.03
519bef7c-63a1-558e-bfb1-1ba494501b15 | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
e5d4caba-88c9-5e31-9e1d-f2bfdf4d92a1 | note | METHOD: Visual
4c8f9c98-4c1b-5389-a265-89a6c366a459 | note | FREQUENCY: Where applicable, prior to placing blinding concrete
c4e69c3c-a6d6-5793-9222-622a357abae5 | note | CATEGORY: HP
21ae826d-f9eb-5d0f-80ab-fb9931c3cdd3 | note | RESPONSIBILITY: Nominated Authority
eb730775-6b5e-53dd-a04f-862aed7f9624 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f0aa6add-37fc-512e-8c64-cfbf11956fa6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
3307ba14-c40b-5f77-81d7-a28c4e621ea9 | note | REFERENCE: IFC Drawings VicRoads: Cl 614.04, Cl 614.05, Cl 614.06
7e64cfb3-d1ed-518a-add1-fe0a3db368d7 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
036e9c4e-ce47-582a-a475-ee0276295426 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
ecb2a619-3ad8-5b5e-974f-a4dd5c1c681f | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
06f13198-9fee-57c7-8504-e6b26580250c | note | METHOD: Document Review, Visual, Measure
b6c734bf-1219-5b81-b648-2d7e7c52e290 | note | FREQUENCY: Each type of element
c16c29d3-85ee-55a5-a1d6-ea2a74465370 | note | CATEGORY: IP
6bcb1542-c0b0-5c6b-9870-38cfbb322a4f | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
03795a16-4f52-5d86-88d3-ce2402c70dbe | note | VERIFYING DOCUMENTS: This ITP
12d84d24-30d6-528f-ab13-b686103e3d01 | date | Date Completed:
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
cc0345b1-9ad6-5d49-9664-04eb305f800a | note | REFERENCE: VicRoads: Cl 614.08 Table 614.041
0f7b052d-66a0-547b-a66e-2d95842a4413 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed and accepted by the Nominated Authority.
af1b2f47-8b1d-5327-bd53-96990ed43410 | note | ○ The submission of formwork documentation and certification for the various concrete members shall be in accordance with the requirements of Table 614.041, For concrete members specified in (b), (c) & (d).
bdc28e5d-9437-535b-8b30-62786f53a07f | note | ○ Attach: Attachment A (as per Clause 614.04) and Attachment B (as per clause 614.08)
e501934e-f827-5c3a-aab7-946383914d22 | note | METHOD: Document Review, Visual, Measure
f12bfffb-1c5e-515d-af7a-0b5e9ea34824 | note | FREQUENCY: Each element (where greater than 2m)
8717b5e3-36df-5abc-9e75-6354afae6f4e | note | CATEGORY: HP
7edf59f5-4cdf-5842-adb1-27ce548e295f | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
da5ce140-87b3-5195-a4c6-336ee9ab927b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
656b8c9e-70a0-5310-914d-a808be6f3559 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
4ef2a5ea-65b8-5192-9aa0-9d4fae3e96c6 | note | REFERENCE: VicRoads: Cl 614.08 Table 614.041
6216bfbf-5ab9-5a88-bfa3-cd63fc23b053 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed and accepted by the Nominated Authority.
b89ba0b7-296d-5a93-b0b8-77632bfe1a08 | note | ○ The submission of formwork documentation and certification for the various concrete members shall be in accordance with the requirements of Table 614.041, for concrete members specified in (a).
84ded593-eee6-57cb-9d79-443296a382c4 | note | ○ Attach: Attachment C (as per clause 614.08)
8dafb3c7-74dd-5927-aff6-19c0b5713a8d | note | METHOD: Document Review, Visual, Measure
7e2da128-132b-5008-8cc0-c718d2bb38b1 | note | FREQUENCY: Each element (where 2m or less)
7e79160d-5d04-5d76-81ad-5b94e16ab05f | note | CATEGORY: HP
bf8b4a02-2b03-5a25-b257-1332559583d0 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
e2116829-8eb7-59bc-9e3f-c2ddc80e6668 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
756f0ce3-f42b-5bae-ba8a-3243ec19d3df | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
037c635d-0abb-5157-aa83-c91a43e60f18 | note | REFERENCE: VicRoads: Cl 610.47 (a) Table 610.472
9b977646-ce36-576e-964f-65e36591c770 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
e4cddcd7-cc23-56b8-984e-cdddde173db3 | note | ○ Erected formwork within the tolerances as per the table 610.472 as applicable to the element.
fbcfff69-945a-5bfb-84e0-e5f7490360a7 | note | METHOD: Measure, Visual
a9bfd9ce-93f3-5cb0-b420-c1f264df2e3a | note | FREQUENCY: Each element
19a2ad59-f178-5a2d-8bce-532fc582af26 | note | CATEGORY: HP*
fe0838d4-9831-5f62-ad0c-d51785686d8a | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
287e4044-d026-508c-8902-662d12f87b73 | note | VERIFYING DOCUMENTS: This ITP
9e99ba22-4fcb-5790-be44-0c1a6722c132 | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement
2b1ab582-81a7-5a98-8500-4e367f72b2ab | note | REFERENCE: IFC Drawings VicRoads: Cl 611.06, Cl 611.09, Cl 611.10, Cl 611.11, Cl 611.12
5e62fbb3-e8c0-53ed-a7a1-8272221e7041 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
c2802563-60e1-5ce3-929a-aad84d137045 | note | ○ Projecting reinforcement is the correct length and location. Projecting steel reinforcement in newly poured concrete shall remain undisturbed for a minimum period of 24 hours
3caa8ac1-d208-5e40-bc73-4e57cea0fddf | note | ○ Splice lengths achieve the minimum length and are in contact for this length, and the specified cover shall be maintained
f147634a-0cab-5501-b7d7-7f4c1a33df4b | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
31883397-7c48-57a4-8574-e096fbd561b9 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
b121e515-dcd6-5655-96f9-85618f8aba0c | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
b91cab93-e497-5d5f-bd53-c87aca644cfe | note | METHOD: Measure, Visual
8e8a495e-231a-5473-8a1c-c80325038278 | note | FREQUENCY: Each element
b2fcd11e-4595-549f-8e5f-83a8e8280477 | note | CATEGORY: IP
1ca91c43-bb14-5251-8810-5ed9fb1d0446 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
27729d7e-0c51-54c9-a6cd-c9cdae56daf1 | note | VERIFYING DOCUMENTS: This ITP
b92cafba-15e8-5d61-9add-598fc7b32787 | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
9ac45784-9049-5a4b-874c-5b677f316e8e | note | REFERENCE: IFC Drawings VicRoads: Cl 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
796a313e-66c4-54d3-9f83-730395c6dfbb | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
f41b1283-d45d-5405-9f94-ba9a5a8bb2a0 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
402e029b-e519-5b4e-8a58-d802ccdc149f | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
68078f65-5536-5cd3-ac30-123eed877d8d | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
9f45a666-27b4-5d7b-99aa-05f3a7f378d8 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
e95c756a-d653-58e4-8655-a39dbaca5774 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
ed7096bf-1b8c-5604-b870-39564b556eff | note | ii. Running dimensions of a group of the above = ±6mm
a086cc18-eec3-571f-b105-dd781332c13c | note | iii. Ducts and conduit location = ±12mm
49b65bcf-32ba-5afe-b380-808eac793b34 | note | iv. Diameter of ducts and conduits = ±3mm
140ce752-868d-5f76-b715-9fd93185744d | note | METHOD: Measure, Visual
7a342dd1-9191-5bae-8dc2-1d86cdb95377 | note | FREQUENCY: Where applicable, each element
9831363b-1833-54ca-8604-81b976579d67 | note | CATEGORY: IP
b6397245-2867-55a7-bfac-54e5eb1fa143 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c91d28bc-b047-591c-b498-2754b5eaadea | note | VERIFYING DOCUMENTS: This ITP
f3a15753-b560-5b7c-9d30-0cdc62fe08e6 | date | Date Completed:
| checkpoint | 5.7 Thermal Differential Monitoring
1742c323-6e0e-58f4-b643-b5c3299a6b8d | note | REFERENCE: VicRoads: Cl 610.22
715536be-51e2-5c81-9d27-4af6ed11da04 | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
04a82b2a-ee00-5dfe-a29e-72e477ed4129 | note | ○ Only applicable if the element has:
936f3bb1-edea-56bb-97ca-bce1dcaa93c5 | note | i. the smallest sectional dimension exceeding 500mm
8370878a-bd4c-5a8a-9070-4fabc94dda74 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
1073f199-eee1-5704-8854-e921dfbd8b8e | note | METHOD: Measure
798e2c11-a033-5315-ba8c-1f692cd06a6c | note | FREQUENCY: Where applicable, each element
26a7180e-a6b8-5992-bfaa-cf5d7c2dd32b | note | CATEGORY: IP
9d512eb6-74b5-5837-8a09-f4a0865aec20 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d7117da6-f9e8-5eee-af19-b8356496aa1b | note | VERIFYING DOCUMENTS: This ITP
91013ebf-2316-50d9-9042-85b7acde8833 | date | Date Completed:
| checkpoint | 5.8 Pre-pour Inspection
62d9ba21-b4bb-5176-97a9-9c5844df9ce7 | note | REFERENCE: IFC Drawings VicRoads: Cl 610.18 (a) (ii) & (iii)
ee4a13a6-9a68-5add-9946-e0fc0e21d68e | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
4f48ea3e-5344-5ea6-aac5-e18cf1e45424 | note | ○ All foreign material has been completely removed from the forms.
e72729d4-047a-58c8-b7d3-59d5cd50d855 | note | ○ ATTACH: Pre-Pour Checklist
5d6ae641-7d6f-5e8c-aee6-b26eaa9f735b | note | METHOD: Measure, Visual
6d22ff80-6e9c-5a81-94a2-2b42acaa38e4 | note | FREQUENCY: Each element
e24358e4-9139-5bfc-8d1e-f28f4ea1dba0 | note | CATEGORY: HP
3e49ea2a-f028-590d-b7f6-c0f1f558fbed | note | RESPONSIBILITY: Nominated Authority
de541fc7-4ad4-52b5-8b4a-5cfbb9903762 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
772c66d8-6ee3-5271-89d2-3ead786342ab | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
03a156ad-6f8d-570d-911b-d16f1a165b7c | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
ac498ece-ddc6-5a4d-ba72-e38e6f388a32 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
b979aa51-abe6-555d-96d3-147e868095f1 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ab4ba1a2-40eb-5d4c-9b28-697843c5b52f | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
937757d9-ea5c-5c8f-8a9c-13ad78239f2b | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
d7e34d93-6755-555b-9303-110ff18ffb83 | note | ○ Record: Required information on the Concrete Pour Record.
1d97f251-0660-557f-9624-c1d6288da5c1 | note | METHOD: Measure, Visual
0879cc11-e003-59ce-8edf-abaf75bbaaa9 | note | FREQUENCY: Each element
737c1972-8761-55d8-959e-a0f0c4f4774c | note | CATEGORY: IP
c5d2c18d-cf66-50e3-b1e0-dbba553fb5f5 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
6ba450c2-92e9-5f73-9353-a5e66d4e3ee4 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
bd24642f-ca35-508c-90ba-b1b75572401c | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
16d0a857-ac3c-53ac-8b9f-7d55df7c9a9b | note | REFERENCE: Site Sampling & Testing Procedure VicRoads: Cl 610.16 (b)
9e246f4d-2a2c-5597-9ee3-3172b97751c0 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
45f00c28-8186-5ffa-a4e6-126e38209997 | note | ○ 0m³ to 10m³ = 1 sample
0b02fa2f-c12e-5538-988b-825139e4430e | note | ○ 10m³ to 25m³ = 2 samples
9882b66a-0133-5a2a-a213-c6b56abe554c | note | ○ 25m³ to 50m³ = 3 samples
3c18298d-3533-54d3-943f-319f2b0e5561 | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
75e98f6f-404c-5f54-8742-65b95b2d70e2 | note | – For each additional 50m³ and additional sample shall be taken.
bae1c345-bd29-533e-a90e-7ab079786d84 | note | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
0a5b26cb-914a-5c3c-9d9e-f6f446ae9c0a | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
0f4877e0-a000-5dd9-88a4-417158814321 | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
2a504353-7bcc-502a-9644-4381feb34c1f | note | – Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
825d2570-ff34-5bda-bee5-d30fd24be444 | note | – Record: Required information on the Concrete Pour Record.
b40702c6-4592-5111-bb40-058b361ce87b | note | METHOD: Test
ab9f9b5d-213d-527f-945f-a3c3c147ea74 | note | FREQUENCY: Each element
bac20b58-cce7-5320-9ce5-73318b8b158e | note | CATEGORY: IP
4796a8ae-8059-517f-880d-1bd2c0f2f0a3 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
3873eae9-d46c-5059-b148-d16c0f1b7ee5 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
efda4afb-fb2c-5677-a521-a2bdb5278a52 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Slump
566270a9-35d3-5433-a754-e28753e40eae | note | REFERENCE: VicRoads: Cl 610.16 (c) Table 610.162
f8e6c941-4de2-54c6-b05e-c5eecbaca55b | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
94b37a75-6d12-552c-b6e7-8d5a73a780f1 | note | ○ <60mm = ±10mm
27addf6a-02e2-5776-a1cb-887d06eec32b | note | ○ ≥60mm to ≤80mm = ±15mm
e998aa6a-7a48-5c9d-83f2-6c03caf1e962 | note | ○ >80mm to ≤110mm = ±20mm
7885882e-34be-582c-a338-8621facffec0 | note | ○ >110mm to ≤150mm = ±30mm
d5add60c-531b-5786-a5fa-96a53799ad4c | note | ○ >150mm = ±40mm
d9399336-1f6b-5608-8c9c-09edce3b92b5 | note | – Record: Required information on the Concrete Pour Record.
1d707337-a5dd-517c-8835-5a394c06a9dd | note | METHOD: Test
755b529a-c2a3-5ab2-96f6-dc0a2591a437 | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
14a28b2a-da4e-584c-8585-08758ebeae4d | note | CATEGORY: IP
a83dfb61-f8db-5c8b-86df-cd97222ecc87 | note | RESPONSIBILITY: Concrete Tester
1109e76c-939a-5cb6-a77b-9cc67b82c89b | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
00d0fa32-5e10-5bc5-b1d7-32eef4799be3 | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
5a95835c-d15d-57a8-b8b1-b958bbcecf1e | note | REFERENCE: VicRoads: Cl 610.13 (b) Table 610.131
3c197d53-6f6c-5d1e-b466-397bccddc1d2 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
9318d252-f6a5-5a89-8f9f-b64f5b4a4cd1 | note | ○ T500 time (measure of viscosity) = 2 seconds to 5 seconds (to reach a spread of 500mm). Final spread shall not exceed 800mm in diameter
b9626927-7569-5c5b-8738-51b39d4abca0 | note | ○ Passability = ≤10mm (aggregate height differential)
2ab84aa0-d1e3-53e6-9154-a1fe2d7a38d9 | note | ○ Record: Required information on the Concrete Pour Record.
3b18d7d4-115a-53dd-8d21-774990a3f0aa | note | METHOD: Test
ccaf009f-7318-5b42-ae17-4df64cb54959 | note | FREQUENCY: Each sample of Self-compacting Concrete
9230ee65-c465-57ff-849d-724807b4a458 | note | CATEGORY: IP
a69c827e-d4c1-5452-b3bc-87166c127cf9 | note | RESPONSIBILITY: Concrete Tester
c3079f45-6f1e-54c5-bd3d-54300149d533 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
615b4be7-6c55-5a0d-a77e-4deb25824b91 | date | Date Completed:
| checkpoint | 5.13 Supply & Discharge Rates
4a84fb51-7ec4-5191-93d9-9675e37993c3 | note | REFERENCE: VicRoads: Cl 610.13 (a) & (f), Cl 610.18 (a)
41bd2a58-f519-565a-9b7e-9af19e9e5957 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
4acee508-d5df-5dd2-b88d-3077f8a9ff4a | note | ○ No water is to be added once discharge commences.
afcb2f08-66c2-5a07-9e3f-b935edbdbd9d | note | ○ Maximum time between batching trucks is 25 minutes.
ed4cdb6c-5d17-5f4c-ac4b-577cfaf4cf0f | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
12841625-c069-5405-8628-d1d4e2263351 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
51b1282c-6b6f-5d7f-a0a0-d9ee50661d7d | note | ○ Record: Required information on the Concrete Pour Record.
f4b98897-09b5-5874-aefc-babe79d0fc4e | note | METHOD: Measure, Visual
036328cc-b1ef-57c1-a408-50a53bc12dae | note | FREQUENCY: Each load
abb5dc66-204a-5fa0-b27f-6105b9aaf600 | note | CATEGORY: IP
436c8527-0389-5db0-b977-9c463985be95 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
80ca5044-5a6a-5e66-8df4-8dfb7f1d2744 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
01edd68f-0563-579a-a8af-7b79c24e49e3 | date | Date Completed:
| checkpoint | 5.14 Placement & Compaction
342d332b-b05b-55d5-b93d-3b7ca0f53d02 | note | REFERENCE: Placement & Compaction Work Procedure VicRoads: Cl 610.18 (a), (b) & (d)(i)
01faad3a-f9bc-5b98-aa0f-10541700d252 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
42c575cb-ff01-53c9-bb35-922eb913f658 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
cfb6e8e7-a4f6-5782-a639-d6abac768ea7 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
e3e4aba4-e0df-5787-8e0e-502e17d77306 | note | ○ Concrete is not moved horizontally by use of vibrators.
1d1002cb-d8c3-51d2-9d9f-ef26cba042e5 | note | ○ Adequate compaction is ensured
0d1ebf83-b597-5523-81e1-5cbd49443a5e | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
196e6dcc-6183-59d6-b08c-d779dc911da1 | note | ○ Concrete layers are not more than 350mm
3e3f3889-b4bc-5c83-aef6-731cb5abb847 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
964cc211-c671-54e4-bcb5-7f056e7e08ad | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
96f44526-d116-5eea-a50d-5aa39767cef3 | note | ○ Record: Required information on the Concrete Pour Record.
b817fb1d-a7d5-5285-a54a-734cb42115ed | note | ○ Attach: Concrete Pour Record and Concrete delivery Dockets
91d7cb54-8ea8-5414-9ec1-dc58d96a64e9 | note | METHOD: Visual
59047662-d300-5e61-b871-5d0331591371 | note | FREQUENCY: Each load
ce9ff350-6d1c-5971-a50c-818f7bc67e71 | note | CATEGORY: SP
02186c98-d989-56d1-96f5-4556f681bb9a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c08d816c-577f-5cdd-9544-e3755d88fc42 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
e40351ab-2d23-5af7-97b5-384753a23980 | date | Date Completed:
| checkpoint | 5.15 Surface Finishes
e7dd78d6-63fa-55bc-b788-23a28d432785 | note | REFERENCE: IFC Drawings VicRoads: Cl 610.20, Cl 610.31
9a7ed73c-0c46-53db-92f0-534c54c7f27e | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
6b7dc023-7397-53a7-a844-1ce13b887397 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
0e78a921-8b65-5840-9246-d54c9c14a69d | note | METHOD: Visual
3781c90c-6790-5d65-ae86-6f1db0bf6bba | note | FREQUENCY: Each element
676a6043-6043-528f-b0ab-32a2d080bd84 | note | CATEGORY: IP
87010fd4-7404-5352-b979-1aa4535cdbc0 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d20d1fe1-9495-54ae-a55e-bf45d5b24daa | note | VERIFYING DOCUMENTS: This ITP
029c6760-a467-5362-bb7d-539bfb7df466 | date | Date Completed:
| checkpoint | 5.16 Curing after formwork removal
14c55205-7f1b-548e-9585-8e26bfbf29f7 | note | REFERENCE: IFC Drawings
f0f85800-b384-50bd-a85c-7a42a9fae923 | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
ae64f2bf-b1f9-5b40-919b-b6c0ccfb93cc | note | METHOD: Visual
234fb03a-0f1f-588a-9f69-072bdf0f3037 | note | FREQUENCY: Each element
aaf20ea4-50c5-5b56-8192-e76cfd639a72 | note | CATEGORY: IP
4b067a9b-3aaf-5277-ad12-d8d21eb298af | note | RESPONSIBILITY: SE
6fda578f-badd-5c31-b7e8-a78c764f8ccd | note | VERIFYING DOCUMENTS: Thip ITP
f4b37166-39b3-56e9-a11d-18f1a2afb7bd | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
cc6d75f6-3e0d-510e-b257-4a92db090847 | note | REFERENCE: VicRoads: Cl 610.22
8e00dfb5-66b7-5ebd-a6c2-92a113636c8b | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
425fbb9e-deda-5211-be40-20940b09d781 | note | ○ Only applicable if the element has:
c2a3a9a7-c4b9-555c-836b-84c7c0d1de33 | note | i. the smallest sectional dimension exceeding 500mm
b7e91c25-6d32-5d9e-a5ed-4ad51ec238b1 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
98766584-e5b0-5bab-b336-fd8f2ccb7a7d | note | ○ Attach: Thermal Monitoring Report
4ae3ff53-23e5-55c3-be7e-25fad0e760eb | note | METHOD: Document Review
eec26ab6-02e7-58a9-b015-cfd90dfe0eef | note | FREQUENCY: Where applicable, each element
24f76c41-9c4c-5abd-821a-3e4548846011 | note | CATEGORY: IP
bf202a27-5497-59d0-96ea-bde3a0c661b4 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
a3a73c37-6ced-5c1c-a33c-37060db2a7db | note | VERIFYING DOCUMENTS: This ITP
065aa7ba-fcf1-5f6e-ad59-96e7eb31f7fb | date | Date Completed:
| checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
8b679690-28b5-57b9-b5eb-2699f28d7fc9 | note | REFERENCE: IFC Drawings
e81e8729-1132-5e6b-96e7-ef8ef696b118 | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
f1313d7a-9612-57db-ade4-d0fc824f6390 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
bca61fef-ebe5-5aff-996b-1392451f2cf0 | note | METHOD: Document Review
93a06816-ec53-56ca-90ce-bfe6680df1cb | note | FREQUENCY: Where applicable, each element
97a4a0f9-393b-5cfc-b5df-a091528d85d8 | note | CATEGORY: IP
6f6610c6-c3f9-5dd7-ac69-77d31f936c80 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1fa0b23a-6899-5e97-ab13-6840caf836fd | note | VERIFYING DOCUMENTS: This ITP
48b17ca7-739c-5159-89d6-661d94610ecd | date | Date Completed:
| checkpoint | 6.3 Surface Inspection - Cracks
1f08de7b-242b-538f-83ba-92570fe9c49b | note | REFERENCE: VicRoads: Cl 610.24
8751f67f-19c5-531b-8903-9331df75bb7c | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
49b51356-388d-5d48-ba52-af8acb45e5ea | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
3a52e3af-1352-5eb6-82fb-d04879890807 | note | METHOD: Visual, Measure
486fde0a-26e4-5ec2-a68d-255c0e8796ed | note | FREQUENCY: Each element
68196b9a-71b3-576c-a7b9-fd864d8e0d73 | note | CATEGORY: IP
828196a6-1472-50c9-99a3-389e11d91c6c | note | RESPONSIBILITY: SE/PE/SPE
a189aa47-ea5d-57a2-8f64-85076dc47c82 | note | VERIFYING DOCUMENTS: This ITP
72cc9009-3c8f-598c-86ac-48a800b4d0c0 | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Surface Finish
c15c82b4-e764-5f80-8575-aa252ae56fcd | note | REFERENCE: IFC Drawings VicRoads: Cl 610.31 (a) - (n), Cl 610.32
f744bd38-728d-5123-8e20-946b5a39d8ed | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
ed5f3a83-d360-549c-a4f9-52bcf6a9d47b | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
66f271bf-6bc9-54d7-a84d-5d4a14da53a4 | note | METHOD: Visual
f67c1b99-92b4-5d1b-a7e6-1d0fd729e53a | note | FREQUENCY: Each element
160a5efc-047d-57cd-8440-9d57aa8e6ec9 | note | CATEGORY: IP
8c36def0-c79f-59cc-9271-4e5a2399f0c4 | note | RESPONSIBILITY: SE/PE/SPE
9a157f57-9fc7-574c-b0d7-e451e3746392 | note | VERIFYING DOCUMENTS: This ITP
30438206-841a-5533-a2c1-7f219e8258b8 | date | Date Completed:
| checkpoint | 6.5 Measurement of Concrete Cover
85a0cdc0-fee0-5d45-971a-b47c05145f59 | note | REFERENCE: 610.34
7512e9fe-b7b0-5a54-9e44-2dae044c2c36 | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
6e1283b4-033c-5494-99c4-662016e350fb | note | ○ Minimum 10 no. measurements recorded in each area.
db5765d1-80db-520c-94a6-55df385b78a1 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
b609dabd-f1cd-5ca1-8c8c-32d36c9d7777 | note | ○ Attach: Covermeter Check Record
96c3df8b-f543-51be-9c1a-230799978f2c | note | METHOD: Measure
13b55bea-11eb-5168-8c2b-5ea64509cbdc | note | FREQUENCY: Each element
bfe28764-975f-5e64-819a-6d03948c444b | note | CATEGORY: IP
ae10689b-a6ea-5aaf-837c-366ae7543746 | note | RESPONSIBILITY: SE/PE/SPE
2924959e-c2b2-54ba-b500-0f4da996df6e | note | VERIFYING DOCUMENTS: This ITP
46d30dfb-aff4-5860-b696-f854661ce401 | date | Date Completed:
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
b0038552-a655-5b06-a972-887ad396fecc | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slabs Procedure VicRoads: Cl 610.35
080797aa-9f7a-5741-b1c1-a4aca25e5b9d | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
8b13ad0f-cd2a-5300-a497-32bcdc834f70 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
d08211fb-4907-5350-9612-2418cbed601f | note | ○ Attach: Concrete Test Results or Maturity Test Results
fcb95adb-4e88-58ee-8983-af46818a2860 | note | METHOD: Document Review
11731938-6c22-5c08-9f2b-3a4955a0137c | note | FREQUENCY: Where applicable, each substructure element
42fb9d45-ffc9-5b43-9afa-fbe45184dc17 | note | CATEGORY: SP
d5fc3632-7706-5825-900f-e086c1847c28 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
15e9c8f0-2405-598b-9bf3-2d0cf84eb15c | note | VERIFYING DOCUMENTS: This ITP
dee33c61-08a4-59ea-a11d-9cc8ddeaeb28 | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
d20f6232-1bb4-52ef-a5a4-baccad08432c | note | REFERENCE: IFC Drawings VicRoads: Table 610.05.051 Cl 610.16 (g)
f78fac10-da82-584a-987f-bb100aebde51 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
012a5413-7147-50d4-9704-f0bb00967d44 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
e6483ac0-fd66-5fb3-bf74-eeddf06ab805 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
9e94d146-1115-514e-ab5d-a73116069bf6 | note | ○ Attach: Compressive Strength Test Results
27401349-e55c-5f51-a81d-ebb46f548bd8 | note | METHOD: Document Review
7d0a17f9-883e-516d-a27b-bf97e6a59e21 | note | FREQUENCY: Each cylinder
f03e601f-c8f0-5a35-8041-0c3a24dae59d | note | CATEGORY: IP
fd38641b-a45b-5bf6-b99b-253bde8c1468 | note | RESPONSIBILITY: SE/PE/SPE
51833133-744f-5783-83c2-6ce6d0e038bb | note | VERIFYING DOCUMENTS: This ITP
a2e92ee6-c700-5018-bdb4-1ca99bb7e4ac | date | Date Completed:
| checkpoint | 6.8 As-built Survey
1e341441-6039-5b43-a9e8-a477d62370b3 | note | REFERENCE: IFC Drawings VicRoads: Cl 610.47 Table 610.472
f0cef8c5-11f5-5769-9ee8-8a238f74e8d2 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
e669b8d9-62ee-5928-a450-0f1137127cd9 | note | ○ Attach: Survey As-builts / Survey Report
d960394e-16f5-5a5b-9d6a-64462033739f | note | METHOD: Document Review
30fa71d3-626e-51c8-bd66-eaf63a1909b2 | note | FREQUENCY: Each element
7a17048c-27aa-56d7-8744-27c077e42eae | note | CATEGORY: IP
225cb827-2a45-56bd-8236-0d9ce6c74163 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
43e73a9e-cd76-51da-8567-244e0fa203f0 | note | VERIFYING DOCUMENTS: This ITP
a62bb5c9-b61d-5749-8b86-45fa65fe06ba | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
153b1e28-8b05-51cf-a433-4619388fdbbe | note | REFERENCE: MRPA Quality Management Plan
fede31f3-620a-5020-8553-43e1769d65e0 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f321338e-5a3d-5c98-85b9-f1cdaf7c8a8b | note | METHOD: Document Review
3dd1b244-a59e-53eb-9f77-288ead7de351 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
1e7f772d-842a-532a-9f8c-e50be504b21e | note | CATEGORY: HP*
fc1dd76b-2fe6-59cf-b8ad-dc02b1c68224 | note | RESPONSIBILITY: SE/PE/SPE
2b7d7083-1660-5a5f-aba4-1c01ad4d2115 | note | VERIFYING DOCUMENTS: This ITP
93c78d2a-eed6-552e-b79f-8c3b2b02f4e5 | date | Date Completed:
| checkpoint | Final Inspection
7e239078-9106-5b9b-92c6-1ce04b024890 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
33688629-5296-5f34-8c83-838fdbeed409 | textbox | Name:
7f77ef9b-80a4-5460-ab9d-87fc6e5050ea | textbox | Position:
8cd610ca-7d07-530f-ba1b-cc8717f3ac8d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-210-CIV-SSO-Kerb & Channel (Supply and Install) Rev 0 | itp | ITP-210-CIV-SSO-Kerb & Channel (Supply and Install) | a0defde4-1c61-42bf-b9c5-8f7eb5cf130c
| section | Referenced Documentation
| checkpoint | Referenced Documentation
8af232b7-7d06-5eef-8711-f88d1a4acaba | note | Document Title: ITP-210-CIV-SSO-Kerb and Channel (Supply and Install)
6359a831-139c-55c5-a86b-2742ac2d1176 | note | ITP Description: SSO-Kerb and Channel (Supply and Install)
335d7aa6-e777-51ba-b366-5c81a6b035ce | note | Discipline (e.g. CIV/STR/RAIL): CIV
eb62a8a2-7fa7-57c6-8ce5-9c90a0687bf6 | note | Revision Number: 0
4c6f4aae-fa84-5035-8346-e6f56b7ec12d | note | Revision Date: 23/10/2024
6b4f80db-e20f-52f4-acbf-1726a29cfaab | note | ITP created by: Dimitri Santoreneos
b5caded6-bfc6-5c0a-a06b-a9fa5410c516 | note | ITP approved for use by: Sandy Escalona
66e4f5c3-18c0-55e5-94b2-62da1b42ca3a | note | 1.1 Non Dependent
7732b94e-4686-5b02-8d35-13d07fd1e69d | note | Reference: VicRoads Section: 703 (August 2021), VR SD2001, VR SD2102, AS 2876, AS1379
| section | Preliminary - Materials
| checkpoint | 2.2 Mix design
38e35668-7f58-584d-8a79-5e0078807f40 | note | REFERENCE: SD2001, AS1379 VicRoads: Cl 703.05 (a)(b), Cl 703.06, Cl 703.07
07341679-f912-5766-adeb-7751a481975b | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
c3ba7df8-27c4-53ef-b259-6ce48edf34c4 | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
cafc82bd-d382-551d-9065-5e314545a3f8 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
020047a2-c4f8-5f95-b734-7dc3e6ebdcf8 | note | ○ Attach: TeamBinder Material Approval No.
0d3294e8-2128-59d9-bf77-6d68bc100a29 | note | METHOD: Verify, Document Review
8f78234c-7705-56bd-996d-04b83a82a0bf | note | FREQUENCY: Prior to commencing any activity
1bd46484-8a90-514d-8cf4-67fe697c09dd | note | CATEGORY: HP
2583831e-c801-5c47-ae52-d40ef8ecb190 | note | RESPONSIBILITY: Nominated Authority
a757a9a8-5c78-5e3e-a58d-57bf93d7934c | note | VERIFYING DOCUMENTS: Conqa HP Release
311c23dc-d57f-54a9-bcb3-75e12e6a2fef | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bedding Material
08fd9c66-b783-588b-baa4-93a18a706d9f | note | REFERENCE: IFC Drawings VicRoads: Cl 703.21
5b9719c4-68cc-53f5-a7af-6f1a179d2a89 | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
47f996c2-be18-54cf-8756-de17bcea13a0 | note | ○ Attach: TeamBinder Material Approval No.
b55853f6-fa28-56c2-aa95-4c1c90b2364d | note | METHOD: Verify, Document Review
8d06916a-f51c-51ba-812c-0513ab5f2e41 | note | FREQUENCY: Prior to commencing any activity
e4a48737-aa66-5a2e-9a6b-793a8660521d | note | CATEGORY: HP
7e3f3ffa-e16d-51f3-b549-437261f1ffdc | note | RESPONSIBILITY: Nominated Authority
090d1474-5f1d-593a-950b-9502cace5f73 | note | VERIFYING DOCUMENTS: Conqa HP Release
87f38723-29f1-5983-9e8d-1a62eff61603 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Curing Compound
0d357305-10aa-513d-a691-857b08a337a2 | note | REFERENCE: VicRoads: Cl 703.10
b67a27cb-5af5-58f3-bba0-f7afab7efd2e | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
c6af2b3c-edd0-5361-a516-711994cd645c | note | ○ Attach: TeamBinder Material Approval No.
5f382cfa-26b8-5c6a-8d2c-695d81fe9163 | note | METHOD: Verify
2c64fec0-57a2-59c8-b968-2fb8bf885421 | note | FREQUENCY: Prior to commencing any activity
2133b1f7-a978-5836-9294-f41911f3c6fc | note | CATEGORY: HP
e313398e-1fdf-5f37-a3ba-fb54c147ebdb | note | RESPONSIBILITY: Nominated Authority
87e39870-86c1-53ca-b9a3-aa9c95617474 | note | VERIFYING DOCUMENTS: Conqa HP Release
7c3db2e4-c035-5c4d-92ca-a6135f16c26f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminary - Documentation
| checkpoint | 3.1 Check for correct documentation
613757a7-8c7d-5030-bebe-a78df35c14d0 | note | REFERENCE: IFC Drawings
bfa76808-9172-5a4d-8121-a479a6a64dd4 | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
112e6b2a-e2b8-5332-8911-a8887fe4e96c | note | – Using the correct and complete set of drawings
026e1abb-66b7-536d-b1e5-d826b118771f | note | – All drawings are the latest version (as per TeamBinder)
3458a30e-b5ab-57e9-b680-35f2862abd40 | note | METHOD: Visual inspection
c339fef3-f839-5fbb-bf2e-aa977488b031 | note | FREQUENCY: Prior to commencing any activity
b5860371-ec3d-5982-b3e8-0f32d35d09e8 | note | CATEGORY: HP*
abfd299f-c48e-5a50-acc0-d656b42846a9 | note | RESPONSIBILITY: SE/Site Supervisor
184a7a6e-0f51-553f-8abf-7e98d3b92834 | note | VERIFYING DOCUMENTS: ITP Signed
a086891c-8d78-5197-a895-fa936905cbaa | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Setting out
a87f7019-048d-5ca8-82c9-ea7204636f5f | note | REFERENCE: IFC Drawings VicRoads: Cl 703.17
f6c5d49a-1bcf-5dbb-898c-26114e7ccad3 | note | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings.
7b535397-1b61-53ae-b750-0bb0b4c274e6 | note | ○ The superintendent will review and confirm set out.
2b2ecb78-f78c-5bb0-8c2c-71c5ee1c2aaf | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
b72bac18-6ed7-5b2a-beaf-0857ef7a0ff4 | note | ○ Attach: Map-Marked up drawing to indicate the location of the Lot
9f05a022-6db1-5307-bba8-265699e7de34 | note | METHOD: Verify
cd695799-2c18-5ecf-a852-564a232430b5 | note | FREQUENCY: Prior to start
6e162954-e032-53f6-ba4a-d6090264f376 | note | CATEGORY: HP
a8bec2c7-5aa1-5f83-a403-9c2c6e081d16 | note | RESPONSIBILITY: Surveyor/Nominated Authority
0bbfcb0d-130c-526c-be1c-3a413c68949b | note | VERIFYING DOCUMENTS: Conqa HP Release
66767d58-173a-529c-94dc-81945607c215 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 Temporary drainage provisions
695ee026-bebf-5d33-9281-fc594bb8ff04 | note | REFERENCE: CEMP VicRoads: Cl 703.18
beb70e8b-42af-5d52-a83e-ace5ac3282dd | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
9995b7cc-b876-5707-8d4b-aee16efedddf | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
c779c87f-ec8a-55a7-9169-395c09081178 | note | ○ Attach: relevant written approval from relevant stakeholder.
b250b513-cf4a-5c07-9579-a34a0b3f90cd | note | METHOD: Visual inspection, Document Review
aae0280a-da90-5d9b-9ff9-f7a9fd3b9544 | note | FREQUENCY: Prior to start (where required)
beb7e10d-33d5-56be-99bc-f6961087d039 | note | CATEGORY: HP*
e3360893-ff5b-5159-a3fb-64fdac281337 | note | RESPONSIBILITY: SE/PE/Site Supervisor
ab59d00a-6b62-532b-9815-e3663fa5ee07 | note | VERIFYING DOCUMENTS: ITP Signed
bc63d1b3-0ed9-5359-87f6-0d97471e1148 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Bedding
0157303b-0a73-5124-8331-82e68f7cd1e0 | note | REFERENCE: VicRoads: Cl 703.21
f37d2881-734d-524a-bd0d-71cdc52acf3e | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
718085da-a0f6-5b0a-a8da-fa1390122570 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
f83e0704-25ba-5a22-8f33-7f0a80afe061 | note | METHOD: Visual inspection
b7040b1c-156d-5abc-9dcf-870685a8f1a1 | note | FREQUENCY: Each lot
71afdff5-e0fa-56bb-b5d4-1f6239f23e48 | note | CATEGORY: WP
73ff938c-991a-5f33-94de-d3ab6b3a29ec | note | RESPONSIBILITY: SE/Site Supervisor
c4f76bb3-c0f7-5157-a6b5-15b15831c8df | note | VERIFYING DOCUMENTS: ITP Signed
a1ed26eb-4bd3-5b49-b60b-1ab52aa54b18 | date | Date Completed:
| checkpoint | 5.2 Formwork
821d33d6-e201-5764-b1d8-a5566d502ea4 | note | REFERENCE: VicRoads: Cl 703.12 AS 3610
988752e8-aae1-5f93-b600-5b2034131313 | note | ACCEPTANCE CRITERIA: The materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610.
37769cf4-5bd4-5e79-941e-dc79a554bbcd | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
5eae8e65-8472-5563-be95-5c93fb103471 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
c962358b-2251-58b2-a641-e59981ef8aef | note | METHOD: Visual inspection
15384adb-fa65-5950-923c-f3a92e296b9d | note | FREQUENCY: Each lot
aa46f787-ff59-599e-95d8-85e3d8e18d1f | note | CATEGORY: WP
93e3411c-8cc1-5260-988f-f7efa2f81d92 | note | RESPONSIBILITY: SE/Site Supervisor
9767dd1e-2b89-512b-ad0f-8fa0d0e82329 | note | VERIFYING DOCUMENTS: ITP Signed
4a309a71-2679-5a71-9ab6-cbb9b7b78b55 | date | Date Completed:
| checkpoint | 5.3 Pre Pour Check
eb8f16d4-13e4-5ab8-a1fa-9925a59ff914 | note | REFERENCE: VicRoads: Cl 703.09, Cl 703.21, Cl 610.17 (a)(b)(c )(d)
d2032c29-eca4-5bdf-ba0b-b228fc863036 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface .
d67c1d46-84e3-584e-809a-938fe7674f2b | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
ef1f25ac-7b90-58e6-a374-3e965b8f8444 | note | ○ Attach: Pre-pour Inspection Record
be95ef6b-9488-56b1-a0c9-feeda0ba4bc6 | note | METHOD: Verify
6b9eeb1a-58ee-56a5-911d-6c9a93c7e328 | note | FREQUENCY: Each lot
5e7dcd57-d265-5b10-b113-26ef4cee2969 | note | CATEGORY: HP*
bb4c5087-1fc9-5a95-bd3b-ea43977b9b45 | note | RESPONSIBILITY: SE/Nominated Authority
3ec2f8c7-c583-51f1-a53d-9b2dbcae1ffe | note | VERIFYING DOCUMENTS: ITP Signed
808024e2-779c-567c-a6e9-41ebeb22f101 | date | Date Completed:
| checkpoint | 5.4 Concrete placement
86f58060-357f-54dd-8f12-d01701843327 | note | REFERENCE: VicRoads: Cl 703.08, Cl 703.23
4e40224a-2540-5d9c-8b13-e77f3aa2a3a8 | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
85309358-f07e-5632-baa7-7b665b2d6cb3 | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
c5081b85-ff1c-5618-a353-e8429e863d92 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
5517c65f-6b4b-5d75-b24f-ce2219a957ef | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
532d43cd-ff61-559d-9aed-e7d3cc1d5d4c | note | ○ Attach: Concrete Pour Records
11e27619-97cf-5854-8ef6-aba581508362 | note | METHOD: Site inspection
fe309a29-bec9-5077-882a-0c5481b405a1 | note | FREQUENCY: Each lot
fbdb50ce-c232-5410-9b65-357139ff9f44 | note | CATEGORY: IP
54486e2b-1efb-54f0-9ce8-e25392c58118 | note | RESPONSIBILITY: SE
40b87d9c-dd32-54fd-a1a7-551310e2ad80 | note | VERIFYING DOCUMENTS: ITP Signed
9df325fe-8703-5bb0-865a-e5ea85b107db | date | Date Completed:
| checkpoint | 5.5 Transitions
3ce85807-7a62-5103-b656-14cd4661de47 | note | REFERENCE: VicRoads: Cl 703.24
2a975422-a499-58ec-999a-c1b4e8e4344f | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
f1b2b381-2fd8-52c4-99e1-5fcb347b000f | note | METHOD: Site inspection
908e58ed-bac4-550d-b570-1a58b9c0e04d | note | FREQUENCY: Each lot
79c4b9bb-dca3-523d-b680-766e4b9faa1d | note | CATEGORY: IP
69c304b4-cda2-5c4a-96ff-268394ade78b | note | RESPONSIBILITY: SE
12f5c588-c2ad-5827-b54b-ef889220b047 | note | VERIFYING DOCUMENTS: ITP Signed
04e71b9c-f50e-511b-a46d-3dbce5a636f1 | date | Date Completed:
| checkpoint | 5.6 Surface Finish
aba25cc6-d464-52e3-b77e-435f8cec149f | note | REFERENCE: VicRoads: Cl 703.25 AS 3610
17482d9f-80c2-5919-9bf6-4ea673cf394d | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
6ad0c0db-769b-55fa-9a94-f8bd0cb19cdd | note | ○ Renderings shall be applied within 30 minutes of extrusion.
a82b3f2a-0f90-5918-9fe6-996b6096fbf1 | note | ○ Concrete to have a neat appearance and uniform colour.
18009361-f9ea-55ad-b50a-6bd78349c353 | note | ○ Class 3 finish required for external surfaces.
f1405946-6d3c-591a-84d3-445cca430308 | note | ○ Class 4 finish required for permanently hidden surfaces.
4951e2c9-0c46-5490-93a8-e35c10dfcb27 | note | METHOD: Visual inspection
857585b2-1ce0-5528-a222-ccc764118e3b | note | FREQUENCY: Each lot
a62b6516-31a7-534e-8fa8-32c0d11d1a5c | note | CATEGORY: IP
39dd7ff4-4562-513d-9852-b814f1ca3879 | note | RESPONSIBILITY: SE/ Site Supervisor
7c340cc7-07bb-5da7-be33-617f9d99f6e3 | note | VERIFYING DOCUMENTS: ITP Signed
314d3438-0669-5169-a0dc-5e1fae6454ce | date | Date Completed:
| checkpoint | 5.7 Formwork Stripping
5afeb890-9a52-59d6-9267-45d6ee2cf808 | note | REFERENCE: VicRoads: Cl 703.12 AS 3610
6e8d4c21-ba98-5e4e-b7d6-c506130f9cc4 | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
66b467ea-a166-5761-b14a-1e2b48b7130b | note | – External faces 2 days
8078aa8c-6f19-5d59-9e8d-fa80b80bc6b9 | note | – Permanently hidden faces 1 day
56b8ec18-6179-5758-87d0-c5d70b77c040 | note | METHOD: Visual inspection
c9044e8c-6835-53af-accc-0a86c4f09984 | note | FREQUENCY: Each lot
4805b0f6-fddd-59c3-ba92-31d12eb79a70 | note | CATEGORY: HP*
0e65abdc-9334-558d-9d21-e6eb73c14d98 | note | RESPONSIBILITY: SE/ Site Supervisor
ff517d36-8325-58b7-8b03-046fa195e137 | note | VERIFYING DOCUMENTS: ITP Signed
f4fe5389-79f2-573c-b179-2103d3be3f09 | date | Date Completed:
| checkpoint | 5.8 Tolerance
57385004-40fc-5bca-8ead-325afce0523b | note | REFERENCE: VicRoads: Cl 703.15
8626ca90-4638-5c15-be2b-75c6fabb85c2 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings.
794683be-4929-555c-a03b-3237e5a006ee | note | ○ Section dimensions shall not differ from those shown on the drawings by more than 5 mm except that overall width shall not exceed the specified width by more than 15 mm , for dimension less than 25mm tolerance to be ±3mm.
3e6e2621-338c-53d2-a084-ab2d7a12d9d0 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm. Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
aad567c5-90f3-5c8c-ae7f-16d62f477e61 | note | METHOD: Verify
805cf800-77f2-5f52-90e9-450e874b334f | note | FREQUENCY: Each lot
ee25f959-4cc9-5ba2-b767-45a4e7369274 | note | CATEGORY: IP
0917b50d-605c-51b2-8624-c143eddb2363 | note | RESPONSIBILITY: SE/Surveyor
51b98507-6310-52ef-850c-f155f562acdc | note | VERIFYING DOCUMENTS: ITP Signed
5c2ff334-a319-5f19-bbef-5ac1db85aefb | date | Date Completed:
| checkpoint | 5.9 Curing
886c5881-a23c-5898-b5fd-8105debaa1d9 | note | REFERENCE: VicRoads: Cl 703.10
b32dd774-9487-52ed-9a7f-fb42f162f934 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
0ac6bdd1-f7a1-5742-993f-a64661455c81 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete.
1309e429-ae9b-5b29-9600-ec104a2d2031 | note | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance.
ea55281a-23f1-512d-b68c-f0ca1a43b5c0 | note | METHOD: Visual inspection
80e23291-5ca0-5b8f-b105-d11f5f07f72e | note | FREQUENCY: Each lot
8f51e89f-6890-579c-ae3a-fc9dcf37f1b8 | note | CATEGORY: IP
258a6cb8-f8f9-5338-b718-82fba0f8b375 | note | RESPONSIBILITY: SE/Site Supervisor
7bc45d72-907a-5a57-afec-e8cb3752d477 | note | VERIFYING DOCUMENTS: ITP Signed
24664e17-e55e-5f73-b164-648f410eef38 | date | Date Completed:
| checkpoint | 5.10 Joints
01304848-b6da-535c-8762-8ae0cabd8a53 | note | REFERENCE: VicRoads: Cl 703.26 (a)(i) (c)
202c85b6-3866-5416-90e8-582e631a4cb8 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
a3583489-c333-5ef7-a5e7-a96ea70a7317 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
1a494ac9-0adc-5911-9469-cb043e93bfc2 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
7ebdc061-fb7f-5ff4-99c0-b8c05506de74 | note | METHOD: Verify
9007876c-dba9-55ee-b38f-8b23f66fd296 | note | FREQUENCY: Each joint
e438729d-7a08-5444-b701-16d0f3db8f69 | note | CATEGORY: IP
0bd53bcd-af1b-50d0-bec0-4549ea3fb360 | note | RESPONSIBILITY: SE / Site Supervisor
e17af6bd-2932-53cd-8da9-95b328ec3c61 | note | VERIFYING DOCUMENTS: ITP Signed
f8957ea7-2cfa-5439-aae2-ac1fe12d576e | date | Date Completed:
| checkpoint | 5.11 Protection of Concrete
27ddd1a6-4021-5426-bef9-f5d9a0da6ce7 | note | REFERENCE: VicRoads: Cl 703.27
1e04f1ba-7cd4-5284-8835-5efebe792949 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
38bbc952-4131-5a0b-ac0f-75f15c48ff7b | note | METHOD: Visual inspection
21687550-62a7-5f8b-aaa1-cfcfbb3847c1 | note | FREQUENCY: Each lot
a4897dbc-fd98-5b3c-96b2-e1c0baa52436 | note | CATEGORY: IP
a6c2bda4-2d0c-5186-8245-8bf69f72ceef | note | RESPONSIBILITY: SE
544e2fdd-4ce2-5245-b34a-d2938f0392c8 | note | VERIFYING DOCUMENTS: ITP Signed
81e48f22-2786-59ec-9b39-8254b9fbf3a9 | date | Date Completed:
| checkpoint | 5.12 Bus Stop Kerb Height
50e127f9-7a58-5b29-bd3b-adf0fd4ddaf2 | note | REFERENCE: DoT Handover Process
b3406644-8430-5cd5-a991-43c982c2cbf2 | note | ACCEPTANCE CRITERIA: Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
71801f2c-8dd7-5db9-b066-3269e4193f4e | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
a99ca79b-da3a-5274-b1df-a34d124fb40e | note | METHOD: Visual Inspection
f9c9315b-6514-5a5e-909f-fbc9138b6540 | note | FREQUENCY: Each lot
8b9cadaf-5797-5132-9322-6c267884c14d | note | CATEGORY: HP*
52fe306b-b200-5b2f-8bc4-9481a5fdcbeb | note | RESPONSIBILITY: SE
daa4c678-7af5-5b2e-a933-76d56eb6e98e | note | VERIFYING DOCUMENTS: ITP Signed
096a9ac0-bdb4-53a9-9098-0ed5764fa93e | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Backfilling
be9d53b3-532d-5039-8cd3-679a50f31201 | note | REFERENCE: VicRoads: Cl 703.29
a4fa0c23-49b1-53dd-be14-57d8ac8a68e9 | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
7466f5cd-00a2-52e3-995c-5979978708e1 | note | METHOD: Verify
fa887bf3-7ad7-5137-8244-720434fecd58 | note | FREQUENCY: Each lot
6662c4cf-4574-5b5a-8259-afc33b943406 | note | CATEGORY: IP
4bcea3dd-d904-55ba-9444-d0c2c6f083bc | note | RESPONSIBILITY: SE
65478a1b-8f41-5e62-b52f-efaac7d475d6 | note | VERIFYING DOCUMENTS: ITP Signed
41f57751-06fe-57f6-8be9-e70b097de829 | date | Date Completed:
| checkpoint | 6.2 Cracking of Concrete
24feb1cf-3ba8-5c92-b5fb-33e4adae1ba4 | note | REFERENCE: VicRoads: Cl 703.30
ce73f252-0979-53fb-863f-19a4076fff44 | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width, greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance.
8f3ff197-7ca7-529f-a13e-a9f7516801e2 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
fc379f97-2e19-54a7-a605-2f0593f26fe1 | note | ○ Attach: Pot-pour Inspection Record
51c5cf74-6b8b-5283-ba92-9e37674704ea | note | METHOD: Visual inspection
ccbaa14c-9e4a-5884-9b61-0a402f61a356 | note | FREQUENCY: Each lot
c004d259-b3fd-53c8-9f2d-0e5c34e7f6f9 | note | CATEGORY: IP
b46e9631-f804-5f27-91a8-acda5a2bc3e1 | note | RESPONSIBILITY: SE
f686f6c9-03b7-53f7-85c6-e3685f5484fa | note | VERIFYING DOCUMENTS: ITP Signed
aeedbe73-ed9f-5bed-a491-590020342c69 | date | Date Completed:
| checkpoint | 6.3 Survey Conformance
71c1067d-9abd-51c2-80b9-04e6d6e8a1ab | note | REFERENCE: VicRoads: Cl 703.15
d21baa65-3274-5c46-be4d-9a5d2387aa22 | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
8c533944-1bcf-50b0-b8a1-27f185a6e741 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
4e58884f-d827-511c-a8c8-112e00ec223b | note | ○ Attach: as-built survey records
bc7fe94e-7d35-538c-bee3-9a4e2d6309e4 | note | METHOD: Document Review
78366115-5ef8-5ef7-b66b-6ba8caa8f6e5 | note | FREQUENCY: Completion of each lot
369c3905-a5ca-56a8-9ef9-7543a59840dc | note | CATEGORY: WP
4840d2c6-c17a-561f-99db-81b3cfcfd06f | note | RESPONSIBILITY: Project Engineer/ Surveyor
2fff6c1b-f93b-5594-8ae5-aa13077283a9 | note | VERIFYING DOCUMENTS: As-built survey records
5e52fb13-979d-5fac-9de4-9af7df514816 | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
58332cd7-a35b-545f-bc80-982bcbb22fcc | note | REFERENCE: MRPA Quality Management Plan
d1bdcece-761c-57a7-8614-4a1dec219f2b | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
d675041a-f28f-5eda-ae03-1247557989ea | note | METHOD: Document Review
044f8dae-7a23-55f6-99b4-a6e2c6655a14 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
fe92a842-9295-5f16-9d29-c93c185313f0 | note | CATEGORY: HP*
cc7b747e-06cc-5b47-a47f-cd9a526a4568 | note | RESPONSIBILITY: SE/PE/SPE
34681787-3b73-5454-90a2-a64f5d3ad702 | note | VERIFYING DOCUMENTS: This ITP
b114f58a-7683-52be-a204-44537b409445 | date | Date Completed:
| checkpoint | Final Inspection
54b5a120-25cb-55cc-adfe-7f49ce2bd0e1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e503a9f2-bb5e-5032-9649-0004c12795a8 | textbox | Name:
07a9498a-78c9-5b29-a0e8-1360fa750cd6 | textbox | Position:
2b0cb46e-4ac2-5bc5-b889-cbb6348af7ae | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install) Rev 0 | itp | ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install) | 97d69a9d-5378-47e4-8acc-95ac8568c666
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d3c8974a-c9ab-50ff-a69a-a1d6a17e8ed3 | note | Document Title: ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install)
3aaeca91-f247-51f5-a44c-b66702dabf63 | note | ITP Description: SSO-Subsurface Drainage (Supply and Install)
9923c642-616d-579e-9ff1-56c9801c7402 | note | Discipline (e.g. CIV/STR/RAIL): CIV
ec60e818-c420-5fae-a206-c7fba26d3739 | note | Revision Number: 0
4ab55770-90a2-539b-8412-b45910e376d3 | note | Revision Date: 24/10/2024
d5b74fe8-3f4d-5e9b-97b4-0b50801a0d70 | note | ITP created by: Dimitri Santoreneos
f15af5a1-9bce-51ec-88ee-067e1f8cecb7 | note | ITP approved for use by: Sandy Escalona
f726415d-df57-54c7-8c1a-f67e703d40da | note | 1.1 Non Dependent
65a1be3d-548d-591c-a26c-8943434b1660 | note | Reference: VicRoads Section 702 (May 2019)
d1448ea4-1579-5972-a5ab-f416f512d3ca | note | 1.2 Non Dependent
b91b13d6-5ec9-594f-a181-37d3200e3e7d | note | Reference: VicRoads Section 204 (Dec 2015)
0834071f-0e18-5c7b-a29b-1a0d23540a99 | note | 1.3 Non Dependent
32f7fa4a-eb2c-5f34-b73a-0e00ea7a972c | note | Reference: VicRoads SD1611
8f2fe119-fd3e-5417-84ac-0daf4dc82abb | note | 1.4 Non Dependent
dacc146e-7156-5c83-b219-76647ac4a32f | note | Reference: VicRoads SD1051
bdedd70a-9a4b-5a0d-9520-63251314a0ea | note | 1.5 Non Dependent
7277fd42-6735-5ec6-9fb9-907399b7e67a | note | Reference: VicRoads SD1631
| section | Preliminaries - Materials
| checkpoint | 2.1 Drainage Pipes
f00a4f49-33ba-5cb4-a3a7-38c599d6397b | note | REFERENCE: IFC Drawings VicRoads: Cl 702.04
62cbebf1-2b27-5196-a43e-e6676062cd84 | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: Category 1: 100mm DIA Class 1000 corrugated perforated plastic pipe. Perforation size of maximum 1.5mm width and minimum length of 150 mm per m2.
68cbd3ea-a3d5-5c60-8e48-050816491a20 | textbox | Enter: Teambinder Material Approval number
91d49ccf-2305-58ef-801f-eeeca04e4559 | note | METHOD: Verify, Document Review
cbb63d74-7ad2-5873-a8c4-46537f6db1c2 | note | FREQUENCY: Each Lot prior to work start
15531728-8b79-5b26-8aed-4137acb6cd81 | note | CATEGORY: HP
6a65b2df-e262-5dfe-81a3-487a8b6ca519 | note | RESPONSIBILITY: Nominated Authority
666592af-7231-551c-9adc-ab4ed7323593 | note | VERIFYING DOCUMENTS: Conqa HP Release
8cc7442c-7fb9-5491-b393-583db9f8ea1a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Granular Filter Material
a2c1dce4-20ac-5297-8217-3ed53dd484c0 | note | REFERENCE: IFC Drawings VicRoads: Cl 702.05 Table 702.051
83e1e0bc-2117-5d5d-9e6a-8f411b78da5b | note | ACCEPTANCE CRITERIA: Granular filter material: Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accredited with VicRoads.
b0f26041-9c99-5a5d-b468-15df344bb8ae | textbox | Enter: Teambinder Material Approval number
14d6b448-cad2-53f9-8f23-4f0b17d74dbd | note | METHOD: Verify, Document Review
36e3af8b-2a03-5c58-8642-c59a8e9d608a | note | FREQUENCY: Each Lot prior to work start
b9a80fd5-4d37-524d-aa6e-93c36c51be27 | note | CATEGORY: HP
a8d94d73-5f37-5611-abda-ab291e10aea0 | note | RESPONSIBILITY: Nominated Authority
31e68886-4069-54bf-9120-fa2b63399779 | note | VERIFYING DOCUMENTS: Conqa HP Release
338c6db2-3f2e-52a1-8d1b-5318bf2c3505 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 No Fines Concrete
29deebc6-2020-561b-a2b4-b420bd7dfd01 | note | REFERENCE: IFC Drawings VicRoads: Cl 702.05
80f56df4-a392-5752-99fc-49a42d53c825 | note | ACCEPTANCE CRITERIA: No Fines Concrete: Shall be grade B4 in accordance with RC500.22, section 6.3 and shall comply with VicRoads Cl 702.05 (e)
0f9bd9cb-1df5-5e23-9923-70a77111bfcb | textbox | Enter: Teambinder Material Approval number
f583d69d-5312-54dd-952a-4078fa3b4dcb | note | METHOD: Verify, Document Review
d4bf18cf-fc57-5870-bb1d-f2378cc1b9d4 | note | FREQUENCY: Each Lot prior to work start
b45f7dfa-2f49-5ec6-be48-f3c55e24e4f3 | note | CATEGORY: HP
69f4acb2-f92b-53e0-b93f-93411061d5a9 | note | RESPONSIBILITY: Nominated Authority
13e420f1-49e4-5af2-bb45-7a70fa866540 | note | VERIFYING DOCUMENTS: Conqa HP Release
e0d049d5-2c6a-598d-87b9-422a360849eb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Geotextile Filter
17135f8d-360d-5302-988a-23d75ecd728f | note | REFERENCE: IFC Drawings VicRoads: Cl 702.06 Table 702.061
ee5715ed-6705-573b-8834-d480650fa070 | note | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with VicRoas Cl 702.06 and Table 702.061 of the requirements for Geotextile Filter
9c3b0af4-216e-5af7-9021-58975242f6d7 | textbox | Enter: Teambinder Material Approval number
06f0c20f-896d-5ddd-8290-352038076a67 | note | METHOD: Verify, Document Review
d19a3eed-7f43-574d-a886-199d18c8f4ce | note | FREQUENCY: Each Lot prior to work start
959347ca-416e-5337-9139-ea6e6532f291 | note | CATEGORY: HP
a2d8fb03-81a4-525c-a8f9-de8b87d8f3dd | note | RESPONSIBILITY: Nominated Authority
9fa58ed0-f777-5546-954d-ce30fc3618af | note | VERIFYING DOCUMENTS: Conqa HP Release
6cbba45a-df1d-54b0-aae6-2be8d6836891 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 SSD Pits, Pit Lids, Flushout Risers
3c4f4f82-bc2d-5ef7-84d2-397b2578d56b | note | REFERENCE: IFC Drawings SD-1051, SD-1611, SD-1631
de5f21b2-2f8d-5e41-9fbc-e3818cc8b434 | note | ACCEPTANCE CRITERIA: Subsurface drain pits: shall be Type S1 (as per SD 1611).
087016c7-3e6d-5dff-896e-fe969c1ac634 | note | ○ Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
d2bd3139-49b5-5c46-9fcc-26eed2a119fc | note | ○ Flushout risers: As per VicRoads, SD 1631
d0a3ceb6-134f-5744-b1da-c54f1aeb6a25 | textbox | Enter: Teambinder Material Approval number
beafc7e6-a44e-5605-8568-ae9836971c87 | note | METHOD: Verify, Document Review
22ddc1ac-b151-5a02-aec9-2623f7b43e52 | note | FREQUENCY: Each Lot prior to work start
14daf7d4-4549-532a-b381-b3b894202ff7 | note | CATEGORY: HP
196fa4a3-a721-5d3a-a724-d0be1d9d711f | note | RESPONSIBILITY: Nominated Authority
9e753a9e-d030-5574-9275-8ce5cf823739 | note | VERIFYING DOCUMENTS: Conqa HP Release
24ab69a7-fa5d-5916-92b1-7eb761a63fb1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Documentations
| checkpoint | 3.1 Check for correct documentation
a5f18718-31b8-54f8-869a-842ceedb59a9 | note | REFERENCE: IFC Drawings
89da3cbf-3245-54d6-9ea7-ed2b3bccc8cf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3a9d71e1-65f7-5ea6-80fa-7ad60cfb4199 | note | – using the correct and complete set of drawings
e5050094-4ce8-50c9-bd67-f7ae41aa3c0b | note | – all drawings are the latest revision (as per TeamBinder)
7b0ca0f8-3b8e-53ab-a78d-da82914bc124 | note | METHOD: Visual inspection
05cfbf17-921d-556a-a952-29f588d72ad1 | note | FREQUENCY: Prior to commencing any activity
6092b86a-65ef-537a-a524-e4c6c24e4232 | note | CATEGORY: WP
30287278-05fa-55c9-8d36-11fd87e47d3f | note | RESPONSIBILITY: SE/Site Supervisor
03fb20a8-c628-55e6-827f-f2b66cbf04d5 | note | VERIFYING DOCUMENTS: This ITP Signed-off
4cffa268-a62c-5a59-ad58-58d7385ad98c | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set Out
7bead5d8-0c01-5728-be99-edd9896fc5ac | note | REFERENCE: IFC Drawings VicRoads: Cl 702.03
9d00cc24-83bd-50ce-b52e-02b60db26839 | note | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
1ac8d390-37dc-5546-9771-d9df7fd8c0f0 | note | METHOD: Visual inspection
04526597-4c3a-58a6-840a-fc732857b5f2 | note | FREQUENCY: Each Lot
65d3e57b-0dc6-5c4a-8f4c-732f55aa9e1a | note | CATEGORY: IP
5e924e2d-459e-568c-a30a-bc4276d7bc55 | note | RESPONSIBILITY: SE/Site Supervisor, Surveyor
47865914-1251-58a4-8480-5fe5a9531487 | note | VERIFYING DOCUMENTS: This ITP Signed-off
e8b7555a-4161-5713-ba11-e47381fa42f6 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Trench Excavation
a13ffac4-926b-55fd-a74c-ed36102295ee | note | REFERENCE: VicRoads: Cl 702.08
1f1bdcfa-5b51-58f3-a0dd-574bcd652bf8 | note | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
5784716f-6104-5e13-99f5-81b99936d1c0 | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
098aa787-6c85-5f94-8839-e182eb5e1521 | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
4430196e-4a4a-5dea-9fd7-24aec87a2766 | note | ○ The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
449cab07-cc25-5dee-8448-f8ea4404999f | note | METHOD: Visual Inspection
8c7acc5b-c9b4-5d06-a328-b87e8f1895d4 | note | FREQUENCY: Each lot
71f7a9fa-6da9-5629-8cd7-69e95ed52521 | note | CATEGORY: HP
ae2c1cb3-3615-58a2-9dfe-5267acd4d419 | note | RESPONSIBILITY: SE, NA (Nominated Authority)
867d2690-a079-50f0-b913-5e920b813bc9 | note | VERIFYING DOCUMENTS: Conqa HP Release
d58acf3f-125d-5161-a996-790871fdeb04 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 Placement of bedding
56afa435-ce26-5036-ab7a-fe5cba7fd3c0 | note | REFERENCE: VicRoads: Cl 702.09 c)
73b2ffd6-826b-5116-97df-b32ce224030a | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
aff6d5df-e4bc-58e7-aea2-4bb764f38e86 | note | ○ Attach: bedding material delivery dockets
be1ad7ae-556d-5c57-b249-4a5e66e69b06 | note | METHOD: Visual inspection
5c8dd682-5afc-5268-934f-8adaf702211a | note | FREQUENCY: Each lot
17911cbb-0fe7-54b8-b565-cd59de949847 | note | CATEGORY: IP
005c5ab4-4ac3-55ea-b1c5-6f7e70bc0d7a | note | RESPONSIBILITY: SE/Site Supervisor
272adb4b-67c2-5da9-8f07-27cd6ae53878 | note | VERIFYING DOCUMENTS: This ITP Signed-off
74090a34-ec8b-5a07-a42e-f24f563a3131 | date | Date Completed:
| checkpoint | 5.3 Pipe and Geotextile Installation (if required)
df5b7914-c9cc-5903-813a-86782aadf6ca | note | REFERENCE: VicRoads: Cl 702.03, Cl 702.09
1417bb0e-ed8e-5870-8944-b98ac23902e0 | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
c9f260fd-e5a3-5606-8e53-0deadc67886f | note | ○ Attach: Suburface pipe and geotextile delievery dockets (if applicable)
4089e9da-2fbe-569e-8f9d-449842943290 | note | METHOD: Visual inspection
2f8cf683-d326-567c-a603-edd55156b531 | note | FREQUENCY: Each lot
5781fb29-42c7-5169-91ce-6a1ca0cab9d5 | note | CATEGORY: IP
52aa30f7-6ff2-5580-924c-536cf6a0022d | note | RESPONSIBILITY: SE/Site Supervisor
21fc05db-901b-5cf0-8f60-983e8f8e5862 | note | VERIFYING DOCUMENTS: This ITP Signed-off
859a9afa-9130-5247-8a62-d1c664eb80ca | date | Date Completed:
| checkpoint | 5.4 Backfill Installation (Granular Filter Material)
c5269a20-0989-5b01-b505-dd70aacaad82 | note | REFERENCE: VicRoads: Cl 702.09 (g)
72895bf7-ad50-5d1f-9a69-13c903bfe334 | note | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
fe4fd39b-aff1-5ef6-b80a-8a5bd7354e04 | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
ea94ed1d-6e69-5bcf-bc0c-c6a0a7f4b405 | note | ○ Attach: Backfill Delivery Dockets
f0d72a47-5232-567b-99bf-427cec104bc6 | note | METHOD: Visual
8200bb0e-2d41-5c26-ac7d-24d52fed41ee | note | FREQUENCY: Each lot
756a795a-d908-53c2-8077-b1d71015857a | note | CATEGORY: HP*
264b0573-3823-5a05-b10d-648690ad13bf | note | RESPONSIBILITY: SE, NA
0967efd4-fb84-593c-9209-49432aa9ca10 | note | VERIFYING DOCUMENTS: This ITP Signed-off
fda5c376-c08d-55cb-b0bd-cf5168ecb7e3 | date | Date Completed:
| checkpoint | 5.5 Backfill Installation (No Fines)
01eb5b47-72be-5d15-b5bc-838341ebaeb5 | note | REFERENCE: VicRoads: Cl 702.09 (g)
f139b3c6-d6c4-58cd-b047-e29b7d9f0161 | note | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
96eb47cc-986e-55c8-80be-746946ce5876 | note | ○ Attach: Backfill Delivery Dockets
f72ffe99-ae6b-5fcd-869d-306ef80d90d4 | note | METHOD: Visual
8b989443-4663-5abb-bcfd-5233ca4dc885 | note | FREQUENCY: Each lot
d4da4f29-a7dd-5b13-a09f-8496db0f5983 | note | CATEGORY: HP*
69d53440-7593-587d-b46f-18b99cfc3176 | note | RESPONSIBILITY: SE, NA
4596a746-75bd-569a-ae01-1f5c1b82b314 | note | VERIFYING DOCUMENTS: This ITP Signed-off
af5dfc13-5398-5798-b1a5-f6d7e3c1f540 | date | Date Completed:
| checkpoint | 5.6 Install Pits and Flushouts
b1e743bf-a91e-586d-b0a7-420319106ca9 | note | REFERENCE: VicRoads: Cl 702.10
65857da4-e5a4-542c-9b25-9cf412a296a1 | note | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run.
11a0ba3c-ef54-58a0-a070-e93c0727f9c1 | note | ○ Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
745d42d1-6b42-5b31-81c3-41ff1a35b475 | note | ○ Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
02f23bde-ee23-5ae4-819e-86e688e6cd10 | note | ○ Attach: Pit and Flushout Delivery Dockets
d1e247ac-6113-546c-a2fd-b0241a71724e | note | METHOD: Visual
4ee71b4b-0271-504e-beb3-4f590004ecfd | note | FREQUENCY: Each lot
fdf85a15-0403-5b60-9cb5-616180ed5ab0 | note | CATEGORY: WP
0afb4db4-16f8-5536-942f-fd6383dd2006 | note | RESPONSIBILITY: SE/Site Supervisor
7907f1ef-f0ca-55ca-9f96-6826a5708c3b | note | VERIFYING DOCUMENTS: This ITP Signed-off
f2487f10-a48a-58aa-8143-26cc18d74e1a | date | Date Completed:
| checkpoint | 5.7 Marker Posts
258e1156-e090-5a41-bb3b-01236b664c33 | note | REFERENCE: VicRoads: Cl 702.11
b471811b-feed-59df-a5ae-8905c954792c | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
09f094fb-46d7-5c4a-9a24-6e4344da5f40 | note | ○ Attach: Marker Post Delivery Dockets
c53649a1-e465-5715-b48e-7def2ba2cf0d | note | METHOD: Visual
cc03795a-f23c-5f0f-8ffa-3c1a7b0e050e | note | FREQUENCY: Each outlet
fc82bda5-e97b-5d1b-8b88-fd8567dc3f94 | note | CATEGORY: IP
c900531b-892e-5e4f-9a21-dbf179b371f9 | note | RESPONSIBILITY: SE/Site Supervisor
984c4a97-992f-59ad-9b36-432d166f1245 | note | VERIFYING DOCUMENTS: This ITP Signed-off
cf040b3d-079d-569d-a4f9-b7948619819b | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As Built Information
8a90c302-12cd-5583-a608-d46508507e8f | note | REFERENCE: VicRoads: Cl 702.03
5e4c010c-2809-5301-9b76-716b461cf311 | note | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
b489dce7-b9c2-5f87-a31b-cedc3fc6dc1c | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
5960da50-f091-50a1-8ec1-7c14500110ad | note | ○ Attach: Survey Conformance Report
51c7d8e6-600c-5c1e-9548-379f32fae6c0 | note | METHOD: Document Review
66a73ca6-5e60-5465-9c25-6d1222a09133 | note | FREQUENCY: Each lot
8070d3d4-bf0b-52fd-8ba4-7c03824237d0 | note | CATEGORY: IP
2bb4a13a-6adc-557d-a50e-da1c163a16d6 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f7abff29-17c4-551b-9eb0-d1b065184109 | note | VERIFYING DOCUMENTS: This ITP Signed-off
c88cc7eb-2b0f-5d69-b413-8a07a3ed1494 | date | Date Completed:
| checkpoint | 6.2 Flushing
39c62f89-4e9c-5fc9-8aef-1abb9d58fcf2 | note | REFERENCE: VicRoads: Cl 702.09 (h)
4a8139a2-c578-5561-b8ef-3b7b7c847f0e | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
e226e59c-264c-5869-ae96-ffb85bb1400a | note | ○ Attach: Flushing Tests Records
07d70746-130c-59d2-a4e1-0a03aa8044cb | note | METHOD: Document Review
f3150f8f-6587-5b8a-9b10-0c40babcaae9 | note | FREQUENCY: Each lot
bc9913a6-b446-5200-880c-b2332b221776 | note | CATEGORY: HP
625da523-7a62-5f90-ab14-633b8b7b6509 | note | RESPONSIBILITY: SE, NA
e99e72ad-ddd5-5897-b385-1423438a595a | note | VERIFYING DOCUMENTS: Conqa HP Release
6f34d901-a340-5d6d-a98a-8f03b7dfdedd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 Inspection of Subsurface Drainage - CCTV
586c8d08-46f2-57a1-a586-3623fa8384dc | note | REFERENCE: VicRoads: Cl 702.09 (i)
1d0273db-75f3-5754-a267-be678a4b535f | note | ACCEPTANCE CRITERIA: All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
51f5ce8b-5afe-5867-8cb0-cb5071828f9b | note | ○ Attach: CCTV Inspection Record
8530b179-525e-5bd9-8b84-fb94b9c02952 | note | METHOD: Document Review
df781b40-6c5f-5c62-b743-b313a2640d18 | note | FREQUENCY: Each lot
12dbb7fa-af8b-5183-adc1-1a4e2564cd22 | note | CATEGORY: HP
ed738d49-0776-51ab-bab6-97e26ce3aaae | note | RESPONSIBILITY: SE, NA
824efb9b-c3d4-552d-b919-618ce587e4dd | note | VERIFYING DOCUMENTS: Conqa HP Release
1061e8d6-7d1e-5433-aab1-75b1f005530e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
a68841a0-5944-5c4d-89fa-d9e7d8d20cd2 | note | REFERENCE: MRPA Quality Management Plan
5bf4e93a-a1bc-5ffb-885d-901391c4eda0 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
fba5850a-ea84-56e9-8d57-bb082a56c0ba | note | METHOD: Document Review
c9816bed-5fe9-5fed-9d49-dc1117186bc9 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
fd63196e-5cd3-5f0d-84b7-ef1a19352056 | note | CATEGORY: HP*
203c4c58-e4ad-556e-a810-61c8b49b5ecd | note | RESPONSIBILITY: SE/PE/SPE
86059800-ee68-5e05-b647-8b22b84d71a2 | note | VERIFYING DOCUMENTS: This ITP Signed-off
c926264d-83fa-5336-b2a9-6b10dea8d595 | date | Date Completed:
| checkpoint | Final Inspection
f4fe8f30-38ac-5d19-a47b-e4b7e51c686c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1432701f-cdfa-520b-8f4c-a47f21e8ea57 | textbox | Name:
c2641697-02fe-5eee-83a3-58b18c068b33 | textbox | Position:
890bacc3-f3c6-5dc1-8622-c5cc7c3d03ef | date | Date Completed:
| signoff | Sign ITP