## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-317-RAIL-SSO-Rail Delineation Permanent Fencing | itp |  |  |  |  | ITP-317-RAIL-SSO-Rail Delineation Permanent Fencing Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-317-CIV-SSO-Rail Delineation Fencing-Permanent
label | ITP Description: SSO-Rail Delineation Fencing-Permanent
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 1/09/2023
label | ITP created by: Diana Delac
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | ○ L1-CHE-STD-005
label | ○ L1-CHE-STD-025
label | ○ VicRoads Section 610
label | ○ VicRoads Section 630
section | Materials
checkpoint | 2.1 Concrete
label | REFERENCE: IFC Drawings Section 610.07, Table 610.071
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ 32MPa concrete to be used as per IFC drawings.
label | METHOD: Document Review
label | FREQUENCY: Each Mix
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | REFERENCE: IFC Drawings AS41000, AS1163
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a grade of C250
label | METHOD: Document review, Visual and Measure
label | FREQUENCY: All elements
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | ○ Offset checked against the running edge prior to installation of posts.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Excavation works
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | METHOD: Visual
label | FREQUENCY:
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Ground Conditions
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | METHOD: Visual
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 MTM OHW Structures
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures.
label | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
label | METHOD: Measure
label | FREQUENCY: Each Overhead
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Fence Post Foundation
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | ACCEPTANCE CRITERIA: 32MPa concrete.
label | ○ Footing to be a min. 1m clear from proposed TTC footing
label | ○ Typical Footing:
label | — Footing dimension 900mm deep, cross section 300mm X 300mm
label | — DN80 MS Pipe (88.9 X 4CHS) to be installed full depth.
label | ○ Alternative Strip Footing:
label | — 800x800x300mm thick
label | — 101.6 x 4.0 CHS sleeve to be cast into footing.
label | — 150x150x5 thick base plate welded to sleeve.
label | ○ Refer to IFC drawing for reinforcement details.
label | METHOD: Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Post and concrete dockets
date | Date Completed:
checkpoint | 4.5 Fence Post Installation
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays.
label | ○ An individual fence space may be increased to Max. 3100mm locally to avois clashes with services.
label | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | ○ Max. post height 1800mm above ground level.
label | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | METHOD: Measure
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.6 Chain Wire Mesh Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | ○ 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP, Delivery dockets
date | Date Completed:
checkpoint | 4.7 Bracing
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | ○ Bracing to be installed on both sides of the fence at the fence corners.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP, Steel delivery dockts
date | Date Completed:
checkpoint | 4.8 Refuge Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | ○ No chain wire mesh to be installed at refuge access.
label | ○ Refuge Access to be located every 20m max. along the fence.
label | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | METHOD: Visual/Measure
label | FREQUENCY: Every 20m Max.
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.9 Gate Post Foundation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 350mm DIA. PILE
label | ○ 1300mm DEPTH
label | ○ 1200mm POST EMBEDMENT
label | ○ 101.6 x 4 CHS GATE POST.
label | ○ 1200 EMBEDMENT
label | ○ 32MPa Concrete
label | METHOD: Visual/Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Post and Concrete Dockets
date | Date Completed:
checkpoint | 4.10 Gate Installation - Post
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts.
label | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | ○ Max. post height 1800mm above ground level.
label | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | METHOD: Measure
label | FREQUENCY: Each Post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
checkpoint | 4.11 Gate Installation - Gate
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE
label | ○ MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED.
label | METHOD: Measure
label | FREQUENCY: Each Gate
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 Fence Height and Track Clearance
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | METHOD: Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-318-CIV-SSO-Handrails (Supply & Install) | itp |  |  |  |  | ITP-318-CIV-SSO-Handrails (Supply & Install) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-318-CIV-SSO - Handrails (Supply & Install)
label | ITP Description: SSO - Handrails (Supply & Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 22/08/2024
label | ITP created by: Sandy Escalona/ Derek Collins
label | ITP approved for use by: Romualdo Magpantay
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix Design
label | REFERENCE: VR Clause 610.07 Table 610.071
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on IFC drawings (32MPa)
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA/ TB Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Drawings
label | REFERENCE: VR Clause 630.05
label | ACCEPTANCE CRITERIA: Subcontractor is responsible for preparation and verification of shop drawings. Prior fabrication, shop drawings are to be verified by a competent Structural Steel Engineer. Evidence of this review and competency of the reviewer shall be submitted to Nominated Authority.
label | METHOD: Verify, Document Review
label | FREQUENCY: Prior fabrication
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA/ TB Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Material Certification
label | REFERENCE: VR Clause 630.07
label | ACCEPTANCE CRITERIA: The Subcontractor shall submit to the Nominated Authority the steel manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate.
label | ○ The test certificates shall be related to the steel by trademarks and heat number.
label | METHOD: Verify, Document Review
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA/ TB Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: IFC Drawings, Manufacture's Installation Guideline
label | ACCEPTANCE CRITERIA: Ensure that all employees and sub contractors are:
label | — Using the correct and complete set of IFC drawings (latest revision as per TeamBinder)
label | — Using approved shop drawings
label | — Follow Manufacturer's recommendations
label | METHOD: Document Review
label | FREQUENCY: Once, prior to the commencement of activities
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 Setting out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings
label | ○ Attach: Lot Map-marked up drawing to indicate the location of the Lot
label | METHOD: Verify
label | FREQUENCY: Prior to starting Works
label | CATEGORY: HP*
label | RESPONSIBILITY: Surveyor/ Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Footing Installation
label | REFERENCE: IFC Drawings, Manufacturer's Installation Guideline
label | ACCEPTANCE CRITERIA: Footings to be constructed by Superintendent following IFC Drawings and Manufacturer's Installation Guidelines.
label | ○ Attach: subcontractors ITP signed off
label | METHOD: Visual, Site Survey
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor/ SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Installing Structures on site snug-tight Condition or tensioned using the Part-turn method if required
label | REFERENCE: IFC Drawings AS 1252, AS 5100.6, Manufacturer's Installation Guideline
label | ACCEPTANCE CRITERIA: Bolts shall be installed as per AS 1252 & AS5100.6. All bolts to be supplied complete with nut, locknut (where specified) & washer.
label | ○ Attach: subcontractors ITP signed off
label | METHOD: Visual, Site Survey
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Grouting of Base Plate Posts
label | REFERENCE: IFC Drawings AS 1252, AS 5100.6, Manufacturer's Installation Guideline
label | ACCEPTANCE CRITERIA: Superintendent to survey posts and confirm it is within tolerances prior to grouting base plates. Grout as per Engineering specifications.
label | ○ Attach: subcontractors ITP signed off
label | METHOD: Check level and alignments
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Completion of Works
label | REFERENCE: IFC Drawings, Approved shop drawings
label | ACCEPTANCE CRITERIA: Ensure that works were constructed as per IFC & approved shop drawings. Subcontractor and Superintendent must inspect works for damages and rectification of defects, including but not limited to protective coating and painting touch ups.
label | ○ Attach: subcontractors ITP signed off
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 DDA audit compliance
label | REFERENCE: IFC Drawings AS 1428.1, AGRD 6A
label | ACCEPTANCE CRITERIA: Ensure compliance for railing heights and offsets from pathways
label | ○ Attach: DDA compliance report
label | METHOD: Document Review
label | FREQUENCY: Completion of each lot
label | CATEGORY: WP
label | RESPONSIBILITY: Surveyor/ SE/PE/SPE
label | VERIFYING DOCUMENTS: DDA compliance report
date | Date Completed:
checkpoint | 6.2 Compressive Strength Test Results
label | REFERENCE: IFC Drawings Table VR, Table 610.051, VR Clause 610.16
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | METHOD: Document Review
label | FREQUENCY: Each cylinder
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 NCR Close out (if applicable)
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot/ element/ work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-319-CIV-SSO-Hot mix Asphalt | itp |  |  |  |  | ITP-319-CIV-SSO-Hot mix Asphalt Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-319-CIV-SSO- Hot Mix Asphalt
label | ITP Description: SSO - Hot Mix Asphalt
label | Discipline (e.g. CIV/STR/RAIL): 319-CIV
label | Revision Number: 0
label | Revision Date: 20/09/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Romouldo Magpantay
label | 1.1 - Non Dependent
label | Reference - VR 407 - July 2022
label | 1.2 - Non Dependent
label | Reference - VR 173 - Oct 2008
section | Preliminaries - Materials
checkpoint | 2.1 Mix Design
label | REFERENCE: VR 407.09
label | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Mix
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Bituminous Materials-Tack Coat
label | REFERENCE: VR 407.08 (d)
label | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder.
label | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
label | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Material
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Asphalt Quality Plan
label | REFERENCE: VR 407.04, VR 407.11
label | ACCEPTANCE CRITERIA: the Contractor shall provide an asphalt quality plan that addresses the following requirements:
label | — RAP Management plan (Approved by DTP)
label | — asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
label | — measuring and recording of pavement temperature, wind speed and weather conditions
label | — achieving a uniform application of tack coat
label | — achieving uniform asphalt placement including determination of paving speed and paving plans
label | — determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
label | — procedures to maximise density at joints.
label | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 RAP Management Plan
label | REFERENCE: VR 407.13 (f)
label | ACCEPTANCE CRITERIA: No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Cold weather placement
label | REFERENCE: VR 407.17 (b)
label | ACCEPTANCE CRITERIA: Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
label | ○ Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Lot Map-and Lot size
label | REFERENCE: VR 407.21 (a), VR 407.27 (b) (i)
label | ACCEPTANCE CRITERIA: A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
label | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
label | ○ ATTACH: Lot Map with planned location of Joints
label | METHOD: Document review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: attached Lot Map
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Ambient Conditions-Surface conditions
label | REFERENCE: VR 407.17 (a), VR 407.18
label | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
label | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Ambient Conditions-Surface Temperature
label | REFERENCE: VR 407.17 (a)
label | ACCEPTANCE CRITERIA: Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
label | ○ Specified binder class of C170 or C320:
label | — Wearing course: 10°C
label | — Other courses: 5°C
label | ○ Specified binder class of C600 or containing a PMB:
label | — Wearing Course 15°C
label | — Other courses 10°C
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Joints and Junctions-Layer by Layer-Transverse Joints
label | REFERENCE: VR 407.21 (b)
label | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | — All transverse joints shall be offset from layer to layer by not less than 2 m.
label | METHOD: Visual, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Joints and Junctions-Layer by Layer-Longitudinal Joints
label | REFERENCE: VR 407.21 (c )
label | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | — Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
label | — Longitudinal joints shall be parallel to the traffic lanes.
label | — Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
label | METHOD: Visual, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Joints and Junctions-Abutting existing pavement
label | REFERENCE: VR 407.21 (c)
label | ACCEPTANCE CRITERIA: Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
label | — At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Joints and Junctions-Junctions at limits of works
label | REFERENCE: VR 407.21 (d), VR 402
label | ACCEPTANCE CRITERIA: At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
label | ○ The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
label | (i) at side streets and median openings – 600 mm
label | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
label | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Application of Tack Coat
label | REFERENCE: VR 407.19
label | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
label | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled.
label | ○ The Contractor may omit the tack coat where asphalt is to be spread over
label | — A clean, un-trafficked, freshly laid asphalt, or
label | — A clean primed surface, or
label | — Granular material where the overall asphalt depth is 150mm or greater.
label | ○ PHOTOGRAPHIC EVIDENCEshall be supplied to show that tack has been applied.
label | ○ ATTACH: Photographic Evidence
label | METHOD: Visual
label | FREQUENCY: Where applicable
label | CATEGORY: SP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Joints and Junctions
label | REFERENCE: VR 407.21 (a)
label | ACCEPTANCE CRITERIA: All joints shall be well bonded and sealed
label | — All cold joints and abutting concrete edges shall be tack coated
label | METHOD: Visual
label | FREQUENCY: Where applicable
label | CATEGORY: SP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Delivery Dockets
label | REFERENCE: VR 407.20
label | ACCEPTANCE CRITERIA: Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
label | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
label | ○ ATTACH: Mix Delivery Docket
label | METHOD: Document review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Commencement of Placement
label | REFERENCE: VR 407.23
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.11 Paving of Asphalt
label | REFERENCE: VR 407.25
label | ACCEPTANCE CRITERIA: Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
label | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Paving of Asphalt
label | REFERENCE: VR 407.25
label | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
label | METHOD: Measure
label | FREQUENCY: Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.13 Compaction
label | REFERENCE: VR 407.26
label | ACCEPTANCE CRITERIA: Asphalt shall be uniformly. Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
label | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Compaction test-Lots larger than 500 sqm
label | REFERENCE: VR 407.27 (b) (i)
label | ACCEPTANCE CRITERIA: The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
label | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
label | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
label | ○ ATTACH: Compaction test report
label | ○ ATTACH: Wearing course joint strip compaction test results
label | METHOD: Document Review
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 Compaction test frequency-Lots smaller than 500 sqm
label | REFERENCE: VR 407.27 (b) (ii), VR 173.04 (d)
label | ACCEPTANCE CRITERIA: acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
label | ○ ATTACH: Compaction test results
label | METHOD: Document Review
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 Surface finish and conformity with drawings-Surface Finish and shape
label | REFERENCE: VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
label | ACCEPTANCE CRITERIA: The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
label | ○ No point on the finished surface of the wearing course: shall lie more than 4 mm below a 3 m straight edge
label | ○ For intermediate and base course layers: the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
label | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
label | METHOD: Measure
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Surface finish and conformity with drawings-Alignment and width
label | REFERENCE: VR 407.29 (a) (iv), VR 407.29 (a) (v)
label | ACCEPTANCE CRITERIA: Where asphalt pavement is not placed against a concrete edging:
label | ○ The edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
label | ○ The width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
label | METHOD: Measure
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor/SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.5 Conformity with drawings-Scale A and Scale B
label | REFERENCE: VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
label | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
label | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
label | METHOD: Measure
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor/SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 Conformity with drawings-Scale C
label | REFERENCE: VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
label | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
label | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
label | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
label | METHOD: Measure
label | FREQUENCY: Each Lot Where Applicable
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor/SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-320-CIV-SSO-Landscaping-Ground Preparation and Planting | itp |  |  |  |  | ITP-320-CIV-SSO-Landscaping-Ground Preparation and Planting Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-320-CIV-SSO-Landscaping-Ground Preparation & Planting
label | ITP Description: Landscaping-Ground Preparation & Planting
label | Discipline (e.g. CIV/STR/RAIL): 320-CIV
label | Revision Number: 0
label | Revision Date: 18/07/2025
label | ITP created by: Rajab Ali
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - VicRoads 720
label | 1.2 - Non Dependent
label | Reference - AS 4454
label | 1.3 - Non Dependent
label | Reference - AS 4419
label | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | Preliminaries-Materials
checkpoint | 2.1 Submission and records
label | REFERENCE: VicRoads Spec: Cl. 720.03
label | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | Following information shall be provided to the NA:
label | ○ Samples
label | — Mulch
label | — Imported topsoil
label | ○ Records
label | — Details of suppliers
label | — Soil tests on imported topsoil
label | — Copies/Photos of fertiliser labels
label | ○ Attach: Records and Certs into Hold Point inTeamBinder and write the Reference No.
label | METHOD: Document Review
label | FREQUENCY: Prior to Commencement of works
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Supply of topsoil
label | REFERENCE: VicRoads Spec: Cl.720.04, Table 720.042
label | ○ IFC Drawings
label | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No.
label | METHOD: Verify, Doc. Review if applicable
label | FREQUENCY: Prior to Commencement of works
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Supply of Mulch
label | REFERENCE: VicRoads Spec: Cl.720.04, Table 720.044, AS4454
label | ○ IFC Drawings
label | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
label | ○ Imported Wood Mulch shall comply with Table 720.044.
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | METHOD: Verify, Doc. Review if applicable
label | FREQUENCY: Prior to Commencement of works
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Supply of Plant
label | REFERENCE: VicRoads Spec: Cl.720.04, Table 720.041
label | ACCEPTANCE CRITERIA: All Plants have been inspected and comply with Sec 720.041
label | ○ Attach: Landscape Architect Approval
label | METHOD: Verify
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Supply of grass seed
label | REFERENCE: VicRoads Spec. Cl.720.04, Table 720.045
label | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | METHOD: Verify
label | FREQUENCY: Prior to Commencing works
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: Drawings and drawing registers
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — Using the correct and complete set of IFC drawings
label | — All drawings are the latest revision
label | METHOD: Document Review
label | FREQUENCY: Prior to Commencement of works
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
checkpoint | 3.2 Subcontractor ITP
label | REFERENCE: Subcontractor ITP
label | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
section | Ground Preparation
checkpoint | 4.1 Soil Additives
label | REFERENCE: VicRoads Spec: Cl. 720.07 (a), AS 4419
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report, Attached Delivery Docket (if applicable)
date | Date Completed:
checkpoint | 4.2 Ripping of subsoil
label | REFERENCE: VicRoads Spec: Cl. 720.07, Table 720.071
label | ACCEPTANCE CRITERIA: Rip Subsoil to min 250mm at 500mm spacing
label | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/NA
label | VERIFYING DOCUMENTS: Sign ITP, Attach Lot Map/Marked Up Area Inspected
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Topsoil application
label | REFERENCE: VicRoads Spec: Cl. 720.07
label | ACCEPTANCE CRITERIA: Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP
date | Date Completed:
checkpoint | 4.4 Mulching
label | REFERENCE: IFC Drawings VicRoads Spec: Cl. 720.08(a)
label | ACCEPTANCE CRITERIA: Mulch to be installed at 100mm and to finish 50mm below pavement.
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
checkpoint | 4.5 Weed and Erosion Control Mat
label | REFERENCE: IFC Drawings VicRoads Spec: Cl. 720.04(i)
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
checkpoint | 4.6 Jute Matting Installation
label | REFERENCE: IFC Drawings VicRoads Spec: Table 720.071
label | ACCEPTANCE CRITERIA: Pre-slit Jute Matt installed as per specification
label | ○ Lay Matting into a trench of min 150mm wide and depth, pin and backfill
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
section | Planting
checkpoint | 5.1 Plant Installation
label | REFERENCE: IFC Drawings VicRoads Spec: Table 720.041
label | ACCEPTANCE CRITERIA: Plants to be removed from Pot and Roots Tickled
label | ○ Ensure Mulch does not overly cover stem of plant
label | ○ Ensure plants to be watered within the same day
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE, Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.2 Fertiliser Application
label | REFERENCE: IFC Drawings VicRoads Spec: Table 720.041
label | ACCEPTANCE CRITERIA: Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant
label | ○ 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant
label | ○ 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE, Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.3 Tree Installation
label | REFERENCE: IFC Drawings VicRoads Spec: Table 720.041
label | ACCEPTANCE CRITERIA: Installation on Grade:
label | — Hole to be 100mm deeper and 600mm wider than pot size
label | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | ○ Installation on Garden Beds/Turf:
label | — Tree Pit Inspected and Minimum 3 times the root ball width
label | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE, Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.4 Soil Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 75mm depth topsoil & 100mm min in swales consolidated as approved
label | METHOD: Verify
label | FREQUENCY: Each Applicable Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE, Site Supervisor
label | VERIFYING DOCUMENTS: Subcontractor ITP, Attach Delivery Dockets
date | Date Completed:
section | Post Construction
checkpoint | 6.1 NCR Closeout
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot/element/work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-321-CIV-SSO-Lighting-MTM Carpark | itp |  |  |  |  | ITP-321-CIV-SSO-Lighting-MTM Carpark Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-321-CIV-SSO-Lighting-MTM
label | ITP Description: SSO-Lighting-MTM
label | Discipline (e.g. CIV/STR/RAIL): 321-CIV
label | Revision Number: 0
label | Revision Date: 21/08/2024
label | ITP created by: VM
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - L1-CHE-STD-059
label | 1.2 - Non Dependent
label | Reference - L1-CHE-STD-035
label | 1.3 - Non Dependent
label | Reference - L1-CHE-SPE-155
label | 1.4 - Non Dependent
label | Reference - AS/NZS 3000
label | 1.5 - Non Dependent
label | Reference - AS/NZS 1158.3.1 (2020)
label | 1.6 - Non Dependent
label | Reference - A9819
section | Preliminaries-Materials
checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
label | REFERENCE: L1-CHE-STD-035, AS/NZS 2053 IFC Drawings
label | ACCEPTANCE CRITERIA: Materials comply with MTM Engineering stadard Lighting and Powerrelevant specifications.
label | ○ All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
textbox | * Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Concrete
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Concrete complies mix complies with VR 400/40.
label | ○ Pile Concrete Grade at 28 days shall be 40 Mpa.
textbox | * Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Reinforcement (Cage)
label | REFERENCE: IFC Drawings VR 611.05
label | ACCEPTANCE CRITERIA: Reinforcement cages shall be according to IFC Drawings
label | ○ Reinforcement complies with VicRoads Section 611.05 (a) & (b), and AS4671 (ACRS)
textbox | * Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 HD Bolts assemblies
label | REFERENCE: A9819, VR 630.20
label | ACCEPTANCE CRITERIA: HD bolt assemblies as per IFC drawings
label | ○ All HD bolts are grade 4.6/S, galvanised
label | ○ All nuts and washers to be galvanised
textbox | * Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY:
label | RESPONSIBILITY:
label | VERIFYING DOCUMENTS:
date | Date Completed:
checkpoint | 2.5 Inspect supplied items upon delivery
label | REFERENCE: QMP L1-CHE-SPE-155
label | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | ○ Luminaires: At the time of delivery, the supplier shall provide three hard copies of the following:
label | — Installation Instruction Manual
label | — Operation Instruction Manual
label | — Storage, handling, loading and off–loading instructions
label | — Test Certificates
label | — Warranty Information
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP, Attach records required
date | Date Completed:
section | Preliminaries-Related Works
checkpoint | 3.1 Conduit & pit installation
label | REFERENCE: L1-CHE-STD-035 IFC Drawings
label | ACCEPTANCE CRITERIA: Conduit and Pit Installation works are to be recorded under ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting in addition to Subcontractors Checklist.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-Construction Works
checkpoint | 4.1 Survey Set Out
label | REFERENCE: IFC Drawings,
label | ACCEPTANCE CRITERIA: Survey to set out position of piles.
label | ○ Attach: Lot Map
label | METHOD: Visual, Documen Review
label | FREQUENCY: Each bore
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Attached Geotechnical Report, Attached Lot Map
date | Date Completed:
section | Construction
checkpoint | 5.1 Prepare the footing foundation (Excavation & levels)
label | REFERENCE: IFC Drawings, Manufacturer specifications
label | ACCEPTANCE CRITERIA: Check levels and diameter conform to manufacturer drawings depending on type of pole to be installed. Foundations to be installed as per manufacturer specification and requirements.
label | ○ Pile holes to be inspected by Geotechnical Engineer.
label | ○ Attach: Geotechnical Report
label | METHOD: Visual, Document Review
label | FREQUENCY: Each bore
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Geotechnical Engineer
label | VERIFYING DOCUMENTS: Attached Geotechnical Report
date | Date Completed:
checkpoint | 5.2 Installation of reinforcement cage
label | REFERENCE: IFC Drawings, Manufacturer specifications A9819
label | ACCEPTANCE CRITERIA: cage shall have enough clearance to the bore to maintain coverage as per IFC.
label | ○ Spacers and supports placed at intervals no more than 2m
label | METHOD: Measure
label | FREQUENCY: Each bore
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: this ITP
date | Date Completed:
checkpoint | 5.3 Cast in items
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Cast in items (conduits, hold down bolts, etc.) are installed in correct orientation and position.
label | ○ Hold down bolts have enough projection out side of the pile to accommodate for grout and base plate installation.
label | METHOD: Measure
label | FREQUENCY: Each bore
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Pre-pour inspection
label | REFERENCE: IFC Drawings, MRPA Construction Management plan
label | ACCEPTANCE CRITERIA: Pre-pour inspection to be conducted. Check the reinforcement cage as per manufacturer spec and IFC.
label | ○ Cast in items (e.g. bolts and conduits) positions to be installed as per IFC drawings/manufacturer drawings. Projection of items to be installed as per IFC drawings. Position and projection to be confirmed during inspection.
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ThisITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 Concrete placement and Compaction
label | REFERENCE: IFC Drawings, MRPA Construction Management
label | ACCEPTANCE CRITERIA: The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ All concrete batches are traceable.
label | ○ All concrete batches are from approved mix
label | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | ○ Attach: Concrete Pour Record
label | ○ Attach: Concrete Dockets
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP, Attached Pour Records, Attached Dockets
date | Date Completed:
checkpoint | 5.6 Concrete Sampling
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Concrete Tester
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Pile Integrity Testing
label | REFERENCE: VR 606.07 (a, d & e), AS2159 Clause 8.8, A9819
label | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | ○ Cross-sectional area = ≥95%
label | ○ If any test fails, all piles shall be tested.
label | ○ Attach: Pile Integrity Test Report
label | METHOD: Document Review
label | FREQUENCY: Piles #1 - #6.
label | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
label | CATEGORY: IP
label | RESPONSIBILITY: Testing Consultant, SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Installation lighting pole bases & columns
label | REFERENCE: IFC Drawings L1-CHE-STD-035
label | ACCEPTANCE CRITERIA: Free standing platform lighting poles shall be at earth potential as mounted in ground or on structure. Light fittings shall be earthed by the earth cable from
label | ○ Concrete and metallic poles at all new installations and station extensions that support low voltage equipment shall be earthed by an underground conductor that is connected to the earth at the origin from which the circuit is supplied in accordance with AS/NZS 3000.9.5.2
label | ○ Lighting installations shall be LED and comply with L1-CHE-SPE-155
label | ○ Car park poles shall be located as per IFC Drawings.
label | ○ Pole access hatches shall be orientated to allow unobstructed access.
label | ○ Level formed ground shall be at each pole for access by ladder or EWP.
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Per Pole
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Assembly of outreaches and luminaires
label | REFERENCE: L1-CHE-STD-035 IFC Drawings
label | ACCEPTANCE CRITERIA: Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
label | — Bracket and luminaire to align at right angles to vehicle path on road
label | METHOD:
label | FREQUENCY: Per Pole
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Installation of lighting distribution cabinet
label | REFERENCE: L1-CHE-STD-035 IFC Drawings
label | ACCEPTANCE CRITERIA: The switchboard or distribution board shall be designed and manufactured from suitable materials appropriate to the location in accordance with AS/NZS 3439.1.
label | METHOD: Visual
label | FREQUENCY: Per lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Installation of cabling
label | REFERENCE: IFC Notes
label | ACCEPTANCE CRITERIA: All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
label | — Each pole to be cables from the pole circuit breaker
label | METHOD: Visual & Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Test Certificate, This ITP
date | Date Completed:
checkpoint | 5.12 Commissioning & testing
label | REFERENCE: L1-CHE-STD-035
label | ACCEPTANCE CRITERIA: Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
label | METHOD: Commissioning & testing
label | FREQUENCY: Upon completion of each section
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE, Services Engineer
label | VERIFYING DOCUMENTS: This ITP, Attach Certificate
date | Date Completed:
checkpoint | 5.13 Labelling of Assets
label | REFERENCE: L1-CHE-STD-035 MTM Standard
label | ACCEPTANCE CRITERIA: Labels fixed to poles as per MTM standard. Pole numbering
label | ○ Labelling of switchboards, distribution boards, circuit breakers, RCDs and all control devices shall be labelled as per Appendix B in MTM standard.
label | ○ Indelible Labelled srawings shall be permanently displayed at the point of supply. Permanent field markers shall clearly identify the extent of the EPZ locations.
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Per pole
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.14 Grouting
label | REFERENCE: IFC Drawings A9819
label | ACCEPTANCE CRITERIA: Install 50mm Grout as per IFC Drawings.
label | ○ Grout completely fills void between op of pile and structure by ramming against fixed support.
label | METHOD: Visual, Measure
label | FREQUENCY: Per pole
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.15 Earth electrode or mat
label | REFERENCE: IFC Drawings A9819
label | ACCEPTANCE CRITERIA: Must be one installed per each lighting and power installation.
label | ○ The minimum distance between Earth electrodes or mats of lighting and power supply systems and rail tracks shall be based on the earthing design but shall be a minimum distance of 3.0 metres from the nearest running rail.
label | ○ Earth mats shall be bonded into a continuous electrical grid using a welded connection in accordance with AS 1554 or approved crimp connection from the MTM Engineering A1215 Remove covered Approved Product List.
label | ○ A certificate of compliance to AS 2832.5 and test results shall be provided for all bonding connections.
label | METHOD: Visual
label | FREQUENCY: per pole
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post Constrution
checkpoint | 6.1 Attached and verify Subcontractor conformance records/signed ITP including relevant verification sheets
label | REFERENCE: IFC Drawing Note
label | ACCEPTANCE CRITERIA: Check conformance report against project conformance criteria
label | METHOD: Doc. Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Sign ITP, Attach documents
date | Date Completed:
checkpoint | 6.2 Compressive Strength Test Results
label | REFERENCE: IFC Drawings Table VR 610.05.051, VR 610.16 (g)
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | METHOD: Document Review
label | FREQUENCY: Each cylinder
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 As-Constructed Plans
label | REFERENCE: IFC Drawing Note
label | ACCEPTANCE CRITERIA: The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
label | METHOD: Document Review
label | FREQUENCY: Upon completion/ Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Sign ITP, Attach As Constructured Plans
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-322-CIV-SSO-Sprayed Seal | itp |  |  |  |  | ITP-322-CIV-SSO-Sprayed Seal Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-321-CIV-SSO-Lighting-MTM
label | ITP Description: SSO-Lighting-MTM
label | Discipline (e.g. CIV/STR/RAIL): 321-CIV
label | Revision Number: 0
label | Revision Date: 21/08/2024
label | ITP created by: VM
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - VR 407 - July 2022
label | 1.2 - Non Dependent
label | Reference - VR 173 - Oct 2008
section | Preliminaries - Materials
checkpoint | 2.1 Aggregate
label | REFERENCE: VR 408.11 (a), VR 831.05 (c)
label | ACCEPTANCE CRITERIA: Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Material
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Bitumen Emulsion
label | REFERENCE: VR 408.08
label | ACCEPTANCE CRITERIA: Bitumen emulsion shall comply with the requirements of AS 1160.
label | ○ The use of any non standard proprietary classes of bitumen emulsion shall be subject to the Contractor providing evidence that the product has demonstrated satisfactory field performance for a period of at least three years.
label | ○ The primer shall be cutback bitumen.
label | ○ Cutback bitumen shall comply with the requirements of AS 2157. An equivalent product may be used subject to the Contractor providing evidence satisfactory to the Superintendent that the proprietary product has demonstrated acceptable field performance for a period of at least three years.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Material
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Application of bituminous material and aggregate
label | REFERENCE: VR 408.13 (a)
label | ACCEPTANCE CRITERIA: At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Application of bituminous material and aggregate
label | REFERENCE: VR 408.13 (f)
label | ACCEPTANCE CRITERIA: Where the Contractor proposes to use forward aggregate spreading plant, written approval is required from the Superintendent prior to use, unless written approval has been previously provided by the Department of Transport.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Claibration of Bitumen Sprayer
label | REFERENCE: VR 408.07
label | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads test methods AGPT T530 through to AGPT T536. The Certificate of Calibration shall be renewed every 12 months. If any sprayer has its spray equipment overhauled or replaced, it shall be calibrated and issued with a new Certificate of Calibration prior to use.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Survey set out - Lot Map-and Lot size
label | REFERENCE: 408.05
label | ACCEPTANCE CRITERIA: Limits of work at the start and finish chainages plus the limit in any side road have been marked on the pavement surface.
label | ○ The Works shall include all existing tapers, bell mouths at intersecting roads, pavement widenings (turn lanes), traffic lanes and sealed shoulders, unless otherwise specified.
label | ○ ATTACH: Lot Map with planned location of Joints
label | METHOD: Document review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: attached Lot Map
date | Date Completed:
checkpoint | 4.3 Pavement Preparation
label | REFERENCE: VR 310.02
label | ACCEPTANCE CRITERIA: The pavement shall be prepared to produce a surface that is:
label | (a) constructed to meet specified shape and level requirements
label | (b) homogenous and consistent with the material in the pavement base layer
label | (c) uniform in texture
label | (d) free of tearing and scabbing
label | (e) free of lamination on or within 75 mm of the finished surface
label | (f) level with adjacent sealed areas and edgings at the joints
label | (g) a hard dense and tight surface capable of being swept with a rotary road broom or similar
label | (h) free of loose and foreign materials
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Dry back of Pavement
label | REFERENCE: VR 310.03
label | ACCEPTANCE CRITERIA: The mean Moisture Ratio shall be determined from six randomly selected sites as a percentage of the optimum moisture content based on Modified compactive effort, and determined in accordance with VicRoads Test Method RC 316.14
label | ○ Scale B: Mean Moisture Ratio Less than 60%
label | ○ Scale C: mean Moisture Ratio Less than 65%
label | ○ No individual result more than 70%
label | ○ Attach: test results:
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE, Tester
label | VERIFYING DOCUMENTS: This ITP, Attached results
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Acceptance of work - Rate of binder application
label | REFERENCE: VR 408.15 (a)
label | ACCEPTANCE CRITERIA: Attach: evidence to show actual rate of application <0.1 L/m2 below design rate of application.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: This ITP, Attached evidence
date | Date Completed:
checkpoint | 5.2 Acceptace of work - Surface texture
label | REFERENCE: VR 408.15 (b)
label | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with VicRoads Test Method RC 317.01
label | METHOD: Visual, Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Acceptance of work - aggregate retention
label | REFERENCE: VR 408.15 ( c)
label | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with the VicRoads Test Method RC 317.03
label | METHOD: Visual, Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Removal of loose aggregate
label | REFERENCE: VR 408.14
label | ACCEPTANCE CRITERIA: After the completion of a sprayed seal treatment, the Contractor shall remove and dispose of all loose aggregate within the maximum time limits as specified in Table 408.141. This includes loose aggregate on all trafficked areas, and areas where loose aggregate has been swept, or moved by traffic onto sealed shoulders or non trafficked areas, or into other areas such as concrete channels, traffic islands, medians, open drains, drainage pits, footpaths, nature strips, or verges. For seals of nominal size 7 mm and under,no more than 60 loose stones in any square metre of pavement shall remain.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Records
label | REFERENCE: VR 408.17
label | ACCEPTANCE CRITERIA: The Contractor shall forward to the Superintendent a Job Completion Report (Sealing) using the proforma included as Attachment A to Section 408
label | ○ Attach: Job Completion Report (Sealing)
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: Nominated authority
label | VERIFYING DOCUMENTS: Attached records
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-323-CIV-SSO-Subgrade Preparation - Road | itp |  |  |  |  | ITP-323-CIV-SSO-Subgrade Preparation - Road Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-321-CIV-SSO-Lighting-MTM
label | ITP Description: SSO-Lighting-MTM
label | Discipline (e.g. CIV/STR/RAIL): 321-CIV
label | Revision Number: 0
label | Revision Date: 21/08/2024
label | ITP created by: VM
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
section | Preliminaries-Materials
checkpoint | 2.1 Material Approval
label | REFERENCE: VR 204.04 ( C)
label | ACCEPTANCE CRITERIA: Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each mix material
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentations
checkpoint | 3.1 - Non Dependent
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | METHOD: Verify
label | FREQUENCY: Prior to commencement of excavation
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
label | REFERENCE: Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | ○ Assigned CBR ≥ 2.5%
label | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type A fill Lot Number:
label | METHOD: Verify-Document Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 Material classified as silt
label | REFERENCE: Section 204.04 b)
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | METHOD: Document Review
label | FREQUENCY: Prior to commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
label | REFERENCE: Section 204.06 f)
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | METHOD: Site Inspection/ Document Review
label | FREQUENCY: Prior construction of the regulating layer
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Unsuitable Material
label | REFERENCE: Section 204.07 d)
label | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 Groundwater
label | REFERENCE: Section 204.06 h)
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Cut to Fill Zones
label | REFERENCE: Section 204.06 g)
label | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | METHOD: Site Inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.7 Proof Roll
label | REFERENCE: Section 173
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 Compaction Testing
label | REFERENCE: Table 204.131
label | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | ○ Scale A: Characteristic Density Ratio 99%.
label | ○ Scale B: Characteristic Density Ratio 98%.
label | ○ Scale C: Mean Value of Density Ratio: 100%
label | ○ Attach: Compaction Test Result:
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
date | Date Completed:
checkpoint | 5.9 Post Compaction Material Property Testing
label | REFERENCE: Section 204.04 (c)
label | ○ Section 204.14 (a) and Table 204.141 For Scale A
label | ○ Section 204.14 (b) for Scale B
label | ○ IFC Drawings
label | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
label | Scale A:
label | ○ CBR and Swell as per IFC for design package:
label | — MRP-DPK-087-00-CDR-0002-0
label | — as per table VR 204.141
label | Scale B:
label | ○ CBR and Swell as per IFC for design package:
label | — MRP-DPK-087-00-CDR-0002-0
label | ○ First Lot for Max Particle Dimension:
label | — After compaction Type B material shall have a maximum particle dimension of not more than:
label | — 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
label | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | METHOD: Review Document
label | FREQUENCY: Refer to Section 204
label | CATEGORY: IP
label | RESPONSIBILITY: PE/SE
label | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
date | Date Completed:
section | Post Construction Activities
checkpoint | 6.1 Survey Conformance
label | REFERENCE: VicRoads 204.03f,g and h
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances (Scale A):
label | — Range x = +5, -15mm
label | — Max S = 12 mm
label | — 80 measurements per lot
label | ○ Level tolerances (Scale B):
label | — Range x = +5, -25mm
label | — Max S = 15 mm
label | — 40 measurements per lot
label | ○ Level tolerances (Scale C):
label | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | METHOD: Review Document
label | FREQUENCY: Each lot
label | CATEGORY: SCP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-324-CIV-SSO-Concrete Paving - Footpath-SUP and Crossings | itp |  |  |  |  | ITP-324-CIV-SSO-Concrete Paving - Footpath-SUP and Crossings Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-324-CIV-SSO-General Concrete Paving - Footpath-SUP and Crossings
label | ITP Description: SSO-General Concrete Paving - Footpath-SUP and Crossings
label | Discipline (e.g. CIV/STR/RAIL): 324-CIV
label | Revision Number: 0
label | Revision Date: 4/09/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 304 August 2013
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 703 April 2019
label | 1.3 - Non Dependent
label | Reference - Council EDCM 401
label | 1.4 - Non Dependent
label | Reference - Council EDCM 501
label | 1.5 - Non Dependent
label | Reference - Council EDCM 502
label | 1.6 - Non Dependent
label | Reference - Council EDCM 503
label | 1.7 - Non Dependent
label | Reference - AS 1379-2007
label | 1.8 - Non Dependent
label | Reference - VicRoads Section 812 July 2016
section | Preliminaries - Materials
checkpoint | 2.1 Bedding Material Placement & Compaction
label | REFERENCE: IFC Drawings: 812.04, 703.21
label | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | ○ SUP: SIZE 40mm CLASS 3 CRUSHED ROCK
label | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Concrete Mix
label | REFERENCE: IFC Drawings: 703.05 (a), 703.07
label | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | — Footpaths, Residential driveways and Median islands infills: 25Mpa
label | — Industrial Crossovers: VR330/32 to be registered by Vicroads
label | — Traffic Islands: 32 Mpa
label | — SUP: VR330/32
label | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Reinforcement
label | REFERENCE: IFC Drawings: 703.16
label | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
label | — Footpaths, Residential driveways and Median islands infills: SL72
label | — Industrial Crossovers: SL82
label | — Traffic Islands: SL72
label | — SUP: SL82
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Evaporative Retardant
label | REFERENCE: 703.09, 610.17 (f)
label | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Curing Compound
label | REFERENCE: 703.10 (a), 610.23 (d)
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Documents
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings 703.17
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ The Nominated Authority will review and confirm the set out.
label | ○ Attach: Survey Report
label | METHOD: Document Review, Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Lot Map
label | REFERENCE: MRPA Lot Management Plan
label | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
label | ○ Attach: Lot Map
label | METHOD: Document
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Attached Lot Map
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Site Clearing & Grubbing
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | METHOD: Document Review, Visual
label | FREQUENCY: Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | — Using the correct and complete set of drawings
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Excavation
label | REFERENCE: 703.20 IFC Drawings
label | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
label | REFERENCE: IFC Drawings:
label | ○ Relevant Council drawings:
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Bedding Material Placement & Compaction
label | REFERENCE: 703.21 IFC Drawings
label | ○ IFC Drawings: Relevant Council drawings:
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
label | ○ Footpath: Bedding shall 100 mm compacted thickness
label | ○ SUP: Bedding shall be 150 mm compacted thickness
label | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | ○ Attach: Bedding Material Delivery Dockets
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Shared User Path - Compaction Testing
label | REFERENCE: 703.21, 304.08 (a) & (b), 304.11 (a)
label | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
label | — Scale of Surface Level Measurement = Scale C
label | — Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | — Mean Value of Density Ratio % (3 tests) not less than 100%
label | ○ Attach: Moisture Content Test Results
label | ○ Attach: Mean Value of Density Ratio
label | METHOD: Document Review, Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Shared User Path - Proof-rolling
label | REFERENCE: 703.21, 304.08 (b)
label | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
label | ○ Withstands Test rolling without visible deformation or springing.
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Formwork Construction & Placement
label | REFERENCE: IFC Drawings 703.12
label | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Construction Joints & Matching Existing Surfaces
label | REFERENCE: IFC Drawings 703.24
label | ○ Relevant Council Standard DrawingsRelevant Council drawings:
label | — EDSM 401
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
label | i. Concrete cutting of a shear-key
label | ii. Surface roughening
label | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | iv. Cutting a groove for sealant
label | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Isolation Joints
label | REFERENCE: IFC Drawings 703.26 (c)
label | ○ Relevant Council Standard Drawings
label | — EDSM 401
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | ii. at any location marked on the drawings
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Expansion Joints
label | REFERENCE: IFC Drawings 703.26 (a) (ii) & (b) (i)
label | ○ Relevant Council Standard Drawings
label | — EDSM 401
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | i. on either side of vehicle crossings
label | ii. at junctions with existing footpaths and shared use paths
label | iii. at junctions with bridges
label | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Reinforcement Placement
label | REFERENCE: IFC Drawings 703.13
label | — EDSM 401
label | — EDCM 501
label | — EDCM 502
label | — EDCM 503
label | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | — Footpaths, Residential driveways and Median islands infills: SL72
label | — Industrial Crossovers: SL82
label | — Traffic Islands: SL72
label | — SUP: SL82
label | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Pre-pour Survey
label | REFERENCE: IFC Drawings 703.15
label | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | ○ Erected formwork and base layer within the tolerances below:
label | — Departure from RL = ±10mm
label | — Departure from alignment = ±10mm
label | — Rate of change of deviation from RL or alignment = 10mm in 10m
label | — Irregularities in alignment = 5mm in 3m
label | — Section dimensions = ±5mm
label | — Section dimensions (less than 25mm) = ±3mm
label | — Width of pavement = -5mm, +15mm
label | ○ Attach: Survey Report
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Pre-pour Inspection
label | REFERENCE: Section 703.09, Section 703.21 Section 610.17a), b) & c)
label | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.13 Weather Conditions & Evaporation Limits
label | REFERENCE: 703.09, 610.17 (a - f), Table 610.171
label | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Measure, Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.14 Concrete Testing - Sampling Frequencies-Footpath
label | REFERENCE: 703.11, AS 1379-2007 Clause 6.2
label | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | ○ Correct quantity of cylinders manufactured per sample.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.15 Concrete Testing - Sampling Frequencies-SUP
label | REFERENCE: 703.11, 610.16 (b)
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ Shared User Path:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | ○ Footpaths:
label | 0m³ to 50m³ = 1 sample
label | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 2 no. 28 day strength.
label | ○ Correct quantity of cylinders manufactured per sample.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.16 Concrete Testing - Slump
label | REFERENCE: 703.11, 610.16 (c)
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each sample
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.17 Placement & Compaction
label | REFERENCE: 703.08
label | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | ○ Record: Required information on the Concrete Pour Record.
label | ○ Attach: Concrete Pour Record
label | ○ Attach: Concrete Dockets
label | METHOD: Visual
label | FREQUENCY: Each load
label | CATEGORY: SP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS:
date | Date Completed:
checkpoint | 5.18 Surface Finishes
label | REFERENCE: IFC Drawings, Relevant Council Drawings 703.25
label | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.19 Footpaths - Crack-control Joints / Weaken Plane Joints
label | REFERENCE: IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
label | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.20 Curing
label | REFERENCE: 703.1
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | REFERENCE: IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
label | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | ○ <20°C = within 24 hours of finishing operations
label | ○ ≥20°C - 35°C = within 4 hours of finishing operations
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Protection of Newly Poured Concrete
label | REFERENCE: 703.27
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | METHOD: Visual
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Stripping Formwork
label | REFERENCE: 703.12, AS3610 Table C2
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | i. 2 days for vertical formwork on external surfaces; and
label | ii. 1 day for vertical forms on permanently hidden surfaces
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Backfilling & Pavement Restoration
label | REFERENCE: 703.29
label | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | METHOD: Visual, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.5 Surface Inspection - Cracks
label | REFERENCE: 703.3
label | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | METHOD: Visual, Measure
label | FREQUENCY: Where applicable, each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 Surface Inspection - Surface Finish
label | REFERENCE: IFC Drawings, Relevant Council Drawings 703.25, 703.10 (a) AS3610 Clause 3.2
label | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | ○ Class of finish:
label | — Permanently hidden surfaces = Class 4
label | — All other surfaces = Class 3
label | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.7 Compressive Strength Test Results
label | REFERENCE: IFC Drawings, Relevant Council Drawings 703.11, Table 703.111, Table 610.05.051, 610.16 (g)
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | METHOD: Document Review
label | FREQUENCY: Each cylinder
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.8 As-built Survey
label | REFERENCE: IFC Drawings 703.15
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from alignment = ±10mm
label | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | ○ Irregularities in alignment = 5mm in 3m
label | ○ Section dimensions = ±5mm
label | ○ Section dimensions (less than 25mm) = ±3mm
label | ○ Width of pavement = -5mm, +15mm
label | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | ○ Attach: Survey As-builts / Survey Report
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP