## Sheet1
2.1 | Concrete | IFC Drawings Section 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance | 2.1 Concrete | REFERENCE: IFC Drawings Section 610.07 Table 610.071 | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings. | METHOD: Document Review | FREQUENCY: Each Mix | CATEGORY: HP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Supplier Certificate of Compliance | Date Completed: | 2.1 Concrete
2.2 | Steel Columns, Cladding, Handrails, etc | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance | 2.2 Steel Columns, Cladding, Handrails, etc | REFERENCE: IFC Drawings AS41000 AS1163 | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | METHOD: Document review Visual and Measure | FREQUENCY: All elements | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Supplier Certificate of Compliance | Date Completed: | REFERENCE: IFC Drawings Section 610.07 Table 610.071
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP | 3.1 Survey Set-out | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. | METHOD: Measure Visual | FREQUENCY: Each element | CATEGORY: IP | RESPONSIBILITY: Surveyor SE/PE | VERIFYING DOCUMENTS: This ITP | Date Completed: | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings.
4.1 | Excavation works | IFC Drawings L1-CHE-STD-005 | Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | Visual |  | IP | SE/Site Supervisor | This ITP | 4.1 Excavation works | REFERENCE: IFC Drawings L1-CHE-STD-005 | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | METHOD: Visual | FREQUENCY: | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP | Date Completed: | METHOD: Document Review
4.2 | Ground Conditions | IFC Drawings | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP | 4.2 Ground Conditions | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | METHOD: Visual | FREQUENCY: Each post | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP | Date Completed: | FREQUENCY: Each Mix
4.3 | MTM OHW Structures | IFC Drawings L1-CHE-STD-005 | Fencing must be a minimum 2m away from OHW Structures. Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level. | Measure | Each Overhead | IP | SE/Site Supervisor | This ITP | 4.3 MTM OHW Structures | REFERENCE: IFC Drawings L1-CHE-STD-005 | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures. Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level. | METHOD: Measure | FREQUENCY: Each Overhead | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP | Date Completed: | CATEGORY: HP
4.4 | Fence Post Foundation | IFC Drawings L1-CHE-STD-005 | 32MPa concrete. Footing to be a min. 1m clear from proposed TTC footing Typical Footing: Footing dimension 900mm deep, cross section 300mm X 300mm DN80 MS Pipe (88.9 X 4CHS) to be installed full depth. Alternative Strip Footing: 800x800x300mm thick 101.6 x 4.0 CHS sleeve to be cast into footing. 150x150x5 thick base plate welded to sleeve. Refer to IFC drawing for reinforcement details. | Measure | Each footing | IP | SE/Site Supervisor | Post and concrete dockets | 4.4 Fence Post Foundation | REFERENCE: IFC Drawings L1-CHE-STD-005 | ACCEPTANCE CRITERIA: 32MPa concrete. Footing to be a min. 1m clear from proposed TTC footing Typical Footing: Footing dimension 900mm deep, cross section 300mm X 300mm DN80 MS Pipe (88.9 X 4CHS) to be installed full depth. Alternative Strip Footing: 800x800x300mm thick 101.6 x 4.0 CHS sleeve to be cast into footing. 150x150x5 thick base plate welded to sleeve. Refer to IFC drawing for reinforcement details. | METHOD: Measure | FREQUENCY: Each footing | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Post and concrete dockets | Date Completed: | RESPONSIBILITY: SE/Site Supervisor
4.5 | Fence Post Installation | IFC Drawings L1-CHE-STD-005 | Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays. An individual fence space may be increased to Max. 3100mm locally to avois clashes with services. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP Concrete Dockets | 4.5 Fence Post Installation | REFERENCE: IFC Drawings L1-CHE-STD-005 | ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays. An individual fence space may be increased to Max. 3100mm locally to avois clashes with services. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | METHOD: Measure | FREQUENCY: Each post | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Concrete Dockets | Date Completed: | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
4.6 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN. | Visual | Each element | IP | SE/Site Supervisor | This ITP Delivery dockets | 4.6 Chain Wire Mesh Installation | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN. | METHOD: Visual | FREQUENCY: Each element | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Delivery dockets | Date Completed: | Date Completed:
4.7 | Bracing | IFC Drawings | 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners. | Visual | Each element | IP | SE/Site Supervisor | This ITP Steel delivery dockts | 4.7 Bracing | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners. | METHOD: Visual | FREQUENCY: Each element | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Steel delivery dockts | Date Completed: | 2.2 Steel Columns, Cladding, Handrails, etc
4.8 | Refuge Installation | IFC Drawings | Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located every 20m max. along the fence. 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | Visual/Measure | Every 20m Max. | IP | SE/Site Supervisor | This ITP | 4.8 Refuge Installation | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located every 20m max. along the fence. 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | METHOD: Visual/Measure | FREQUENCY: Every 20m Max. | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP | Date Completed: | REFERENCE: IFC Drawings AS41000 AS1163
4.9 | Gate Post Foundation | IFC Drawings | 350mm DIA. PILE 1300mm DEPTH 1200mm POST EMBEDMENT 101.6 x 4 CHS GATE POST. 1200 EMBEDMENT 32MPa Concrete | Visual/Measure | Each footing | IP | SE/Site Supervisor | Post and Concrete Dockets | 4.9 Gate Post Foundation | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: 350mm DIA. PILE 1300mm DEPTH 1200mm POST EMBEDMENT 101.6 x 4 CHS GATE POST. 1200 EMBEDMENT 32MPa Concrete | METHOD: Visual/Measure | FREQUENCY: Each footing | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Post and Concrete Dockets | Date Completed: | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
4.1 | Gate Installation - Post | IFC Drawings | 3000mm nominal clear between the gate posts. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | Measure | Each Post | IP | SE/Site Supervisor | Delivery Dockets | 4.1 Gate Installation - Post | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | METHOD: Measure | FREQUENCY: Each Post | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Delivery Dockets | Date Completed: | METHOD: Document review Visual and Measure
4.11 | Gate Installation - Gate | IFC Drawings | 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED. | Measure | Each Gate | IP | SE/Site Supervisor | Delivery Dockets | 4.11 Gate Installation - Gate | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED. | METHOD: Measure | FREQUENCY: Each Gate | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: Delivery Dockets | Date Completed: | FREQUENCY: All elements
5.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | This ITP | 5.1 Fence Height and Track Clearance | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | METHOD: Measure | FREQUENCY: Each lot | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP | Date Completed: | CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: Supplier Certificate of Compliance
Date Completed:
3.1 Survey Set-out
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts.
METHOD: Measure Visual
FREQUENCY: Each element
CATEGORY: IP
RESPONSIBILITY: Surveyor SE/PE
VERIFYING DOCUMENTS: This ITP
Date Completed:
4.1 Excavation works
REFERENCE: IFC Drawings L1-CHE-STD-005
ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor
METHOD: Visual
FREQUENCY:
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP
Date Completed:
4.2 Ground Conditions
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
METHOD: Visual
FREQUENCY: Each post
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP
Date Completed:
4.3 MTM OHW Structures
REFERENCE: IFC Drawings L1-CHE-STD-005
ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures. Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
METHOD: Measure
FREQUENCY: Each Overhead
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP
Date Completed:
4.4 Fence Post Foundation
REFERENCE: IFC Drawings L1-CHE-STD-005
ACCEPTANCE CRITERIA: 32MPa concrete. Footing to be a min. 1m clear from proposed TTC footing Typical Footing: Footing dimension 900mm deep, cross section 300mm X 300mm DN80 MS Pipe (88.9 X 4CHS) to be installed full depth. Alternative Strip Footing: 800x800x300mm thick 101.6 x 4.0 CHS sleeve to be cast into footing. 150x150x5 thick base plate welded to sleeve. Refer to IFC drawing for reinforcement details.
METHOD: Measure
FREQUENCY: Each footing
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: Post and concrete dockets
Date Completed:
4.5 Fence Post Installation
REFERENCE: IFC Drawings L1-CHE-STD-005
ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays. An individual fence space may be increased to Max. 3100mm locally to avois clashes with services. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
METHOD: Measure
FREQUENCY: Each post
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Concrete Dockets
Date Completed:
4.6 Chain Wire Mesh Installation
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN.
METHOD: Visual
FREQUENCY: Each element
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Delivery dockets
Date Completed:
4.7 Bracing
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners.
METHOD: Visual
FREQUENCY: Each element
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Steel delivery dockts
Date Completed:
4.8 Refuge Installation
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located every 20m max. along the fence. 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
METHOD: Visual/Measure
FREQUENCY: Every 20m Max.
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP
Date Completed:
4.9 Gate Post Foundation
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: 350mm DIA. PILE 1300mm DEPTH 1200mm POST EMBEDMENT 101.6 x 4 CHS GATE POST. 1200 EMBEDMENT 32MPa Concrete
METHOD: Visual/Measure
FREQUENCY: Each footing
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: Post and Concrete Dockets
Date Completed:
4.1 Gate Installation - Post
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
METHOD: Measure
FREQUENCY: Each Post
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: Delivery Dockets
Date Completed:
4.11 Gate Installation - Gate
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED.
METHOD: Measure
FREQUENCY: Each Gate
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: Delivery Dockets
Date Completed:
5.1 Fence Height and Track Clearance
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
METHOD: Measure
FREQUENCY: Each lot
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP
Date Completed: