## Sheet1
1.1.1 | Bedding and Backfill GAP65 or AP40 | Per Batch | CIV Spec - S12.3.5 DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject | N/A | Dockets / Material Data Sheets | R | SUB | R | Hold Point | — | 1.1.1 - Bedding and Backfill GAP65 or AP40 | Frequency - Per Batch | Spec/standard - CIV Spec - S12.3.5 DP001-MMD-DRW- UT-B-Z-3100-3117 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets / Material Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | 1.1.1 - Bedding and Backfill GAP65 or AP40
1.2.1 | PCC Risers/Chambers With HN-HO-72 Load Bearing Capacity | Each Unit | CIV Spec - S12.3.3 | Accept/Reject | N/A | Dockets / Material Data Sheets | R | SUB | R | Hold Point | — | 1.2.1 - PCC Risers/Chambers With HN-HO-72 Load Bearing Capacity | Frequency - Each Unit | Spec/standard - CIV Spec - S12.3.3 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets / Material Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | Frequency - Per Batch
1.2.2 | Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G | Each unit | CIV Spec - S9.3.8 | Shop drawings, Dockets/ Visual Checks | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | — | 1.2.2 - Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G | Frequency - Each unit | Spec/standard - CIV Spec - S9.3.8 | Acceptance Criteria - Shop drawings, Dockets/ Visual Checks | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | Spec/standard - CIV Spec - S12.3.5 DP001-MMD-DRW- UT-B-Z-3100-3117
1.3.1 | Standard Concrete Mix | Each Structure | CIV Spec - S13.3.1.1 | Accept/Reject | N/A | Design Mix | R | SUB | R | Hold Point | — | 1.3.1 - Standard Concrete Mix | Frequency - Each Structure | Spec/standard - CIV Spec - S13.3.1.1 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Design Mix | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | Acceptance Criteria - Accept/Reject
1.4.1 | Reinforcement Bending Schedules | Each Structure | CIV Spec - S14.3.1 | Accept/Reject | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | — | 1.4.1 - Reinforcement Bending Schedules | Frequency - Each Structure | Spec/standard - CIV Spec - S14.3.1 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | Measuring Devices - N/A
1.4.2 | Bending Schedules | Each Structure | CIV Spec - S14.4.6 | Accept/Reject | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | — | 1.4.2 - Bending Schedules | Frequency - Each Structure | Spec/standard - CIV Spec - S14.4.6 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - — | Reporting Format - Dockets / Material Data Sheets
1.5.1 | Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 3K or Similar | Each Pipe and Structure | DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject | N/A | Dockets/ Technical Data Sheets | R | SUB | R | — | — | 1.5.1 - Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 3K or Similar | Frequency - Each Pipe and Structure | Spec/standard - DP001-MMD-DRW- UT-B-Z-3100-3117 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets/ Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | HCL - R
2.1.1 | Survey Setout Chambers/Pits Position and Heights | Each Manhole | N/A | Survey Setout records and Setout pegs, Plans | GPS, Total Station | Setout CSV file, QC Checklist | — | — | — | — | Coordinates mentioned in plans | 2.1.1 - Survey Setout Chambers/Pits Position and Heights | Frequency - Each Manhole | Spec/standard - N/A | Acceptance Criteria - Survey Setout records and Setout pegs, Plans | Measuring Devices - GPS, Total Station | Reporting Format - Setout CSV file, QC Checklist | HCL - — | SC - — | Consult - — | Hold Points Sign off - — | Remarks - Coordinates mentioned in plans | SC - SUB
2.2.1 | Excavation Extents | Each element installed | CIV Spec - S13.4.1 CIV Spec - S4.5.9 (earthworks section) | N/A | Rotating level and GPS | N/A | M | — | — | — | — | 2.2.1 - Excavation Extents | Frequency - Each element installed | Spec/standard - CIV Spec - S13.4.1 CIV Spec - S4.5.9 (earthworks section) | Acceptance Criteria - N/A | Measuring Devices - Rotating level and GPS | Reporting Format - N/A | HCL - M | SC - — | Consult - — | Hold Points Sign off - — | Remarks - — | Consult - R
2.2.2 | Chambers/Pits subgrade testing | Utility Access Chambers: 2 tests at the base of excavation | CIV Spec - S4.6.2.2 (earthworks section) | Bearing Capacity as mentioned in the drawings For cohesive soil Shear Vane Test at EGL (0.0m), 0.5m and 1.0m depths For non-cohesive soil scala test to 1m depth. Inspection required by engineer for acceptance | Shear Vane Scala Penetrometer | QC Checklist, Visual Checks, Excel CHAR(AMP) pdf | M | SUB | W | Witness Point | If ground failing, Engineer to advise MM will attend all witness points | 2.2.2 - Chambers/Pits subgrade testing | Frequency - Utility Access Chambers: 2 tests at the base of excavation | Spec/standard - CIV Spec - S4.6.2.2 (earthworks section) | Acceptance Criteria - Bearing Capacity as mentioned in the drawings For cohesive soil Shear Vane Test at EGL (0.0m), 0.5m and 1.0m depths For non-cohesive soil scala test to 1m depth. Inspection required by engineer for acceptance | Measuring Devices - Shear Vane Scala Penetrometer | Reporting Format - QC Checklist, Visual Checks, Excel CHAR(AMP) pdf | HCL - M | SC - SUB | Consult - W | Hold Points Sign off - Witness Point | Remarks - If ground failing, Engineer to advise MM will attend all witness points | Hold Points Sign off - Hold Point
2.2.3 | 200mm thick 20MPa concrete bedding | Each structure | DP001-MMD-DRW- UT-B-Z-3100-3117 | Accept/Reject, 20MPa Concrete | N/A | QC Checklist, Dockets | M | SUB | R | — | — | 2.2.3 - 200mm thick 20MPa concrete bedding | Frequency - Each structure | Spec/standard - DP001-MMD-DRW- UT-B-Z-3100-3117 | Acceptance Criteria - Accept/Reject, 20MPa Concrete | Measuring Devices - N/A | Reporting Format - QC Checklist, Dockets | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Remarks - —
2.2.4 | Formwork | Each Structure | CIV Spec - S13.4.2 | Accept/Reject Dimension Accuracy, Alignment and position | GPS/ Total Station/ Rotating Laser | QC Checklist, As-Built drawings to confirm the tolerances | M | SUB | I | — | Engineer inspection will be done along with the reinforcement | 2.2.4 - Formwork | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.2 | Acceptance Criteria - Accept/Reject Dimension Accuracy, Alignment and position | Measuring Devices - GPS/ Total Station/ Rotating Laser | Reporting Format - QC Checklist, As-Built drawings to confirm the tolerances | HCL - M | SC - SUB | Consult - I | Hold Points Sign off - — | Remarks - Engineer inspection will be done along with the reinforcement | 1.2.1 - PCC Risers/Chambers With HN-HO-72 Load Bearing Capacity
2.2.5 | Reinforcement Laps | Each unit | CIV Spec - S14.4.7 DP001-MMD-DRW- CS-B-Z-3013 | Accept/Reject | N/A | QC Checklist, Visual Checks | M/I | SUB | — | — | Reinforcement Laps to be followed as shown in the plans | 2.2.5 - Reinforcement Laps | Frequency - Each unit | Spec/standard - CIV Spec - S14.4.7 DP001-MMD-DRW- CS-B-Z-3013 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - M/I | SC - SUB | Consult - — | Hold Points Sign off - — | Remarks - Reinforcement Laps to be followed as shown in the plans | Frequency - Each Unit
2.2.6 | Reinforcement fixing and spacing | Each Structure | CIV Spec - S14.4.8 | Accept/Reject | N/A | QC Checklist, Visual Checks | M/I | SUB | I | — | — | 2.2.6 - Reinforcement fixing and spacing | Frequency - Each Structure | Spec/standard - CIV Spec - S14.4.8 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - M/I | SC - SUB | Consult - I | Hold Points Sign off - — | Remarks - — | Spec/standard - CIV Spec - S12.3.3
2.2.7 | Concrete Cover/Spacer blocks | Each Structure | CIV Spec - S14.4.8 CIV Spec - S14.4.11 Shop Drawings | Min 50mm unless noted on plans | N/A | QC Checklist, Visual Checks | M/I | SUB | I | — | — | 2.2.7 - Concrete Cover/Spacer blocks | Frequency - Each Structure | Spec/standard - CIV Spec - S14.4.8 CIV Spec - S14.4.11 Shop Drawings | Acceptance Criteria - Min 50mm unless noted on plans | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - M/I | SC - SUB | Consult - I | Hold Points Sign off - — | Remarks - — | Acceptance Criteria - Accept/Reject
2.2.8 | Duct Penetrations and Water proofing | Each Duct | Plans and Shop Drawings | Penetration reinforcement installed as shown on the drawings, Hydrotite CJ 0725 3K wrapped around the duct | N/A | Pre-Pour QC Checklist | M/I | SUB | R | — | Refer to drawings, shop drawings and plans | 2.2.8 - Duct Penetrations and Water proofing | Frequency - Each Duct | Spec/standard - Plans and Shop Drawings | Acceptance Criteria - Penetration reinforcement installed as shown on the drawings, Hydrotite CJ 0725 3K wrapped around the duct | Measuring Devices - N/A | Reporting Format - Pre-Pour QC Checklist | HCL - M/I | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - Refer to drawings, shop drawings and plans | Measuring Devices - N/A
2.2.9 | Inspection of Reinforcement steel and Formwork | Each Structure | CIV Spec - S13.4.2 | Accept/Reject Hydrotite CJ 0725 3K installed in construction joints as per drawings | N/A | QC Checklist, Visual Checks | R | SUB | I | Hold point | Back formwork shall not be placed until the Engineer Inspection is completed. | 2.2.9 - Inspection of Reinforcement steel and Formwork | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.2 | Acceptance Criteria - Accept/Reject Hydrotite CJ 0725 3K installed in construction joints as per drawings | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - R | SC - SUB | Consult - I | Hold Points Sign off - Hold point | Remarks - Back formwork shall not be placed until the Engineer Inspection is completed. | Reporting Format - Dockets / Material Data Sheets
2.2.2010 | Concrete Placement | Each Structure | CIV Spec - S13.4.3.1 | Mix Design Docket | N/A | Dockets, Pre- Pour QC Checklist | M | SUB | R | — | Pumping concrete to be done with prior approval. | 2.2.2010 - Concrete Placement | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.3.1 | Acceptance Criteria - Mix Design Docket | Measuring Devices - N/A | Reporting Format - Dockets, Pre- Pour QC Checklist | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - Pumping concrete to be done with prior approval. | HCL - R
2.2.2011 | Concrete Finish | Each Structure | CIV Spec - S13.4.5 | Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 | N/A | QC Checklist, Visual Checks | M | SUB | R | — | — | 2.2.2011 - Concrete Finish | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.5 | Acceptance Criteria - Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | SC - SUB
2.2.2012 | Concrete Testing Slump Test 4x Concrete Cylinder tests | Each Batch | CIV Spec - S13.5.3.2 | 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour | N/A | Test Results, QC Checklist | R/M | SUB | R | — | — | 2.2.2012 - Concrete Testing Slump Test 4x Concrete Cylinder tests | Frequency - Each Batch | Spec/standard - CIV Spec - S13.5.3.2 | Acceptance Criteria - 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour | Measuring Devices - N/A | Reporting Format - Test Results, QC Checklist | HCL - R/M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Consult - R
2.2.2013 | Grout Testing | Each Batch | CIV Spec - S13.5.3.3 | Test at 28 days | N/A | Test Results | R/M | SUB | R | — | — | 2.2.2013 - Grout Testing | Frequency - Each Batch | Spec/standard - CIV Spec - S13.5.3.3 | Acceptance Criteria - Test at 28 days | Measuring Devices - N/A | Reporting Format - Test Results | HCL - R/M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Hold Points Sign off - Hold Point
2.3.1 | Formwork | Each Structure | CIV Spec - S13.4.2 CIV Spec - S13.4.3.2 | Accept/Reject Dimension Accuracy, Alignment and position | GPS/ Total Station/ Rotating Laser | QC Checklist, Visual Checks | M | SUB | I | Hold Point | — | 2.3.1 - Formwork | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.2 CIV Spec - S13.4.3.2 | Acceptance Criteria - Accept/Reject Dimension Accuracy, Alignment and position | Measuring Devices - GPS/ Total Station/ Rotating Laser | Reporting Format - QC Checklist, Visual Checks | HCL - M | SC - SUB | Consult - I | Hold Points Sign off - Hold Point | Remarks - — | Remarks - —
2.3.2 | Concrete Placement | Each Structure | CIV Spec - S13.4.3.2 | 20MPa Concrete | N/A | Dockets, Pre- Pour QA Checklist | M | SUB | R | — | — | 2.3.2 - Concrete Placement | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.3.2 | Acceptance Criteria - 20MPa Concrete | Measuring Devices - N/A | Reporting Format - Dockets, Pre- Pour QA Checklist | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | 1.2.2 - Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G
2.3.3 | Duct Penetrations and Water proofing | Each Duct | Plans and Shop Drawings | As shown on the drawings, Hydrotite CJ 0725 3K wrapped around the pipe | N/A | Pre-Pour QA Checklist | M/I | SUB | R | — | Refer to Shop drawings and Plans | 2.3.3 - Duct Penetrations and Water proofing | Frequency - Each Duct | Spec/standard - Plans and Shop Drawings | Acceptance Criteria - As shown on the drawings, Hydrotite CJ 0725 3K wrapped around the pipe | Measuring Devices - N/A | Reporting Format - Pre-Pour QA Checklist | HCL - M/I | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - Refer to Shop drawings and Plans | Frequency - Each unit
2.3.4 | Curing | Each structure | CIV Spec - S13.4.3.6 | A1/A2 Environment: 3 Days B1/B2 Environment: 7 Days | N/A | QC Checklist | M | SUB | R | — | — | 2.3.4 - Curing | Frequency - Each structure | Spec/standard - CIV Spec - S13.4.3.6 | Acceptance Criteria - A1/A2 Environment: 3 Days B1/B2 Environment: 7 Days | Measuring Devices - N/A | Reporting Format - QC Checklist | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Spec/standard - CIV Spec - S9.3.8
2.3.5 | Grouting of Ducts and Voids | Each Duct and Each Structure | CIV Spec - S13.4.3.7 | All voids, and gaps of duct penetrations | N/A | QC Checklist | M | SUB | I | — | — | 2.3.5 - Grouting of Ducts and Voids | Frequency - Each Duct and Each Structure | Spec/standard - CIV Spec - S13.4.3.7 | Acceptance Criteria - All voids, and gaps of duct penetrations | Measuring Devices - N/A | Reporting Format - QC Checklist | HCL - M | SC - SUB | Consult - I | Hold Points Sign off - — | Remarks - — | Acceptance Criteria - Shop drawings, Dockets/ Visual Checks
2.3.6 | Backfilling GAP65 or AP40 | Each Structure | CIV Spec - S13.4.4 Table 4.3 (Earthworks Section) | CIV > 25 Clegg Test corelated to an NDM | Clegg Hammer | QC Checklist, QVC, Clegg Sheets | M | SUB | R | Witness Point | Engineer to inspect before backfilling | 2.3.6 - Backfilling GAP65 or AP40 | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.4 Table 4.3 (Earthworks Section) | Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM | Measuring Devices - Clegg Hammer | Reporting Format - QC Checklist, QVC, Clegg Sheets | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - Witness Point | Remarks - Engineer to inspect before backfilling | Measuring Devices - N/A
2.3.7 | Concrete Finish | Each Structure | CIV Spec - S13.4.5 | Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 | N/A | QC Checklist, Visual Checks | M | SUB | R | — | — | 2.3.7 - Concrete Finish | Frequency - Each Structure | Spec/standard - CIV Spec - S13.4.5 | Acceptance Criteria - Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5 | Measuring Devices - N/A | Reporting Format - QC Checklist, Visual Checks | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Reporting Format - Dockets / Technical Data Sheets
2.3.8 | Concrete Testing Slump Test 4x Concrete Cylinder tests | Each Batch | CIV Spec - S13.5.3.2 | 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour | N/A | Test Results, QC Checklist | R/M | SUB | R | — | — | 2.3.8 - Concrete Testing Slump Test 4x Concrete Cylinder tests | Frequency - Each Batch | Spec/standard - CIV Spec - S13.5.3.2 | Acceptance Criteria - 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour | Measuring Devices - N/A | Reporting Format - Test Results, QC Checklist | HCL - R/M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | HCL - R
2.3.9 | Grout Testing | Each Batch | CIV Spec - S13.5.3.3 | Test at 28 days | N/A | Test Results | R/M | SUB | R | — | — | 2.3.9 - Grout Testing | Frequency - Each Batch | Spec/standard - CIV Spec - S13.5.3.3 | Acceptance Criteria - Test at 28 days | Measuring Devices - N/A | Reporting Format - Test Results | HCL - R/M | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | SC - SUB
3.1 | As built Works | Each Chamber | CIV Spec - S12.4.10 CIV Spec - S13.4.7 | Position tolerance +/- 20mm Level Tolerance 0mm to +3mm | Surveyor Equipment, Total Station | Certified As- built PDF and DWG file | R | SUB | R | — | — | 3.1 - As built Works | Frequency - Each Chamber | Spec/standard - CIV Spec - S12.4.10 CIV Spec - S13.4.7 | Acceptance Criteria - Position tolerance +/- 20mm Level Tolerance 0mm to +3mm | Measuring Devices - Surveyor Equipment, Total Station | Reporting Format - Certified As- built PDF and DWG file | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - — | Remarks - — | Consult - R
Hold Points Sign off - Hold Point
Remarks - —
1.3.1 - Standard Concrete Mix
Frequency - Each Structure
Spec/standard - CIV Spec - S13.3.1.1
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Design Mix
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks - —
1.4.1 - Reinforcement Bending Schedules
Frequency - Each Structure
Spec/standard - CIV Spec - S14.3.1
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Dockets / Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks - —
1.4.2 - Bending Schedules
Frequency - Each Structure
Spec/standard - CIV Spec - S14.4.6
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Dockets / Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks - —
1.5.1 - Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 3K or Similar
Frequency - Each Pipe and Structure
Spec/standard - DP001-MMD-DRW- UT-B-Z-3100-3117
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Dockets/ Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.1.1 - Survey Setout Chambers/Pits Position and Heights
Frequency - Each Manhole
Spec/standard - N/A
Acceptance Criteria - Survey Setout records and Setout pegs, Plans
Measuring Devices - GPS, Total Station
Reporting Format - Setout CSV file, QC Checklist
HCL - —
SC - —
Consult - —
Hold Points Sign off - —
Remarks - Coordinates mentioned in plans
2.2.1 - Excavation Extents
Frequency - Each element installed
Spec/standard - CIV Spec - S13.4.1 CIV Spec - S4.5.9 (earthworks section)
Acceptance Criteria - N/A
Measuring Devices - Rotating level and GPS
Reporting Format - N/A
HCL - M
SC - —
Consult - —
Hold Points Sign off - —
Remarks - —
2.2.2 - Chambers/Pits subgrade testing
Frequency - Utility Access Chambers: 2 tests at the base of excavation
Spec/standard - CIV Spec - S4.6.2.2 (earthworks section)
Acceptance Criteria - Bearing Capacity as mentioned in the drawings For cohesive soil Shear Vane Test at EGL (0.0m), 0.5m and 1.0m depths For non-cohesive soil scala test to 1m depth. Inspection required by engineer for acceptance
Measuring Devices - Shear Vane Scala Penetrometer
Reporting Format - QC Checklist, Visual Checks, Excel CHAR(AMP) pdf
HCL - M
SC - SUB
Consult - W
Hold Points Sign off - Witness Point
Remarks - If ground failing, Engineer to advise MM will attend all witness points
2.2.3 - 200mm thick 20MPa concrete bedding
Frequency - Each structure
Spec/standard - DP001-MMD-DRW- UT-B-Z-3100-3117
Acceptance Criteria - Accept/Reject, 20MPa Concrete
Measuring Devices - N/A
Reporting Format - QC Checklist, Dockets
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.2.4 - Formwork
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.2
Acceptance Criteria - Accept/Reject Dimension Accuracy, Alignment and position
Measuring Devices - GPS/ Total Station/ Rotating Laser
Reporting Format - QC Checklist, As-Built drawings to confirm the tolerances
HCL - M
SC - SUB
Consult - I
Hold Points Sign off - —
Remarks - Engineer inspection will be done along with the reinforcement
2.2.5 - Reinforcement Laps
Frequency - Each unit
Spec/standard - CIV Spec - S14.4.7 DP001-MMD-DRW- CS-B-Z-3013
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - M/I
SC - SUB
Consult - —
Hold Points Sign off - —
Remarks - Reinforcement Laps to be followed as shown in the plans
2.2.6 - Reinforcement fixing and spacing
Frequency - Each Structure
Spec/standard - CIV Spec - S14.4.8
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - M/I
SC - SUB
Consult - I
Hold Points Sign off - —
Remarks - —
2.2.7 - Concrete Cover/Spacer blocks
Frequency - Each Structure
Spec/standard - CIV Spec - S14.4.8 CIV Spec - S14.4.11 Shop Drawings
Acceptance Criteria - Min 50mm unless noted on plans
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - M/I
SC - SUB
Consult - I
Hold Points Sign off - —
Remarks - —
2.2.8 - Duct Penetrations and Water proofing
Frequency - Each Duct
Spec/standard - Plans and Shop Drawings
Acceptance Criteria - Penetration reinforcement installed as shown on the drawings, Hydrotite CJ 0725 3K wrapped around the duct
Measuring Devices - N/A
Reporting Format - Pre-Pour QC Checklist
HCL - M/I
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - Refer to drawings, shop drawings and plans
2.2.9 - Inspection of Reinforcement steel and Formwork
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.2
Acceptance Criteria - Accept/Reject Hydrotite CJ 0725 3K installed in construction joints as per drawings
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - R
SC - SUB
Consult - I
Hold Points Sign off - Hold point
Remarks - Back formwork shall not be placed until the Engineer Inspection is completed.
2.2.2010 - Concrete Placement
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.3.1
Acceptance Criteria - Mix Design Docket
Measuring Devices - N/A
Reporting Format - Dockets, Pre- Pour QC Checklist
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - Pumping concrete to be done with prior approval.
2.2.2011 - Concrete Finish
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.5
Acceptance Criteria - Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.2.2012 - Concrete Testing Slump Test 4x Concrete Cylinder tests
Frequency - Each Batch
Spec/standard - CIV Spec - S13.5.3.2
Acceptance Criteria - 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour
Measuring Devices - N/A
Reporting Format - Test Results, QC Checklist
HCL - R/M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.2.2013 - Grout Testing
Frequency - Each Batch
Spec/standard - CIV Spec - S13.5.3.3
Acceptance Criteria - Test at 28 days
Measuring Devices - N/A
Reporting Format - Test Results
HCL - R/M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.3.1 - Formwork
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.2 CIV Spec - S13.4.3.2
Acceptance Criteria - Accept/Reject Dimension Accuracy, Alignment and position
Measuring Devices - GPS/ Total Station/ Rotating Laser
Reporting Format - QC Checklist, Visual Checks
HCL - M
SC - SUB
Consult - I
Hold Points Sign off - Hold Point
Remarks - —
2.3.2 - Concrete Placement
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.3.2
Acceptance Criteria - 20MPa Concrete
Measuring Devices - N/A
Reporting Format - Dockets, Pre- Pour QA Checklist
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.3.3 - Duct Penetrations and Water proofing
Frequency - Each Duct
Spec/standard - Plans and Shop Drawings
Acceptance Criteria - As shown on the drawings, Hydrotite CJ 0725 3K wrapped around the pipe
Measuring Devices - N/A
Reporting Format - Pre-Pour QA Checklist
HCL - M/I
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - Refer to Shop drawings and Plans
2.3.4 - Curing
Frequency - Each structure
Spec/standard - CIV Spec - S13.4.3.6
Acceptance Criteria - A1/A2 Environment: 3 Days B1/B2 Environment: 7 Days
Measuring Devices - N/A
Reporting Format - QC Checklist
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.3.5 - Grouting of Ducts and Voids
Frequency - Each Duct and Each Structure
Spec/standard - CIV Spec - S13.4.3.7
Acceptance Criteria - All voids, and gaps of duct penetrations
Measuring Devices - N/A
Reporting Format - QC Checklist
HCL - M
SC - SUB
Consult - I
Hold Points Sign off - —
Remarks - —
2.3.6 - Backfilling GAP65 or AP40
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.4 Table 4.3 (Earthworks Section)
Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM
Measuring Devices - Clegg Hammer
Reporting Format - QC Checklist, QVC, Clegg Sheets
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - Witness Point
Remarks - Engineer to inspect before backfilling
2.3.7 - Concrete Finish
Frequency - Each Structure
Spec/standard - CIV Spec - S13.4.5
Acceptance Criteria - Formed Structure: ○ Below Ground: F1 ○ With Tanking: F4 Unformed Structures: ○ Buried Foundations: U1 ○ Exposed Foundations: U5
Measuring Devices - N/A
Reporting Format - QC Checklist, Visual Checks
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.3.8 - Concrete Testing Slump Test 4x Concrete Cylinder tests
Frequency - Each Batch
Spec/standard - CIV Spec - S13.5.3.2
Acceptance Criteria - 1x Test results at 7 days 3x test results at 28 day Slump test during the concrete pour
Measuring Devices - N/A
Reporting Format - Test Results, QC Checklist
HCL - R/M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
2.3.9 - Grout Testing
Frequency - Each Batch
Spec/standard - CIV Spec - S13.5.3.3
Acceptance Criteria - Test at 28 days
Measuring Devices - N/A
Reporting Format - Test Results
HCL - R/M
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —
3.1 - As built Works
Frequency - Each Chamber
Spec/standard - CIV Spec - S12.4.10 CIV Spec - S13.4.7
Acceptance Criteria - Position tolerance +/- 20mm Level Tolerance 0mm to +3mm
Measuring Devices - Surveyor Equipment, Total Station
Reporting Format - Certified As- built PDF and DWG file
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - —
Remarks - —