## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-009 - Geotechnical Equipment Installation Rev 2 | itp |  |  |  |  | ITP-009 - Geotechnical Equipment Installation Rev 2 | deba3ec5-36d6-489e-888b-4d2fe8dcd74b
section | 1.0 Pre-Construction
checkpoint | 1.01 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to personnel starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.02 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.03 - IFC's specification
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Approved setout locations of instrumentations
label | Method/Description - Designer Confirmation
label | Test frequency - Once for every fill site prior to work commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Written Confirmation from Designeer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - Method Statements Approval
label | Method/Description - Document Review
label | Test frequency - Prior to installation of instrumentation
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Method Statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Calibration of Read Out Equipment
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Contractor - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Calibration Certificate
section | 2.0 Material Compliance
checkpoint | 2.01 - Vibrating Wire Piezometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Vibrating Wire Piezometer calibration
label | Method/Description - Document review of manufacturer's calibration certificate of piezometer
label | Test frequency - Delivery and acceptance of piezometer material; prior to installation
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Extensometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Inclinometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Inclinometer casing material
label | Method/Description - Inspection of Inclinometer Casing Materials
label | Test frequency - After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation.
label | Installer - I
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint | 2.06 - Inclinometer grouting materials
label | Method/Description - Review & approval of approved grout mix
label | Test frequency - Prior to Equipment Installation
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Inclinometer materials
label | Method/Description - Inspection of Inclinometer Measuring Equipment
label | Test frequency - After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation.
label | Installer - I
label | Contractor - W
checkpoint | 2.08 - Rod and Plate Settlement Markers
label | Method/Description - Inspection of Settlement Plate Materials
label | Test frequency - After Delivery and acceptance of Settlement Plate Materials; Prior to Installation.
label | Installer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint | 2.09 - Surface settlement marker material
label | Method/Description - Inspection of Surface Settlement Marker Materials
label | Test frequency - After Delivery and acceptance of Settlement Marker Materials; Prior to Installation.
label | Contractor - W
checkpoint | 2.10 - Surface monitoring marker material
label | Method/Description - Inspection of Surface Monitoring Marker Materials
label | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | Contractor - W
checkpoint | 2.11 - Lateral deformation marker material
label | Method/Description - Inspection of Lateral Deformation Marker Materials
label | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | Contractor - W
checkpoint | 2.12 - Profilometer material
label | Method/Description - Inspection of Profilometer Tubing & Backfill Materials
label | Test frequency - After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation.
label | Installer - I
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
section | 3.1.0 Vibrating Wire Piezometer Installation
checkpoint | 3.1.1 - Piezometer location per construction drawings
label | Method/Description - Inspection of borehole location
label | Test frequency - Before borehole drilling
label | Installer - I
label | Contractor - W
checkpoint | 3.1.2 - Borehole Drilling
label | Method/Description - Inspection of borehole
label | Test frequency - After borehole drilling
label | Installer - I
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint | 3.1.3 - Depth of piezometers
label | Method/Description - Review & approval of depths of piezometer based on the results of the core logging
label | Test frequency - After borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Core materials
label | Method/Description - Inspection of all retaining cores
label | Test frequency - After borehole installation
label | Installer - I
checkpoint | 3.1.5 - Heavy duty connecting cable placement
label | Method/Description - Inspection of completed heavy duty connecting cable placement
label | Test frequency - After placement of heavy duty connecting cable
label | Installer - I
label | Contractor - W
checkpoint | 3.1.6 - Splicing of heavy duty connecting cable
label | Method/Description - Review & approval regarding acceptance of cable splicing
label | Test frequency - Prior to splicing of heavy duty connecting cable
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Readout unit/data logger placement
label | Method/Description - Inspection of completed readout unit/data logger placement
label | Test frequency - After placement of readout unit/data logger
label | Installer - I
label | Contractor - W
checkpoint | 3.1.8 - Ground surface finish of installed piezometer
label | Method/Description - Inspection After completion of the installation process of Piezometer
label | Test frequency - After completion of the installation process of Piezometer
label | Installer - I
label | Contractor - W
checkpoint | 3.1.9 - Ground surface finish of installed connecting cables
label | Method/Description - Inspection After completion of the installation process of Piezometer
label | Test frequency - After completion of the installation process of Piezometer
label | Installer - I
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
section | 3.2.0 Inclinometer Installation
checkpoint | 3.2.1 - Inclinometer location per construction drawings
label | Method/Description - Inspection of Inclinometer Placement
label | Test frequency - After Placement of Inclinometer
label | Installer - I
label | Contractor - W
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Borehole drilling
label | Method/Description - Inspection of Borehole Installation
label | Test frequency - After Borehole drilling
label | Installer - I
label | Contractor - W
checkpoint | 3.2.3 - Depth of inclinometer
label | Method/Description - Review & Approval regarding depth of Inclinometer based on the results of the core logging
label | Test frequency - During Borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Core materials
label | Method/Description - Inspection of all retained cores
label | Test frequency - After Borehole drilling
label | Installer - I
label | Contractor - W
checkpoint | 3.2.5 - Grouting installation
label | Method/Description - Inspection of Grouting Installation
label | Test frequency - After Grouting Installation
label | Installer - I
label | Contractor - W
checkpoint | 3.2.6 - Ground surface finish of installed inclinometer
label | Method/Description - Inspection After completion of the installation process of Inclinometer
label | Test frequency - After completion of the installation process of Inclinometer
label | Installer - I
label | Contractor - W
section | 3.3.0 Profilometer Installation
checkpoint | 3.3.1 - Profilometer tubing levels and location per construction drawings
label | Method/Description - Inspection of profilometer tubing Placement
label | Test frequency - After placement of the profilometer tubing
label | Installer - I
label | Contractor - W
checkpoint | 3.3.2 - Profilometer installation
label | Method/Description - Inspection of profilometer tubing Placement
label | Test frequency - After placement of the profilometer tubing
label | Installer - I
label | Contractor - W
checkpoint | 3.3.3 - Ground surface finish of installed profilometer
label | Method/Description - Inspection after completion of the installation process of profilometer
label | Test frequency - After completion of the installation process of profilometer
label | Installer - I
label | Contractor - W
section | 3.4.0 Rod and Plate Settlement Plate Installation
checkpoint | 3.4.1 - Settlement plate installation
label | Method/Description - Inspection of Settlement Plate Placement
label | Test frequency - Before placement of the Settlement Plate
label | Contractor - W
checkpoint | 3.4.2 - Ground surface finish of installed settlement plate
label | Method/Description - Inspection After completion of the installation process of Settlement Plate
label | Test frequency - After completion of the installation process of Settlement Plate
label | Contractor - W
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.5.0 Surface Settlement Marker Installation
checkpoint | 3.5.1 - Ground surface finish of installed surface settlement marker
label | Method/Description - Inspection After completion of the installation process of Surface Settlement Marker
label | Test frequency - After completion of the installation process of Settlement Marker
label | Contractor - W
section | 3.6.0 Surface Monitoring Marker Installation
checkpoint | 3.6.1 - Ground surface finish of installed surface monitoring marker
label | Method/Description - Inspection After completion of the installation process of Surface Monitoring Marker
label | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | Contractor - W
section | 3.7.0 Lateral Deformation Marker Installation
checkpoint | 3.7.1 - Ground surface finish of installed lateral deformation marker
label | Method/Description - Inspection After completion of the installation process of Lateral Deformation Marker
label | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | Contractor - W
section | 3.8.0 UAV Survey/Face Scan
checkpoint | 3.8.1 - Ground surveys using unmanned aerial vehicles (UAVs)
label | Method/Description - Survey
label | Test frequency - 1. Prior to any ground disturbance;
label | 2. Upon completion of vegetation and topsoil strip;
label | 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys);
label | 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths;
label | 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season;
label | 6. Following removal of surcharge and final embankment profiles have been formed;
label | 7. Immediately prior to pavement construction;
label | 8. At completion of pavement construction;
label | 9. Practical Completion;
label | 10. Every 3 months during Defects Liability Period;
label | 11. End of Defects Liability Period.
label | ○ Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar.
label | Contractor - W
section | 3.9.0 Extensometer Installation
checkpoint | 3.9.1 - Extensometer location per construction drawings
label | Method/Description - Inspection of extensometer Placement
label | Test frequency - After Placement of extensometer
label | Installer - I
label | Contractor - W
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.2 - Borehole Drilling
label | Method/Description - Inspection of Borehole Installation
label | Test frequency - After Borehole drilling
label | Installer - I
label | Contractor - W
checkpoint | 3.9.3 - Extensometer tubes
label | Method/Description - Inspection of Grouting Installation
label | Test frequency - After Grouting Installation
label | Contractor - W
checkpoint | 3.9.4 - Spider magnets
label | Method/Description - Review & Approval regarding depth of based on the results of the core logging
label | Test frequency - During Borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.5 - Reading and recording settlement
label | Method/Description - Inspection after completion of the installation process
label | Test frequency - After completion of the installation process
label | Contractor - W
section | 3.10.0 Reflected Survey Marker Installation
checkpoint | 3.10.1 - Reflective survey target marker installation
label | Method/Description - Inspection of Reflective Survey Target Marker Placement
label | Test frequency - Before placement of the Reflective Survey Target Marker
label | Contractor - W
checkpoint | 3.10.2 - Reflective survey target marker installation completion
label | Method/Description - Inspection After completion of the installation of Reflective Survey Target Marker
label | Test frequency - After completion of the installation process of Reflective Survey Target Market
label | Contractor - W
section | 4.0 Completion of Instrumentation Installation
checkpoint | 4.01 - Vibrating Wire Piezometer completion of placement
label | Method/Description - Document Review submitted through Hold Point
label | Test frequency - After Piezometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Inclinometer Completion of Placement
label | Method/Description - Document Review submitted through Hold Point
label | Test frequency - After Inclinometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Profilometer Completion of Placement
label | Method/Description - Document Review submitted through Hold Point in Aconex
label | Test frequency - After Profilometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Instrument has been received and approved by the Designer
label | Method/Description - Document Review submitted through Hold Point in Aconex
label | Test frequency - After Completion of Instrumentation Installation
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - If an instrument is blocked, obstructed or damaged
label | Method/Description - Inspection and Document Review
label | Test frequency - After completion of the remedials work on the instrument
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Monitoring
checkpoint | 5.01 - Base Line Readings
label | Method/Description - Survey
label | Test frequency - Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT
section | 6.0 Verification Testing
checkpoint | 6.01 - Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground.
label | Method/Description - Document Review
label | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02 - Geonor Shear Vane Test in Borehole
label | Method/Description - Document Review
label | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT