## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-013 - Fill 13 Rev 2 | itp |  |  |  |  | ITP-013 - Fill 13 Rev 2 | df1538e2-6c7e-41a9-a4d1-dfde850c4234
section | 1.0 Pre-Construction
checkpoint | 1.01 - CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.02 - Design
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material
label | Method/Description - NZS 4402:1986, Test 4.1.2
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 2.02 - Atterberg limits test for Structural fill Material
label | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | Test frequency - 1 test per 20,000m3
label | Contractor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
label | Method/Description - NZS 4402:1986, Test 4.1.2
label | Test frequency - 1 test per 20,000m3
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
label | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | Test frequency - 1 test per 20,000m3
label | Contractor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | Method/Description - NZS 4402:1986, Test 4.1.2
label | Test frequency - Source approval 3 no. tests
label | Contractor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 2.06 - Particle size distribution (PSD) Test for GAP 65 material
label | Method/Description - NZS 4402:1986, Test 2.8
label | Test frequency - Source approval 3 no. tests then every 2000m3.
label | Contractor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Permeability test for GAP 65 material
label | Method/Description - ASTM D5084 - 16a
label | Test frequency - Source approval 3 no. tests
label | Contractor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Large Shear Box test for GAP 65 material (Minimum 3 normal stresses)
label | Method/Description - BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear
label | Test frequency - Source approval 3 no. tests
label | Contractor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Direct Shear Strength Test Report
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 During Construction
checkpoint | 3.01 - Set out extents of fill and check against design
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Contractor - W
checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Contractor - W
checkpoint | 3.03 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. Except for Fill 12 and 13 where the fill height is >=5m.
label | Method/Description - Survey/visual
label | Test frequency - Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
label | Method/Description - Inspection
label | Test frequency - Prior to Filling
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.05 - Undercuts
label | Method/Description - Visual inspection
label | Test frequency - 100% of works area
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.06 - When required Undercuts (cut-to-fill operations)
label | Method/Description - Visual inspection
label | Test frequency - Prior to Filling
label | Contractor - H
label | Designer - H
label | Lab - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Sub soil Drainage
label | Method/Description - Inspection
label | Test frequency - During subsoil construction
label | Contractor - I
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint | 3.08 - Monitoring Equipment
label | Method/Description - Survey/ data logging
label | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Drill logs, borehole logs and monitoring instrumentation asbuilts.
checkpoint | 3.09 - Filling operations
label | Method/Description - Visual inspection
label | Test frequency - Daily
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - checksheet
checkpoint | 3.10 - Filling operations
label | Method/Description - Survey/visual
label | Test frequency - Daily
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - checksheet/ Survey Report
checkpoint | 3.11 - insitu fill testing-Plateau Test
label | Method/Description - Plateau Test
label | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
label | ○ Buttress Fill - 1 test per material type per earthworks zone
label | ○ GAP65 - 1 test per material type per structure / location
label | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.12 - insitu fill testing-In situ moisture content and density
label | Method/Description - In situ moisture content and density
label | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
label | ○ Buttress fill - 1 test per 200m length Average
label | ○ GAP65 - 4 tests per lift per structure
label | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
label | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.13 - insitu fill testing- Undrained shear Strength
label | Method/Description - Undrained shear Strength
label | Test frequency - Structural fill - 1 test per layer per 1000m2
label | ○ Buttress Fill - 1 Test per layer per 2000m2
label | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint | 3.14 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
label | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | Test frequency - Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.15 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
label | Method/Description - Benkelman beam or FWD Testing
label | Test frequency - 10m interval in each wheel path at the following levels: 1) 1.0m below Subgrade Formation Level 2) 0.5m below Subgrade Formation Level 3) At Subgrade Formation Level
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.16 - Laboratory Soaked CBR testing for Subgrade Fill
label | Method/Description - Laboratory Soaked CBR
label | Test frequency - Test per 5000m2 at subgrade formation level
label | Contractor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
section | 4.0 Post Construction
checkpoint | 4.01 - Monitoring Data
label | Method/Description - Data Recordings
label | Test frequency - During construction and at end
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
checkpoint | 4.02 - Survey As-builts
label | Method/Description - Survey As-built
label | Test frequency - During construction and at end
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint | 4.03 - As-builts
label | Method/Description - Red Pen Mark up
label | Test frequency - End of Construction
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint | AUTHORITY HOLDPOINT