## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Passive Fire Checks |  |  |  |  | Yes | Passive Fire Checks | 4601e23b-a02c-405b-b38b-4b45f374b6af
checkpoint-status |  |  | checkpoint | Remove brick from required location
checkpoint-status |  |  | checkpoint | Photo shows if timber installed
text | 3b48b53a-a279-556e-82e0-8d07982f87c3 |  | textbox | Timber measurement
checkpoint-status |  |  | checkpoint | Reinstall bricks
checklist-flat |  |  | checklist | QA - Tiling |  |  |  |  | Yes | QA - Tiling | 6dfce74e-f052-40a5-bcb1-c984dab8d585
checkpoint-status |  |  | checkpoint | Screeding of tiled shower bases.
checkpoint-status |  |  | checkpoint | Install and screed/FLC undertile heating where required (supplied, tested and connected by the electrician).
checkpoint-status |  |  | checkpoint | Waterproofing on shower areas as requested
checkpoint-status |  |  | checkpoint | Kitchen splashback
checkpoint-status |  |  | checkpoint | Floor tiling
checkpoint-status |  |  | checkpoint | Wall tiling
checkpoint-status |  |  | checkpoint | Tile skirting
checklist-flat |  |  | checklist | QA - Brickwork |  |  |  |  | Yes | QA - Brickwork (Zone 2) | 9d361cfd-1b72-46eb-a921-91f7715c4cbd
checkpoint-status |  |  | checkpoint | Mortar mixed correctly and colour consistent
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct
checkpoint-status |  |  | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
checkpoint-status |  |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
checkpoint-status |  |  | checkpoint | Façade bricks are installed as per plan
checkpoint-status |  |  | checkpoint | Brick lock installed as required
checkpoint-status |  |  | checkpoint | Flashing tape for shelf angle/ DPC and flashing tape for lintel above window
checklist-flat |  |  | checklist | QA - Blockwork |  |  |  |  | Yes | QA - Blockwork | d686934d-482c-432e-be2b-23990a60d1ae
checkpoint-status |  |  | checkpoint | Mortar mixed correctly and colour consistent
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct
checkpoint-status |  |  | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
checkpoint-status |  |  | checkpoint | Façade bricks are installed as per plan
checkpoint-status |  |  | checkpoint | Brick waterproof on foundation head as required
checklist-flat |  |  | checklist | QA - Brickwork |  |  |  |  | Yes | QA - Brickwork | e6f1edbf-bf84-4198-bc4b-e59413423ae1
checkpoint-status |  |  | checkpoint | Mortar mixed correctly and colour consistent
checkpoint-status |  |  | checkpoint | Mortar joints are in alignment
checkpoint-status |  |  | checkpoint | Cavity width correct
checkpoint-status |  |  | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
checkpoint-status |  |  | checkpoint | Cavity and brick ties free of mortar and debris
checkpoint-status |  |  | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
checkpoint-status |  |  | checkpoint | Brick sill installed and checked – 15 degree consistent fall
checkpoint-status |  |  | checkpoint | Façade bricks are installed as per plan
checkpoint-status |  |  | checkpoint | Brick waterproof on foundation head as required
checklist-sectioned |  |  | checklist | QA - Blocklaying |  |  |  |  | Yes | QA - Blocklaying | eacb5550-d23d-4654-8424-139b41cc3e9f
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Approval from Summerset foreman to begin blocklaying
checkpoint-status |  |  | checkpoint | Set up accurate stringline for entire face
checkpoint-group |  |  | section | Blocking Installation
checkpoint-status |  |  | checkpoint | Check blocks and any broken ones discarded
checkpoint-status |  |  | checkpoint | Temporary bracing has been installed as required
checkpoint-status |  |  | checkpoint | Walls have been properly grouted
checkpoint-status |  |  | checkpoint | Any openings are temporarily braced / Supported
checkpoint-status |  |  | checkpoint | Space is warm, with proper air flow to promote drying of mortar
checkpoint-status |  |  | checkpoint | Temporary lighting has been installed on both sides of wall(to avoid dark spaces)
checkpoint-status |  |  | checkpoint | Any reinforcement including lintels, rebar etc have been installed as per engineering design
checkpoint-status |  |  | checkpoint | Wash holes in tidy conditions
checkpoint-status |  |  | checkpoint | Wall is installed true / plumb and in line with layout
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Block installation completed to specified satandard & finish