## CHK-CIV-RSS Pre-cast panel
ConQA Team Notes:
Document Title: |  | CHK-CIV-CAMMS-RSS Walls-Pre-cast Panlel Installation
ITP Description: |  | RSS Walls - Panel installation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 1/05/2023
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | To be Available for Camms Road Only
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Panels-survey set out-Tolerance | IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1201 MRP-052-C-RFL-DRG-33-CBE-CSW-1202 MRP-052-C-RFL-DRG-33-CBE-CSW-1203 MRP-052-C-RFL-DRG-33-CBE-CSW-1204 VR 682.20 | - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) | Measure | Base course panels | IP | Surveyor/PE | This Checklist
2 | Mark-up panel for construction team | Construction Manual | - Mark number of strips per row on the back of each panel. - Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel | Visual | Each panel | IP | SE | This Checklist
3 | Panel installation | IFC Drawing: Schedules: MRP-052-C-RFL-DRG-33-CBE-CSW-1302 MRP-052-C-RFL-DRG-33-CBE-CSW-1403 MRP-052-C-RFL-DRG-33-CBE-CSW-1503 MRP-052-C-RFL-DRG-33-CBE-CSW-1602 Instructions: MRP-052-C-RFL-DRG-33-CBE-CSW-1803 MRP-052-C-RFL-DRG-33-CBE-CSW-1804 | RSS Panels are to be installed as per IFC Drawings and specified schedule. - Check for correct architectural pattern - Check for Weephole Locations -Check the 19mm nominal gap to be maintained - check the 1 in 40 slope is to be maintained | Visual Measure | Each panel | WP | SE | This Checklist
4 | Panel installation-Abutment interfaces | IFC Drawings MRP-052-C-SME-DRG-32-MPK-CSW-2052 MRP-052-C-RFL-DRG-33-CBE-CSW-1105 | - 20mm nominal gap between panels and Abutment wall is to be mainatined - 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings. - 600mm wide BITAC tape installed | Measure | Where applicable | IP | SE/PE | This Checklist
5 | Filter fabric -Installation | IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1803 | Install Filter Fabric against all vertical and horizontal joints | Visual | Each course of panel installation | IP | SE | This Checklist
6 | Drainage-Strip Drain | IFC Drawings MRP-052-C-SME-DRG-32-MPK-CSW-2053 | Install 150mm wide vertical strip drain "PRODRAIN PD20"-at every vertical joint between panels in RSS wall. Ensure no gap is formed between strip drain and RSS panels | Visual | Each course of panel installation | Ip | SE | This Checklist
7 | Panel installation-Survey reference points | VR 682.21 | To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS | Visual | Each course of panel installation | IP | Surveyor/SE | This Checklist
8 | Traceability of precast units and records | VR 620.09 | Unique ID of precast panel is recorded. - ATTACH: marked-up elevation drawings or installation record with reference to panel ID | Visual | Each panel | Ip | SE/PE | Attached marked-up drawing or installation record
9 | Panels installation-Conformance Survey | IFC Drawings VR 682.06 VR 682.17 VR 682.20 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions - Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall - Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm - Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap - the wall level shall not deviate from the specified level by more than ±20mm - the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height - The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V) Attach: Survey Report | Survey Measure | Each course of panel installation | HP* | Surveyor/PE | Survey Report