## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Manhole / Catchpit Checklist Record Checklist |  |  |  |  | Yes | Manhole / Catchpit Checklist Record Checklist V2 | 071c7572-c055-4bdf-8554-32c5182fa231
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Details input
text | 5f7eaa6b-4ec6-5b49-932b-199e43053cf1 |  | textbox | Location:
text | c39efc70-e39b-5149-a6d4-a829a6f96938 |  | textbox | Manhole / Catchpit Area:
text | 3b5683c9-4eef-572e-9ffe-e0abcf39fef8 |  | textbox | Drawing No:
text | ef3428ca-ab19-5c40-aaf5-0e66ffc952c4 |  | textbox | Rev:
text | 15b6d114-386f-5c2e-a103-afbe14caa1d3 |  | textbox | Work Pack No
text | 23a69227-ddd4-5e02-9c13-8378a14f99c2 |  | textbox | Package Ref. No:
checkpoint-status |  |  | checkpoint | Set-Out
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Prepare & Level Base Bedding
checkpoint-status |  |  | checkpoint | Confined Space Permit Required
checkpoint-status |  |  | checkpoint | Installation of Precast Base Unit on Bedding
checkpoint-status |  |  | checkpoint | Installation of Precast Risers to Lid Level
checkpoint-status |  |  | checkpoint | Installation of Manhole / Catchpit Furniture, Steps / Clamps
checkpoint-status |  |  | checkpoint | Haunching / Make Good Base. Joints sealed
checkpoint-status |  |  | checkpoint | Installation of Precast Lid
checkpoint-status |  |  | checkpoint | Backfill Around Manhole / Catchpit
checkpoint-status |  |  | checkpoint | Installation of Cast Iron Frame and Cover Lid Level Ð Set with Contour
checkpoint-status |  |  | checkpoint | Final Inspection
checklist-flat |  |  | checklist | ITP - Pavement Detail 'I' | itp |  |  |  | Yes | ITP - Pavement Detail 'I' | 082f66a3-2a8b-4330-a3a9-bb101376016b
checkpoint-status |  |  | checkpoint | 1 - Existing Pavement
label | d889d7e9-c41b-41b3-b6f7-275307155d0c |  | note | Activity Task: Construction
label | 7609759b-1d6b-47c3-b355-6a1ac119a5c1 |  | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
label | dac0b54c-c1e7-4c0b-84e5-57818f9243bc |  | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
label | 688635c1-1335-4222-aadb-ca2defd10acc |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | 90496242-3397-4462-a6cc-cc523ee8b65f |  | note | Activity Task: Construction
label | 3c024914-90dc-4df1-beb1-7282f17bb7bd |  | note | Acceptance Criteria: Subgrade levels captured with GPS
label | c1357111-1213-4a96-873a-f2dabcc7d7c3 |  | note | Certifying Documents and Frequency: Asbuilt report
label | 98696cb7-f21d-4ef5-b20e-637be892d622 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 3 - Subgrade/Dig outs
label | dffd43ab-db82-41ad-9978-2d68a429eadd |  | note | Activity Task: Construction/Test
label | 58fb3ced-4ac2-408a-b77b-94775a226625 |  | note | Acceptance Criteria: Check insitu subbase Minimum 150mm over a Subgrade of Min CBR 9. If not undercut to 200mm and use GAP65 as imported subgrade.
label | 8e1c4f3f-e4ce-4610-b185-39b136c598d7 |  | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala Test sheet
label | 5898380d-3dd0-4708-932e-3b53468c900f |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Proof Roll
label | e5a7c038-8072-45b0-9a73-51685f2730aa |  | note | Activity Task: Construction
label | 7a24a66c-0e71-4868-85e9-f5a27f6ec088 |  | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
label | a336a263-d703-4976-bc36-6c687f934ad2 |  | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
checkpoint-status |  |  | checkpoint | 5 - Subsoil
label | c76c3c1d-990f-4cdc-aa26-cf4d75827b2c |  | note | Activity Task: Material supply
label | 63a244bd-406a-41da-8c85-52d48c36052d |  | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE.
label | 1f9d370e-6f82-4605-8b47-c5508f58079a |  | note | Certifying Documents and Frequency: Compliance certification from supplier. Supplier to provide testing data for filter cloth material
checkpoint-status |  |  | checkpoint | 6 - Subsoil
label | f26fcc90-6c19-4a5b-9533-de4ad0e2b628 |  | note | Acceptance Criteria: Construction
label | 05930862-2a09-4626-87f7-3ee5d0be2042 |  | note | Certifying Documents and Frequency: Photos, Asbuilts and Checklist
checkpoint-status |  |  | checkpoint | 7 - Sub-base aggregate
label | f6bc2707-4cd8-42e3-bb19-c704a55b76c4 |  | note | Activity Task: Material Supply
label | 6b4e0fe7-0f16-46b9-9b5d-c943eb5925d9 |  | note | Acceptance Criteria: Gap 65. Certifying Documentation: Material supply documentation.
checkpoint-status |  |  | checkpoint | 8 - Sub-base aggregate
label | 78ec0b33-dc47-496d-afb7-e1c080d9ef46 |  | note | Activity Task: Test/ Material Supply
label | bf9135cf-b6d3-4b0c-b8e7-e8f3a1e6c212 |  | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
label | 6bf05959-c01c-442e-905d-616578a0f8ad |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 98d2d621-995e-4ce5-a3f9-ff351abf4c2f |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 9 - Sub-base aggregate
label | f7031270-4588-4e06-bf4d-1a2c4f694986 |  | note | Activity Task: Test/ Material Supply
label | 692266c7-db6f-4ef5-b05b-d7e4afeb91c1 |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6 Sand equivalent to meet specification
label | 5e2f398e-e9cb-4a9d-b8a6-71542074994a |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | dd921768-9cbf-4604-84eb-65500678e1a5 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 10 - Sub-base aggregate
label | 470b5e6b-7a97-4ef9-a363-d58c4ea45a24 |  | note | Activity Task: Test/ Material Supply
label | 0850ea2f-f7fa-47f9-96f2-37ccf62e6793 |  | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
label | 66be3980-fb13-43db-8a6c-142adc571f03 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 1552de68-b80c-4acb-951d-36310390c5c3 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 11 - Sub-base aggregate
label | 27f5ef09-96f2-4272-80dc-122cc9317c72 |  | note | Activity Task: Test/ Material Supply
label | f028295f-a65f-42b9-9861-d2a568f260f5 |  | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
label | 7e6440c8-619d-4645-99ca-1a6ea5b472a5 |  | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
label | 0cb444b9-f985-4ac9-805d-cc087757ee7a |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 12 - Sub-base aggregate
label | c1e87c5b-8ffe-4649-b610-9c2c0a8c9e12 |  | note | Activity Task: Construction/Test
label | f4b59066-6eda-4d19-a55a-4fe6dbfd1a99 |  | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
label | 29b0f8ae-59fd-4089-8c99-5989e4b3c5dc |  | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
label | c9f8fbc9-d3db-4fbe-95b0-05999539b97a |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 13 - Completed Sub-base prior to placement of Basecourse
label | 475bc144-f90e-4987-84cf-3ae381f47496 |  | note | Activity Task: Test/ Material Supply
label | 5a0722c0-3f9e-40b9-9dea-5b0a30de0a76 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | c3a219df-85b0-48ea-9645-f1ff6aacd9cc |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
label | 7ff67184-fa5e-4f73-9749-3fb2c8d23923 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 14 - Completed Sub-base prior to placement of Basecourse
label | 5f1a02b9-8476-4364-ace7-3dc0099d7229 |  | note | Activity Task: Construction
label | e403c093-74b4-4c12-b815-a7910aff059d |  | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | d207a74c-54d6-460e-803e-d6a09037499c |  | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
label | 2e87a06a-94dd-4955-b764-39c39ff1199f |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 15 - Completed Sub-base prior to placement of Basecourse
label | 25d17920-38f7-43fb-9424-3bcd1d1e5c49 |  | note | Activity Task: Construction
label | 7ce48933-c327-406c-b0ca-056a8e69684e |  | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification
label | 6300a303-e8a4-4141-b60c-68adaffb9101 |  | note | Certifying Documents and Frequency: Visual inspection by Engineer. Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | 79a06dbb-61b5-4af6-ae43-c2e2542fe28d |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 16 - Basecourse
label | b235b50e-8b6a-4c4d-b33b-569766f73939 |  | note | Activity Task: Material supply
label | e83eb411-1731-49b5-b5e6-fbeb2c292889 |  | note | Acceptance Criteria: Unless otherwise specified all basecourse operations shall be in accordance with TNZ B/2, M/4 and the drawings and specifications.
label | 7fc35378-195a-4f4d-883f-4c0ebf507e9e |  | note | Certifying Documents and Frequency: Compliance certification to be supplied from sub-contractor
checkpoint-status |  |  | checkpoint | 17 - Basecourse Cement Supply
label | 358198c0-8fa9-43a5-8220-09c8c8c8106d |  | note | Activity Task: Material supply
label | 7b69ea1f-3767-47af-9725-22c6ba861c10 |  | note | Acceptance Criteria: Application rate to be 2% as specified.
label | 95436112-da1b-4ebb-9b57-bc4dc85cc04a |  | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation
checkpoint-status |  |  | checkpoint | 18 - Basecourse
label | f60eec08-b2ae-47e2-83a7-5b6beedf58dc |  | note | Activity Task: Construction
label | 03ac271d-6515-4fe0-b712-12b0528a1037 |  | note | Acceptance Criteria: Basecourse to be 150mm Cement modified M/4 AP40
label | 0dcf51c8-31d1-470f-9e05-8a5885b394db |  | note | Certifying Documents and Frequency: Photos
label | 3b8b9580-f4bf-420c-890c-2f6fd225cde0 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 19 - Basecourse
label | 431ccc80-9cbe-4c82-9900-732c3fdff31d |  | note | Activity Task: Testing
label | 79ab7c50-37e9-41a6-a8b9-76b3da38d3d0 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 8d574f99-4e35-496e-96b7-8f600175c9df |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
checkpoint-status |  |  | checkpoint | 20 - Basecourse
label | 962bbb93-9605-4d7c-ac63-8ab59e2c581d |  | note | Activity Task: Straight Edge Checks
label | 5831febc-aa4d-49c5-b8eb-dba50cf3f17c |  | note | Acceptance Criteria: No point on the surface shall vary more than 10 mm from a 3m straight edge. No area of the completed surface shall pond water
label | e10aa4bf-1121-4936-8294-efe5686181c5 |  | note | Certifying Documents and Frequency: Straight edge checks on surface shape at randomly staggered transverse positions at 20 m intervals throughout.
checkpoint-status |  |  | checkpoint | 21 - Basecourse
label | ee2b4666-1429-447d-ba38-3d23b5fe98de |  | note | Activity Task: String Line checks
label | 75559c76-b79c-422c-954b-08e734ab7066 |  | note | Acceptance Criteria: Surface shape matches design and minimum pavement depth provided.
label | 50a49829-e58e-4444-9340-15dd2fa21513 |  | note | Certifying Documents and Frequency: Stringing records, 3 points minimum per cross section.
checkpoint-status |  |  | checkpoint | 22 - Basecourse
label | c5f58094-00ad-4079-a3c2-8520128ea409 |  | note | Activity Task: Visual Inspection
label | b7deb871-3c34-417f-a95d-0e585b54de44 |  | note | Acceptance Criteria: Surface to be as specified
label | 3f88173f-2f50-4bef-92b9-feea4dad7a9d |  | note | Certifying Documents and Frequency: Visual inspection by Engineer
label | 0431ef91-941b-4627-938c-6e4adc823b7e |  | note | Activity Task: Construction
label | 5b83c022-c057-4a03-94c4-1d737c8f0c78 |  | note | Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3
label | 6e69ae04-d925-4c06-963e-84ff86b15361 |  | note | Certifying Documents and Frequency: Two samples per distributor load On Request Refer to Subcontractors QA in Separate ITP
label | 16dc581f-fe66-47fc-9ba2-4ac171c2f353 |  | note | Project Manager or Delegated Person: W
checkpoint-status |  |  | checkpoint | 23 - Structural Asphalt
label | e399dff8-288a-4dc3-a4ba-7befc6512774 |  | note | Activity Task: Material Supply
label | ea50b13b-23aa-45ea-9ade-bc32605963ea |  | note | Acceptance Criteria: As detailed in AAPA National Asphalt specification and RNZ/TNZ supplement to AAPA National Asphalt Specification
label | edc5353e-846c-46d4-beb8-a0293a33606d |  | note | Certifying Documents and Frequency: As detailed in AAPA National Asphalt specification and RNZ/TNZ supplement to AAPA National Asphalt Specification Refer to Subcontractors QA in Separate ITP
label | 06fbdf1b-30eb-45b5-a0a1-8906ea96e570 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 24 - Structural Asphalt
label | d7c60025-4e75-4e22-b705-69d5336d7aa5 |  | note | Activity Task: Construction
label | dce17826-6318-4817-a5f5-cfc129676176 |  | note | Acceptance Criteria: Method of determining density location tests
label | 9a71a1ac-8c6a-4fd2-9bb1-d00e17aa3062 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
label | 714b927e-f683-45f0-a115-e4d6dc0fb4f6 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 25 - Asphaltic Concrete
label | 4e1e0b95-e573-409a-aa5e-c1ed0da8b082 |  | note | Activity Task: Material supply
label | 0ab766f7-450b-4596-9bad-c7bff8694bc4 |  | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
label | 35410349-eb5e-4e86-861d-551a57426c33 |  | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification Refer to Subcontractors QA in Separate ITP
label | 243967b5-555a-46ff-8041-73cae16b535f |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 26 - Asphaltic Concrete
label | 47fd51f0-db34-4bbb-8a34-a06e77047979 |  | note | Activity Task: Construction
label | d28c8305-8f9f-49a8-a97e-c814c936b324 |  | note | Acceptance Criteria: Grade 5 Membrane seal and 50mm AC 14
label | 49a998e7-301f-4691-b03a-db474d9b77c4 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
label | 3783ccf5-5aed-4b58-8c78-3af3455f8066 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 27 - As -Builts
label | cd713f20-71c1-4232-b0bd-4d08c2b815e3 |  | note | Activity Task: As -Builts
label | 6bdac20e-c43e-403e-a704-158cf29291a2 |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
label | 9d8cc96f-f574-4de0-a1dc-c0c66cb99738 |  | note | 1. The subgrade under new pavement areas;
label | 5234e9aa-c562-4625-a1b9-cdd03f4975a6 |  | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | 5c41652e-27b1-4a1e-a0c7-0c5e11b15e6c |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
label | e720ab44-d336-4f93-bc3a-e103c5dfbb7f |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checklist-flat |  |  | checklist | ITP - Pavement Detail 'K' | itp |  |  |  | Yes | ITP - Pavement Detail 'K' | 2692d050-fdf9-498f-8b58-1b3c53913ff7
checkpoint-status |  |  | checkpoint | 1 - Existing Pavement
label | a642cec7-51db-4e18-be5d-e3e7fb202ba4 |  | note | Activity Task: Construction
label | 9162e37a-90c2-4843-85e5-23e4dd5d930d |  | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
label | 14863fa0-ef0e-4f5b-85a6-455784089c52 |  | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
label | f24eb60a-a5cc-43e4-a2b5-36e3fb2e2b16 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | 7370bd47-16af-4a56-9c6b-0abd6874bc42 |  | note | Activity Task: Construction
label | 4a39e5c2-5375-4855-9ccd-0c9f48434408 |  | note | Acceptance Criteria: Subgrade levels captured with GPS
label | b65aa318-4121-4567-9bdb-073a41e2bc2f |  | note | Certifying Documents and Frequency: Asbuilt report
label | f2dd2499-920c-4c63-a5ff-87829a50e014 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 3 - Subgrade/Dig outs
label | 9d70989c-c7bf-48e3-a885-b90329589f1b |  | note | Activity Task: Construction/Test
label | 25605a3f-22dc-4ee7-814e-2795b2196f9c |  | note | Acceptance Criteria: Check insitu subgrade of Min CBR 5. If not undercut to 200mm and use GAP65 as imported subgrade.
label | 6fca623e-5e65-45a7-8b01-adf9fc104991 |  | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala test sheet
label | cf46c93e-404c-42a4-94e2-2cdfb57f4090 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Proof Roll
label | a8ef9dc4-bcbe-408d-89ae-5ddd0c29d109 |  | note | Activity Task: Construction
label | 23ff07a7-5fa3-4e9d-83ae-2ea05a4bfb48 |  | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
label | 569f387c-db5c-45c2-b856-fa663a9704d8 |  | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
checkpoint-status |  |  | checkpoint | 5 - Subsoils
label | 1f5228a5-863f-4bc7-8d68-153b699bcbe9 |  | note | Activity Task: Material Supply
label | 4ff07381-8754-4e8d-b2c4-eba91039e572 |  | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted110mm diameter corrugated HDPE
label | 05da8440-981a-41a0-b35a-66509f75e787 |  | note | Certifying Documents and Frequency: Compliance certification from supplier. Supplier to provide testing data for filter cloth material
checkpoint-status |  |  | checkpoint | 6 - Subsoils
label | 10215af4-51a2-4aed-a176-084e708e7219 |  | note | Activity Task: Construction
label | e66392c6-312f-4d56-b6d6-988733148b05 |  | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe. Subsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
label | 8a4efc30-a463-43ad-81af-82e915ef2656 |  | note | Certifying Documents and Frequency: Photos, Asbuilts and Checklist
checkpoint-status |  |  | checkpoint | 7 - Sub-base aggregate
label | 07c72bc0-0e45-4ebd-91a7-5329ec186771 |  | note | Activity Task: Material Supply
label | 486d7725-61a5-4fe3-9dea-8e4f9d94aecf |  | note | Acceptance Criteria: Gap 65. Certifying Documents: Material supply documentation
checkpoint-status |  |  | checkpoint | 8 - Sub-base aggregate
label | 77f06b59-215f-495e-9ef9-c2d65ccbdc3b |  | note | Activity Task: Test/ Material Supply
label | fce30e4a-2e31-40e1-aeac-61a26400e790 |  | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
label | d6564059-387e-4d31-b1dc-0ff7294375c4 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 222e7ae7-5688-46de-8b84-93ede6194965 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 9 - Sub-base aggregate
label | d7d4c299-65f1-4a7e-84ba-4aa378df133c |  | note | Activity Task: Test/ Material Supply
label | ab264cfa-ce83-4dfe-b393-e26f1b303ab5 |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6 Sand equivalent to meet specification
label | 517f5091-ea2c-474b-9d36-d0ad3e08e355 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 80b62380-a6c5-46e4-ad7a-857a6ceb3741 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 10 - Sub-base aggregate
label | a6d2d5b3-72ca-428e-85db-fbf8cb6368e8 |  | note | Activity Task: Test/ Material Supply
label | c53ae613-c9bb-4a2e-b7a2-d74460bf7391 |  | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
label | 85a27385-a16f-4de9-80a7-9cf0b8670f60 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 6b3fbded-40e6-4367-8b6d-76e777ca8c63 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 11 - Sub-base aggregate
label | 06ce7d2e-3775-425b-b812-8f0d222b7302 |  | note | Activity Task: Test/ Material Supply
label | 79e6f2d6-7aad-41aa-a96d-e4efecf88bf3 |  | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
label | c07b4977-1bd5-4f42-adb7-a0479fd95745 |  | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
label | 09bde656-4706-487d-84a5-88ef9e099993 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 12 - Sub-base aggregate
label | 87d2d7b0-e52e-4408-8629-ad621e498796 |  | note | Activity Task: Construction/Test
label | d927bc06-062c-4ea3-91fb-f0ac2dc24715 |  | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
label | 8688eb87-f5e6-4773-8528-c7c62e448497 |  | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
label | f6483b07-ce81-427f-81b9-6b16a5450fdc |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 13 - Lower Sub-base
label | 3072c6cc-a50a-4fd5-9f2a-f572ad78bcd6 |  | note | Activity Task: Construction
label | 93c0c168-f86a-4bad-b275-ddb0bc0ec3bc |  | note | Acceptance Criteria: Lower Subbase to be 150mm layer GAP 65
label | 7c81d1eb-179a-42dd-bd0a-f4d9b1624418 |  | note | Certifying Documents and Frequency: Photos
label | 7511d491-3dce-48ba-a9fd-ec36d8c9ab72 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 14 - Upper Sub-base
label | 120713c3-b15a-4ad1-a7a2-dbd6bb24bbad |  | note | Activity Task: Construction
label | 197f3fea-c163-4646-939a-7e29732d627d |  | note | Acceptance Criteria: Upper Subbase to be 150mm layer GAP 65
label | 0fbe2893-91cb-48e3-8da1-0305090d6c60 |  | note | Certifying Documents and Frequency: Photos
label | 91d57e5f-5ea3-4412-922c-18cb49c9202e |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 15 - Completed Sub-base prior to placement of Basecourse
label | 26369fba-d97a-484a-8262-e90481227ca7 |  | note | Activity Task: Test/ Material Supply
label | 0707ea26-79c1-447b-a745-65c057981fda |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 3d00aa56-fe13-4b44-996f-aea69f8ede01 |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
label | f71ddc79-a672-40da-852b-8627b57d9440 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 16 - Completed Sub-base prior to placement of Basecourse
label | 83e59a32-35b4-436b-a391-57436e495f3f |  | note | Activity Task: Construction
label | 1d36fe4d-3ab0-4e9c-8968-b5ae2cd07f6d |  | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | 97e4a221-7a99-4644-a3f1-a4b34e8c5129 |  | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
label | 34dd1c0c-85a6-4520-a999-aa7cee423f48 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 17 - Completed Sub-base prior to placement of Basecourse
label | 0962d19f-03aa-4ac5-95a7-4dfe5a2c9c2d |  | note | Activity Task: Construction
label | 5881010f-c717-41ea-be75-87656376bd3d |  | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification
label | 305d70e6-4b9b-4d5f-a274-9b2703bbf196 |  | note | Certifying Documents and Frequency: Visual inspection by: Engineer, Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | 6931a18d-3f21-49d3-8ede-b17af23f8591 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 18 - Basecourse
label | 2b161ef2-ec2b-4bcb-b42b-403f6a728706 |  | note | Activity Task: Material Supply
label | 8e1de0cd-9cdd-4830-a3ca-e44dc6cf2eab |  | note | Acceptance Criteria: Unless otherwise specified all basecourse operations shall be in accordance with TNZ B/2, M/4 and the drawings and specifications.
label | 9a59dc7e-91ba-4058-8197-db03e716bd83 |  | note | Certifying Documents and Frequency: Compliance certification to be supplied from sub-contractor
label | 331a0e40-92c1-4fa7-a9da-442b23af0bf9 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 19 - Basecourse Cement Supply
label | 3d5db169-b08a-436c-ba4b-919ec570fc7f |  | note | Activity Task: Material Supply
label | 0ca2d4be-149b-481c-8ca6-c7c9f4a2d9a7 |  | note | Acceptance Criteria: Application rate to be 2% as specified.
label | d10cd50b-06ef-45f7-98e4-041c4aebba3c |  | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation
checkpoint-status |  |  | checkpoint | 20 - Basecourse
label | b976500c-ce99-4799-bb4c-d3778a1a0fc1 |  | note | Activity Task: Construction
label | 7eb8b156-b5d0-4bb7-ac20-7b1f92feb9e4 |  | note | Acceptance Criteria: Basecourse to be 160mm Cement modified M/4 AP40
label | d6611f14-fb62-4d27-b309-5c01c0a71eeb |  | note | Certifying Documents and Frequency: Photos
checkpoint-status |  |  | checkpoint | 21 - Basecourse
label | 493847db-4ecd-4fc8-8a6f-89a8146493db |  | note | Activity Task: Construction
label | cf94049f-cf21-4785-8f73-bf101d445bc7 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | ff4194e0-31db-4eba-8b89-018391d439db |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
label | 89842056-2926-4027-8b10-2c7521899c18 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 22 - Basecourse
label | a547c693-9783-4986-9e97-ddc9bf8e8986 |  | note | Activity Task: Straight Edge Checks
label | ca141a27-3f1d-4b33-85f1-ba3acc19cfd9 |  | note | Acceptance Criteria: No point on the surface shall vary more than 10 mm from a 3m straight edge. No area of the completed surface shall pond water.
label | 3d5490dd-6f72-4282-9c5d-eef5e4a4bf7a |  | note | Certifying Documents and Frequency: Straight edge checks on surface shape at randomly staggered transverse positions at 20 m intervals throughout.
checkpoint-status |  |  | checkpoint | 23 - Basecourse
label | fd1c36b9-3538-4881-be8a-4bc75791d9ec |  | note | Activity Task: String Line checks
label | 348df899-687a-46b4-a2b3-cea0a187f083 |  | note | Acceptance Criteria: Surface shape matches design and minimum pavement depth provided.
label | f09263cc-8238-47a4-8184-b5fff7fa50b4 |  | note | Certifying Documents and Frequency: Stringing records, 3 points minimum per cross section
checkpoint-status |  |  | checkpoint | 24 - Basecourse
label | 081b8a7b-e641-48f6-8d71-f5abc136ba77 |  | note | Activity Task: Visual Inspection
label | 83ad979e-db30-4d44-9fe8-6e3da49fdf62 |  | note | Acceptance Criteria: Surface to be as specified
label | 2de8adec-05f0-44ad-976c-c6cf3260757b |  | note | Certifying Documents and Frequency: Visual inspection by Engineer
checkpoint-status |  |  | checkpoint | 25 - Tack Coat
label | 3e0be985-5f32-4c14-9657-79f109dd2c3e |  | note | Activity Task: Construction
label | ed7443d5-fc91-4f7c-979b-a7aefb8dc798 |  | note | Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3
label | c78cec85-2275-40bf-af72-cddd1966dd4f |  | note | Certifying Documents and Frequency: Two samples per distributor load On Request
label | 976b3f38-7ff7-45fb-ba12-67a61e8aad3a |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 26 - Asphaltic Concrete
label | 43dc1f83-5629-40e9-b9cc-954a2f83babe |  | note | Activity Task: Material supply
label | 61f9a232-451c-496a-b5ef-8d2912fc80d1 |  | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
label | 4b4b2154-1d87-43da-a9d0-f448f91e0fed |  | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification Refer to Subcontractors QA in Separate ITP
checkpoint-status |  |  | checkpoint | 27 - Asphaltic Concrete
label | 86bd5ca5-3370-4f72-86a1-afb35eb9d04d |  | note | Activity Task: Construction
label | 8d3d7626-cc58-47d9-9e65-53b8d2700317 |  | note | Acceptance Criteria: Grade 5 Membrane seal and 50mm AC14 Method of determining density location tests
label | 164f3e26-7d65-4f92-b3f4-1b740a7d09ac |  | note | Certifying Documents and Frequency: Prior to placement of Asphaltic Concrete Refer to Subcontractors QA in Separate ITP
checkpoint-status |  |  | checkpoint | 28 - As -Builts
label | 2f0efd73-beb0-42be-b215-aae810d77321 |  | note | Activity Task: As -Builts
label | c13ddcc5-5185-4d45-b78c-557a84e55d39 |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
label | 55e29c9a-b900-4517-9b3e-c5f8986ffdff |  | note | 1. The subgrade under new pavement areas;
label | 21d8bb8a-cf6d-4ecb-bbf4-1d5867be803d |  | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | 907becce-ccc2-42ac-bcc5-51437c9b5d83 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
checklist-flat |  |  | checklist | ITP - Kerb and Channel | itp |  |  |  | Yes | ITP - Kerb and Channel | 274a6d45-85d2-4e5c-82ee-bdef71ca0812
checkpoint-status |  |  | checkpoint | 1 - Set out
label | 88d099f4-7dac-564a-b0b7-d23fc0c74bd5 |  | note | Acceptance Criteria: As per IFC drawings, Horizontal +/- 10mm, Vertical +/- 10mm
label | d85936f1-5990-56aa-acef-2baed7af6a52 |  | note | Frequency: All Kerb and Channel and Dish Channel
label | c176c030-8159-5cd3-b4df-375b03455747 |  | note | Supervisor, Foreman or Subcontractor: Check sheet, No ponding of water
label | 668c15cb-fb5e-5a8e-b67d-2f3d1dd4612e |  | note | Project Manager or Delegated Person:
label | ad6f75b0-0ebf-507b-b693-76e82ab861f6 |  | note | Engineer’s Representative: H
checkpoint-status |  |  | checkpoint | 2 - Bedding
label | 203c4cf9-699d-5158-b158-96e73c5008f2 |  | note | Activity Task: Subbase
label | 5797aab6-5800-51ab-b5d7-2a00c39021e4 |  | note | Acceptance Criteria: Clegg CIV 20 or NDM 95% MDD
label | 42b293cb-5c6b-590c-b11d-fdbe5b2b938a |  | note | Frequency: All Kerb and Channel and Dish Channel
label | a7b16535-81fc-54cd-b075-415dc3b1ae7e |  | note | Supervisor, Foreman or Subcontractor: Clegg sheet
checkpoint-status |  |  | checkpoint | 3 - General
label | 2a21c5c1-47a0-58b0-bd66-d951ae6bf7b3 |  | note | Activity Task: Concrete Strength
label | c14de149-e567-58f3-a8c0-031dee892df9 |  | note | Acceptance Criteria: Concrete to meet required specification for specific kerb detail
label | 268e2589-60c2-5723-a504-f7f59f04b73a |  | note | Frequency: All Kerb and Channel and Dish Channel
label | e6dd9d94-1d36-534a-823c-fde9179eeecb |  | note | Supervisor, Foreman or Subcontractor: Supplier documentation
checkpoint-status |  |  | checkpoint | 3.1 - General
label | 7cc6d9a5-5cd9-5e00-bd7d-4b2114adf8e9 |  | note | Activity Task: Tapered ends
label | 27660ec0-43a3-52b9-9f3b-bd960d1db203 |  | note | Acceptance Criteria: Evenly tapered from full height to channel level
label | 3fde7e67-98b6-557f-906f-8384cbaf207f |  | note | Frequency: All Kerb and Channel and Dish Channel
label | 665db9b4-f539-5a5f-84c6-5dc4e8df5619 |  | note | Supervisor, Foreman or Subcontractor: Taper over 1m, maintaining the same profile
checkpoint-status |  |  | checkpoint | 3.2 - General
label | 4a192b46-c6bf-50f9-a290-41ccb98e9ea1 |  | note | Activity Task: Construction
label | fe791941-5e99-502e-9369-b77ed38f2124 |  | note | Acceptance Criteria: Cannot commence until sub base layer completed and checked by the engineer
label | 17f99283-629e-568d-9d73-7c2fb45b024d |  | note | Frequency: All Kerb and Channel and Dish Channel
label | 04219225-44df-5f11-bc85-a185542943d6 |  | note | Supervisor, Foreman or Subcontractor: Sign off by Engineer
checkpoint-status |  |  | checkpoint | 4 - As -Builts
label | f7fd6391-7d38-53b0-b40b-0a93ec95bad8 |  | note | Activity Task: As -Builts
label | 81af03ee-cebb-5d0f-a11e-450fbbb58b0e |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project.
label | 462854bf-7a2c-5590-aa6a-2a9b53b6ab08 |  | note | Frequency: Every Kerb or Dish Channel
label | 017cce30-7cd8-597c-83db-08c2669372bb |  | note | Supervisor, Foreman or Subcontractor:
checklist-flat |  |  | checklist | Manhole / Catchpit Checklist Record | itp |  |  |  | Yes | ITP - Manhole / Catchpit Checklist Record | 34fe4401-fca7-499a-98d4-012bb3b72243
checkpoint-status |  |  | checkpoint | Set-Out
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Prepare & Level Base Bedding
checkpoint-status |  |  | checkpoint | Confined Space Permit Required
checkpoint-status |  |  | checkpoint | Installation of Precast Base Unit on Bedding
checkpoint-status |  |  | checkpoint | Installation of Precast Risers to Lid Level
checkpoint-status |  |  | checkpoint | Installation of Manhole / Catchpit Furniture, Steps / Clamps
checkpoint-status |  |  | checkpoint | Haunching / Make Good Base. Joints sealed
checkpoint-status |  |  | checkpoint | Installation of Precast Lid
checkpoint-status |  |  | checkpoint | Backfill Around Manhole / Catchpit
checkpoint-status |  |  | checkpoint | Installation of Cast Iron Frame and Cover Lid Level – Set with Contour
checkpoint-status |  |  | checkpoint | Final Inspection
checklist-flat |  |  | checklist | ITP 01 - SUPPLY AND PLACE 180MM AC20 |  |  |  |  | Yes | ITP 01 - SUPPLY AND PLACE 180MM AC20 | 587fb13c-e9d1-4de4-99ab-9f9ee4c43eb5
checkpoint-status |  |  | checkpoint | Area clear of deleterious materials
label | 51df61f3-f854-58ea-b263-b1193b5a0560 |  | note | Specification / Procedure - Visual inspection
label | 37d2a580-6750-5830-96e9-26f3bd016106 |  | note | Record - Visual inspect all areas
label | b7ba5b2f-5558-5129-815a-ca2c6ea6e372 |  | note | Control - Supervisor - Holdpoint
label | 66e9aa68-7c90-500f-8f42-3bf59630e079 |  | note | Control - Head Contractor - Holdpoint
label | a1254838-9e6c-5915-bb8f-4edcedf1e735 |  | note | Control - Eng.- Verify
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Apply tack coat
label | 75ae2511-1913-503b-8433-31b7af6ff59b |  | note | Specification / Procedure - Max 0.33L/m2 net binder
label | c9fa3612-8a8c-5003-b384-0d8bdfc01b4f |  | note | Record - Binder application sheet
label | 25e550ef-6b12-51b9-a74e-e8b2a85cd3a5 |  | note | Remarks - Include in Q Pack
label | c9f84ac3-8b30-5636-a30c-8365ef070d9b |  | note | Control - Supervisor - Monitor
checkpoint-status |  |  | checkpoint | Testing of tack coat
label | 6f4b5c00-2de1-5c17-b408-ea917db2be52 |  | note | Specification / Procedure - 2 samples per distributor load
label | a7a2d3f7-a10f-523b-ba1b-79a2e45dad85 |  | note | Remarks - Test if requested by engineer
checkpoint-status |  |  | checkpoint | Mark paving lanes/longitudinal joints
label | 29716c69-748f-5776-9797-2be8db859761 |  | note | Specification / Procedure - Minimize paver joints under wheel track
label | e267c120-da2a-5301-ad79-503da60a82a6 |  | note | Record - Paving plan
label | 90916d74-c1c5-5d75-a2e4-d36b0bd0a3ed |  | note | Control - Supervisor - Holdpoint
label | ab52ec22-1694-593a-8b98-4e527b750f35 |  | note | Control - Head Contractor - Monitor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Transverse joints
label | 30f688e7-2022-5cb5-9dc8-6d0b3b570149 |  | note | Specification / Procedure - Check with 3m straight edge to nearest level and cut back with diamond saw
label | b867a99b-b029-5533-b8a1-36c210f3bd9e |  | note | Record - Visual inspection
label | 543baf1d-83d8-5de3-9c3a-176adfb8c6d9 |  | note | Remarks - We expect limited to no transverse joints in the mix
label | ae342449-718c-598a-9353-96bb801ab04d |  | note | Control - Supervisor - Monitor
checkpoint-status |  |  | checkpoint | Temperature testing of asphalt
label | f3e1a418-c06d-5c1e-afe7-74af11023b2f |  | note | Specification / Procedure - 110 deg to 165 deg
label | 31a06074-3cbb-5f6c-9325-5da17ee32b2e |  | note | Record - Record on field report
label | bfa69a22-08d9-5455-8083-d77c2509bf62 |  | note | Remarks - All trucks prior to placement
label | 18104e6d-b497-5f0a-b05b-bfd58b52beff |  | note | Control - Supervisor - Test
label | 3c750a28-f8e7-509d-9bc9-7cc5d1ea4418 |  | note | Control - Head Contractor - Witness
checkpoint-status |  |  | checkpoint | Level control
label | 11701cd7-528f-5520-9b9a-283aa634e8a3 |  | note | Specification / Procedure - Within 10mm of design level
label | 772aea81-1d3f-578e-ab69-256b7af1637e |  | note | Record - Visual inspection
label | 9c33fb73-211c-5638-a6c9-80701070a0d9 |  | note | Remarks - 2 Layers of 90mm
label | dd769b15-8575-50cc-8434-01ab87f373e4 |  | note | Control - Supervisor - Monitor
label | 6d7c1f53-c1d7-5ed7-90b0-209c46d4d1fc |  | note | Control - Head Contractor - Monitor
checkpoint-status |  |  | checkpoint | Inspect for thickness
label | 5508dee0-e8d0-5578-9c74-809f99872033 |  | note | Specification / Procedure - Check thickness by hand prodder (146 mm prior to compaction)
label | ba74485e-1cfb-56e1-8099-402115650519 |  | note | Record - Visual inspection
label | 31e89877-069a-5d95-929f-5b8448801ce8 |  | note | Remarks - Check at random
label | 003e7882-6702-594e-8ace-10197ae5cdf2 |  | note | Control - Supervisor - Test
label | 7cdb44b0-1159-5a56-b59e-fc9f3ac377e7 |  | note | Control - Head Contractor - Monitor
checkpoint-status |  |  | checkpoint | NDM testing
label | 26b2042c-3bdb-5c9c-a1b3-9071275bef34 |  | note | Specification / Procedure - Adequate compaction
label | 650d1bfb-5ad9-5c6c-aea2-c6ccc75ed6a7 |  | note | Record - NDM
label | 13cacd38-630c-5664-afce-b1e9a4644d92 |  | note | Remarks - Random testing by head contractor
label | 1002e2f0-4ccc-5653-95ef-b4fb0e444a33 |  | note | Control - Supervisor - Monitor
label | 9d33abc1-be07-5f64-9760-75b12e77598c |  | note | Control - Head Contractor - Test
label | 46864ea8-b7c5-511f-bcef-232c14dec70b |  | note | Control - Eng.- Monitor
label | df88b054-f2b9-509a-8a83-6ec0786f2bee |  | note | Control - Lab- Test
checkpoint-status |  |  | checkpoint | Paving lanes
label | 35f5125b-48d2-52d8-b7b0-c9cfb117628c |  | note | Specification / Procedure - Stagger longitudinal joints if possible
label | de84a43c-26cf-516c-8aab-fa87e1d667db |  | note | Record - Paving plan
label | 06bbc61f-70e8-514f-a8a7-63cc7c8acca6 |  | note | Remarks -
label | 7bb1c019-77de-52ac-8fa2-cad3cc609274 |  | note | Control - Supervisor - Monitor
checkpoint-status |  |  | checkpoint | Core Testing
label | 821c21d3-f40f-5365-82e4-1c7ee6ec1dee |  | note | Specification / Procedure - Core drilling by accredited lab / four cores per lot
label | 168d6f26-9bd1-596c-b11b-c87d629f9f3f |  | note | Record - Lab Results
label | c41e2e21-1f16-555e-a5ad-eef9e6b0ba16 |  | note | Control - Head Contractor - Holdpoint
label | 1c25da06-deec-59b9-969c-a2c0210f360b |  | note | Control - Eng.- Holdpoint
label | d5fe4ae7-95d2-5b5f-b29c-407bb7392697 |  | note | Control - Lab- Test
checkpoint-status |  |  | checkpoint | Grading and binder
label | 7f58f25d-cea8-53ae-bdd7-46d19d48790e |  | note | Specification / Procedure - Collect samples prior to dispatch. Results to conform to table 3.1 in the NZTA M10
label | bfd72522-ae40-542c-a420-f70b57b12780 |  | note | Record - Attach to Q pack
label | 7ff08b5c-fb4c-5c8e-bddc-3bb21b4b0dff |  | note | Control - Lab- Test
checklist-sectioned |  |  | checklist | ITP - Lighting |  |  |  |  | Yes | ITP - Lighting | 824c32c6-2005-4232-ba97-3b0f711c9268
checkpoint-group |  |  | section | Procurement/Material Properties
checkpoint-status |  |  | checkpoint | Material Supply
label | c9075385-efa2-56aa-9fca-651b968a6d5f |  | note | INSPECTION BY: Visual Inspection
label | a953a76f-ab1f-5824-93c4-dff7c2f218e8 |  | note | TASK TIMING OR TASK FREQUENCY: 1 statement per batch per material type supplied to site.
label | f08bcfdc-15d8-57ea-869e-6a8c63fc6984 |  | note | ACCEPTANCE CRITERIA: Written statement from supplier that all items and components comply in all respects with lighting and electrical requirements of the Specification
label | 5cb7c7e5-7b97-5547-9322-cc1b167cd4eb |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | c955f98b-b7b8-5c96-8f5a-59f320f49e8b |  | note | INSPECTION BY: Visual Inspection
label | e3d36178-7899-5f20-884e-516f9001d252 |  | note | TASK TIMING OR TASK FREQUENCY: 1 completed checklist for each Light pole installed.
label | 3402f5a9-e2c2-5078-9d78-292dd48c191a |  | note | ACCEPTANCE CRITERIA: Contractor to develop checklist(s) that will ensure that all testing has been carried out to the requirements of NZECP:11. The checklist shall be included in the Quality Plan.
label | 5f021715-59ef-5be5-8cce-cb6c4f2b417d |  | note | HOLD POINT (H) OR WITNESS POINT (W): H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Construction
label | 352c84f1-7664-5d87-be76-8d5d2700dd64 |  | note | INSPECTION BY: Visual Inspection
label | 764ef4c9-47f7-5197-bd4c-4795d91540f7 |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | e197ab15-e22a-5fa8-a2c5-ee74b696e7f4 |  | note | ACCEPTANCE CRITERIA: Megger Testing: Contractor to develop checklist(s) that records the resistance reading of the phase-earth, phase-neutral, neutral earth reading of the cabling after trench back-filling and compaction but before connection to pole gear- plate.
label | 5063a6cb-da9d-5717-b018-1189e31f70ca |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | 27fd91ca-8130-5939-bb82-3a404266133a |  | note | INSPECTION BY: Visual Inspection
label | 2dea8af2-61a3-546f-9ee9-1b7dd4b41b2e |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | 9ddb2893-0428-55bb-beeb-5bec7f7e5247 |  | note | ACCEPTANCE CRITERIA: Flange Positioning: Contractor to develop checklist(s) that ensure the stub orientation is correct in relation to the road direction and that the level does not exceed ±20 in two directions
label | b22d171f-7f1b-5521-9ecd-9104a1c838ef |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | 76d12c4a-c0c4-5135-82ec-a5d23e32fa39 |  | note | INSPECTION BY: Visual Inspection
label | 5db202ec-7519-56cc-9e3e-5a5dd0310f1f |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | 78051d50-cbf2-50d6-841d-4ca5cd523748 |  | note | ACCEPTANCE CRITERIA: Flange Height: Contractor to develop GO/NO gauge that checks that the underside of the flange is under the 75mm height requirement and to develop checklist(s) that records that the flange measurement complies with that requirement.
label | 3bfd4f94-7b6e-56d6-b7ea-8f3052f2ef72 |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | 3d85d460-6604-5fc3-ac54-a796641524e9 |  | note | INSPECTION BY: Visual Inspection
label | 59d6ce83-645e-5b86-ba30-6bf360207b3f |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | c1f07ad4-3436-5120-ae70-9f67d7f12067 |  | note | ACCEPTANCE CRITERIA: Pole Compression: Contractor to develop GO/NO gauge that checks that the pole has been assembled and compressed correctly before the arm piece is assembled and to develop checklist(s) to record the above
label | 316c5022-7a97-5b4a-b95f-c5384dee258d |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | f4c64271-932a-5288-af2d-80b0c5341ef9 |  | note | INSPECTION BY: Visual Inspection
label | bc9cbdd9-a9ad-58b0-969b-3fd081bcd943 |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | f96a4763-767a-5b62-9419-6689fc789b83 |  | note | ACCEPTANCE CRITERIA: Bolt Tensioning: Contractor to calibrate torque wrench(es) before installation and to develop checklist(s) that records the torque tightness reading of each frangible pole retention bolt.
label | a399f3ca-6fba-5c84-bfa6-992b480f3231 |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | 8492b802-7e13-524a-b969-67d695a678a4 |  | note | INSPECTION BY: Visual Inspection
label | 805b2283-bcc6-5f54-a9d8-c6f2d191c3b1 |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | 9cb4514b-aa3e-5ada-bda8-54053224bd28 |  | note | ACCEPTANCE CRITERIA: Pole positioning: Contractor to develop checklist(s) that records the vertical alignment is within the ±20 criteria and the orientation is correct for the road alignment.
label | b3f52dff-4c26-51da-bf56-6d7743872e4e |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Construction
label | b6e314c3-c30f-5479-8173-1596f53378c7 |  | note | INSPECTION BY: Visual Inspection
label | 274e6cd0-e157-591e-b380-6b363c52bfa0 |  | note | TASK TIMING OR TASK FREQUENCY: See Checklist
label | 88557adf-f292-535c-9e58-d73f1d00de96 |  | note | ACCEPTANCE CRITERIA: Protection devices: Contractor to develop checklist(s) that records the checking that the protective device is installed is suitable for the electrical load and cable protection.
label | fae6ee7a-80b8-57f9-9080-685e55154037 |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checkpoint-status |  |  | checkpoint | Commissioning
label | fd3174ef-272a-5d56-875b-0444116957b0 |  | note | INSPECTION BY: Visual Inspection
label | b90a9453-4419-5880-9518-5973c4775157 |  | note | TASK TIMING OR TASK FREQUENCY: 1 completed Certificate
label | 4550bfc4-8729-522b-9231-9a7bda1f12ea |  | note | ACCEPTANCE CRITERIA: Final Testing: Commissioning and testing to NZCEP11 – Certificate of Electrical Compliance for acceptance by the Engineer.
label | fa226144-cd7d-5f80-95f3-5aa2ee2cd7df |  | note | HOLD POINT (H) OR WITNESS POINT (W): H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Asbuilts
label | e69b3053-081d-5be3-9bd5-45de6cbb1732 |  | note | INSPECTION BY: Visual Inspection
label | c026b9e6-7be2-50ad-97f5-112c31c1392a |  | note | TASK TIMING OR TASK FREQUENCY: Survey records for every pole
label | f84a1450-cbdc-5c0b-aeff-3831d2a4bcee |  | note | ACCEPTANCE CRITERIA: Verification of pole position and reduced level of lamp: Within ±50 mm plan location and ±25 mm height.
label | cc2a7b45-e5e1-5730-b34c-1949b868a796 |  | note | HOLD POINT (H) OR WITNESS POINT (W): W
checklist-flat |  |  | checklist | ITP - Pavement Detail 'H' RAB | itp |  |  |  | Yes | ITP - Pavement Detail 'H' RAB | c5ae5522-f7f2-4e4a-ac60-cfd03c9e665f
checkpoint-status |  |  | checkpoint | 1 - Existing Pavement
label | 4110ad7a-77f4-41ee-addd-23a8f894a06b |  | note | Activity Task: Construction
label | 2c5bda63-7cad-46f5-b581-0bf7e48eeadb |  | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
label | 977e2c34-ec20-49aa-9ff3-5963b524aef0 |  | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
label | 40c004ec-59e4-41ae-962d-7918d7539674 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | 9d307d61-1daa-4935-9a6c-2f69be83d13e |  | note | Activity Task: Construction
label | 0ba80f38-5f38-45d6-afe6-ecceba91175a |  | note | Acceptance Criteria: Subgrade levels captured with GPS
label | 16b350b2-4820-4d28-8a66-c9a6c2462b08 |  | note | Certifying Documents and Frequency: Asbuilt Report
label | a9efc592-ba54-434a-acac-0fcf0ae816a9 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 3 - Subgrade/Dig outs
label | cc6f4a90-5735-4116-b190-58685a0c8b27 |  | note | Activity Task: Construction/Test
label | 72fb6962-f70b-4d16-afaa-2bb5e7eeb81f |  | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65
label | 4460a5cd-5d23-4787-828d-4f71f18e9b4c |  | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala Test sheet
label | 2835080b-df7b-412b-a068-40f17d10b83e |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Proof Roll
label | 2cdf64fd-d110-4c96-abe0-e40c836cc36b |  | note | Activity Task: Construction
label | eb4a4640-2917-4f32-8391-c0d6403e4b9d |  | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
label | ad5698e6-362b-48d4-9de9-d683b0ea2bbf |  | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
checkpoint-status |  |  | checkpoint | 5 - Subsoils
label | e2399b80-ceb2-46a7-bbf3-f703d2fffdad |  | note | Activity Task: Material Supply
label | dfe6f441-2bdc-4962-b804-b7cdce4dd84e |  | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE.
label | 2b18eb4d-2a1c-44ee-ac1c-12ee43612eef |  | note | Certifying Documents and Frequency: Compliance certification from supplier. Supplier to provide testing data for filter cloth material
checkpoint-status |  |  | checkpoint | 6 - Subsoils
label | ef3bb461-3ae1-4cf8-92a5-dccf7edf60c6 |  | note | Activity Task: Construction
label | 5cf03f74-2598-49ae-a106-abf117df7729 |  | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe. Subsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
label | 64171071-ed0d-4cd9-a3b2-0d1d1f0420c2 |  | note | Certifying Documents and Frequency: Photos, Asbuilts and Checklist
checkpoint-status |  |  | checkpoint | 7 - Sub-base
label | 72afa857-d1f5-441f-8dd7-8a303f984d08 |  | note | Acceptance Criteria: Gap 65
label | 0012d7ad-7169-44f5-b6b9-c43814b04bd6 |  | note | Activity Task: Material Supply
checkpoint-status |  |  | checkpoint | 8 - Sub-base
label | 96415c76-6bb4-4950-8ab8-f49390f8d273 |  | note | Activity Task: Test/ Material Supply
label | bd0677e1-3585-4f48-bc75-41b781d45049 |  | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
label | 96e4f4d0-511c-4b10-a849-8b0eda991460 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 3cdee05e-6e0d-47a2-bd0b-b55e8715e776 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 9 - Sub-base
label | ddc6d472-0c7d-467f-8af1-d06004e8662b |  | note | Activity Task: Test/ Material Supply
label | 5dfd18b1-e744-4893-bb5d-e7426bcb2518 |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6. Sand equivalent to meet specification
label | 3f89314b-4883-4fbc-8d2d-2b94001c9161 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 8999844c-2a62-4043-a20a-5683f26de4c4 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 10 - Sub-base
label | 967bbd3b-79fb-4140-af75-85c6f537f100 |  | note | Activity Task: Test/ Material Supply
label | 7047924b-4f14-4e32-bdc6-067a73e265a5 |  | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
label | 1d152566-3743-42fc-9d55-75773a46778b |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 6cc43409-eece-49ff-a161-767c5fb246e2 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 11 - Sub-base
label | 0470060d-4533-49ba-aa43-4225b2d86acd |  | note | Activity Task: Test/ Material Supply
label | 11063b13-3d7b-4a69-8b96-616abacd4f5c |  | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
label | 5e83f876-f240-459a-be3f-adbb6a2d7d97 |  | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
label | 0bfccc44-f78b-4f66-b67c-ab2055801904 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 12 - Sub-base
label | 9e6a9491-983f-4e25-a928-1360c1ed107c |  | note | Activity Task: Construction/Test
label | 1af2714c-71a2-4519-8fec-63802fba4cb7 |  | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
label | efe2eda9-c8c9-4927-a02b-301c3c073689 |  | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
label | 2a931fa4-3e1c-4717-b8b4-3ace503fe63d |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 13 - Lower Subbase
label | 872a3bd8-c64c-428f-9158-445803f764aa |  | note | Activity Task: Construction
label | 02ae493d-30f3-4969-840e-c2f037b74c14 |  | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65. Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | ed6d34e2-55dc-4af3-ba82-7d7e35439e5e |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
label | 107f7b53-f51c-4cd0-bd2d-55136ee5b8a4 |  | note | Project Manager or Delegated Person: P
checkpoint-status |  |  | checkpoint | 14 - Upper Subbase
label | 0268ce79-d03c-4bed-bdcd-3fc3de506db2 |  | note | Activity Task: Cement Supply
label | 7b1b52a5-f4f9-4423-ae5e-54ff782fee2f |  | note | Acceptance Criteria: Application rate to be 2% as specified
label | 98ab10fb-a0d3-42b2-8956-6e98a1c82f82 |  | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation.
checkpoint-status |  |  | checkpoint | 15 - Upper Subbase
label | e4eb3601-a79a-46b8-9580-1bee564d0004 |  | note | Activity Task: Construction
label | 2a747d5d-d00f-4640-975e-eabee78f5957 |  | note | Acceptance Criteria: 150mm Cement modified AP65 upper subbase
label | af2b1eb5-e599-449a-b60a-110836fc296c |  | note | Project Manager or Delegated Person: P
checkpoint-status |  |  | checkpoint | 16 - Completed sub-base prior to placement of AC20
label | 7145f854-50ee-49c8-afe5-bef6e3af0c2a |  | note | Activity Task: Test
label | 5fd0cf98-a185-4c75-ac6a-d0c681bd0e3a |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 6671c9d6-2227-4008-990f-4784a2ebd890 |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
label | 983fe555-1e69-49de-8ab1-38517248704c |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 17 - Completed sub-base prior to placement of AC20
label | 462d7b35-fb93-40a4-b249-8a2cd5abfc11 |  | note | Activity Task: Construction
label | 10ed2c82-ba33-4272-94c6-bfe3bfaa2436 |  | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | 53615b9d-d0c4-47ad-8caf-3f39ca2178b0 |  | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
label | 3ca552ce-55c0-4c7e-9d46-4820b205ec8b |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 18 - Completed sub-base prior to placement of AC20
label | 752d4a67-ab34-4eda-bcf4-7adfd5f82af1 |  | note | Activity Task: Construction
label | 59f272d5-73ea-4769-82d7-15cda5bf749c |  | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification. Surface shape matches design and minimum pavement depth provided.
label | 996bf5de-12cd-48a6-b2a5-4c5920a34abd |  | note | Certifying Documents and Frequency: Visual inspection by Engineer. Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | 01611e15-cce6-4ceb-aacf-0591cf72adfd |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 19 - Tack Coat
label | 7598989f-db9e-4a4a-a198-1eced07925e0 |  | note | Activity Task: Construction
label | ea20250f-c5ba-468c-98f2-411c7a29e7f7 |  | note | Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3. Apply Tack Coats between asphalt layers
label | 45b37ac6-d1a6-495b-8ccf-72dbd9756180 |  | note | Certifying Documents and Frequency: Two samples per distributor load on Request. Refer to Subcontractors QA in separate ITP
checkpoint-status |  |  | checkpoint | 20 - Asphaltic Concrete
label | bad0e199-a41f-4403-9959-0fee881c5aaf |  | note | Activity Task: Material supply
label | fb2f973a-7656-4eec-a9b3-722269591923 |  | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
label | 225bc549-172f-4b33-9de9-663ab620052d |  | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification. Refer to Subcontractors QA in separate ITP
checkpoint-status |  |  | checkpoint | 21 - AC20
label | 30863a0c-9401-41c6-9494-984b5e18e996 |  | note | Activity Task: Construction
label | 216115ad-87ca-43b2-8c29-255c173d0429 |  | note | Acceptance Criteria: 180mm AC20 to be laid in two layers
label | d513a6fb-9a8f-4da8-b2f6-66eceac82d87 |  | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in Separate ITP
checkpoint-status |  |  | checkpoint | 22 - A14
label | 54f50d76-9181-4011-b2f4-8fdbb1a5a209 |  | note | Activity Task: Construction
label | 0e61d885-2a38-415e-b269-7f429f50a172 |  | note | Acceptance Criteria: 50mm A14
label | a6f23a6b-7d06-4237-8f54-d47395d4e026 |  | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in separate ITP
checkpoint-status |  |  | checkpoint | 23 - As -Builts
label | 23d89377-4fa3-45d5-aba6-089802a97036 |  | note | Activity Task: As -Builts
label | fdf71285-16c0-4f7e-ac5f-c6cc878bb27d |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
label | c8cfc826-0da5-4939-bf9d-d0e727f62e4b |  | note | 1. The subgrade under new pavement areas;
label | b3879031-f42e-492b-ac65-1a2d965d5b15 |  | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | 350c37ac-7edf-43ca-a2a5-a17de0e07e24 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
checklist-flat |  |  | checklist | ITP - Clearing | itp |  |  |  | Yes | ITP - Clearing | c644d70e-ee40-4cf0-8806-32ed8718a214
checkpoint-status |  |  | checkpoint | Limits of Clearing 1.1
label | 27fe9669-9912-4895-bfad-97bcf51ef1f3 |  | note | ACTIVITY TASK: Construction
label | a4de03cc-877e-4eab-9841-b70d667902a3 |  | note | ACCEPTANCE CRITERIA: Engineer approval
label | c220be82-a962-45bc-97a0-4f05bdd7321a |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: At commencement of works
label | 21629efd-e310-4445-a11c-d2847d99762f |  | note | H
checkpoint-status |  |  | checkpoint | Approval for Clearing 1.1
label | 7c36749f-3e83-4e5a-a39d-70fbdc4a7e0f |  | note | ACTIVITY TASK: KDC Property
label | 12bf0edd-e497-4959-a459-c98855c1ef7b |  | note | ACCEPTANCE CRITERIA: Engineer approval
label | 6f467a75-1a54-412c-b733-30e28a181b8f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Photos- Before, During and After
checkpoint-status |  |  | checkpoint | Approval for Clearing 1.2
label | c6f8123f-0cbb-5002-b905-e9cffdaf2a77 |  | note | ACTIVITY TASK: Private Property
label | 67cb1c4c-4138-4219-8164-b8925ac9cf8b |  | note | ACCEPTANCE CRITERIA: Property owner sign off
label | f4fee0e5-3008-4e23-8197-16526a26e6f4 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Sign off sheet. Photos - Before, During and After
label | 89b1692b-ff84-47f3-9229-c2aea4641434 |  | note | R
checkpoint-status |  |  | checkpoint | Remove vegetation/ redundant signs
label | 62e9c590-44c1-4956-bf5f-3f4de2f0c006 |  | note | ACTIVITY TASK: Construction
label | 7b48fc27-c7a7-47aa-bdd6-dca7525a7f0f |  | note | ACCEPTANCE CRITERIA: In accordance with Drawing C012/C013. All tree stumps to be a minimum 750mm below ground surface or subgrade. Backfill with bulk granular fill material. Worksafe to be notified with 24 hours notice of any tree felling.
label | e7800a2d-9009-4bed-b1c6-f7be6b3c72a9 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: At commencement of works
label | 3394c83c-92fc-454a-93f9-d3c6c80df335 |  | note | W
checkpoint-status |  |  | checkpoint | Remove/Relocate existing fences
label | 089e69dd-0746-4b9f-84e3-194517d3b526 |  | note | ACTIVITY TASK: Construction
label | 10707c01-e425-4fa8-b3d4-fc87e9aeb734 |  | note | ACCEPTANCE CRITERIA: In accordance with Drawing C012/C013
label | 4c7baa8d-5e9a-40a0-b258-9d68cf60d9bf |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: On completion of vegetation/sign removal
label | d12bbdc5-cb60-4c59-8250-7f8d2ed82b00 |  | note | W
checkpoint-status |  |  | checkpoint | Remove existing kerb, channel and traffic island
label | 5e38cc26-4b84-437c-b4d7-66ee045b4983 |  | note | ACTIVITY TASK: Construction
label | c72927bc-cd76-4794-9768-305c546a2133 |  | note | ACCEPTANCE CRITERIA: In accordance with Drawing C012/C013
label | d2d416fa-669e-4a3f-9cd2-ddc73213095d |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: On completion of fence removal/relocation
label | bc9ec717-dfe2-40f7-aaae-5b28a49c4409 |  | note | W
checkpoint-status |  |  | checkpoint | Remove existing footpath
label | b1ba91ac-6d24-4811-8304-c8ae9629ea01 |  | note | ACTIVITY TASK: Construction
label | 772eb25e-fb7a-4102-960f-a202a3b37c97 |  | note | ACCEPTANCE CRITERIA: In accordance with Drawing C012/C013
label | ac8e9807-2fa5-4531-b9fa-5c4b6a384edf |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: On completion of Kerb and channel removal
label | 99917dcb-54d5-40c4-a463-82a29b5c52dd |  | note | W
checklist-flat |  |  | checklist | ITP 1 - Drainage MH01-MH02 |  |  |  |  | Yes | ITP - Drainage | d65cec84-48fd-48cf-95d6-cf44046e3ad9
checkpoint-status |  |  | checkpoint | Trenching/ Potholes 1.1
label | 0b6d41a7-5437-520f-9fce-a2c6e92c7259 |  | note | ACTIVITY TASK: Construction
label | 4de3059d-8883-5be3-9d64-2389bd3b4f4a |  | note | ACCEPTANCE CRITERIA: Location, alignment and level. Check for existing services
label | 166cdbb3-bc82-5283-b812-ab456a2285ce |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Between every section (MH to MH)
label | a7fe59af-3ec9-5587-aaec-ec07ab380ab6 |  | note | W
checkpoint-status |  |  | checkpoint | Trenching/ Potholes 1.2
label | 6f2b33a8-76a1-53c7-9ed5-552363425bba |  | note | ACTIVITY TASK: Test
label | a444549f-71b8-5fec-8751-fc697f2da904 |  | note | ACCEPTANCE CRITERIA: Test subgrade of trenches. 3 Blows per 100mm with Scala
label | a74c2ec7-c20c-56db-bd77-4e09dfc200c1 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every 50m
checkpoint-status |  |  | checkpoint | RCRRJ Pipes 1.1
label | bcfd955e-7aa6-5bf7-a80e-a69f2118d944 |  | note | ACTIVITY TASK: Material Supply
label | ab68a8ea-5c17-5b20-b5a9-3a02ed9f2075 |  | note | ACCEPTANCE CRITERIA: Certification from Manufacturer that materials comply with specification
label | 3e6b5664-748c-5e3b-80b2-6c2aef6f4edb |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All pipes shall be checked immediately prior to placing in the trench. Specification ref 10.2.1
checkpoint-status |  |  | checkpoint | RCRRJ Pipes 1.2
label | be69126f-6fb5-5e63-bfdf-61fefd43475a |  | note | ACTIVITY TASK: Construction
label | 3dce0b6a-7d06-5ac6-8ded-93eea2c52f58 |  | note | ACCEPTANCE CRITERIA: Location, alignment and level of invert ±10mm
label | b2a312e7-a497-59ec-b167-b7904cf8c3ef |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Survey on request of the Engineer
label | 9cc04b5f-f103-56dd-9a3a-178d6dfee922 |  | note | W
checkpoint-status |  |  | checkpoint | RCRRJ Pipes 1.3
label | 26648016-2522-519d-9eff-9a27c52f6c99 |  | note | ACTIVITY TASK: Construction
label | 377b78e8-2740-51b4-84fd-0b37290175cd |  | note | ACCEPTANCE CRITERIA: Compaction of bedding and backfill to Clegg of 20. Bedding to be 100mm D <1500 or D> 1500mm 150mm Bedding, haunch zone and overlay material to be Gap 20
label | 1c0e52ff-2606-55fe-876e-20a09b737675 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every 50m. Checklist
checkpoint-status |  |  | checkpoint | RCRRJ Pipes 1.4
label | f6b717c2-bfe6-5366-b9a4-62056d25f335 |  | note | ACTIVITY TASK: Construction
label | be5c760e-e7c5-58da-a9a0-315914fe6248 |  | note | ACCEPTANCE CRITERIA: Haunching to be 1/3 of pipe diameter (0.3 *D).
label | ac7e400b-c73a-54b4-a4dd-dabb3cf9487d |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Manufacturer certifies performance, material delivered is as specified. Checklist
checkpoint-status |  |  | checkpoint | RCRRJ Pipes 1.5
label | cc128f4a-5a2b-59cb-84c3-a35a00ccf89a |  | note | ACTIVITY TASK: Construction
label | 24e724fa-71dc-5a10-9f44-6d233498cc90 |  | note | ACCEPTANCE CRITERIA: Compaction of backfill to sub- base compacted to Clegg 20 Backfill to be Gap 65
label | 19a4c7ea-63cd-558a-b92c-88f80d5ed332 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every 50m. Checklist
label | 554c33ee-ec68-5aed-931e-e2f9a62d545b |  | note | P
checkpoint-status |  |  | checkpoint | Manhole 1.1
label | 2d6136b2-fee3-5c5d-b064-5797db7b9a7b |  | note | ACTIVITY TASK: Material Supply
label | dfad2876-32ad-5f15-a611-da1ce2738ed4 |  | note | ACCEPTANCE CRITERIA: Certification from Manufacturer that materials comply with specification
label | 23fe0c07-78cc-5b9a-87e9-7299d91b26cd |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All manholes and sumps shall be checked immediately prior to placement.
label | 5ba045fd-545c-5073-93fb-8b7538ba73ef |  | note | W
checkpoint-status |  |  | checkpoint | Manhole 1.2
label | d6f11d73-68a9-5996-8b91-ac6fd9bb80d6 |  | note | ACTIVITY TASK: Construction
label | 96f98177-e05e-57f2-9563-9fecccb073ba |  | note | ACCEPTANCE CRITERIA: Location, alignment and level of invert ±25mm
label | 5ff78f35-1c62-57c1-89f6-0a0a0d60503a |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Survey on request of the Engineer
label | 420dabe7-0af4-5486-8370-1ff6cda8863e |  | note | H
checkpoint-status |  |  | checkpoint | Manhole 1.3
label | 4303f05e-c0cd-5e9d-bc43-3e7d5435b9aa |  | note | ACTIVITY TASK: Test
label | dd6e8bbe-2035-535c-ae43-5b180f211929 |  | note | ACCEPTANCE CRITERIA: Test subgrade under MHs. 3 Blows per 100mm with Scala
label | fe206a05-16ff-52bc-8535-8a0370c12e6d |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every proposed MH location
checkpoint-status |  |  | checkpoint | Manhole 1.4
label | 750c2913-1c9e-5d54-91ae-744a172ec369 |  | note | ACTIVITY TASK: Construction
label | b6f9df39-c52e-56e6-acfb-6fac00f2b871 |  | note | ACCEPTANCE CRITERIA: Compaction of backfill to sub- base compacted to Clegg 20 Manholes to be laid on 50mm of ‘weak mix’ concrete 1:6
label | 6e68d78b-f0ae-58b4-ac7e-f7ca92279637 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Records every Proposed MH. Checklist
label | c4d2140f-58bc-549b-816e-91a9010718b6 |  | note | H
checkpoint-status |  |  | checkpoint | Manhole 1.5
label | 3b962006-7103-5d53-ade7-4c674a0455c8 |  | note | ACTIVITY TASK: Construction
label | 5ab8afe2-7061-5617-9d6c-046388d036c6 |  | note | ACCEPTANCE CRITERIA: Compaction of backfill to sub- base compacted to Clegg 20
label | 787f53d1-8221-55f8-8f16-2d153715d79f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every MH. Checklist
label | a61cb427-2866-553e-b705-8d406e46b0d0 |  | note | P
checkpoint-status |  |  | checkpoint | Manhole 1.6
label | cfd0b1c1-ad71-5c98-8785-b88540be2f11 |  | note | ACTIVITY TASK: Construction
label | bc73cc31-5a27-50b0-80b4-3effe793d89c |  | note | ACCEPTANCE CRITERIA: Compaction of backfill to sub- base compacted to Clegg 20.
label | a9445225-bbba-590c-8b05-eae045741c27 |  | note | Inside of manhole to be benched at 1:3 with 17.5MPa concrete. Top of pipe invert to be a min 1000mm below GL All inlet and outlet pipes into MH to be haunched with 20 MPa concrete Stepped rungs at 300mm centres (Dropper or safety type, galv) Excavations for MHs to be benched or shored if excavation perimeter is deemed too large.
label | e0197853-2ea8-5202-93f5-c1578a632020 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records every MH. Checklist
label | c82ddd10-c0f3-599c-b46b-c9f7f4aac40c |  | note | P
checkpoint-status |  |  | checkpoint | Catchpit CP1
label | 72f7ebf4-b2df-5f2c-8ec2-a148e4c9c831 |  | note | ACTIVITY TASK: Material Supply
label | 10323e36-b701-5507-8d4a-37b55238058e |  | note | ACCEPTANCE CRITERIA: Install new 675x450 1200 deep catchpits cast in-situ concrete apron and pre-cast double splay catchpit lid. Concrete apron shall have a minimum compressive strength of 20 MPa at 28 days.
label | 8dbd8722-c535-5e8e-86ad-df698e43e7d5 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Each Catchpit. Manufacturer certifies performance, material delivered is as specified.
label | c0e941c9-d238-5853-b146-692463a150f4 |  | note | W
checkpoint-status |  |  | checkpoint | Catchpit CP1.1
label | 5a36a578-a12b-5b71-a554-c964b7c9e220 |  | note | ACTIVITY TASK: Construction
label | 091a68cf-41a5-5ebe-9dee-73fa1ca0f2f1 |  | note | ACCEPTANCE CRITERIA: Double splay and single catchpits shall be installed in the positions and to the levels shown on the plans.
label | c5e1a099-4017-5aa6-bd3a-4ddbd4699acf |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All catchpits and sumps shall be checked immediately prior to placement. As Builts, Photos
label | 707b7072-9993-5167-bbaa-944f34627706 |  | note | P
checkpoint-status |  |  | checkpoint | Catchpit CP1.2
label | 06f853fe-dedc-5de7-88c5-16faaa8d4060 |  | note | ACTIVITY TASK: Construction
label | 3d2e9bb8-92c9-51ed-a5a7-a8aca626193f |  | note | ACCEPTANCE CRITERIA: Compaction of backfill to sub- base compacted to Clegg 20 in 150mm layers
label | 4df64a90-8d09-5292-ae3b-48a5883c178a |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Conforming compaction records. Checklist
label | 29853d2d-e091-5049-b4f7-4167c9a6df73 |  | note | P
checkpoint-status |  |  | checkpoint | As-Builts
label | cbd08873-8590-5e80-8e34-0c0e92245297 |  | note | ACTIVITY TASK: As-Builts
label | ec08c67f-9301-5c45-a3c5-dcbbb422e880 |  | note | ACCEPTANCE CRITERIA: A complete set of as-builts shall be provided on the completion of the project. This will include but not limited to
label | 1ee1f437-cdb0-500c-9508-90901d8de8c1 |  | note | 1. Storm Water drains and culvert extensions, including the invert levels of their inlets and outlets, together with related structures;
label | 00ed78d6-9c67-5ab0-9aca-2d66f4b6a5a4 |  | note | 2. Subsoil drains, kerb and channel, cess pits, sumps and manholes; Connections to Storm Water reticulation;
label | d60c518d-5765-5dfe-b9c4-8dfe32fbacff |  | note | 3. Location and size of Storm Water;
label | 65be5d04-1cf3-5e83-a4be-d018b8436891 |  | note | 4. Location of manholes, lid level and invert levels to LINZ datum, including the distances to the adjoining boundaries of sewers and Storm Water laterals
label | 31cfeff4-44e5-50f7-832d-e406790080fc |  | note | CERTIFING DOCUMENTATION AND FREQUENCY:
label | 7f271b73-29a5-5d30-a98a-db15549e914d |  | note | P
checklist-flat |  |  | checklist | ITP - Establishment | itp |  |  |  | Yes | ITP - Establishment | db5796f7-01d2-47da-837a-323ef97f8128
checkpoint-status |  |  | checkpoint | Management Plans
label | 380ea783-9476-424f-8062-b6ea971fbab6 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | d82f54d5-6c45-40ee-ad1f-e1515d763ae3 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | d0fc379c-ce41-4c72-8ccd-002208831c66 |  | note | H
checkpoint-status |  |  | checkpoint | Health and Safety Plan
label | 2c8a5dcd-b252-45a9-9449-7fefd8b39c6b |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | 5b98ccac-a73b-4d40-8d6c-41553e07fd49 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | 95ae5315-e6ff-41b5-b64b-2932a3b386f2 |  | note | H
checkpoint-status |  |  | checkpoint | Environmental Plan
label | 0c9e423a-54ad-4ad4-887c-e4f8d051a2f0 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | b830b118-4a76-4585-80d0-8a0060cb734e |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | b284e40e-e2b4-491b-8d4d-3c708f0f2b56 |  | note | H
checkpoint-status |  |  | checkpoint | Quality Plan
label | 9fc0c727-e766-4f15-8e20-947b6dfd4bf2 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | 8cf53988-aca3-45fe-9829-e6d2abf42a2a |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | 41f4b79b-22ff-4046-ba3b-ff2bded2b570 |  | note | H
checkpoint-status |  |  | checkpoint | Traffic Management Plan
label | 1e70d65e-9248-45aa-8e1c-e1dc1db89771 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | 1690f71b-b50a-4775-a9fe-b228f35cc907 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | 3a2e33d3-e5f9-4c2d-a628-e23b0c35d588 |  | note | H
checkpoint-status |  |  | checkpoint | Insurances
label | c488c80c-2f91-4bd5-90b7-32e65c0ee619 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | ebc1b552-a37c-4829-b76a-3bb5d29dd515 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | 4b4bf77d-4642-4468-b500-ef450e7abc71 |  | note | H
checkpoint-status |  |  | checkpoint | Bond
label | ee1934a7-f63f-45a5-99d8-49a0ed926ff8 |  | note | ACCEPTANCE CRITERIA: Engineer to Accept
label | ea0fbbc5-6f33-4de5-b11b-52113a273645 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to work beginning
label | e8ca5f40-4f29-4bcc-9845-30f2821dcae9 |  | note | H
checkpoint-status |  |  | checkpoint | Monitoring of Cottage at 48 Moir Street
label | 0d1b6a6b-c458-4a82-a9f7-dd67f3f4076c |  | note | ACTIVITY TASK: Monitoring
label | f1643973-399e-4d46-94d5-f39d5373aaee |  | note | ACCEPTANCE CRITERIA: The Contractor shall engage an independent, suitably experience qualified professional Architect or CPEng Chartered Engineer to perform the monitoring of the Historical building.
label | 1753c33a-1acf-4bbc-962c-e59308b1061d |  | note | The Second Phase -four weeks or no later than six weeks after the First Phase of monitoring, or at some other time, directed by the Engineer
label | 2f13c678-14a2-40c1-9151-1c79b28c384e |  | note | The Third -12 weeks or no later than 14 weeks after the First Phase of monitoring, or at some other time, directed by the Engineer.
label | 48375ed9-a8c9-48da-a19f-ca1ab9f212b1 |  | note | The Fourth Phase- before the Practical Completion Certificate is issued by the Engineer.
label | dc5977f6-7d70-4a89-8fb8-283cdf657cbc |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: The First Phase -prior to physical works commencing on site.
label | 203df324-2120-493c-a349-cc29b7ba9505 |  | note | H
checkpoint-status |  |  | checkpoint | Set out of Boundaries
label | d75a9142-996c-43c2-8f03-daab2f4edc89 |  | note | ACCEPTANCE CRITERIA: As agreed between Engineers Representative and Contractor's Representative. The engineer shall be notified at least 24 hours before any excavation
label | 7b124c59-e697-4f6b-9dc4-2ea5e13c5793 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to any works in private property occurring
label | 0f3a9616-911b-4d7a-9f9e-1eb98380dda6 |  | note | H
checkpoint-status |  |  | checkpoint | Mark out of existing services
label | 13fcb129-8584-44cb-86d7-53d87b6208c7 |  | note | ACCEPTANCE CRITERIA: Service authority's mark out their known services. The engineer shall be notified at least 24 hours before any excavation
label | 7e620c2f-a145-4c4a-978e-352003958654 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to any excavations on site
label | 0d138b0a-1e3d-4162-ba6f-ef229bf8fb79 |  | note | H
checkpoint-status |  |  | checkpoint | Extent of Site Fencing
label | 1ad4d4fc-9fd5-4cb1-9323-1fbdd6d57191 |  | note | ACCEPTANCE CRITERIA: As agreed between Engineers Representative and Contractor's Representative
label | befb3d4c-376c-4266-8021-a9d862b2a878 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to any works start
label | f3d1549b-d06e-489d-9806-1b203fe9c196 |  | note | W
checklist-flat |  |  | checklist | ITP - Pavement Detail 'J' | itp |  |  |  | Yes | ITP - Pavement Detail 'J' | dd3c0a3a-bfbf-44d1-ab19-e796d7723dc9
checkpoint-status |  |  | checkpoint | 1 - Existing Pavement
label | e7b9c3c8-3166-4d28-b83f-5ba9e81b59f8 |  | note | Activity Task: Construction
label | 4cc6eedf-1d32-4e84-ac8e-7f5b2a86515e |  | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
label | 10972162-1dd2-411a-b09d-45595172072e |  | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
label | 8f5c4a82-9661-45c9-93c5-39798aaec5f5 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | 9e58db6e-807c-496b-8cb8-11facac60180 |  | note | Activity Task: Construction
label | 10e720dd-117e-4272-a55b-946978b3a3c8 |  | note | Acceptance Criteria: Subgrade levels captured with GPS
label | 4f226928-5c6d-4b94-99d6-85498f23b706 |  | note | Certifying Documents and Frequency: Asbuilt report
label | cfbf10e9-4f15-4995-bfba-0d5f0288774f |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 3 - Subgrade/Dig outs
label | ffce2ef9-0c8c-45f7-bc91-8d33af238339 |  | note | Activity Task: Construction/Test
label | 56b46efe-c9b8-4fb9-8805-353749f827ef |  | note | Acceptance Criteria: Check insitu subgrade of Min CBR 5. If not undercut to 200mm and use GAP65 as imported subgrade. Inspection Check sheet
label | 19959e75-9cc4-4495-929b-67b5b0084d0a |  | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala Test sheet
label | 4f0a6177-5b5e-49ab-94f2-5386cdda01e6 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Proof Roll
label | 7547c44b-8c5b-42fa-a9cf-cb18ac90849a |  | note | Activity Task: Construction
label | 1b1971ec-52dd-45d3-9ede-c7b897586e56 |  | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
label | 08cca6a8-abcb-4b2d-8e16-ee2362705810 |  | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
checkpoint-status |  |  | checkpoint | 5 - Subsoils
label | d0ce1272-2826-4bfb-aff2-78a012e9826f |  | note | Activity Task: Material Supply
label | 3da85511-82a4-48fd-9eb6-511074f03bc0 |  | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE
label | d1cad846-521f-4efa-8126-7c34bd070ce5 |  | note | Certifying Documents and Frequency: Compliance certification from supplier
checkpoint-status |  |  | checkpoint | 6 - Subsoils
label | ac1dfe50-b7b5-416c-8eeb-7846fcaa0b04 |  | note | Activity Task: Construction
label | 3fa37161-f903-4f82-b148-e8f2809fa502 |  | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe.mSubsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
label | 9cabfb10-1158-48ac-b3a9-95447eb25a54 |  | note | Certifying Documents and Frequency: Photos and checklist
checkpoint-status |  |  | checkpoint | 7 - Sub-base aggregate
label | bd96034c-6e34-4304-a5c8-9c269770be1b |  | note | Activity Task: Material Supply
label | 9be54234-6740-4444-88e2-20d3b110a470 |  | note | Acceptance Criteria: Gap 65. Certifying Documentation: Material supply documentation
checkpoint-status |  |  | checkpoint | 8 - Sub-base aggregate
label | c2a4b1c2-6456-4bf2-944c-b011f8a83f95 |  | note | Activity Task: Test/ Material Supply
label | 6130ce04-4788-4b2f-8740-59444bcb117a |  | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
label | 79a1dc96-6a06-42ee-85a4-e1922fc8f7d0 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 732ae408-7cb2-4ab7-a816-87c570283b61 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 9 - Sub-base aggregate
label | f2bf6390-bb60-4a2d-9783-ce36bafc8977 |  | note | Activity Task: Test/ Material Supply
label | 30cce113-b127-4216-bb33-44d0a0fa7ddf |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6 Sand equivalent to meet specification
label | 1baac8df-5313-493b-a7e2-890099fd17f2 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 727b5d2f-c7b9-4e7a-a84c-314d83df5e71 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 10 - Sub-base aggregate
label | a017e29f-59cc-4e80-a801-05f24d085656 |  | note | Activity Task: Test/ Material Supply
label | d4fbd139-494a-4581-b5d0-1f89917ac700 |  | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
label | 80026286-7fdf-474a-8efd-5ad29e092566 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 23667063-c22e-48b5-9466-ed52af7892a0 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 11 - Sub-base aggregate
label | 3aa7c7ac-bca6-41fc-98b8-644dd92c2b9b |  | note | Activity Task: Test/ Material Supply
label | 5e2b879e-7e42-4b12-afc1-0935ea6be877 |  | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
label | 7ac0c949-77a7-4b48-aa41-97b04bca08ba |  | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
label | a1a6019d-ba0f-4458-9cfe-9c53c66f0b00 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 12 - Sub-base aggregate
label | 9ceed4c8-5091-4a32-805c-bdd2dc4dc40f |  | note | Activity Task: Construction/Test
label | 33f5f9b0-2c61-4c05-a9d4-70311a61e20d |  | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
label | 3335a141-6467-41e8-a004-1a4ffd0ec21a |  | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
label | f22684fa-c701-4e67-a7af-fcdc6f5de933 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 13 - Lower Sub-base
label | 233a949c-2dc7-41f2-9de2-9a4802528c59 |  | note | Activity Task: Construction
label | 612687fa-0dc9-413c-8610-26996564333c |  | note | Acceptance Criteria: Lower Subbase to be 150mm layer GAP 65
label | 8bbf3ec0-8c8b-4a58-85b7-afc3870a2010 |  | note | Certifying Documents and Frequency: Photos
label | 5ff44c35-1c31-4bcc-b1ec-83c203bc9c02 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 14 - Upper Sub-base
label | 1fb55e36-3ec3-4dd3-8e9f-ae55bfe50c34 |  | note | Activity Task: Construction
label | 97f06f6d-dffc-46dc-9313-1168e744b1de |  | note | Acceptance Criteria: Upper Subbase to be 150mm layer GAP 65
label | 6e07084b-594f-428d-9ec0-9dc2cc06f81c |  | note | Certifying Documents and Frequency: Photos
label | 5cce19ee-4408-471a-a174-e513d61a1b77 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 15 - Completed Sub-base prior to placement of Basecourse
label | 77a78723-38e1-4fa2-b5bd-ab4f846dabc7 |  | note | Activity Task: Test/ Material Supply
label | c84ee6d9-eb5e-4327-95c0-c414bae98916 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 7437b87a-f46c-49aa-9926-a4f431805deb |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
label | 6fb062e2-354a-4451-b4f5-9f3ddb14b217 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 16
label | d19192bb-017e-4aea-9a2b-83e08eb40215 |  | note | Activity Task: Construction
label | 3751ed5d-2752-4b55-94d9-566778cb10e0 |  | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | 7829eaad-989a-446c-aa87-8aa55d2f0806 |  | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water Checklist
label | b0d50b8a-6110-4229-bb87-e3e805d0c342 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 17
label | da4ea9c2-1be9-45cb-a220-41470efde989 |  | note | Activity Task: Construction
label | 1bd61c8d-5a4b-4c44-bf89-e77f50682baf |  | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification
label | 2329459e-8f2b-4196-be30-cbccc20b6a65 |  | note | Certifying Documents and Frequency: Visual inspection by Engineer Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | c402b85d-b452-4b59-8c92-3e097ae219ee |  | note | Supervisor, Foreman or Subcontractor:
label | 51b86747-6499-4023-a80e-04f40000c875 |  | note | Project Manager or Delegated Person:
label | e53cf5cc-5dbd-42eb-844d-668d828eec1b |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 18 - Basecourse
label | 418512ce-293e-4e09-ba5b-5870580f8140 |  | note | Activity Task: Material Supply
label | 8ab94b94-644a-484f-b6e3-9a33eb52629b |  | note | Acceptance Criteria: Unless otherwise specified all basecourse operations shall be in accordance with TNZ B/2, M/4 and the drawings and specifications.
label | b0915bbd-60ac-4c5c-b095-3b2b874b0fe2 |  | note | Certifying Documents and Frequency: Compliance certification to be supplied from sub-contractor
checkpoint-status |  |  | checkpoint | 19 - Basecourse Cement Supply
label | cb251a60-eec8-4cc7-8629-959a19276a23 |  | note | Activity Task: Material Supply
label | d855aae7-499c-40d0-85da-3e7ab8c5d732 |  | note | Acceptance Criteria: Application rate to be 2% as specified.
label | 3dc7dcc6-bf15-4950-a00b-b76efb8b39f3 |  | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation.
checkpoint-status |  |  | checkpoint | 20 - Basecourse
label | c0a7f32a-fb0a-424b-b86e-3ed41f20216f |  | note | Activity Task: Construction
label | 284b0138-27e1-4669-b3ae-3a77ae7b0e87 |  | note | Acceptance Criteria: Basecourse to be 210mm Cement modified M/4 AP40
label | 540bf780-d681-4e50-ad64-ff51e0023101 |  | note | Certifying Documents and Frequency: Photos
label | f1487e24-eb68-4916-b870-94a2ec14abb0 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 21 - Basecourse
label | 05797578-b861-40cd-b042-e93582d16ce3 |  | note | Activity Task: Testing
label | 9db283b3-fe2b-4058-8367-26d515ab7d06 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 9e95102e-b159-4147-90d2-9149f999c0d5 |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
checkpoint-status |  |  | checkpoint | 22 - Basecourse
label | 24e90b74-b2bf-4ad8-be27-dd339d893a1c |  | note | Activity Task: Straight Edge Checks
label | a82d0ab9-eaa3-4f61-942b-9a96641e5b22 |  | note | Acceptance Criteria: No point on the surface shall vary more than 10 mm from a 3m straight edge. No area of the completed surface shall pond water.
label | 0bc84606-c3d1-464e-a597-69bdd44602b4 |  | note | Certifying Documents and Frequency: Straight edge checks on surface shape at randomly staggered transverse positions at 20 m intervals throughout.
checkpoint-status |  |  | checkpoint | 23 - Basecourse
label | b7334ac0-b4e0-4904-b974-c25f92895c10 |  | note | Activity Task: String Line checks
label | dbf23da4-d6ce-42db-b3fc-0022b7a0794c |  | note | Acceptance Criteria: Surface shape matches design and minimum pavement depth provided.
label | e2a9e3a4-ea7e-4a51-a16e-d839bf5c9c1e |  | note | Certifying Documents and Frequency: Stringing records, 3 points minimum per cross section
checkpoint-status |  |  | checkpoint | 24 - Basecourse
label | 60b3ef34-54e6-451f-868d-d7976f2a3e4b |  | note | Activity Task: Visual Inspection
label | fad407fb-54dd-43af-bb02-5e085e0fce23 |  | note | Acceptance Criteria: Surface to be as specified
label | 738b8355-4491-46b8-91bc-b19455655a02 |  | note | Certifying Documents and Frequency: Visual inspection by Engineer
label | 6de62ab9-0018-4760-8139-30a07aba7655 |  | note | Engineer’s Representative: H
holdpoint |  | Data not allowed on signoff: Activity Task: Construction(a6bf5b67-e3bf-4a4a-b677-a752b217e72f), Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3(abf90c44-36b8-4950-a851-6aae66a7fc09), Certifying Documents and Frequency: Two samples per distributor load On Request(a220fa43-a4b4-4d7e-8cb1-c56e6db54bdd), Supervisor, Foreman or Subcontractor: W(18753bba-750d-4abb-a35e-a0cd5ead051b) | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 25 - Chipseal
label | 0bd05398-93c3-404f-8c38-f71b236d9245 |  | note | Activity Task: Material Supply/Construction
label | 8793e979-c0e4-43b9-a97f-27f264cc8e46 |  | note | Acceptance Criteria: Grade 3/5 Chipseal
label | 421fbecc-295f-4d6e-a347-4a9959c1b86b |  | note | Certifying Documents and Frequency: Refer to Subcontractors QA in Separate ITP
checkpoint-status |  |  | checkpoint | 26 - As -Builts
label | 9dc5508a-ad98-48e4-bfd8-df4cc51d46b6 |  | note | Activity Task: As -Builts
label | c854a2b5-12cc-4f7b-b09e-212cadf489a8 |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
label | e141222b-a346-48df-ae0a-b32439759da5 |  | note | 1. The subgrade under new pavement areas;
label | b3317052-453b-40cf-9cdf-16978bfb2a26 |  | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | 70a0da7f-046d-4ee7-8431-c8998aa74fe7 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
checklist-sectioned |  |  | checklist | Manhole / Chamber / Sump Check Sheet |  |  |  |  | Yes | Manhole / Chamber / Sump Check Sheet | de14c1dd-198a-4bdc-a3c4-eb8bae73df28
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Details input
text | ff6da4d8-f6b9-54fe-829c-4310d0f30377 |  | textbox | Location:
text | a9e9f3b6-9cf8-533b-b10a-29d7177a6315 |  | textbox | Chainage:
text | 246533a2-bef6-5dbc-bd9a-58501ea5c77c |  | textbox | Drawing No:
text | dae38bc5-9f87-5364-aaec-309b3a719673 |  | textbox | Rev:
text | 3e349702-d2c2-5d92-a866-5f93b1216405 |  | textbox | Work Pack No
text | 7d6a968c-04e0-5733-b2cc-9b804f80ba0a |  | textbox | Package Ref. No:
checkpoint-status |  |  | checkpoint | Lid Coordinates
text | 2419c783-da03-5da0-bad1-5272053a5a88 |  | textbox | Design (As per Drawing)
text | 5d6c8cbe-341d-59b8-b594-810736b232a8 |  | textbox | As-Built
checkpoint-status |  |  | checkpoint | Lid Level
text | 7a197f5f-5edd-59c7-bdbd-3875be05b5e9 |  | textbox | Design (As per Drawing)
text | 10908b15-4f19-5052-893a-40a6b7532dd2 |  | textbox | As-Built
checkpoint-status |  |  | checkpoint | Diameter / Size of Manhole Chamber
text | 519c1158-69de-56f2-a12a-8ba8c807d3b0 |  | textbox | Design (As per Drawing)
text | 89730c0d-bc05-5c3d-9fe2-9e47d0ba3e01 |  | textbox | As-Built
checkpoint-status |  |  | checkpoint | Make / Type
select | 84c6833a-fa79-53fc-8578-f73008a07a84 |  | dropdown | Select the option | In-situ Concrete, Precast
text | c85ceb6b-ac22-5f8a-8365-ed9b63630600 |  | textbox | As-Built
checkpoint-status |  |  | checkpoint | Sump Invert Level
text | aab09300-21e9-5911-8769-4c09ee37e54b |  | textbox | Design (As per Drawing)
text | cf5c13b0-737d-5a17-b97b-126b23bb5ae2 |  | textbox | As-Built
checkpoint-status |  |  | checkpoint | MH Centre Coordinates
text | bf0969c7-2438-5eb8-bc47-2180fba61abb |  | textbox | Design (As per Drawing)
text | 21b50d3e-d1e5-5a0d-afe3-93c6c305113a |  | textbox | As-Built
checkpoint-group |  |  | section | Pipe Details
checkpoint-no-status |  |  | checkpoint | Pipes numbered consecutively, Clockwise from outlet.
checkpoint-status |  |  | checkpoint | IL Outlet Out
text | fe907197-1155-5ad1-8a32-b1f1615bbee4 |  | textbox | Design (As per Drawing)
text | dd22c1a0-c8f6-56bd-8349-50879978f4a9 |  | textbox | As-Built
text | 87c42cef-338c-5530-9361-ef27f9daf8e8 |  | textbox | To - From
text | d1fadd35-289c-5f55-8f0d-aecd5a914c04 |  | textbox | Pipe Type
text | 609955ee-bf38-5850-977e-5370e1f0d073 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 1
text | 0e6494b2-bd9f-540b-a89b-7c041e072347 |  | textbox | Design (As per Drawing)
text | dbafdec2-b55c-568d-b548-c6c0efae5bc1 |  | textbox | As-Built
text | fd5e26f3-2ad6-584b-9f1e-4d8d1c27d8fd |  | textbox | To - From
text | 2ab69a64-d19c-5e03-9d07-5f0e410f2e3c |  | textbox | Pipe Type
text | 18153765-9cdc-53d4-9bf1-ac8d3b21924f |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 2
text | 386cd99b-ccdc-5ba3-b9dc-569a321338ab |  | textbox | Design (As per Drawing)
text | 1029fbf8-0fb9-5b01-8ec0-a6fed3eebec3 |  | textbox | As-Built
text | 263432c7-7d7c-5fbd-8c22-49b07acc8e63 |  | textbox | To - From
text | 7cee67ff-059b-5346-bc79-b0b43445453c |  | textbox | Pipe Type
text | a045c146-3610-5f53-a9e3-93f0876b9fe6 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 3
text | defacc71-00c7-5cf9-8971-5e2da6a116c5 |  | textbox | Design (As per Drawing)
text | 6d9dc28f-7ecc-5ad7-881b-aded37c26a94 |  | textbox | As-Built
text | 2c90786e-2706-5056-b6ce-00b98245677d |  | textbox | To - From
text | 53c57e36-4905-5f2d-bec9-76d2a6e4f400 |  | textbox | Pipe Type
text | a3555710-5145-5d7d-93f7-72961e1e55ef |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 4
text | 52510c46-0859-510e-be4f-e37432739555 |  | textbox | Design (As per Drawing)
text | 819410cb-6d70-50f9-be98-1ebeeb15d301 |  | textbox | As-Built
text | 006ecfce-8f31-5ac1-a084-f959e61be80f |  | textbox | To - From
text | 4ef3869e-2adf-530c-8790-ebcb307dafdb |  | textbox | Pipe Type
text | fa7951e1-91fb-5d27-8031-e208f9d7ba83 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 5
text | c1f8a9b7-e553-59b6-a18b-21350dceb681 |  | textbox | Design (As per Drawing)
text | 953fb0c7-2423-54d8-8fd9-7cf1d95bf917 |  | textbox | As-Built
text | 8727628f-bca0-56cf-a4d8-3f9c479c376e |  | textbox | To - From
text | 2729291d-3ec2-583d-9dc2-65565119c76b |  | textbox | Pipe Type
text | e0060df6-ee36-5dd3-acf1-6fbfe49b1443 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 6
text | 59665245-88f8-5e84-acbf-585b4a9ccc9f |  | textbox | Design (As per Drawing)
text | f604da67-c1c8-5e81-8991-ca86c435c748 |  | textbox | As-Built
text | b1d6aee7-f25b-5895-bebb-05677b3f7043 |  | textbox | To - From
text | 7552af88-5910-51ec-a4fb-cd3ab988df17 |  | textbox | Pipe Type
text | d39e402a-0d82-584d-a906-75afe627d892 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 7
text | 917989e6-a1e5-5713-b0e0-6def92d6b250 |  | textbox | Design (As per Drawing)
text | 6a9dddf6-d57b-5e3e-a9a1-1612353ea63b |  | textbox | As-Built
text | ec7c0ce8-f71d-5e0a-b8c2-ed39b6d07a48 |  | textbox | To - From
text | abdb451c-7114-5f0a-a06c-de7d119f5f6f |  | textbox | Pipe Type
text | 82ecb06f-f69e-525e-9480-cd7ad8d23c94 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | IL In 8
text | 5f176438-c4ce-553c-927c-b789f8b4f1f8 |  | textbox | Design (As per Drawing)
text | 9341b2e2-a0ba-52f2-b343-ed9a65c3b638 |  | textbox | As-Built
text | 2d404128-fa45-5fd7-93dc-842748f43fc1 |  | textbox | To - From
text | 86eae82a-9ee0-5188-bada-24fff8bfbbe4 |  | textbox | Pipe Type
text | 4c9f58f7-eee5-52c3-a119-718af0632315 |  | textbox | Pipe Size
checkpoint-status |  |  | checkpoint | Test
text | db232fa4-f099-51f2-9a1d-4d3c767395e3 |  | textbox | Type
text | 0663d35c-5445-5be8-bb87-17ae74780a3f |  | textbox | Location
text | 13f58f56-889c-51b2-bb4d-9fa7a49c19bb |  | textbox | Drain Layer Name
text | e5f9c9a6-2c3e-529d-a77b-155b3b16a7ba |  | textbox | ID/Certificate No:
checklist-flat |  |  | checklist | ITP - Services |  |  |  |  | Yes | ITP - Services | df1a397e-5bcb-4e42-aeeb-0e5eb534dcf7
checkpoint-status |  |  | checkpoint | Services
label | 9c036cd4-df80-5422-a05a-1c8e92377a13 |  | note | ACTIVITY TASK: Locate services/ Dial before you Dig
label | 184158de-5160-5fde-8bd2-1c4f38a42b76 |  | note | ACCEPTANCE CRITERIA: Service authority's to mark out their known services
label | 35e1f504-0155-5b82-95ae-26e2e30af79d |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to any excavations on site
label | 77528d97-6a17-5d48-a69f-6d77a2e5ccc0 |  | note | H
checkpoint-status |  |  | checkpoint | Permit to Dig
label | e7f64891-b60e-5145-9ba1-f1f66afd2cae |  | note | ACTIVITY TASK: Permit
label | 68e4fabc-20cd-5140-92cf-de11b544b5ae |  | note | ACCEPTANCE CRITERIA: In accordance with Permit to Dig document
label | 37c1e137-3af4-58b9-b8f2-0c26fe5a0241 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Prior to any excavations on site. Checklist
label | 6e132c5c-6c1a-5923-95c9-169b1025b370 |  | note | H
checkpoint-status |  |  | checkpoint | Trench Alignment/Depth
label | 0d69c59b-7e74-5e3f-8f40-f7742ef80e52 |  | note | ACTIVITY TASK: Construction
label | b7a093c7-100c-5bc0-b894-6aced00ef3e3 |  | note | ACCEPTANCE CRITERIA: As Per design or directed otherwise
label | dac278f6-af40-59ba-b3d5-bbc56b11d03d |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Engineer to sign off
label | 26f91a54-79a4-5db9-9fc3-8b8b1d6ca1cf |  | note | H
checkpoint-status |  |  | checkpoint | Laying Ducts
label | e056d16d-aa57-5792-8c87-35c7515069aa |  | note | ACTIVITY TASK: Construction
label | c0d764a2-bef8-5ee1-be42-4ce48c8fff27 |  | note | ACCEPTANCE CRITERIA: As per design or directed otherwise
label | 1dfdcdc9-d007-5f93-a5e3-9ec6360f33ea |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Every service trench. Photos
label | b9aad5f4-4989-5caf-b64a-a8ad4df7cdb4 |  | note | W
checkpoint-status |  |  | checkpoint | Duct As builts
label | 679f2431-c465-5e4c-bba0-9f71b8ece4d5 |  | note | ACTIVITY TASK: As Built
label | 1f551177-0eb7-5a92-93fd-a2dd50de3b75 |  | note | ACCEPTANCE CRITERIA: Alignment, Level
label | 6bcb3a1c-26de-589f-9789-8e88927d3410 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: As builts. Every trench and all services. Photos
label | 414a5028-9fb8-5f95-894d-1454867fc49e |  | note | P
checkpoint-status |  |  | checkpoint | Exposure of existing services/prior to re-location or amendment.
label | e422531d-3ff9-5068-975b-8bada8eb5604 |  | note | ACTIVITY TASK: Construction
label | 7bd61667-07ac-5772-8249-bbea664fb2a7 |  | note | ACCEPTANCE CRITERIA: The engineer shall be notified at least 24 hours before any excavation
label | 52abcc08-87ed-5c48-a9d5-0a7f6da83578 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All service trenches/ excavations
label | c0ab79bd-3f46-5044-b101-8e65b2e98407 |  | note | H
checkpoint-status |  |  | checkpoint | After excavation of new service trenches, to allow site inspection and visual reporting by designer of trenches in order to confirm pavement design
label | 39bbefc7-1cfc-5c0c-9f70-bc2db69513a2 |  | note | ACTIVITY TASK: Construction
label | 64249ec5-a6db-5366-88d7-13393383f307 |  | note | ACCEPTANCE CRITERIA: The engineer shall be notified at least 24 hours before any excavation. All trenches to follow proposed route as per drawings C090-C093 or as close as possible.
label | c0d7650a-5727-5d74-921d-5b4e67898a47 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All service trenches/ excavations
label | 7dd8d2e2-302b-5851-8b81-84ba3b364042 |  | note | H
checkpoint-status |  |  | checkpoint | Upon relocation of services, prior to backfilling.
label | 3c4d012b-330c-55fa-9b61-efbe10289a76 |  | note | ACTIVITY TASK: Construction
label | 76a1822b-b218-5d4d-93df-bfa87d6c1cb6 |  | note | ACCEPTANCE CRITERIA: The engineer shall be notified at least 24 hours before any excavation. All trenches to follow proposed route as per drawings C090-C093 or as close as possible.
label | 5fd9d650-e5ee-56b9-9462-b5f83fd55c06 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All service trenches/ excavations
label | 18635405-bba9-59f0-974e-facd7aa75500 |  | note | H
checkpoint-status |  |  | checkpoint | After laying and connecting services and prior to backfilling Services
label | fc483bd0-b01b-55f9-b58d-ed1701bb98de |  | note | ACTIVITY TASK: Construction
label | 88fdcdac-18ed-5001-bf67-5b3b8bdb951b |  | note | ACCEPTANCE CRITERIA: The engineer shall be notified at least 24 hours before any excavation. All trenches to follow proposed route as per drawings C090-C093 or as directed otherwise.
label | a26b1f70-b34f-54c2-9652-486ccc6fd0d5 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All service trenches/ excavations
label | 03e02fbf-e180-5e45-a1c4-46c557206875 |  | note | H
checkpoint-status |  |  | checkpoint | Backfilling Trenches
label | 632c7fbb-1e50-5357-b70c-4b0b15bddbc8 |  | note | ACTIVITY TASK: Material Supply
label | 539ba5cb-d979-5d62-a15f-58b1ecdfdc33 |  | note | ACCEPTANCE CRITERIA: Trenches in berm to be backfilled with same material as excavated in 150mm layers. Backfilling across carriageways shall be in 200mm layers with AP 40, and Gap 65 as appropriate.
label | e14caeeb-02ee-5672-8f36-bdf971717079 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: All service trenches/ excavation
label | bb260060-a776-5824-b260-45770006a823 |  | note | W
checkpoint-status |  |  | checkpoint | Ducting- Power, Telecom, Lighting
label | ea3295b9-a9fa-5aeb-ab27-3fb60391412a |  | note | ACTIVITY TASK: Material Supply
label | ef55860a-5cab-5ebd-a63e-b8d07208329b |  | note | ACCEPTANCE CRITERIA: Certification from manufacturer that materials comply with the manufacturer’s specification
label | 34fca35e-e5e7-508b-a955-3b89b18b6ed6 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY: Delivery Dockets. All service trenches/ excavations
label | 53d55701-f190-5a96-b59a-dd461fd1d50f |  | note | W
checklist-flat |  |  | checklist | ITP 02 - SUPPLY AND PLACE 50MM AC14 |  |  |  |  | Yes | ITP 02 - SUPPLY AND PLACE 50MM AC14 | f13b795e-4208-43a7-8a8f-534f6923ac49
checkpoint-status |  |  | checkpoint | Area clear of deleterious materials
label | a3581871-3c5d-5a3c-8d5d-51071d4ec33d |  | note | Specification / Procedure - Visual inspection
label | ee4ec147-3642-5b5f-985e-6032c33be98e |  | note | Record - Visual inspect all areas
label | ede98e91-fbf7-5604-a0b8-3617ab925633 |  | note | Control - Supervisor - Holdpoint
label | 3064db33-ff25-5e21-9a2f-f2720bc3d1f7 |  | note | Control - Head Contractor - Holdpoint
label | 0c02294a-b4c0-5e8d-95dd-276e50d03be0 |  | note | Control - Eng.- Verify
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Apply tack coat
label | b6e79123-226d-5be2-929d-e548cd8296e1 |  | note | Specification / Procedure - Max 0.33L/m2 net binder
label | b3240546-acb0-53d2-92f2-9785c216f1bd |  | note | Record - Binder application sheet
label | 1bf46065-ae0b-5348-be4f-c2458108c1da |  | note | Remarks - Include in Q Pack
label | 1860cfb3-ae43-5cb0-b982-ac5051623e28 |  | note | Control - Supervisor - Monitor
checkpoint-status |  |  | checkpoint | Testing of tack coat
label | 8055a9ef-fa54-5674-9c74-f78d39c1668e |  | note | Specification / Procedure - 2 samples per distributor load
label | 7b6cd472-bfcb-5009-95ec-53adcf4a6dcb |  | note | Remarks - Test if requested by engineer
checkpoint-status |  |  | checkpoint | Mark paving lanes/longitudinal joints
label | 43430901-fb9e-5ed8-ab26-22c35c88f2b1 |  | note | Specification / Procedure - Minimize paver joints under wheel track
label | 12b69270-9f7c-51c2-b5f1-8403cc241f30 |  | note | Record - Paving plan
label | 944ff421-2519-5ab6-bb9e-6d35f60f01a1 |  | note | Control - Supervisor - Holdpoint
label | 0cb30a66-8816-5175-aad5-edd9326515f2 |  | note | Control - Head Contractor - Monitor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Transverse joints
label | fd11c65b-f28c-56ef-87a2-69b6561ebdb1 |  | note | Specification / Procedure - Check with 3m straight edge to nearest level and cut back with diamond saw
label | c4741898-cd7b-55cf-9205-72ef5d05a1b9 |  | note | Record - Visual inspection
label | 0ac95a31-4542-5b8c-ba4a-fbf68a0de94b |  | note | Remarks - We expect limited to no transverse joints in the mix
label | 76be93cd-eced-5d92-9ba4-4c41b53c0094 |  | note | Control - Supervisor - Monitor
checkpoint-status |  |  | checkpoint | Temperature testing of asphalt
label | 33d6a08a-7e58-504a-b710-60eff3035aaa |  | note | Specification / Procedure - 110 deg to 165 deg
label | 3092773e-3a33-5b04-a7fc-fa5adeb88652 |  | note | Record - Record on field report
label | 25fabea7-5ea3-50dc-98b3-2b2b0f8220a0 |  | note | Remarks - All trucks prior to placement
label | 5e7dc3ba-ca8e-5a53-af77-423a5a57fbdb |  | note | Control - Supervisor - Test
label | 12e273cb-7381-525e-85fa-513244c1dd5f |  | note | Control - Head Contractor - Witness
checkpoint-status |  |  | checkpoint | Level control
label | 8a673cf4-7599-5ba0-bad6-31bdf37439d0 |  | note | Specification / Procedure - Within 10mm of design level
label | 3e59dbb4-e0d9-53e0-9f58-fc1f70e3d8a8 |  | note | Record - Visual inspection
label | 3b0b6a98-db6e-5a4c-be64-1b79004daaf2 |  | note | Remarks - 2 Layers of 90mm
label | f9d6b351-5562-5b56-93a3-862260396b46 |  | note | Control - Supervisor - Monitor
label | f59f07fb-19bc-5038-8d2f-f2f8a90614bd |  | note | Control - Head Contractor - Monitor
checkpoint-status |  |  | checkpoint | Inspect for thickness
label | c1f5b418-32c8-56e0-bc96-9fc754134b7d |  | note | Specification / Procedure - Check thickness by hand prodder (61mm prior to compaction)
label | bb397b3b-f3ea-5ebd-a9f6-72229d57e9db |  | note | Record - Visual inspection
label | 544f4b72-ad22-5cf4-b592-046c0a82a225 |  | note | Remarks - Check at random
label | f50120a7-5aef-5999-9e55-9b0e589f4876 |  | note | Control - Supervisor - Test
label | 29575323-2823-59b7-aa8b-6638e8469906 |  | note | Control - Head Contractor - Monitor
checkpoint-status |  |  | checkpoint | NDM testing
label | 9679b680-0453-571c-94fc-12b77daf1628 |  | note | Specification / Procedure - Adequate compaction
label | 3a876864-da7b-5a2f-99be-76e5c465212e |  | note | Record - NDM
label | 201c50ee-627f-5e39-9b68-8aecde59755f |  | note | Remarks - Random testing by head contractor
label | b65bfe97-b31d-51b8-a21c-2f4e7c70ec3e |  | note | Control - Supervisor - Monitor
label | 6331fb21-b756-5ac9-9a67-d84776c37f8b |  | note | Control - Head Contractor - Test
label | e9d7ee21-59a1-522d-9132-cc8ac4e4cd0c |  | note | Control - Eng.- Monitor
label | df320e1d-0e79-5ff1-a134-58da97b52283 |  | note | Control - Lab- Test
checkpoint-status |  |  | checkpoint | Core Testing
label | 0e566d17-72a9-5df9-8ef6-4d693074b07a |  | note | Specification / Procedure - Core drilling by accredited lab / four cores per lot
label | 09166498-9476-505f-9c4a-5fa4cdcd21a3 |  | note | Record - Lab Results
label | d6535f33-8a8e-5e3c-89b0-ba2a3e758b1b |  | note | Control - Head Contractor - Holdpoint
label | 2934cd2b-4034-5b3b-a172-cd9817a0f6d3 |  | note | Control - Eng.- Holdpoint
label | 19a0f9e2-feff-5bee-895c-dfb9a29d8c92 |  | note | Control - Lab- Test
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Grading and binder
label | 141c80cd-b259-56ad-9965-44c9ce902551 |  | note | Specification / Procedure - Collect samples prior to dispatch. Results to conform to table 3.1 in the NZTA M10
label | 3b39c0cd-4f5a-55d3-868e-6cbe23f76470 |  | note | Record - Attach to Q pack
label | 18f852f5-b0d9-5396-abf9-26eaa931ea32 |  | note | Control - Lab- Test
checklist-flat |  |  | checklist | ITP - Concrete Footpaths and Driveways |  |  |  |  | Yes | ITP - Concrete Footpaths and Driveways | f58e3fdd-6338-422e-9c4b-f7d37e1ca863
checkpoint-status |  |  | checkpoint | 1 - Set out
label | b0ffb6c4-4cbb-5d2d-8c25-aa70a9463d86 |  | note | Activity Task: Construction
label | cd69162d-f392-536c-88d6-8feb966f4af8 |  | note | Acceptance Criteria: As per IFC Drawings
label | 7c6ad268-1e4a-56c1-9496-63024887b960 |  | note | Certifying Documents and Frequency: Every footpath or Driveway
label | 74596d4b-e489-5278-bf37-ae7f7e5a481d |  | note | Supervisor, Foreman or Subcontractor: As built Records
label | 6d0f56fe-142e-561a-9bd3-a17bce419622 |  | note | Project Manager or Delegated Person: W
label | 6ffc688e-1b2c-5634-b3b4-14d9c1842c59 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | b82dde65-0c12-5858-b168-d36fd4d6ea3d |  | note | Activity Task: Construction
label | afeedd07-2bf9-5042-9d46-162278df18c1 |  | note | Acceptance Criteria: Verify subgrade is a minimum CBR 7. If not Undercut 100mm and backfill with 100mm of GAP40
label | 359eaa15-22f5-59d1-b0fd-31598149f36a |  | note | Certifying Documents and Frequency: Every footpath or Driveway
label | 5fbb6d9b-61dd-5ea5-a56b-c92f20b29e9e |  | note | Supervisor, Foreman or Subcontractor: As built Records Photos
label | c53517bf-78d7-5293-b91c-5d291abad6d2 |  | note | Project Manager or Delegated Person: P
label | 195354af-ab3e-5b21-bfc9-8315d8fe9755 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | 3 - Basecourse
label | 8eb99bd4-c8a0-5286-9478-1d6d5a6968b3 |  | note | Activity Task: Material Supply
label | fcb94141-3841-591c-8f64-fd3314084bfd |  | note | Acceptance Criteria: GAP 40 and GAP 20
label | 3a63e904-fca8-512a-b813-ae17d07a61e0 |  | note | Certifying Documents and Frequency: Every footpath or Driveway
label | 19a180f0-ade3-5da1-a5d6-0466c6fcc544 |  | note | Supervisor, Foreman or Subcontractor: Delivery dockets
label | a10c8d33-7c07-5188-a139-290229895faa |  | note | Project Manager or Delegated Person: W
label | 6801db3c-c278-5ef6-b0bd-9803b1da44f7 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | -
label | 6e755bfd-917e-51f9-8839-09a1f8a08535 |  | note | Activity Task: Testing
label | 80a1672a-e92b-5ad7-9659-4ffe8eafa81e |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6 Crushing resistance to NZS 4407:1991 Test 3.10. Weathering quality to NZS 4407:1991 Test 3.1.1
label | e61191ce-be80-5ffb-8041-0ebc699bc2a4 |  | note | Certifying Documents and Frequency: Every footpath or Driveway
label | 7401ad75-1cb5-57b5-b429-151a6ac7a604 |  | note | Supervisor, Foreman or Subcontractor: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | b075b3b0-6144-56ad-a628-8f5e12d69d42 |  | note | Project Manager or Delegated Person:
label | 9678d0cb-e5d3-5473-8cdd-666f15b48f8a |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Compaction
label | f2e30570-50ee-5624-ae2d-fcf02cda8bc5 |  | note | Activity Task: Construction
label | 51950d79-6277-5953-9eb4-d2debcb6f8de |  | note | Acceptance Criteria: Compaction to be CBR 15 or Clegg equivalent (CIV 12)
label | 55875785-a63f-5403-b3ab-6c967e787252 |  | note | Certifying Documents and Frequency: Every footpath or Driveway
label | bc2cb81c-c06e-55a4-912d-02a93d67dfe6 |  | note | Supervisor, Foreman or Subcontractor: As per KDC Engineering Specifications
label | 783f9f91-cda9-54a3-b7ba-cda6d8fb85c9 |  | note | Project Manager or Delegated Person: W
label | 2b04812a-7d92-57de-b831-1c0b59ed03b2 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | 5 - Reinforcing Steel
label | d8bab6a4-2d1e-5320-8e28-1080d019475e |  | note | Activity Task: Material Supply
label | 3bcf1c0c-4a04-51fc-93c7-e97795682901 |  | note | Acceptance Criteria: Certification from Manufacturer that materials comply with AS/NZS 4671: 2019, Grades shall be as indicated on the drawings
label | 53bd0c28-2996-59fb-b1bc-1cd8f00ea455 |  | note | Certifying Documents and Frequency: All materials delivered to site
label | fe1d0a5e-f442-5d6c-ba35-e385245c4155 |  | note | Supervisor, Foreman or Subcontractor: Delivery dockets – with payment claim
label | f8e29a46-c2df-5327-8c96-f37d648d15bd |  | note | Project Manager or Delegated Person: W
label | d7e7805c-1c7d-506c-8143-ea418ad4e6e1 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | 6 - Concrete Footpaths, Cycleways & vehicle crossings
label | 9428f20c-30d8-5a46-a72b-44051971d220 |  | note | Activity Task: Concrete Material Supply
label | 9f08b1b2-524f-5887-bc65-ad72a9b3c4a3 |  | note | Acceptance Criteria: Written statement from supplier confirming compliance with specification. Compressive strength test report from Lab
label | 4f577020-b71f-57ef-938f-65adae5637f4 |  | note | Certifying Documents and Frequency: 1 statement per batch per material type supplied to site. Compressive strength report for every batch per material type
label | d383f5c6-ddb0-5b45-8136-a979aef554b8 |  | note | Supervisor, Foreman or Subcontractor: Delivery dockets – with payment claim
label | d5353433-863c-51d9-a580-0c9c7b4f2be3 |  | note | Project Manager or Delegated Person: W
label | 0e930cb3-32a6-556c-a7d5-84d8db0e0fa0 |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | -
label | db39cca3-b568-5161-9a06-dfc9abfef432 |  | note | Activity Task: Concrete Material Supply
label | ec9f8854-f941-58f5-b3b8-f3a9ee6fcf52 |  | note | Acceptance Criteria: Batch certificate with date and time of manufacture and concrete strength (MPa) confirming compliance with the specification.
label | 5dc600b3-32aa-5af4-84f3-e5f7eb482c8f |  | note | Certifying Documents and Frequency: 1 statement per batch delivered to site
label | f9ab0a0d-723c-5a84-af87-0a1773c18dde |  | note | Supervisor, Foreman or Subcontractor: Delivery dockets – with payment claim
label | 8070ac85-4b5f-5464-9296-8ea8a86184e0 |  | note | Project Manager or Delegated Person: W
label | 13af3959-3fe0-5b4d-9e48-6424df74b11f |  | note | Engineer’s Representative:
checkpoint-status |  |  | checkpoint | -
label | 72606a6f-4515-534b-bec1-72da51844b7c |  | note | Activity Task: Construction
label | df26fd29-6bd9-5f36-a83b-a7550f8ab28e |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect reinforcement, formwork and cover.
label | 91cb68c3-3f31-5208-b560-859dd00fa287 |  | note | Certifying Documents and Frequency: Every pour prior to delivery of concrete to site
label | 288aeea1-7871-5f99-81be-7887c2a048e7 |  | note | Supervisor, Foreman or Subcontractor: As per drawing and Contract Specifications
label | c9779939-b35a-5967-9f89-00eb52b828f1 |  | note | Project Manager or Delegated Person:
label | b21b9772-cb41-5165-aa3b-82e7dc094c6a |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | -
label | 09273010-001f-573f-8d65-201aed24b8b0 |  | note | Activity Task: Construction
label | 3f820c4d-3172-57a2-9de9-e5ba39ffa8ad |  | note | Acceptance Criteria: Surface to be broom finish Channel levels ± 10 mm from design drawings. No variance on a flat surface greater than 3mm on a 3m straight edge. No concrete works shall retain water, unless otherwise indicated.
label | 86b84445-7fc0-53da-8a93-2f859c25f849 |  | note | Certifying Documents and Frequency: Visual inspection
label | 03561f99-f27e-5040-ba48-0b973c8ad99a |  | note | Supervisor, Foreman or Subcontractor: Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | 26712804-9f69-565b-a6c5-de8d0ed9efd1 |  | note | Project Manager or Delegated Person:
label | a7ab5bbd-d310-549f-a2fe-46aee919b8b1 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7 - As Builts
label | 8f47ab01-901f-5f0f-861c-4677f1c57321 |  | note | Activity Task: As Builts
label | 3cd0e760-221f-5871-b401-97c6902ca76f |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to 1. The subgrade under new pavement areas; 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | 93b3c94c-d42f-516b-9ac6-6fed14203efd |  | note | Certifying Documents and Frequency:
label | 7ee28e23-dd55-5fc1-b77e-404fb01d31c9 |  | note | Supervisor, Foreman or Subcontractor:
label | 230d6eaa-111a-5f41-89f8-9cf12b3071a3 |  | note | Project Manager or Delegated Person:
label | 2d763aef-414d-5051-833c-0b3c62fdaf8a |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checklist-flat |  |  | checklist | ITP - Pavement Detail 'Carpark Areas' | itp |  |  |  | Yes | ITP - Pavement Detail 'Carpark Areas' | f9ae365c-e622-4873-8336-ce2390496d65
checkpoint-status |  |  | checkpoint | 1 - Existing Pavement Service Location
label | 71ff59ae-c2f1-4aae-b94d-ee86f96ef273 |  | note | Activity Task: Construction Potholing of Existing Services
label | 3ed325bc-8212-40d6-a672-835bacb1fa26 |  | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area. Excavation of services to be carried out in accordance with service providers recommendations.
label | 47df6d19-93b9-44c1-9ee6-d858ce6ad148 |  | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction. Pothole records to be kept in spreadsheet form and provided when required. All potholes to be photographed and information picked up by surveyor (information to be supplied northing / easting and RL level).
label | 0b723a3f-7ed4-4324-a48e-2fca76a58dde |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2 - Subgrade
label | 0367d84c-3a13-48e9-b5f1-7f1f2902b795 |  | note | Activity Task: Construction
label | 9b2c99ab-8d21-43f7-b50a-692657f92090 |  | note | Acceptance Criteria: Subgrade levels captured with GPS
label | 2074d9dc-57f0-4764-af39-ede56eb7c37c |  | note | Certifying Documents and Frequency: Asbuilt report
label | 641c45d0-6cdb-433b-aafc-43e1fc9fbe13 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 3 - Subgrade/Dig outs
label | 6e621aa9-dc69-430b-8e71-d69d2fa5d6d2 |  | note | Activity Task: Construction/Test
label | 797bed12-4bca-4199-9e56-412f8aa71965 |  | note | Acceptance Criteria: Check insitu subgrade of Min CBR 5. If not undercut to 200mm and use GAP65 as imported subgrade. Inspection Check sheet
label | 05ae3b54-995c-4285-97cd-0824c74a87ee |  | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala test sheet
label | daa2f148-8d03-4917-b732-e5179a8b5773 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4 - Proof Roll
label | 51e6e2ef-df2c-4898-b5cf-4159b150dba0 |  | note | Activity Task: Construction
label | b03ee309-21b6-4dec-b1ac-71ec1cb822e2 |  | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
label | c23fae0d-428a-4c1c-99a9-9658bbb29b4e |  | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
checkpoint-status |  |  | checkpoint | 5 - Subsoils
label | 3e93fcef-caaf-426c-b1cb-2b69f9666fd4 |  | note | Activity Task: Material supply
label | c9a138d6-a48c-4e9b-a386-a2054349b757 |  | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE.
label | 9950b473-4d68-4ea7-afb9-314532b68296 |  | note | Certifying Documents and Frequency: Compliance certification from supplier. Supplier to provide testing data for filter cloth material
checkpoint-status |  |  | checkpoint | 6 - Subsoils
label | d2dd6ea0-738b-431b-ab1a-dc8ff232bd6a |  | note | Activity Task: Construction
label | bb2c0716-ea99-49bd-af47-b7ec316f0c25 |  | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe. Subsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
label | e62f9733-f0f9-4ed1-aa94-2d68b3171dd3 |  | note | Certifying Documents and Frequency: Photos, Asbuilts and Checklist
checkpoint-status |  |  | checkpoint | 7 - Sub-base aggregate
label | 56268ceb-8b29-4910-ad86-5377ca9c2d1d |  | note | Activity Task: Material Supply
label | af4ff49c-d001-45e8-a2d6-4483335827ac |  | note | Acceptance Criteria: Gap 65. Certifying documentation: Material supply documentation
checkpoint-status |  |  | checkpoint | 9 - Sub-base aggregate
label | 735eaf9d-7498-4e42-bf82-66ae2626be0c |  | note | Activity Task: Test/ Material Supply
label | 6613d89d-9cde-401e-ab3e-885fd8a55013 |  | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
label | facb2a94-798d-4082-8b1a-86e7d5e149f7 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 115958fc-6e5c-4ffa-81ca-aa03a903400a |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 10 - Sub-base aggregate
label | 14fe064e-2124-4392-a83d-e290fb552fcc |  | note | Activity Task: Test/ Material Supply
label | e94c207a-089a-4f6b-aac5-c299f64c4c48 |  | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6 Sand equivalent to meet specification
label | 3463b6bf-60fd-4235-a401-60d7e8439b1d |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | adac4165-be40-4455-a2cf-9fe408500226 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 11 - Sub-base aggregate
label | ee4d15c6-84db-4079-8e3d-ed710b0afff8 |  | note | Activity Task: Test/ Material Supply
label | f93d8840-c086-4ed6-9ccf-3d7b6bc6cd5b |  | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
label | 0ca3a730-6c78-4fff-b792-c6c4f3a9cda2 |  | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
label | 0fd872f6-a7d5-4159-a98a-cac2be5f745d |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 12 - Sub-base aggregate
label | 0f95b97f-69c9-48a2-8d05-97a2d17b3f8a |  | note | Activity Task: Test/ Material Supply
label | 190923ef-1cb7-44b6-83d5-dbab8151602a |  | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
label | 58791f3a-7921-40af-a878-6ad21c05a499 |  | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
label | 9ab565a6-701e-4ee0-b021-13eaa1af3887 |  | note | Supervisor, Foreman or Subcontractor:
label | f8a17b3d-a7d1-4c5a-ae53-83b5614e95f5 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 13 - Sub-base aggregate
label | bcce738b-f8c7-46a2-9507-58920dcd009d |  | note | Activity Task: Construction/Test
label | d3b978e1-656f-42ac-956c-84c8d42956b3 |  | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
label | 64ba3b66-4eaf-4a0e-baba-af1b313526f0 |  | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
label | 585b101b-0bde-446e-9e73-7abe5a7f7034 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 14 - Sub-base
label | 144a2592-0cc4-4988-9628-f52b0b23139c |  | note | Activity Task: Construction
label | c9073676-9795-4fb3-9c5a-b4e542536241 |  | note | Acceptance Criteria: Subbase to be 170mm GAP65
label | 419d6315-ed43-4f84-984a-b230480064fd |  | note | Certifying Documents and Frequency: Photos
label | 2bc74053-156e-4e89-bdb3-4ece42f94c90 |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 15 - Completed Sub-base prior to placement of Basecourse
label | be2bd289-d113-441e-84ef-7f744a15812d |  | note | Activity Task: Test/ Material Supply
label | f8b8cac0-16d1-4781-8f3b-9c90a54b9293 |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | c0a8dc81-cd50-4493-a9c3-218f190dac97 |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
label | bec0bef2-ff7a-4f55-a49d-eddeba665c1b |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 16 - Completed Sub-base prior to placement of Basecourse
label | 7b10d1ce-5bcf-467f-8e0b-70c6a0ed4767 |  | note | Activity Task: Construction
label | 9e8fbd7e-6ed3-49db-98a2-7784017f2e11 |  | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | ab6f1fd8-43e3-446c-99c6-6b96a8750c70 |  | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
label | 0743f744-8007-46d7-8745-dd9ff2a842c7 |  | note | Supervisor, Foreman or Subcontractor: W
checkpoint-status |  |  | checkpoint | 17 - Completed Sub-base prior to placement of Basecourse
label | 4c047be8-a797-4556-8627-523f1e600e65 |  | note | Activity Task: Construction
label | e3ad49d7-f348-48e8-9fed-10cb05527415 |  | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification
label | cc68133a-c0a6-4ea7-8fce-fc204d02a6c5 |  | note | Certifying Documents and Frequency: Visual inspection by Engineer Surface to be as specified. Engineer to be informed when surface is ready for inspection.
label | f5f2c2ba-222d-42db-8241-f1c014a3c466 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 18 - Basecourse
label | 41bf8709-69ff-4fe0-b156-a1d76e1f18fc |  | note | Activity Task: Material Supply
label | 37c08a0e-6c1b-45b6-aec2-407f5d61dc06 |  | note | Acceptance Criteria: Unless otherwise specified all basecourse operations shall be in accordance with TNZ B/2, M/4 and the drawings and specifications.
label | 05f68c02-6ee8-4743-8b7c-117024efef5e |  | note | Certifying Documents and Frequency: Compliance certification to be supplied from sub-contractor
label | 1e1aa370-144b-496f-b001-5f5be8c7b38e |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 19 - Basecourse Cement Supply
label | 06b6bf18-2568-44d8-9b4e-59d7f21bbb6f |  | note | Activity Task: Material Supply
label | d9b0f69a-b658-4c77-ad52-61c7b1cc42ef |  | note | Acceptance Criteria: Application rate to be 2% as specified.
label | aca926c7-9127-46f0-8fb9-f0067aaf0935 |  | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation.
checkpoint-status |  |  | checkpoint | 20 - Basecourse
label | 88cbbcf7-7ce7-4e81-9a2b-5a78c172a31a |  | note | Activity Task: Construction
label | 5b85edf8-e39a-40ce-ba97-78c58406ed60 |  | note | Acceptance Criteria: Basecourse to be 120mm Cement modified M/4 AP40
label | 4c2814b0-4bd3-44af-8ce1-3e21569c2630 |  | note | Certifying Documents and Frequency: Photos
label | e67dcf57-1117-458d-9cec-4897470e6edb |  | note | Supervisor, Foreman or Subcontractor: P
checkpoint-status |  |  | checkpoint | 21 - Basecourse
label | 2b46d7ff-19ca-4af8-8f59-8e9d82350234 |  | note | Activity Task: Testing
label | 2c0b6962-ebff-4c6c-98d3-3bb355bb7cbc |  | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
label | 57271b47-b13b-423a-a9b0-10b0c3aa5bec |  | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
checkpoint-status |  |  | checkpoint | 22 - Basecourse
label | c7ce8365-b7ee-4f8a-942c-694bfc05cc70 |  | note | Activity Task: Straight Edge Checks
label | c804f844-0281-4d12-966c-d1d3a9f41920 |  | note | Acceptance Criteria: No point on the surface shall vary more than 10 mm from a 3m straight edge. No area of the completed surface shall pond water.
label | 257bbb40-c902-487c-9ce9-3c3698b27443 |  | note | Certifying Documents and Frequency: Straight edge checks on surface shape at randomly staggered transverse positions at 20 m intervals throughout.
checkpoint-status |  |  | checkpoint | 23 - Basecourse
label | 608a2d23-d991-4f1b-9d63-161fce457f8c |  | note | Activity Task: String Line checks
label | ad43b60a-193f-4d4b-86f5-a790de271a8a |  | note | Acceptance Criteria: Surface shape matches design and minimum pavement depth provided.
label | ac18cd8b-6471-4439-ac9a-835a561d638f |  | note | Certifying Documents and Frequency: Stringing records, 3 points minimum per cross section.
checkpoint-status |  |  | checkpoint | 24 - Basecourse
label | 4a9adef0-0bdd-45da-8d79-adb8b48dd23b |  | note | Activity Task: Visual Inspection
label | 2b37076c-d287-4c40-bf67-e787332a9c5a |  | note | Acceptance Criteria: Surface to be as specified
label | 7fee6a90-f176-40bb-8b0b-826c2dbc1bb6 |  | note | Certifying Documents and Frequency: Visual inspection by Engineer
label | 0bd38112-f241-435d-8f34-8748654bb4a0 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 25 - Structural Asphalt
label | 7c7761d3-1bdf-4614-96b3-0b67b7dba0eb |  | note | Activity Task: Material Supply
label | 139448a9-743f-4410-b6c4-329f5e70f013 |  | note | Acceptance Criteria: As detailed in AAPA National Asphalt specification and RNZ/TNZ supplement to AAPA National Asphalt Specification
label | b992ba2c-3cd9-44b2-8fe3-270791a0ea9e |  | note | Certifying Documents and Frequency: As detailed in AAPA National Asphalt specification and RNZ/TNZ supplement to AAPA National Asphalt Specification Refer to Subcontractors QA in Separate ITP
label | cab9aaa8-7db4-4d0f-9d14-e67e02438cba |  | note | Supervisor, Foreman or Subcontractor:
label | 1dec9367-e089-4c11-915c-a10dbcbeda13 |  | note | Project Manager or Delegated Person: W
checkpoint-status |  |  | checkpoint | 26 - Structural Asphalt
label | 50cb4109-574c-4bdc-99d8-cc60b12a1ebf |  | note | Activity Task: Construction
label | 43139a1f-87a9-4204-844a-0c2f793b7c4a |  | note | Acceptance Criteria: Method of determining density location tests
label | e1812e90-01b9-430f-b63d-d6d32c5f0f32 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
label | ec5a5dec-16b3-4ebc-918b-7e2ea30f5a2b |  | note | Engineer’s Representative: H
holdpoint |  | Data not allowed on signoff: Activity Task: Material supply(8771a0b6-bb13-4a6e-84fd-b97691dfa545), Acceptance Criteria: Method of determining density location tests(1244048c-c713-4b16-bfd5-5130a326c833), Certifying Documents and Frequency: Prior to placement of Structural Asphalt. Refer to Subcontractors QA in Separate ITP(fb2dff0b-412f-418d-8200-ac3ec7a95328), Supervisor, Foreman or Subcontractor:(e71a316e-ba87-4410-82d3-0a82e8e444a5), Project Manager or Delegated Person:(0ac9bf80-c224-47f1-8ee8-bce0cabae8d2), Engineer’s Representative: H(c9dd98ae-65c6-4f7a-8266-c8113c4f6edc) Multiple signoffs are not allowed | signoff | HOLD POINT AUTHORITY
holdpoint |  | Multiple signoffs are not allowed | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 28 - Asphaltic Concrete
label | aed26efb-6f5a-4888-b435-90c181a63fd8 |  | note | Activity Task: Material supply
label | f4049d87-f9ed-4b09-bba8-273f31721554 |  | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
label | 028cf243-5deb-464a-afad-ee36314f3630 |  | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification` Refer to Subcontractors QA in Separate ITP
label | ee15001b-acf6-48b3-9d1f-7f611476f152 |  | note | Project Manager or Delegated Person: R
checkpoint-status |  |  | checkpoint | 29 - Asphaltic Concrete
label | 9afae1e8-fd8c-44f8-815d-6a1cde5b5c7d |  | note | Activity Task: Construction
label | f883dc7a-46df-4556-ba22-a05f6cb0b35d |  | note | Acceptance Criteria: Membrane seal and 40mm AC 10 Method of determining density location tests
label | f4682efe-78b0-418c-a526-7e1aad84258e |  | note | Certifying Documents and Frequency: Prior to placement of Asphaltic Concrete Refer to Subcontractors QA in Separate ITP
label | f0d77bde-1718-49c4-9eff-4f9d4226a1ed |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 30 - As -Builts
label | 52ccdad7-4ced-4c22-8c43-06aa6cf95ec0 |  | note | Activity Task: As -Builts
label | bda37497-c92d-4c7a-9fbb-2454ffc84380 |  | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
label | ac7edf7a-6481-4742-8e13-df51e9cb9b5a |  | note | 1. The subgrade under new pavement areas;
label | 7dd129d6-f80f-499d-ab10-a4ec58883692 |  | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
label | f70e39cd-ce35-4c72-8a15-45e6389ef7c1 |  | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
label | 011548d2-a137-41ca-acdf-e3ef8741fd94 |  | note | Engineer’s Representative: H
holdpoint |  |  | signoff | HOLD POINT AUTHORITY