## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - SEPARABLE PORTION 2 | itp |  |  |  | Yes | ITP - SEPARABLE PORTION 2 | 134768c5-2b1d-489d-8e41-869e63ac0381
checkpoint-group |  |  | section | BRIDGE ANCILLARY ITEMS
checkpoint-status |  |  | checkpoint | 4.1 - Barrier Rail Fabrication
label | 74d1c066-9303-5a5d-aa26-89afd3bc74c9 |  | note | ITEM: Barrier Rail Fabrication
label | 76ba7c4c-c802-58a6-b6ee-aa12e85118df |  | note | ACTIVITY TASK: Barrier rail fabrication.
label | 5fff8b74-faca-5470-8393-ea604fceb996 |  | note | ACCEPTANCE CRITERIA: Barrier rails match drawings and comply with NZTA M/23 and TNZ M/17P. Construction of the new barrier is not to proceed before the set out has been checked and approved by the Engineer.
label | b609139a-2371-545f-a527-efc79d5d49da |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
label | e0e0886d-f47a-511d-aa22-d534d8f247bc |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4.2 - New Handrail
label | 4be3ce03-e5ea-5768-ba10-8633d49dd8a0 |  | note | ITEM: New Handrail
label | 8f2a58b7-3150-5baa-b266-05220f47e45a |  | note | ACTIVITY TASK: Prior to the installation of the new handrail.
label | df701863-97e7-5292-9ca6-d2dff6e52365 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | c0bedbbe-0304-5713-b195-503248f3f897 |  | note | FREQUENCY: Prior to the installation of the new handrail.
label | aa9225e2-792d-53fe-a30e-1b94b1dad124 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 0a1aebf4-9b5a-535e-bc76-b8e4136ece23 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | DRAINAGE AND SERVICES
checkpoint-status |  |  | checkpoint | 4.1 - Barrier Rail Fabrication
label | 17cc88ee-91a4-5fdb-ba2c-b640c6f74426 |  | note | ITEM: Barrier Rail Fabrication
label | fae79acc-bea7-5942-a99f-d57c97fd0779 |  | note | ACTIVITY TASK: Barrier rail fabrication.
label | 2f3c8bf8-1f3b-575e-810e-aa5b737e5bc9 |  | note | ACCEPTANCE CRITERIA: Barrier rails match drawings and comply with NZTA M/23 and TNZ M/17P. Construction of the new barrier is not to proceed before the set out has been checked and approved by the Engineer.
label | 6a526088-5dd1-5f76-bbca-98da55b2f2d2 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
label | 7daa8d66-412f-5b72-a05b-065b5dae878a |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4.2 - New Handrail
label | d59ae0d2-ff3c-54d4-8cf7-db3d5b3b2052 |  | note | ITEM: New Handrail
label | b944fe58-aeba-589a-b5cc-327135ab05ec |  | note | ACTIVITY TASK: Prior to the installation of the new handrail.
label | 55b00857-bb99-5ead-aaea-6aeae7676417 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | f01b0d5f-0609-5fb0-981d-94865c2f253e |  | note | FREQUENCY: Prior to the installation of the new handrail.
label | 777ae38f-4491-59e7-b8ef-7358db56e6c2 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 004bff4a-45cb-5eaf-8882-7970b2e54849 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | DRAINAGE AND SERVICES
checkpoint-status |  |  | checkpoint | 5.1 - Contractor Construction Methodology
label | 0987996d-3861-5d87-8f76-ea5bcbdffceb |  | note | ITEM: Contractor Construction Methodology
label | 13e8210f-51c3-5b11-a23a-52bd54827803 |  | note | ACTIVITY TASK: Contractor construction methodology required for installing services.
label | f548caaf-8a40-5a97-a027-b068f0d362f3 |  | note | ACCEPTANCE CRITERIA: Signoff by Engineer.
label | ab4f9344-8b99-597c-960c-f9c1d81042d2 |  | note | FREQUENCY: Methodology provided to Engineer for review at least 14 days prior to the commencement of the specific works.
label | b0130b75-58dc-5e12-96a1-74e46d0348fa |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Methodology submitted and approved. Signoff by Engineer.
label | af89ddf0-7e30-56dc-8a70-cdc391c6f2b3 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.2 - Temporary Service Relocations
label | c01dc4f1-5e1e-5ff4-a105-9194ea92bfb7 |  | note | ITEM: Temporary Service Relocations
label | 49dde963-c21a-5e64-8a04-d5b9fae2b4e2 |  | note | ACTIVITY TASK: Set out of temporary service relocations.
label | c5d75e08-34cc-514c-9abb-9b85f69f2ed9 |  | note | ACCEPTANCE CRITERIA: Service authorities agree to relocation positions. Relocated positions do not clash with other services or proposed works. visual inspection and acceptance by Engineer.
label | 4d445b76-13bf-5877-964f-27a427f6c186 |  | note | FREQUENCY: Prior to commencing any service relocation.
label | 387438f3-3775-5f89-bae0-4d98f148342d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 7a2d2738-4eca-59e2-a972-951ac62b8ff8 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.3 - Granular Backfill
label | 518e0f01-a27f-596a-8e62-089bcfe95057 |  | note | ITEM: Granular Backfill
label | df7fb9f9-f41d-57a7-aa4f-dabb7ed10315 |  | note | ACTIVITY TASK: Prior to backfilling to any part of the abutment or any abutment drainage. (Note: Existing drainage to systems behind abutments shall be protected during backfilling operations).
label | e90fee53-4bb0-5202-9ed9-f428407060af |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | d2a2200a-48fe-54f9-94f8-731b033a588d |  | note | FREQUENCY: Prior to backfilling.
label | ca702cee-a2d7-5413-b23c-d370b199d3ed |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
label | 3ef7e601-70fe-58a1-a7c2-ba9c2ece858e |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | EARTHWORKS AND PAVEMENTS
checkpoint-status |  |  | checkpoint | 1.7 - Confirmation of Ground Conditions
label | 1e26d49f-976c-55ae-a867-dddac977c479 |  | note | ITEM: Confirmation of Ground Conditions
label | e58e063d-9b07-5e74-9895-8aae686638a8 |  | note | ACTIVITY TASK: Confirmation of ground conditions.
label | d539eb6c-0e52-5a3d-bd5f-8682fa605082 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | ff4f3608-a068-545a-8cac-1daf16f021a2 |  | note | FREQUENCY: After excavation and prior to any construction, installation or backfilling.
label | fc14342d-6a06-5318-bea4-0376f91b85e1 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 93820de2-d070-5061-b536-e8557164d892 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.1 - Granular Backfill
label | adf5765b-e68f-51be-8397-16f913f8779b |  | note | ITEM: Granular Backfill
label | 5017eaa5-0b8c-5e6f-9a19-8bd0b71f514a |  | note | ACTIVITY TASK: Test sample to be used to determine maximum dry density and optimum moisture content (NZS 4402:1986 Test 2.8.2).
label | e26fdc9e-6960-5ffa-98f6-8ed5f3dcb9ff |  | note | ACCEPTANCE CRITERIA: Acceptance by Engineer.
label | 9c06ecd9-0cf1-59bd-80e5-15a40e9c884d |  | note | FREQUENCY: Prior to commencement of works.
label | 8075708d-1c35-504a-a212-3a170c53bca4 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
label | 0e2ecdce-7c3d-525f-8981-cd6030d52619 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.2 - Pavement Works
label | b3a3d328-732d-5a4b-bc8b-84d66d231936 |  | note | ITEM: Pavement Works
label | c23b67b8-8023-5825-bc01-567be782da77 |  | note | ACTIVITY TASK: Set out extent of pavement works.
label | 67d8644b-3fd6-5bcf-b67b-5b9346855f35 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | baa868c0-9ccb-5296-b16c-43a85657874f |  | note | FREQUENCY: Prior to commencing any pavement works.
label | ecdd6f00-49f7-53c1-a401-cff90e873713 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | faf8217e-8a7a-55b9-8ec1-cfbe38595c9e |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.3 - Surfacing Works
label | 76041a15-f465-5feb-94b7-92fcd5ff2747 |  | note | ITEM: Surfacing Works
label | 5dc397e8-ea38-58dc-a8b1-5079e3599049 |  | note | ACTIVITY TASK: Set out extent of surfacing works.
label | 4b6e3a2a-546f-56c9-aff9-2dae3ef723a7 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | d0014ace-873e-53c9-bcbb-c0870cd5cc7c |  | note | FREQUENCY: Prior to commencing any surfacing works.
label | 9764fd1e-9871-5c4c-871d-9fc03a729c59 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 63a64a04-2818-5394-bd64-9046722bc914 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.5 - Existing Pavement Depths
label | 18d513b3-9b0f-5994-b463-f3e8f6cf14c9 |  | note | ITEM: Existing Pavement Depths
label | ea5bfcaa-1ca0-57af-98cb-53f9313732d1 |  | note | ACTIVITY TASK: Visual inspection during shoulder checkout works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area (Clause 23.8 of specification).
label | 75111075-7dab-52e5-a1ea-05f470120ddd |  | note | ACCEPTANCE CRITERIA: Observations provided to Engineer immediately.
label | 73511b53-027c-5ab8-a952-b362d2ee8ed3 |  | note | FREQUENCY: At 25m intervals.
label | 9ce09cc9-fec0-57f2-9450-00ce94f391ae |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. Record.
checkpoint-status |  |  | checkpoint | 6.6 - Existing Subgrade Strength
label | c4c5d3a2-216a-5838-87ff-aaf6cc76f2aa |  | note | ITEM: Existing Subgrade Strength
label | 737f03d4-01e3-5005-933c-c06d98a67b4d |  | note | ACTIVITY TASK: Scala CBR equivalent tests. Three minimum per exposed area.
label | 903d4847-40e3-5e22-bebe-8655c97451f1 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | f3d87246-4f11-5bc1-b0e8-b5706c08c532 |  | note | FREQUENCY: Three minimum per exposed area.
label | 66afc18a-d48e-5611-be10-c8c72bba0435 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Results of Scala CBR equivalent tests.
checkpoint-status |  |  | checkpoint | 6.7 - Benkelman Beam Deflections - Subgrade
label | 83fff387-fb82-52a5-9d25-c48ca0baa366 |  | note | ITEM: Benkelman Beam Deflections - Subgrade
label | 0f08e3f7-5669-5969-83aa-a15eb09692d2 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the subgrade.
label | 437e2427-8a84-5816-a86d-03a21085fbcf |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | 5db6533e-db56-5df4-8ed6-b42d83750c69 |  | note | FREQUENCY: At the completion of each layer.
label | d7f35136-d256-5af1-a8cf-bc3a9ba1d5bf |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Modified Subgrade
label | b88f7ca0-bdec-56e1-894b-6b66d2db87af |  | note | ITEM: Benkelman Beam Deflections - Modified Subgrade
label | 26bf0214-4fe7-5d32-a67d-530e7e9507b7 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the modified subgrade.
label | bd4fe463-bee6-5bb3-89dd-7559313a6a29 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | b5ec8007-0d91-5e97-a024-72e73ec6c5b5 |  | note | FREQUENCY: At the completion of each layer.
label | 8ad00f91-39b8-564a-ba59-61025bebb18a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Subbase
label | 5d64ac06-f1c3-538d-8e79-f29cafa5a64a |  | note | ITEM: Benkelman Beam Deflections - Subbase
label | d3692033-dddc-5f15-806c-8098781aa19f |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the subbase.
label | 57ba0e2b-d1c0-5079-91d1-e7549e813c27 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | d1569b22-6fef-5b10-864e-bcc68acdcef8 |  | note | FREQUENCY: At the completion of each layer.
label | 58d9d853-5296-5619-bb9d-730ce981290b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Basecourse
label | aa9f6353-64c3-56fb-8d30-ac3e02a0f84d |  | note | ITEM: Benkelman Beam Deflections - Basecourse
label | ed26b9cc-7d0a-5eaf-b9dc-60b80af417db |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the basecourse.
label | 0c1f3e1f-e46a-5fd0-b1bb-9ed1b994812f |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | 8ea64400-5cf9-5ff0-b3db-a986852d290f |  | note | FREQUENCY: At the completion of each layer.
label | fca88490-d98b-502d-83ce-75ee335449e9 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Waering Course
label | efa6ff9b-be93-5173-8b22-7fd2600e6827 |  | note | ITEM: Benkelman Beam Deflections - Waering Course
label | 96e7e4a0-6243-5efd-991c-4b44405e0d87 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the wearing course.
label | f9f2c8ff-3abc-57a5-9fa8-e0cbe366ce40 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | 69d15a6e-33a6-5457-845d-0e7c0a95ad70 |  | note | FREQUENCY: At the completion of each layer.
label | fd7a2a74-d990-503c-92a6-b6cc870d2a8d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 6.8 - Subbase and Basecourse Aggregate – Proportion of Broken Faces
label | c2414faf-4cbf-58f2-a2de-5bbf43400294 |  | note | ITEM: Subbase and Basecourse Aggregate – Proportion of Broken Faces
label | 2277668f-40db-5c73-abb4-23ea979c5a8d |  | note | ACTIVITY TASK: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407:1991 Test 3.14 no less than 70%.
label | faec6371-aaa4-57db-a7e7-599ac971fd53 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 4d4cea4d-5440-540d-8f59-cb4352296bb8 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | 3f5812b1-f270-5aee-b02b-68fdc765b735 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test results.
checkpoint-status |  |  | checkpoint | 6.9 - Subbase and Basecourse Aggregate – Sand Equivalent
label | b6ada5a1-c74c-5db2-90c0-20e9494a54b2 |  | note | ITEM: Subbase and Basecourse Aggregate – Sand Equivalent
label | d2dec7d6-9b3f-545f-9f26-3532067e3dd7 |  | note | ACTIVITY TASK: Sand equivalent to NZS 4407:1991 Test 3.6. Sand equivalent to meet specification.
label | 579ffa4f-ca48-5bc3-ba2e-f427d5122271 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 2ac94ba3-311d-56dc-a7c2-c62fdd1f8b36 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | 0d160a30-66eb-5e96-886c-7ea030fb7391 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.1 - Subbase and Basecourse Aggregate – Crushing Resistance
label | 819cd294-7e32-5cda-b80a-f1793bff68d7 |  | note | ITEM: Subbase and Basecourse Aggregate – Crushing Resistance
label | 3f9021f3-5577-5cbd-8c8d-5ebc53550625 |  | note | ACTIVITY TASK: Crushing Resistance to NZS 4407:1991 Test 3.10
label | c2ac6223-be95-52a9-a5de-01adcec044d1 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | de4492f3-2ff8-563d-b6ae-cfd151405eb2 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | 10c8c509-41ab-525c-bb78-bce54658b6d1 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.11 - Subbase and Basecourse Aggregate – Weathering Quality
label | 6f10751c-72fb-507b-9a95-5f358cf41dbe |  | note | ITEM: Subbase and Basecourse Aggregate – Weathering Quality
label | 6ae43969-523d-5a4f-928e-eb3920f79e91 |  | note | ACTIVITY TASK: Weathering quality to NZS 4407:1991 Test 3.1.1
label | ab915f06-5694-5a55-9c05-89b22e5689a0 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 8fc2758d-d14d-552c-ba57-d6777e717505 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | c22715dc-49e7-5f22-97d9-291390d03c2d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.12 - Subbase and Basecourse Aggregate – Maximum Dry Density (Laboratory)
label | 7815a5eb-775d-5a66-9ca3-c102cef9d424 |  | note | ITEM: Subbase and Basecourse Aggregate – Maximum Dry Density (Laboratory)
label | 9b958391-d95d-520e-b4e1-821cfa11e940 |  | note | ACTIVITY TASK: Maximum laboratory dry density (MDD) of aggregate at optimum moisture content (OMC) to NZS 4402:1986 Test 4.1.3
label | cca24b08-9d20-53b6-a80e-bc0429c4c19e |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 327dfe61-3cd3-5c75-841d-7337863ce2ac |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | 5023613d-f5e2-590a-9632-f951cd125556 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.13 - Completed Subbase – Nuclear Densometer
label | 0544a5e5-6b8c-5f9a-8abc-9b8f35213e90 |  | note | ITEM: Completed Subbase – Nuclear Densometer
label | 791a7622-a58c-5f5b-ac41-9b5711a776d7 |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20m intervals throughout.
label | c76511ec-985c-5c4e-abf2-daa5a432e152 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement of basecourse.
label | a3fd532e-c628-57a6-b2bf-56cb873c93ae |  | note | FREQUENCY: Prior to placement of basecourse. Mean value of density tests shall not be less than 95% of MDD. No individual test less than 92% of MDD.
label | 0e5d37c4-c6a9-5a72-959d-fcf59ba70c0f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: MDD results.
checkpoint-status |  |  | checkpoint | 6.14 - Completed Subbase – Straight Edge
label | 624b129d-dc24-5720-8024-a0d8ca21b18d |  | note | ITEM: Completed Subbase – Straight Edge
label | 2ef20620-29b4-50cc-9ca5-8b6e47a241e8 |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | 9b455d8a-4e52-53c3-a404-c475670e2f31 |  | note | ACCEPTANCE CRITERIA: No point on the surface shall vary more than 10mm from a 3m straight edge. No ponding of water. Provided to Engineer prior to placement of basecourse.
label | 381e4e7a-7fc9-5aab-a486-9296510912aa |  | note | FREQUENCY: Prior to placement of basecourse. Randomly staggered transverse positions at 20m intervals throughout.
label | e663f405-2d1c-5059-b706-3a884ce836d7 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.15 - Completed Subbase – Finished Level
label | c6cea075-de2f-5baa-b16f-de9cb8e43aac |  | note | ITEM: Completed Subbase – Finished Level
label | d02319db-b1bf-5f5e-a925-c11e77ae9cea |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Provide a sound finished surface to line and level as per specification.
label | 62c59ce3-feaf-5c74-b56c-2fbc0ec8bf49 |  | note | ACCEPTANCE CRITERIA: Visual inspection by Engineer.
label | 0ea93428-2a14-5547-88f7-56fd0cbbc585 |  | note | FREQUENCY: Prior to placement of basecourse.
label | 80243e0b-0d45-51a9-9f7d-fe9d09c8228b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.16 - Completed Basecourse – Nuclear Densometer
label | fd665ed6-517a-5d0f-aab3-1d15a74017a9 |  | note | ITEM: Completed Basecourse – Nuclear Densometer
label | 03577945-a6f5-59ee-8e45-7ff2faa2e1cc |  | note | ACTIVITY TASK: Completed basecourse prior to placement of surfacing. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20m intervals throughout.
label | a5641628-5e60-53c4-8b62-c2cab1078a7f |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement of surfacing.
label | 07f1b9e2-1a1c-5703-b01c-ee488907340d |  | note | FREQUENCY: Prior to placement of surfacing.
label | 8b3e1d92-4bac-5e8b-8084-86e78c915e90 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.17 - Completed Basecourse – Finished Level
label | 74fc1758-5a99-5bc6-9633-57e3e6b71f73 |  | note | ITEM: Completed Basecourse – Finished Level
label | 820c9d8c-8dca-5410-b05b-7ca23d39748a |  | note | ACTIVITY TASK: Provide a sound finished surface to line and level as per specification.
label | ad686eae-806d-5594-9ee9-c69093ff7f59 |  | note | ACCEPTANCE CRITERIA: Visual inspection by Engineer.
label | d990c38f-fa7e-5732-9d41-53cc96b2f614 |  | note | FREQUENCY: Prior to placement of surfacing.
label | 54f89569-5186-5b9c-92d0-1684bf63a92b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.18 - Prior to Surfacing
label | 97fd0d0b-9da5-5afe-bb33-a55dcc0a446a |  | note | ITEM: Prior to Surfacing
label | d8d9b35d-6fe4-53bf-98ea-1e645c93c7b4 |  | note | ACTIVITY TASK: Prior to surfacing.
label | 7640c8db-a46a-5110-aea9-e133c5f73ba9 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 21246a5e-1503-5cef-adeb-d8466b599b47 |  | note | FREQUENCY: Prior to surfacing.
label | 429ff284-e192-5d11-846e-1fcf34fcb862 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 9adbe2df-07b8-5393-aba4-dd676466ef89 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.19 - Sealing Binder
label | 63117508-a0ae-5b96-80a7-3cfe1fc500b7 |  | note | ITEM: Sealing Binder
label | ed913f4f-1eb6-532b-b935-b7ade3e18877 |  | note | ACTIVITY TASK: Shall comply with NZTA M1 and TNZ M13
label | 683e5763-e9fb-582b-818e-b50eecd1521f |  | note | ACCEPTANCE CRITERIA: Provide to Engineer on request.
label | d302e6dd-7dbf-5c50-97b4-c2acfe64a20d |  | note | FREQUENCY: Upon completion.
label | bfddb272-1679-599f-85c6-4afe1273e616 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier QA documentation.
checkpoint-status |  |  | checkpoint | 6.2 - Asphaltic Concrete
label | bfebf32d-a99a-5e2f-86a5-7a27d2974e8a |  | note | ITEM: Asphaltic Concrete
label | c5913076-2c10-597a-b8e0-7d599c52b390 |  | note | ACTIVITY TASK: As detailed in NZTA M10. Method of determining density location tests.
label | 5fbb5ca1-a4c4-5d4e-b2e4-59071a6df1e1 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to the placement of asphaltic concrete.
label | 9fa2a4fb-b479-558e-ada1-436c25109d5b |  | note | FREQUENCY: Prior to the placement of asphaltic concrete.
label | 4325e691-cbc2-5bd8-aa49-bb81ac04622a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier dockets/certificates.
checkpoint-group |  |  | section | OFF BRIDGE CONCRETE
checkpoint-status |  |  | checkpoint | 7.1 - Concrete Mix Design
label | 4040a0f4-b033-5643-97ff-1d2df9db70ce |  | note | ITEM: Concrete Mix Design
label | 82c1cf04-ec9c-5221-b3d7-3cc654d66fe6 |  | note | ACTIVITY TASK: Concrete mix design required for footpaths.
label | 332d1fdb-e4b0-5442-bc41-7114df341efd |  | note | ACCEPTANCE CRITERIA: Signoff by Engineer.
label | af7f9416-6301-5b42-940d-c08d4c06b784 |  | note | FREQUENCY: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 22adb12f-92e8-5402-8e72-c652ba65a9c7 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Concrete mix designs.
label | 1c48188a-7c8e-5f62-8986-3b89e83cb1ed |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.2 - Reinforcing
label | b15f6d0a-f50d-5ea5-ad61-c43a7fd40d43 |  | note | ITEM: Reinforcing
label | e5220af9-be1b-5320-a622-de433fa800b3 |  | note | ACTIVITY TASK: All reinforcing prior to concrete pours, including pre-fabricated elements.
label | b03307f7-a032-56db-be8c-93babf6fb47c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | daf61545-c9ff-5a5e-95eb-591804bdb9f6 |  | note | FREQUENCY: Prior to pouring concrete.
label | 7b50f5dc-8c2d-56fb-9c13-6661bf5f78c9 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 7bf37093-365e-5185-bf3e-d6f6af6a7f6d |  | note | WITNESS POINT
checkpoint-status |  |  | checkpoint | 7.3 - Formwork
label | 004165d6-0e04-5100-9f78-c3a8ef3ca045 |  | note | ITEM: Formwork
label | f9ee18f2-038c-5f63-9884-7f652491fbc0 |  | note | ACTIVITY TASK: All formwork prior to placement of reinforcing and/or concrete.
label | c92f84e9-90ae-5d59-9532-19442a822126 |  | note | ACCEPTANCE CRITERIA: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | ae13a570-4976-5193-8ff0-e9fb8dd09703 |  | note | FREQUENCY: Prior to placement of reinforcing and/or concrete.
label | f8c521db-8306-5ff3-8bdd-9527c70cdc1a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 6d47ede0-4689-5dd2-b7dd-2fa0b23592f4 |  | note | WITNESS POINT
checkpoint-status |  |  | checkpoint | 7.4 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | 397e62f3-48bd-574e-880a-0165040ef610 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 2bd76490-646f-5a28-9d6e-da6bc3f92e5a |  | note | ACTIVITY TASK: Compliance with NZS 3116 Bedding Sand.
label | be521cbf-517d-56bc-b1ea-a872843b2b87 |  | note | ACCEPTANCE CRITERIA: Meets specification.
label | 6c51eba3-dc34-56e8-9db9-9359e01e5a80 |  | note | FREQUENCY: One test per 50m³ of bedding sand supplied to site with a minimum of three tests for the contract works. Provided to Engineer with payment claim.
label | 15d6c9a9-6262-575f-a7e5-8d6805a4e7c1 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 7.5 - Footpath and Kerb Works
label | 630ad0c2-4538-543c-948b-0aaff453a317 |  | note | ITEM: Footpath and Kerb Works
label | a63448f9-4fa0-5701-8be4-1adbe336c1d0 |  | note | ACTIVITY TASK: Set out of footpath and kerb works.
label | 385f549f-c3ed-5b7d-8748-17ade87f2f02 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 1ea9cb83-80fc-5559-acae-a6458f19c96e |  | note | FREQUENCY: Prior to commencing footpath and kerb works.
label | a66b2bf1-8f36-5d88-b21d-5d3ba982294c |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 72e03148-ea5d-5083-a7f9-d2502adecca7 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.6 - Bridge Footpath
label | 82b86a35-327a-574b-bfb5-d6ec49d9f693 |  | note | ITEM: Bridge Footpath
label | 97e8fb4b-bc4d-580f-8f15-38775c14face |  | note | ACTIVITY TASK: Pre pour inspection for the bridge footpath.
label | f7ab871c-20aa-54cb-a876-a5db6967ca3b |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 73ef4444-20f8-53ae-97e3-b774db9d59f7 |  | note | FREQUENCY: Prior to pouring concrete.
label | 6c2beaca-31b3-5ea6-b4c4-2782c674da2f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | bd2224b1-e374-5296-91f6-3c99bfafe462 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | Bridge Kerb and Channel
label | 14353cca-7c93-5222-823c-65139aaa0e11 |  | note | ITEM: Bridge Kerb and Channel
label | 773664a5-9f65-5fd8-8fc9-a46ef21375ae |  | note | ACTIVITY TASK: Pre pour inspection for the bridge kerb and channel.
label | 7798cc40-d1fb-5d24-984a-355ac5a6bbf6 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 68a18950-cbd8-5350-98df-4cdc5b368a51 |  | note | FREQUENCY: Prior to pouring concrete.
label | a7d35caf-e7ec-5d4b-b653-e694372a3fa5 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | 2bd21469-95dd-5a37-9ccf-418686665fd7 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | Bridge Retaining Walls
label | 207a6a8c-edc7-5d92-8d35-da898b2f1a5e |  | note | ITEM: Bridge Retaining Walls
label | 3bc179fa-cf92-5cb4-96b2-1b64d69c256a |  | note | ACTIVITY TASK: Pre pour inspection for the retaining walls.
label | 177590e8-84f4-5ee9-9b94-6f0e157d1cc9 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | b5b650f9-b840-5048-9b46-ca0e6ce565a7 |  | note | FREQUENCY: Prior to pouring concrete.
label | 4b52fc8b-4de2-5aaa-9b9a-b206713fb862 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | 23f5dc07-afef-55ad-8e0f-97438e52b764 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.7 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | 52261d57-0233-5c63-a2d8-81dfdef328b1 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 74832c4a-9499-58d7-ac73-c77d25a49c71 |  | note | ACTIVITY TASK: Alignment to plan. Free draining.
label | 989627af-6578-5eaf-9034-a5fc18009a14 |  | note | ACCEPTANCE CRITERIA: Meets specification.
label | 48901e40-c157-5219-b71d-3e43944be720 |  | note | FREQUENCY: One completed checklist per 100m of footpath or shared path constructed. Provided to Engineer with payment claim.
label | bd7c82aa-9781-55ca-905c-17bcb5d421b1 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Completed checklists.
checkpoint-status |  |  | checkpoint | 7.8 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | 165a46a6-6ce7-50b3-b92b-a0940be02691 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 1960b5f2-c504-54c5-9cb1-f2cc0393e8e1 |  | note | ACTIVITY TASK: Surface to be broom finished
label | 3f73bf0f-676c-50f6-9090-cd4f1c74912c |  | note | ACCEPTANCE CRITERIA: Visual inspection. Engineer to be informed when surface is ready for inspection.
label | c84db2e8-01b9-5ec8-84b3-9b4890de84e9 |  | note | FREQUENCY: As completion of paths.
label | 39f19cb3-c716-5865-9d0d-d32686304855 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-group |  |  | section | FINISHING WORKS
checkpoint-status |  |  | checkpoint | 6.4 - On Completion of the Rip Rap
label | 56b91022-6e2e-521f-ae66-460165e0f381 |  | note | ITEM: On Completion of the Rip Rap
label | 3514c3bb-3506-56ce-b79c-18dd5a9892cf |  | note | ACTIVITY TASK: On completion of the rip rap protection to the banks adjacent to the abutments. Note: Placement of rip rap shall not commence without Engineer’s approval.
label | 5f2aa48c-a684-5d2b-a920-e08c069a81bc |  | note | ACCEPTANCE CRITERIA: Placement within tolerances set out in clause 27.13.7.3 in specification. Visual inspection and acceptance by Engineer.
label | aad634ee-da7b-585d-be7c-cd52132364f7 |  | note | FREQUENCY: On completion of rip rap protection.
label | 9dbe99ff-b811-53d9-8324-d6c303c28ba4 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 03573ef8-cf9c-570c-9963-e903ae7516c6 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.1 - Barrier Rail Fabrication
label | 97f40a65-d106-5c7a-89f8-7684408efe57 |  | note | ITEM: Barrier Rail Fabrication
label | a2b42265-42be-579e-9d8d-539ef494ed00 |  | note | ACTIVITY TASK: Barrier rail fabrication.
label | bf95a711-c995-58dc-9b3b-315d88c0ac7d |  | note | ACCEPTANCE CRITERIA: Barrier rails match drawings and comply with NZTA M/23 and TNZ M/17P. Construction of the new barrier is not to proceed before the set out has been checked and approved by the Engineer.
label | 0bdaa7b5-ec1c-57fa-91d1-2d503c7d969c |  | note | FREQUENCY: Prior to installation of the barrier rails.
label | eb900435-3f1a-5d4c-a159-7aa9bba322e8 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Barrier rail specifications. ITP signoff.
label | 819eb164-a448-50f6-b6a5-e264cabdda0a |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.2 - Prior to the Installation of the New Handrail
label | 2c656b7f-1b97-5c49-a387-e485450bdcbf |  | note | ITEM: Prior to the Installation of the New Handrail
label | 6746b94d-5e45-5db9-9249-d7a91225ac67 |  | note | ACTIVITY TASK: Prior to the installation of the new handrail.
label | ee90e0ee-3c2b-58ee-8e54-c835c27c87f5 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | f082677b-ac04-54f0-8e24-51fdd7e2296c |  | note | FREQUENCY: Prior to the installation of the new handrail.
label | f8ff5d0b-9d2e-5a68-a95c-aa7f50dc983e |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 035013b6-5787-506d-8b24-5284e0d14253 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.3 - Marking Paint
label | f980e525-7365-51f9-924b-e28402962290 |  | note | ITEM: Marking Paint
label | f12310b0-b684-5bc4-bc4a-60527cb311b6 |  | note | ACTIVITY TASK: Shall comply with NZTA M07 to B standard.
label | 880dcb97-1122-5cab-8147-cfc431808e99 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer.
label | 97e5cd6d-0f6f-5d2b-90ef-c735fa650ee6 |  | note | FREQUENCY: One per batch.
label | 968914f2-0dba-5474-bbd1-aea10665bac9 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.4 - Marking Paint – Setout
label | 50237281-16f5-5fb1-96f0-de8dc722913a |  | note | ITEM: Marking Paint – Setout
label | 676c891b-86d1-5d1a-9544-6899c884193d |  | note | ACTIVITY TASK: As per set-out coordinates.
label | 46ffbaee-670c-5a2a-975a-5784a9a09f7b |  | note | ACCEPTANCE CRITERIA: Engineer invited to check set-out.
label | a79e8a35-941b-5d73-b6ad-49efe6cb0ac6 |  | note | FREQUENCY: Each portion prior to road marking.
label | 4cfa12fc-cdd2-5d92-b7a5-f5931490aab9 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As-built drawings.
checkpoint-status |  |  | checkpoint | 8.5 - Tactile Paving
label | 266acd5b-be11-5e89-bf67-e0e4f9bcb6c8 |  | note | ITEM: Tactile Paving
label | 97cf67c5-3432-5a51-971c-db0460cc709f |  | note | ACTIVITY TASK: Manufacturer certification and delivery dockets.
label | 97231ae6-0753-5784-afd5-179a01ea31a1 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 0b3c130d-303a-5720-bee0-b1b5ea56abb4 |  | note | FREQUENCY: On supply of materials
label | 2123dc5d-3867-5480-aa9f-8bc675398953 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturers dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.6 - Tactile Paving – Setout
label | c70da8ec-fbe4-52d9-bbd2-24d2ca132356 |  | note | ITEM: Tactile Paving – Setout
label | f51d607a-198a-567c-b8c5-695af342463b |  | note | ACTIVITY TASK: As per drawings.
label | 951e5028-a6ad-57f3-aec2-7b22e1bf2c3b |  | note | ACCEPTANCE CRITERIA: Engineer invited to check set-out.
label | fd951671-05f4-5286-baff-f6cafe6fff06 |  | note | FREQUENCY: Prior to installation.
label | 79ee8868-9fb6-5075-970e-9bc4cf3e7095 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
checkpoint-status |  |  | checkpoint | 8.7 - Prior to Vehicular or Pedestrian Traffic
label | 7c04ff13-5ca2-58b0-9027-ef4f9c0b067e |  | note | ITEM: Prior to Vehicular or Pedestrian Traffic
label | 348ef85c-2d19-504f-ab46-2f377a748341 |  | note | ACTIVITY TASK: Prior to allowing any vehicular or pedestrian traffic over the new structure.
label | 598bf053-a101-5f98-a5fa-d2ec4095fb1b |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | d42196ff-b774-5f9e-a974-014e66be4755 |  | note | FREQUENCY: Prior to allowing any vehicular or pedestrian traffic over the new structure.
label | 2f2c29d1-7015-590d-832d-b57a088ae5ac |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 32d9659d-1813-53f4-900e-890fb71756ef |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.8 - Traffic Signals
label | f2b001cd-7c99-5aa0-ab52-e5ab654865d6 |  | note | ITEM: Traffic Signals
label | c8bc2a12-bfa6-59ee-8cde-d3e3e4e7f67a |  | note | ACTIVITY TASK: As per drawings. As per drawings. Manufacturer certifies performance, material delivered is as specified.
label | 9321e6dd-e8c1-5793-aec0-15d1a830df96 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 8c9fa138-08c9-515b-b5c7-7f1e9a4505b4 |  | note | FREQUENCY: On supply of materials.
label | 687bfb6b-07f5-5b84-9be6-db0bacc8fe68 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturer dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.9 - Lighting – Material Supply
label | 7ddc6428-39e7-5357-970b-40500d2d70c4 |  | note | ITEM: Lighting – Material Supply
label | d0496692-543f-56b7-918f-4172286f5d46 |  | note | ACTIVITY TASK: Written statement from supplier that all items and components comply in all respects with specification requirements.
label | 0321a81d-d381-5222-8c75-94b816d3523b |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 30d2f05f-227e-5ddc-bc6e-d4edfa5c5e41 |  | note | FREQUENCY: One statement per batch per material type supplied.
label | 949356b6-2a8e-5fa8-a883-c209e240b570 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturer dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.1 - Lighting Installation
label | 16ef0407-9716-5a66-b0a6-fc5e9b512141 |  | note | ITEM: Lighting Installation
label | e306bd23-9fd4-5ba2-babb-68a305dc987e |  | note | ACTIVITY TASK: Contractor to develop checklists as per Clause 26.3 in specification covering the following; All testing has been carried out as per NZECP:11: Cabling. Megger testing. Flange positioning. Flange height. Pole compression. Bolt tensioning. Pole positioning. Luminaire alignment. Protection devices.
label | f11df242-9809-5370-b261-d7f8aeb2d23d |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | d920c9bb-83cc-58c5-9f37-be12431a9fe1 |  | note | FREQUENCY: One completed checklist for each pole.
label | 04a2ca1b-7eb2-5f3c-be47-602acd817945 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Completed checklists.
checkpoint-status |  |  | checkpoint | 8.11 - Lighting – Trenching
label | 53aaa656-f59e-5301-9b91-778762fad843 |  | note | ITEM: Lighting – Trenching
label | 7418cc67-3711-5c0b-8c2c-831b62de0088 |  | note | ACTIVITY TASK: Trenching under shoulder or open ground. Clegg impact hammer test: Single test (average of 5 readings) > 6
label | 3e7811fb-5a04-5d50-94fd-4af5c93e328b |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | a1eb968c-b205-5771-8d90-810a5034e71b |  | note | FREQUENCY: One test per 500mm depth of trench per 50m length.
label | 6b558fe5-3a46-53a6-8464-3f7a98c19656 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 8.12 - Lighting – Trenching
label | c1d471c8-9af8-5f27-9c2f-3caa9d6b3192 |  | note | ITEM: Lighting – Trenching
label | 992b6002-986e-5987-9369-da67a175862c |  | note | ACTIVITY TASK: Trenching under pavements and driveways. Clegg impact hammer test: Single test (average of 5 readings) > 10.
label | fc99c7d9-fc78-579c-85b4-cfa6c7793df7 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 2cce0310-20cf-5a7e-8713-6e6f6b392d7e |  | note | FREQUENCY: One test per 500mm depth of trench per 50m length.
label | 08d2c8f5-8e39-540d-924a-ed1222cb06e3 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 8.13 - Lighting – Completion
label | 1117d890-b337-5df2-a723-d459393b0679 |  | note | ITEM: Lighting – Completion
label | 51cd5d4e-320a-5bc2-9814-6737c243bfac |  | note | ACTIVITY TASK: Contractor to produce and sign a Certificate of Electrical Compliance. Testing done to NZCEP:11.
label | 8d8468b0-6215-520c-b196-6a3e3ec5cb44 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claim.
label | 49fb0e1d-8dfc-55ad-9070-1ae9904c8914 |  | note | FREQUENCY: One completed certificate at conclusion of installation.
label | eaf72008-7082-5485-bbb3-a8e78151f898 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Certificate of Electrical Compliance.
checkpoint-status |  |  | checkpoint | 8.14 - As-Built Drawings.
label | 9b6289eb-fdda-540a-bb3d-a954fa569338 |  | note | ITEM: As-Built Drawings.
label | 3e19e2d1-4d65-5934-91c9-0e9c2075df91 |  | note | ACTIVITY TASK: As-built drawings shall consist of the construction drawings, updated to reflect all significant as-built variations, including defects and their rectification.
label | 82441a74-22a7-53e6-9e08-9ccced795b00 |  | note | ACCEPTANCE CRITERIA: Acceptance by Engineer.
label | 49dfc4f2-730a-5555-bd7b-16d6da7ee874 |  | note | FREQUENCY: At the end of the Defects Notification Period.
label | b5ea9d5b-11ef-5814-b14d-46d6cfaa05e3 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: One complete set of AutoCAD (or agreed equivalent) files. One set of un-editable Adobe PDF files exported from the CAD as-built files.
checklist-sectioned |  |  | checklist | ITP - SEPARABLE PORTION 3 | itp |  |  |  | Yes | ITP - SEPARABLE PORTION 3 | 2e5f2668-e900-49bd-a9cf-698a580e0e4a
checkpoint-group |  |  | section | DRAINAGE AND SERVICES
checkpoint-status |  |  | checkpoint | 5.1 - Contractor Construction Methodology
label | 0639e8a0-b1f1-5cc6-8e63-a8808f836ac3 |  | note | ITEM: Contractor Construction Methodology
label | 9114dbf9-b3d2-5eb9-acc2-7e7ea6bd1bbe |  | note | ACTIVITY TASK: Contractor construction methodology required for installing services.
label | 53d0eeb5-b88d-52f2-bd0b-70a0c528d53a |  | note | ACCEPTANCE CRITERIA: Signoff by Engineer.
label | ef77c749-cbf5-539a-9868-3bfdf0c5fda2 |  | note | FREQUENCY: Methodology provided to Engineer for review at least 14 days prior to the commencement of the specific works.
label | b67719fe-25c4-59e7-b044-cf4631a81cc8 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Methodology submitted and approved. Signoff by Engineer.
label | 05e6432a-929c-5552-b892-0d399820e70e |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.2 - Temporary Service Relocations
label | f2faaf00-f11d-5d6c-bb11-e934667eeaeb |  | note | ITEM: Temporary Service Relocations
label | 48b8eb6f-11de-52b9-a704-35b4dc3860b8 |  | note | ACTIVITY TASK: Set out of temporary service relocations.
label | feeee8a9-cc38-5acb-a43c-acaf08fbf47c |  | note | ACCEPTANCE CRITERIA: Service authorities agree to relocation positions. Relocated positions do not clash with other services or proposed works. visual inspection and acceptance by Engineer.
label | e5daebe4-d862-5294-8dfd-b5d33f1bdc9b |  | note | FREQUENCY: Prior to commencing any service relocation.
label | 8ef9f359-22dc-5078-8ee7-613921cd2709 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 6de38c34-2a46-5296-8936-f0620ab7f664 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.3 - Granular Backfill
label | f8a37b04-f358-5edd-a87c-3f1baea26bdc |  | note | ITEM: Granular Backfill
label | d14e4a1b-460f-5475-b907-73a29d52d325 |  | note | ACTIVITY TASK: Prior to backfilling to any part of the abutment or any abutment drainage. (Note: Existing drainage to systems behind abutments shall be protected during backfilling operations).
label | 6fed2933-423e-5761-b5da-8b0b7070ba31 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 684678dc-739a-53ec-b815-b15c56c8a0ee |  | note | FREQUENCY: Prior to backfilling.
label | af07c733-b315-596d-94b9-878fd083a04a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
label | 459dea7b-2307-5049-b0c8-bd82316b5dfd |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | EARTHWORKS AND PAVEMENTS
checkpoint-status |  |  | checkpoint | 1.7 - Confirmation of Ground Conditions
label | 895aee3c-2434-54c9-bd9e-46e7f6b2118e |  | note | ITEM: Confirmation of Ground Conditions
label | 2c3e54f0-35c4-5cb8-b501-4ad69bee587d |  | note | ACTIVITY TASK: Confirmation of ground conditions.
label | 40160c86-2f21-54be-9942-6eee96c8453c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | b94ed85c-464a-5cc1-89b2-7a9cc7cfa330 |  | note | FREQUENCY: After excavation and prior to any construction, installation or backfilling.
label | 3850c87f-47ee-5b32-9d49-0bf93eddf41f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | c6898b71-2d90-5ce5-bea6-b13686c4b868 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.1 - Granular Backfill
label | d1872d11-4885-50c5-b4fc-b6d3e8316e25 |  | note | ITEM: Granular Backfill
label | d25ce95f-e67f-5746-a505-52f7a99d54a5 |  | note | ACTIVITY TASK: Test sample to be used to determine maximum dry density and optimum moisture content (NZS 4402:1986 Test 2.8.2).
label | 694a4065-d207-5928-b532-cdffc931f4d4 |  | note | ACCEPTANCE CRITERIA: Acceptance by Engineer.
label | 112b3e08-36df-5427-b29e-fdc1a00cf69e |  | note | FREQUENCY: Prior to commencement of works.
label | e334749e-700f-5270-a347-e4765ec55484 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
label | 05c7c1b3-5140-50f8-9412-60eea7eca7c2 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.2 - Pavement Works
label | 3ac9e884-993f-5c27-9c71-3df742d7395b |  | note | ITEM: Pavement Works
label | fe44ba34-e7f9-52d8-8d62-51309f0bbe5b |  | note | ACTIVITY TASK: Set out extent of pavement works.
label | 470fc714-6e98-5be7-baa8-2f9ef6417048 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 06dee266-6011-5dd1-b7bf-799961693b65 |  | note | FREQUENCY: Prior to commencing any pavement works.
label | 5b863951-30a0-520d-9823-2361bc286b4a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 16783a46-7bc3-57ac-bf63-590bf5c64b2b |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.3 - Surfacing Works
label | 2877f48e-6022-5b9a-8cac-a407e6956e0a |  | note | ITEM: Surfacing Works
label | 766c4484-5e87-5f72-a842-18b417ce62be |  | note | ACTIVITY TASK: Set out extent of surfacing works.
label | e5e7017b-167d-5f57-8b9f-cdbeca89da8c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | eec87598-82b6-5aa9-9f8b-965fb3f337c3 |  | note | FREQUENCY: Prior to commencing any surfacing works.
label | 287af5d5-e168-54d2-ac71-480ec1960862 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 7b368d50-6b1c-5c70-b4bf-27d05a0acac6 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.5 - Existing Pavement Depths
label | f4bba8e8-7ef5-5cce-9973-ce3721cecad9 |  | note | ITEM: Existing Pavement Depths
label | d18afc64-7dd9-5aa3-9fe5-54114eba87bf |  | note | ACTIVITY TASK: Visual inspection during shoulder checkout works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area (Clause 23.8 of specification).
label | cf23c7a9-3d63-5862-9119-0c42478d96ac |  | note | ACCEPTANCE CRITERIA: Observations provided to Engineer immediately.
label | f3ffcc5a-6028-50fd-866e-be4f1f42571d |  | note | FREQUENCY: At 25m intervals.
label | 4a1af2ea-41a0-58c6-9f1a-2a917a043422 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. Record.
checkpoint-status |  |  | checkpoint | 6.6 - Existing Subgrade Strength
label | b6b7986e-6189-5850-bede-0d203c1da9ac |  | note | ITEM: Existing Subgrade Strength
label | f1fbd1fe-b47d-5061-860c-0fa94492e802 |  | note | ACTIVITY TASK: Scala CBR equivalent tests. Three minimum per exposed area.
label | f451e1d6-a040-5ec3-ab49-163567c1535b |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 52c6ea6f-015c-5a8a-b0b8-b27320c70d14 |  | note | FREQUENCY: Three minimum per exposed area.
label | 87ba53a7-2b61-5c5f-bae5-cba94975c4e2 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Results of Scala CBR equivalent tests.
checkpoint-status |  |  | checkpoint | 6.7 - Benkelman Beam Deflections - Subgrade
label | 77a842d2-e749-5831-9349-8e61e6b27853 |  | note | ITEM: Benkelman Beam Deflections - Subgrade
label | 1eef9a9a-a276-5753-91a0-3a33b6b38ce6 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the subgrade.
label | 477f8b69-d7fc-5e6d-be12-b978b21d287f |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | f6a848b2-07bb-520b-92fd-6363fced0687 |  | note | FREQUENCY: At the completion of each layer.
label | 03de24cc-715b-5bd0-a9e6-4d154c503b2d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Modified Subgrade
label | 0c229f21-b746-5c53-9954-1aee202e9b2a |  | note | ITEM: Benkelman Beam Deflections - Modified Subgrade
label | 4097af9d-762e-5c47-8517-59917f6570f1 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the modified subgrade.
label | 4f6fab6f-afd8-5a7d-8954-964e05968915 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | 590049dc-59bd-5184-89b6-403bf67db50b |  | note | FREQUENCY: At the completion of each layer.
label | 6836e25a-86a2-5d54-abb9-33c566938451 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Subbase
label | 630fe161-7dba-5d4a-bc52-61309b67d256 |  | note | ITEM: Benkelman Beam Deflections - Subbase
label | ef40617c-496e-5526-a194-fdc17af37ae2 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the subbase.
label | 66dd9d00-76b6-580a-96ba-26c861360525 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | f6a98b85-72a0-5d7b-8347-6f0563febf68 |  | note | FREQUENCY: At the completion of each layer.
label | ce077eda-655e-52df-894c-3988a7968c99 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Subbase
label | 5edb5872-a6ef-55ba-a350-7f27cc134575 |  | note | ITEM: Benkelman Beam Deflections - Subbase
label | d76e1a55-0bd6-5748-8039-eb19515f6777 |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the subbase.
label | 1399bea9-fda9-58cc-8abd-90147e360306 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | de344db6-5798-5df6-8b52-384e450ca7a7 |  | note | FREQUENCY: At the completion of each layer.
label | ab061883-ac35-56b5-85c7-090acf6125cf |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | Benkelman Beam Deflections - Waering Course
label | 3f34fe16-c8a2-5520-934a-70b2f2c64b2d |  | note | ITEM: Benkelman Beam Deflections - Waering Course
label | 45dcfbbd-074f-56c2-a161-459ac4ae0c0f |  | note | ACTIVITY TASK: Benkelman beam deflections to be measured at maximum intervals of 20m. Testing shall be at the completion of the wearing course.
label | 1d827b31-f5b6-5a08-943d-ace6c192a339 |  | note | ACCEPTANCE CRITERIA: Deflection requirements will be notified to the Contractor by NTT.
label | 097cee9e-c068-5e9f-b813-650f9c3ee23a |  | note | FREQUENCY: At the completion of each layer.
label | e2a8886a-ed30-52d0-9679-2aa8c1458ded |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 6.8 - Subbase and Basecourse Aggregate – Proportion of Broken Faces
label | 0f4d348c-3194-5140-8adc-a66ac84110b1 |  | note | ITEM: Subbase and Basecourse Aggregate – Proportion of Broken Faces
label | edccba20-1d35-572b-98aa-fa2fb07054d9 |  | note | ACTIVITY TASK: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407:1991 Test 3.14 no less than 70%.
label | 48520a2f-13c0-5f66-9d5e-8f0eb412aa84 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 0f00a445-f0f2-50ba-8031-d6490a885553 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | 0f4cef14-2efb-549a-830e-2b90c58c7274 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test results.
checkpoint-status |  |  | checkpoint | 6.9 - Subbase and Basecourse Aggregate – Sand Equivalent
label | 1698533e-ef4e-54d8-9926-5d31b71d9780 |  | note | ITEM: Subbase and Basecourse Aggregate – Sand Equivalent
label | 50dfba5d-4c06-5f6a-8a28-d12a1d5f63c2 |  | note | ACTIVITY TASK: Sand equivalent to NZS 4407:1991 Test 3.6. Sand equivalent to meet specification.
label | 308689a8-3543-5532-9e93-ccc05525c838 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | f7013cb4-fb4e-5dc4-8aeb-da0bc63f8799 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | f72a346d-d4ba-5303-8244-2f8ad4500b9b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.1 - Subbase and Basecourse Aggregate – Crushing Resistance
label | fbf97102-e6ae-5d06-b341-50dbc6f7a62c |  | note | ITEM: Subbase and Basecourse Aggregate – Crushing Resistance
label | 3884a523-1497-5767-abcd-a004023aaf20 |  | note | ACTIVITY TASK: Crushing Resistance to NZS 4407:1991 Test 3.10
label | 2d6b2d37-edad-5be2-be9c-48a80e552347 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | 1c68e382-ab46-53d9-8ad4-81d5333114f8 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | bbcd9ffa-acba-5377-b030-11031b518909 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.11 - Subbase and Basecourse Aggregate – Weathering Quality
label | 545fab7d-40ec-5304-a6f5-b50a6b107b97 |  | note | ITEM: Subbase and Basecourse Aggregate – Weathering Quality
label | e004e78c-7a48-526d-aa17-7394978cc606 |  | note | ACTIVITY TASK: Weathering quality to NZS 4407:1991 Test 3.1.1
label | 8997b521-84d8-5e35-b330-eef6c8ff8b46 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | aeed70f7-afcf-55bf-9a10-1bcd9621ebc6 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | fdd180c1-f7e7-56f4-a717-b9adbc2982b9 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.12 - Subbase and Basecourse Aggregate – Maximum Dry Density (Laboratory)
label | 7ec19f42-cd09-5c28-aa8b-3890640b7f8c |  | note | ITEM: Subbase and Basecourse Aggregate – Maximum Dry Density (Laboratory)
label | 8bdc1b4e-144e-5ff3-9030-fc6471e072e0 |  | note | ACTIVITY TASK: Maximum laboratory dry density (MDD) of aggregate at optimum moisture content (OMC) to NZS 4402:1986 Test 4.1.3
label | 5db68d5f-8c0e-5316-96e7-ad4e7857bcc6 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement.
label | e30b656d-eb28-500c-abef-7a2732fb48f2 |  | note | FREQUENCY: Compliance certificate less than 6 months old or test result on sample from site, per source (stockpile) and for every 1000m³ delivered to site.
label | b5473605-0d52-5697-93c1-a88eb7cd743f |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Compliance certificate or test result.
checkpoint-status |  |  | checkpoint | 6.13 - Completed Subbase – Nuclear Densometer
label | 84eb49d8-38c2-5593-969a-f40defdf6a14 |  | note | ITEM: Completed Subbase – Nuclear Densometer
label | 0e9d14fc-ac17-5a4b-becd-734b0e915dc6 |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20m intervals throughout.
label | e6f721eb-d0a3-5d2b-b275-e3c6d9c18c08 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement of basecourse.
label | 5efc1b3e-3b7a-5f4d-80f8-d72543293bdb |  | note | FREQUENCY: Prior to placement of basecourse. Mean value of density tests shall not be less than 95% of MDD. No individual test less than 92% of MDD.
label | 99918e7f-81a6-5368-a222-c0946aba7c99 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: MDD results.
checkpoint-status |  |  | checkpoint | 6.14 - Completed Subbase – Straight Edge
label | 3ab2c5e2-9756-5b4d-818b-11840348e2ba |  | note | ITEM: Completed Subbase – Straight Edge
label | 91ff0afe-ce04-51c3-9c7a-a2bee80ce68e |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
label | a2252e8c-61ad-51b9-a617-5ebd10fe0030 |  | note | ACCEPTANCE CRITERIA: No point on the surface shall vary more than 10mm from a 3m straight edge. No ponding of water. Provided to Engineer prior to placement of basecourse.
label | 96cdedcd-bbf9-535a-b83f-183e5ffa5b1f |  | note | FREQUENCY: Prior to placement of basecourse. Randomly staggered transverse positions at 20m intervals throughout.
label | 49d4244c-70ac-5a29-93ad-b938fba61e5c |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.15 - Completed Subbase – Finished Level
label | c2fb475d-f82c-5844-b557-4960390b11da |  | note | ITEM: Completed Subbase – Finished Level
label | 43f4e722-45c5-5acc-8e99-5fadca6ab80f |  | note | ACTIVITY TASK: Completed subbase prior to placement of basecourse. Provide a sound finished surface to line and level as per specification.
label | 7f4da91e-7881-5c54-975f-340338daedec |  | note | ACCEPTANCE CRITERIA: Visual inspection by Engineer.
label | 9fc293f3-9803-57bb-a1db-bd7b5649f13d |  | note | FREQUENCY: Prior to placement of basecourse.
label | cc1dc914-68d7-511e-bbaf-23048d962273 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.16 - Completed Basecourse – Nuclear Densometer
label | 7990fe66-3fd5-52fa-b992-c1818d45e454 |  | note | ITEM: Completed Basecourse – Nuclear Densometer
label | 3c7e8e57-72cb-5001-9e0e-f8f1412e9051 |  | note | ACTIVITY TASK: Completed basecourse prior to placement of surfacing. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20m intervals throughout.
label | 08b039b3-a508-5e78-9b3a-e0a7365f8f39 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to placement of surfacing.
label | 4bb0e3b3-4ba8-5077-8a24-8662491c5515 |  | note | FREQUENCY: Prior to placement of surfacing.
label | c642ab34-99ef-5e00-b22e-328935787d18 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.17 - Completed Basecourse – Finished Level
label | 8889eb6e-eea0-5a6c-8565-88f6199995e9 |  | note | ITEM: Completed Basecourse – Finished Level
label | 547c4d38-68c0-595e-bc5d-419d532a3060 |  | note | ACTIVITY TASK: Provide a sound finished surface to line and level as per specification.
label | 47b6113f-2058-5fe4-8fde-c80906a2e054 |  | note | ACCEPTANCE CRITERIA: Visual inspection by Engineer.
label | d9d57732-059a-5c5c-a0b0-b51730609eba |  | note | FREQUENCY: Prior to placement of surfacing.
label | e7b385b0-6c6a-5eac-81b6-c071ad2ff3a6 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-status |  |  | checkpoint | 6.18 - Prior to Surfacing
label | e41f2e3f-be2a-5861-af4b-861dc00bce90 |  | note | ITEM: Prior to Surfacing
label | c5b9b5c0-a090-5c20-a129-cf5fcef0dd5e |  | note | ACTIVITY TASK: Prior to surfacing.
label | 51d75f1b-721d-5918-be14-2f67356a0a8c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 723e864c-cc12-5967-bc36-d360df46d662 |  | note | FREQUENCY: Prior to surfacing.
label | 60534eca-db00-57e5-8e37-b1a741f63a3c |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 411b4a20-c3a4-5d20-b02f-b9fd1b187783 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.19 - Sealing Binder
label | 094d64c6-fd23-50dd-afa7-6960fcb3a3ac |  | note | ITEM: Sealing Binder
label | 7a010012-80c3-5b6e-a80d-537cb19ad0ef |  | note | ACTIVITY TASK: Shall comply with NZTA M1 and TNZ M13
label | c654eb35-a228-5dca-9d32-6f004014477e |  | note | ACCEPTANCE CRITERIA: Provide to Engineer on request.
label | d88602c3-0437-5884-ab93-a3f5a28bf2d5 |  | note | FREQUENCY: Upon completion.
label | a102ce18-bda6-5eb9-a99a-d504006cd399 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier QA documentation.
checkpoint-status |  |  | checkpoint | 6.20 - Asphaltic Concrete
label | 154198a8-b737-54e1-b664-dce9f7496091 |  | note | ITEM: Asphaltic Concrete
label | ccd26d33-d91e-52f5-94c4-db9b6239c90e |  | note | ACTIVITY TASK: As detailed in NZTA M10. Method of determining density location tests.
label | db621dc2-75a1-597b-94a1-7cc6ef2fd284 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer prior to the placement of asphaltic concrete.
label | dbdc5332-d2a8-55bf-8758-ce058e8524f2 |  | note | FREQUENCY: Prior to the placement of asphaltic concrete.
label | 5bfa52d5-4b4d-55d7-815d-d0d2a2b54b0a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier dockets/certificates.
checkpoint-group |  |  | section | OFF BRIDGE CONCRETE
checkpoint-status |  |  | checkpoint | 7.1 - Concrete Mix Design
label | 118e9ee9-e7cb-5aac-856c-527049d3f7a6 |  | note | ITEM: Concrete Mix Design
label | 1c647161-8981-5085-81a6-28f5adb4e89c |  | note | ACTIVITY TASK: Concrete mix design required for footpaths.
label | 19885155-bcc3-5b4c-a47c-b4e545d0101f |  | note | ACCEPTANCE CRITERIA: Signoff by Engineer.
label | c499bc0e-3553-54dc-a498-975b2f04bd30 |  | note | FREQUENCY: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 0038096a-9809-521e-988e-2a4a6173124a |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Concrete mix designs.
label | 4407a7e9-bc2e-5c76-a8f5-e5afdbee1b86 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.2 - Reinforcing
label | 9e8887df-1ced-564c-b83f-aff801d58c53 |  | note | ITEM: Reinforcing
label | f7040ebb-b9c1-56ab-9918-8513075b70c7 |  | note | ACTIVITY TASK: All reinforcing prior to concrete pours, including pre-fabricated elements.
label | bc128fe6-d544-57d2-9ab2-0a5fdb14ad04 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 76e2354a-efa1-5bf8-affc-6c5031478dfe |  | note | FREQUENCY: Prior to pouring concrete.
label | 1775f743-dee0-5680-b90f-81cdc546f706 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | b26986ef-ce35-508d-9c38-635c4c1211e5 |  | note | WITNESS POINT
checkpoint-status |  |  | checkpoint | 7.3 - Formwork
label | 5723e27f-dd13-5599-9f2d-6b621421bf57 |  | note | ITEM: Formwork
label | d4217987-0c6f-520a-85e1-a7486b6a1e17 |  | note | ACTIVITY TASK: All formwork prior to placement of reinforcing and/or concrete.
label | 7bc600ea-605d-5a43-8703-73ac967d5b00 |  | note | ACCEPTANCE CRITERIA: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 817ef723-127f-5ab5-bacb-10a569522fb1 |  | note | FREQUENCY: Prior to placement of reinforcing and/or concrete.
label | 3571c41c-d8e6-53c6-91e0-b4be11ac148d |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | d13308b1-e264-5396-b146-89ba079ffab3 |  | note | WITNESS POINT
checkpoint-status |  |  | checkpoint | 7.4 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | 810d511f-507a-5630-a1d4-7f33eaed8cd6 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 936cc54e-51a6-5b3d-aad4-7a7b7db647f1 |  | note | ACTIVITY TASK: Compliance with NZS 3116 Bedding Sand.
label | e39bd0a5-a5fc-579c-97c3-524ebc60c6f2 |  | note | ACCEPTANCE CRITERIA: Meets specification.
label | deb05fbb-fb0e-575d-b96d-53b4879b4ed3 |  | note | FREQUENCY: One test per 50m³ of bedding sand supplied to site with a minimum of three tests for the contract works. Provided to Engineer with payment claim.
label | a44aac0e-7218-515a-89c9-7d0e639ff1f6 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 7.5 - Footpath and Kerb Works
label | 0c20e5aa-73f0-5953-8eb5-3e81d4493d35 |  | note | ITEM: Footpath and Kerb Works
label | 2cb8f5e7-e999-5c2b-b151-4704f424503b |  | note | ACTIVITY TASK: Set out of footpath and kerb works.
label | e53a3926-dd84-504d-b76f-47d484b5428b |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 323eecbb-ea1c-5bf1-9ca3-4a861d2768ed |  | note | FREQUENCY: Prior to commencing footpath and kerb works.
label | 6f7b8834-1b56-56b5-8fc4-46ec8f68fbca |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey records and photos. ITP signoff.
label | 09e303d3-7020-55bb-b9a6-bc6446d4f063 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.6 - Footpath
label | 828c9480-dd2d-51c5-9af9-4dfc8c688585 |  | note | ITEM: Footpath
label | 71531aec-7bf1-56bc-8b99-eba6ca674c2c |  | note | ACTIVITY TASK: Pre pour inspection for the bridge footpath.
label | a9dbf901-d9a7-52ed-812b-dd505fa599ff |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 5fd5a043-4419-5e71-9c58-b4ef49198bcc |  | note | FREQUENCY: Prior to pouring concrete.
label | b8461992-d774-5fc4-b110-7faa314d28f3 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | b95eacfd-1827-5d52-bb3a-792fc6ad53eb |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | Kerb and Channel
label | be289fc8-e83d-50ec-a11e-1ae797339b23 |  | note | ITEM: Kerb and Channel
label | bc2a7042-0be0-5f4b-ac81-11842cf76b3b |  | note | ACTIVITY TASK: Pre pour inspection for the bridge kerb and channel.
label | b7fa4b49-22c2-521e-8776-eccb5cc9a510 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | e4a9b591-78cf-56a8-890b-3ec9bce81b9d |  | note | FREQUENCY: Prior to pouring concrete.
label | 181b236d-3210-5518-aba0-550c3508e5d4 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | 71cc89bc-d7a0-59a6-9ee3-1ed4aa5c2844 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | Bridge Retaining Walls
label | 8c37cf86-4713-5d44-8ff5-ddc7a88af608 |  | note | ITEM: Bridge Retaining Walls
label | d2647973-1ccb-58f7-a5f3-ac4352b5a818 |  | note | ACTIVITY TASK: Pre pour inspection for the retaining walls.
label | 9759ae8e-bcda-5efb-b346-8ca2d0e0df5c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 13155eca-6a2d-5fe9-8d5e-cd7be94f1e11 |  | note | FREQUENCY: Prior to pouring concrete.
label | fe1ec4d8-5163-5108-b299-fd321abf1c48 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Mix design accepted. Photos. ITP signoff.
label | e66c6c55-b6ef-52c6-b95e-578032ae2c47 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 7.7 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | 6664d83d-432c-52ad-a10e-c695a9705754 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 0b764bce-f6b7-50ee-bf7a-1238c762da27 |  | note | ACTIVITY TASK: Alignment to plan. Free draining.
label | 2d5bd61d-65f6-5297-86d9-664a71e6f12d |  | note | ACCEPTANCE CRITERIA: Meets specification.
label | 21df86d8-2053-50a7-bf4f-9485a78de1a4 |  | note | FREQUENCY: One completed checklist per 100m of footpath or shared path constructed. Provided to Engineer with payment claim.
label | 2888906e-d708-5aea-9829-f243a6209a21 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Completed checklists.
checkpoint-status |  |  | checkpoint | 7.8 - Concrete Paths, Shared Paths, and Vehicle Crossings
label | d09ccc9e-c74c-5979-b6fe-a389447b34f6 |  | note | ITEM: Concrete Paths, Shared Paths, and Vehicle Crossings
label | 26a41911-b311-5fa3-b19a-c441fbbaecca |  | note | ACTIVITY TASK: Surface to be broom finished
label | 99c4c3be-6790-541e-9fa5-4a2705850145 |  | note | ACCEPTANCE CRITERIA: Visual inspection. Engineer to be informed when surface is ready for inspection.
label | aa0201d7-bce7-5397-ae72-787b01d627aa |  | note | FREQUENCY: As completion of paths.
label | d56954f9-6fe1-560f-9532-9b3fae84b045 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Photos. ITP signoff.
checkpoint-group |  |  | section | FINISHING WORKS
checkpoint-status |  |  | checkpoint | 6.4 - On Completion of the Rip Rap
label | de5cc737-b182-5474-8081-a0c321ad2f7c |  | note | ITEM: On Completion of the Rip Rap
label | 5117323b-3be6-515f-8297-52e55c33c11a |  | note | ACTIVITY TASK: On completion of the rip rap protection to the banks adjacent to the abutments. Note: Placement of rip rap shall not commence without Engineer’s approval.
label | 52706725-8f62-5409-a428-687694d87299 |  | note | ACCEPTANCE CRITERIA: Placement within tolerances set out in clause 27.13.7.3 in specification. Visual inspection and acceptance by Engineer.
label | d8c1277b-1afe-5293-aae4-abfb7507373c |  | note | FREQUENCY: On completion of rip rap protection.
label | 7aa56ece-4ec0-5be5-9016-f0ba73adfa83 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 26bcb4f5-78c4-5361-a1e1-73fa7f2a0401 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.1 - Barrier Rail Fabrication
label | e9208243-5df7-54ba-a1a6-106c56345658 |  | note | ITEM: Barrier Rail Fabrication
label | 5eddf8f0-a43e-5aca-8f54-d24dff653113 |  | note | ACTIVITY TASK: Barrier rail fabrication.
label | 7e8057a9-d515-5611-b9c6-25d7634caee9 |  | note | ACCEPTANCE CRITERIA: Barrier rails match drawings and comply with NZTA M/23 and TNZ M/17P. Construction of the new barrier is not to proceed before the set out has been checked and approved by the Engineer.
label | 6d3da251-9cab-51d9-b864-dbdabfb406d0 |  | note | FREQUENCY: Prior to installation of the barrier rails.
label | e0822fad-75cc-5e93-943a-91699b96ac70 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Barrier rail specifications. ITP signoff.
label | 57f4ef9d-5f11-5ee7-acc3-fa99fca66bc8 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.2 - Prior to the Installation of the New Handrail
label | 3a716de1-8816-5172-b050-3985ef4d1165 |  | note | ITEM: Prior to the Installation of the New Handrail
label | c1396bde-72e5-5cd0-afd1-3f4495d54e14 |  | note | ACTIVITY TASK: Prior to the installation of the new handrail.
label | 6884d52c-64f4-5454-a93b-f6c80a255a7c |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 8a14a970-1c29-5cbe-9d49-1b03000f7ccd |  | note | FREQUENCY: Prior to the installation of the new handrail.
label | c591c3dd-6d5d-56c2-8be1-d3e2ca6818b0 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 7389086e-4d92-5959-9335-097e13b52d37 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.3 - Marking Paint
label | 1a174417-b1a7-5efc-a603-fff76ad3dfe7 |  | note | ITEM: Marking Paint
label | 709ee732-6044-5fdf-bb35-cc5ff9b277a1 |  | note | ACTIVITY TASK: Shall comply with NZTA M07 to B standard.
label | 102a7244-50cc-560a-994a-b7d89cb42931 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer.
label | 627abf79-c31c-553d-8f4d-d9460a821527 |  | note | FREQUENCY: One per batch.
label | d99d48e2-d899-5699-b8ce-930cccefa3dc |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Supplier dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.4 - Marking Paint – Setout
label | bf06d1be-f017-5ee7-9c91-fb27aafb83a8 |  | note | ITEM: Marking Paint – Setout
label | e1c1e7d2-4848-54ec-afb2-67b7d230008e |  | note | ACTIVITY TASK: As per set-out coordinates.
label | f0f78c3f-f100-56e5-a33e-d57f2c430cf9 |  | note | ACCEPTANCE CRITERIA: Engineer invited to check set-out.
label | fcccb2b8-593b-531c-8400-88bac142c447 |  | note | FREQUENCY: Each portion prior to road marking.
label | 65bd4845-b464-5dea-9418-bd994d516b83 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As-built drawings.
checkpoint-status |  |  | checkpoint | 8.5 - Tactile Paving
label | edd962e9-ccbb-5f6f-93d6-36d2fb62e03c |  | note | ITEM: Tactile Paving
label | f02ef0e7-fef5-5680-a425-c85835dd1248 |  | note | ACTIVITY TASK: Manufacturer certification and delivery dockets.
label | 4f544388-ec97-5ad1-a3cb-3bcaf30ad33a |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 3addddd9-891c-5c57-a616-2144fecd92e8 |  | note | FREQUENCY: On supply of materials
label | 0415d24d-58d1-54b6-8f89-c88aecac00b1 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturers dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.6 - Tactile Paving – Setout
label | f8d0b8d3-6fe7-5b5c-a82c-e1bd333f06fc |  | note | ITEM: Tactile Paving – Setout
label | 9c5e2f8b-16b0-55ea-afab-45280f072283 |  | note | ACTIVITY TASK: As per drawings.
label | 031e3432-c610-5e80-ae16-42412cdca9aa |  | note | ACCEPTANCE CRITERIA: Engineer invited to check set-out.
label | e8b2780f-d6af-5236-a348-b21137c3d43f |  | note | FREQUENCY: Prior to installation.
label | 9c3c83a2-d3ad-5b8f-97e4-89ca72748007 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET:
checkpoint-status |  |  | checkpoint | 8.7 - Prior to Vehicular or Pedestrian Traffic
label | 357aff55-c0f1-5dfc-a12e-4cce1e7c3817 |  | note | ITEM: Prior to Vehicular or Pedestrian Traffic
label | d863358d-ca9c-5c1a-abd6-4e21af70c52d |  | note | ACTIVITY TASK: Prior to allowing any vehicular or pedestrian traffic over the new structure.
label | 193dca11-625b-5092-8201-77b753312b30 |  | note | ACCEPTANCE CRITERIA: Visual inspection and acceptance by Engineer.
label | 99e9baea-0d2c-5f4b-ae41-19f99b383282 |  | note | FREQUENCY: Prior to allowing any vehicular or pedestrian traffic over the new structure.
label | fedd3d02-e42d-5936-812e-37f7c4939574 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: ITP signoff.
label | 813c0d03-8578-54fe-b8aa-5918a1cc8233 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 8.8 - Traffic Signals
label | 5327737a-6e18-5b5b-b8ad-10a86af6e374 |  | note | ITEM: Traffic Signals
label | 2871701b-527e-500d-885a-6c777749ca01 |  | note | ACTIVITY TASK: As per drawings. As per drawings. Manufacturer certifies performance, material delivered is as specified.
label | 786e09c1-571f-5d28-9c9d-95417d389776 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | bd988803-9975-54b1-9e42-97ee65bcc55f |  | note | FREQUENCY: On supply of materials.
label | 8cbdc563-248d-5ac6-8451-495bc0d27c2b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturer dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.9 - Lighting – Material Supply
label | e8675a26-a781-53ff-b81c-35c30eeae403 |  | note | ITEM: Lighting – Material Supply
label | b41c76d1-295b-576c-a478-3b7d381ee7b7 |  | note | ACTIVITY TASK: Written statement from supplier that all items and components comply in all respects with specification requirements.
label | d3973232-caca-5f4b-ae17-03cd29c4d270 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | c6ece88c-9e96-56e3-9766-8405de9c52e6 |  | note | FREQUENCY: One statement per batch per material type supplied.
label | 56941311-3888-59af-b473-5ea8fa78daec |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Manufacturer dockets/certificates.
checkpoint-status |  |  | checkpoint | 8.1 - Lighting Installation
label | fe3318f8-68c3-5fbc-bf64-b4c35f4f9d4c |  | note | ITEM: Lighting Installation
label | e494fba3-6c99-53ed-a600-4541f4458d71 |  | note | ACTIVITY TASK: Contractor to develop checklists as per Clause 26.3 in specification covering the following; All testing has been carried out as per NZECP:11: Cabling. Megger testing. Flange positioning. Flange height. Pole compression. Bolt tensioning. Pole positioning. Luminaire alignment. Protection devices.
label | 5aa84b00-c310-53cd-bc12-93a4df0b08f1 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 463e841c-e3bd-53ff-bf5b-3b57d989e135 |  | note | FREQUENCY: One completed checklist for each pole.
label | f36e401d-7742-5169-b82e-1b628885044b |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Completed checklists.
checkpoint-status |  |  | checkpoint | 8.11 - Lighting – Trenching
label | 95b04a85-f12f-5af2-8b13-16a0f2baa756 |  | note | ITEM: Lighting – Trenching
label | 6a9a7256-d589-5a34-a190-6731ee0dc10e |  | note | ACTIVITY TASK: Trenching under shoulder or open ground. Clegg impact hammer test: Single test (average of 5 readings) > 6
label | 2f60d8cc-ddd0-5a0c-8fc1-1ce363447f28 |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 609e8b14-fde6-5fa8-b132-a9fef7bafcc5 |  | note | FREQUENCY: One test per 500mm depth of trench per 50m length.
label | a2e491f4-acdc-50f2-85d7-890aae8c1090 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 8.12 - Lighting – Trenching
label | eeabf0b6-694c-5272-be4c-ef2f04ce0b1d |  | note | ITEM: Lighting – Trenching
label | 698eed6d-f66f-5bdd-887c-12cd6a01dafd |  | note | ACTIVITY TASK: Trenching under pavements and driveways. Clegg impact hammer test: Single test (average of 5 readings) > 10.
label | 53f945f3-a5cb-5f1e-b3bb-cc8775e95e8e |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claims.
label | 82d80bfd-7687-554e-94d3-62317a6e81e5 |  | note | FREQUENCY: One test per 500mm depth of trench per 50m length.
label | b1410349-dd15-5332-bd0f-f6ded6c98da7 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Test results.
checkpoint-status |  |  | checkpoint | 8.13 - Lighting – Completion
label | 6e82aafd-3dda-58e3-aab9-4bc13d07820f |  | note | ITEM: Lighting – Completion
label | 1c7d00b2-33f8-55ff-a714-174ab09c50dd |  | note | ACTIVITY TASK: Contractor to produce and sign a Certificate of Electrical Compliance. Testing done to NZCEP:11.
label | 738915ed-c142-5017-baa5-d16a85c9865d |  | note | ACCEPTANCE CRITERIA: Provided to Engineer with payment claim.
label | 70db06b4-5e30-5ce3-b8a3-e8766ace3d6b |  | note | FREQUENCY: One completed certificate at conclusion of installation.
label | 8383146a-4aef-50db-b0e0-fb5a5c27b914 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Certificate of Electrical Compliance.
checkpoint-status |  |  | checkpoint | 8.14 - As-Built Drawings.
label | 9e3a94f6-e6ee-5214-a01f-4ecc77ec0352 |  | note | ITEM: As-Built Drawings.
label | 9c7f9cfa-ead0-546e-8f63-b2507bfb453e |  | note | ACTIVITY TASK: As-built drawings shall consist of the construction drawings, updated to reflect all significant as-built variations, including defects and their rectification.
label | c5b22496-018c-53ca-8081-89b0af997800 |  | note | ACCEPTANCE CRITERIA: Acceptance by Engineer.
label | e8db1345-0892-50d0-b943-ba83364c5991 |  | note | FREQUENCY: At the end of the Defects Notification Period.
label | 81a971c6-4cb6-51c6-9174-2cbd8fff7e11 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: One complete set of AutoCAD (or agreed equivalent) files. One set of un-editable Adobe PDF files exported from the CAD as-built files.
checklist-sectioned |  |  | checklist | ITP - SEPARABLE PORTION 1 | itp |  |  |  | Yes | ITP - SEPARABLE PORTION 1 | 785a9c53-d02e-47d4-96a6-e7ba700957e8
checkpoint-group |  |  | section | PRELIMINARY
checkpoint-status |  |  | checkpoint | 1.1 - Contract Plan
label | 6a7d1041-e1c2-5881-b659-0f0ed9de6b9b |  | note | Activity Task: Contract Plan to be prepared and submitted to Engineer prior to any works commencing on site.
label | 56177477-0f41-590b-9a7e-fc41840d3817 |  | note | Acceptance Criteria: Acceptance by Engineer.
label | 8f7d2951-a573-59f6-9652-9c578c92c919 |  | note | Frequency: Prior to the commencement of site works.
label | 8bdecddb-3ba8-50dc-bb14-3956d316959e |  | note | Certifying Documentation, Record or Checksheet Approved Contract Plan.
checkpoint-status |  |  | checkpoint | 1.2 - Construction Programme
label | 5dd9a745-49f1-5f96-b814-447f1ab61702 |  | note | Activity Task: The contractor shall submit to the Engineer a programme showing how the key aspects of the project will be programmed, resourced, and coordinated to meet the required contract completion dates.
label | 58744606-c223-5597-b228-0a5755636993 |  | note | Acceptance Criteria: Acceptance by Engineer.
label | 3282b37a-8007-5bc7-92d9-d0882c4397a4 |  | note | Frequency: Prior to the commencement of works. Updated monthly.
label | 2b12121e-6f5d-55e1-9409-9fd0c25a03ed |  | note | Certifying Documentation, Record or Checksheet Approved Construction Programme.
checkpoint-status |  |  | checkpoint | 1.5 - Precondition Survey
label | c7b93a45-612f-5ec6-b6d4-5a9f2b8b7749 |  | note | Activity Task: Precondition survey of the public/private assets within the extent of the site and immediately beyond the boundary. Contractor to extend invitation to relevant stakeholders to join in inspection.
label | e54dc83b-d775-5a84-821b-24356b11c3f4 |  | note | Acceptance Criteria: Survey notes provided to Engineer.
label | e6962819-2936-5553-9f30-0d47f817e5e7 |  | note | Frequency: Undertaken with Engineer prior to the contractor taking possession of the site.
label | 1480b0fd-4360-512b-ab30-bde310212387 |  | note | Certifying Documentation, Record or Checksheet Photos, sketches and notes of any defects identified at the time of inspection.
checkpoint-status |  |  | checkpoint | 1.6 - Repairs to Existing Elements
label | b4dfa2da-8b5a-51c0-9c75-44a195fd067f |  | note | Activity Task: Repair work to cracks/spalls/patches on existing concrete elements.
label | 35633dfc-a0bc-5e5a-82f7-67a19c36f732 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect prior to work on existing concrete elements.
label | 8d7567fc-ebc8-5e66-88e6-881a7740d456 |  | note | Frequency: Prior to work on existing concrete elements.
label | 13187aee-13cb-5e9c-872b-240e70b9d923 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 31425377-876a-51e7-b41d-a415e844a154 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 1.8 - Settlement Monitoring Plan
label | 5c53a8ee-0af8-57c5-b847-470d1f5de014 |  | note | Activity Task: Settlement monitoring plan for existing bridge and adjacent building.
label | 22061d12-fd23-5fb5-b537-b1c20cc22664 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 89ca2729-955c-5da9-bfa3-c2214608f9a5 |  | note | Frequency: Settlement plan to be provided to Engineer for review prior to any works being carried out that may affect the existing bridge structure and/or adjacent building.
label | f061f65f-7527-5131-873b-1eabde6279a2 |  | note | Certifying Documentation, Record or Checksheet Settlement monitoring plan. ITP signoff.
label | 686b6188-f555-5c18-b230-e795ff47fa80 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.3 - Pile Installation Method Statement
label | d8bf185a-4a1a-5a68-a300-1abddefa09f9 |  | note | Activity Task: Contractor to submit a detailed method statement for the installation of the pile to the Engineer for acceptance.
label | 4ab0f2a5-a89e-5c2e-b4a6-cb87a651c637 |  | note | Acceptance Criteria: Acceptance by Engineer.
label | 8ff27be2-c1a2-5606-8edd-7932e9901882 |  | note | Frequency: At least one month prior to commencement of piling works.
label | e1a695f2-2755-542e-8617-59a33d936887 |  | note | Certifying Documentation, Record or Checksheet Approved method statement.
checkpoint-status |  |  | checkpoint | 2.3 - Pile Installation Method Statement
label | 58ce429d-1137-50cf-99ae-956d549ed914 |  | note | Activity Task: Contractor to submit a detailed method statement for the installation of the pile to the Engineer for acceptance.
label | 4dc19a6b-1184-53cb-a456-71c05f42cff6 |  | note | Acceptance Criteria: Acceptance by Engineer.
label | 27af7096-fbc5-5f93-9ae3-72140c2087ba |  | note | Frequency: At least one month prior to commencement of piling works.
label | 2ed0ce96-a9f0-52d8-9b34-52ee7a99103b |  | note | Certifying Documentation, Record or Checksheet Approved method statement.
checkpoint-status |  |  | checkpoint | 3.1 - Contractor Construction Methodology - Abutment Beam Construction
label | 0312a81f-1645-5847-a1ff-6a4c2cb8a774 |  | note | Activity Task: Contractor construction methodology required for the abutment headstock construction.
label | d61d5ac4-e898-5ebb-8fd1-aeb1ae40de06 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 46327302-90cd-5e91-ab78-de0e1f13a911 |  | note | Frequency: Methodologies provided to Engineer for review at least 14 days prior to the commencement of the specific works.
label | 4efdf870-262e-5d27-bdb1-c41090ad5324 |  | note | Certifying Documentation, Record or Checksheet Methodologies submitted and approved. Signoff by Engineer.
label | e9701d72-6ebc-5de9-92e4-95d1dfc7dd1c |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.1 - Contractor Construction Methodology - Pier Capping Beam Construction
label | a26200a5-24de-5d36-ae7f-3fd754e17fe2 |  | note | Activity Task: Contractor construction methodology required for the pier capping beam construction.
label | 14269b4b-c31b-5578-8288-33ddde0b1296 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 21233c44-5d3e-5962-8e6e-7ae15cc19a66 |  | note | Frequency: Methodologies provided to Engineer for review at least 14 days prior to the commencement of the specific works.
label | c06f6c6e-ad9c-5a5c-b7d0-80a0b39b9b77 |  | note | Certifying Documentation, Record or Checksheet Methodologies submitted and approved. Signoff by Engineer.
label | 0e8fd2b5-a152-506b-9743-37a9bc9eefdc |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.1 - Contractor Construction Methodology - Placement of Beams
label | bf6a6b5a-fe43-54d2-a439-6af968cceed0 |  | note | Activity Task: Contractor construction methodology required for the placement of the precast bridge beams.
label | 30d2912a-1a3a-526f-8977-965e032464e5 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 295dad2c-413a-514f-b1b7-710e6619a14a |  | note | Frequency: Methodologies provided to Engineer for review at least 14 days prior to the commencement of the specific works.
label | 1fdd69a9-6bef-5cac-b41c-8e52044c17df |  | note | Certifying Documentation, Record or Checksheet Methodologies submitted and approved. Signoff by Engineer.
label | 655918ce-6073-523d-95f1-f95eee247a2a |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.3 - Casting of Precast Beams
label | 3bee09c1-ad23-58a6-9df1-dc236b66c07b |  | note | Activity Task: Casting of precast beams.
label | 729b2e71-53a9-5f3d-bc8d-071efcfb9f97 |  | note | Acceptance Criteria: Manufacture of the precast beam units shall comply with T-CES 221. Concrete shall comply with T-CES 102. Beam drawings and specifications to be signed off by Engineer.
label | f4b7bcb4-b993-5380-b561-f3e3a88e6a98 |  | note | Frequency: Prior to the casting of the precast beam units.
label | 2bb404a9-9491-583f-8ad8-26b54dd72f15 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | ccb3e50f-e759-5710-8cfe-d244a7c7927c |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | ABUTMENT A
checkpoint-status |  |  | checkpoint | 1.7 - Confirmation of Ground Conditions
label | 06dcbf3e-aa41-58f2-a9ee-4430f7ee8c19 |  | note | Activity Task: Confirmation of ground conditions.
label | e983a325-1d64-5a00-8387-b9ff8d984bdd |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 2ab2b7c9-ac59-5976-9714-36f06abf5ac4 |  | note | Frequency: After excavation and prior to any construction, installation or backfilling.
label | 596364c0-8278-58f8-8e8d-7525517c07d4 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 810c312e-b810-5ca2-88d2-8ec364962258 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.13 - On the Completion of the Installation of Each Timber Pile
label | 31850f31-9e99-51d2-833e-4bb9a15a189d |  | note | Activity Task: Provide records of the installation of each timber pile.
label | 5f91d553-db56-5653-aea9-57c9318c8abc |  | note | Acceptance Criteria: Records completed and accepted by the Engineer.
label | d04812ba-d7f0-56b5-adb9-34097065093f |  | note | Frequency: At the completion of timber piling works.
label | 9de80572-2cc6-5c08-8efd-3ff70e70f2c6 |  | note | Certifying Documentation, Record or Checksheet Completed pile card for each pile installed.
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Piles
label | a356cbd3-3926-57a9-8d5d-559cef00b02c |  | note | Activity Task: Concrete mix design for abutment A piles.
label | 74566e78-a8f9-57c9-a66c-6c8b9b53c4c3 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 78c68fe9-6e9a-5e20-b2bd-023767a4b33d |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 44cfbe64-e38d-5da2-aff7-031bf122fdc4 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 63784bd4-7fb5-5506-8b07-42585d35f318 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Abutment Beam and Wingwalls
label | 6d9b315f-a43a-5c71-85fe-68d8851a3e62 |  | note | Activity Task: Concrete mix design for abutment A beam and wingwalls.
label | 5526386e-c202-533c-be60-851cd4e590d2 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 2e05a0c6-b3a2-51f3-868b-52e8736cdb1e |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | bffc874b-5719-5efe-a292-199652120837 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | c004e2a5-95c4-535a-a03e-5ff510412ac2 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Settlement Slab
label | b234b290-5325-568e-b128-6240a8dca681 |  | note | Activity Task: Concrete mix design for the settlement slab.
label | 4158d72c-826a-5063-825a-8bdd6e392dfd |  | note | Acceptance Criteria: Signoff by Engineer.
label | 4fdb40c5-acbd-5b1a-89d5-5dc0256a6f3b |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 49abd927-e28d-5c48-b2de-3506d81f5070 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 64037143-8030-533e-87b7-eef4e5cddb18 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.7 - Pile Setout
label | 1876b16a-9e6f-5f7f-9227-afecaddf29b4 |  | note | Activity Task: Set out of each pile
label | 447d9924-c5fb-5f1e-8223-ea73f9b24a9f |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | 115f130b-af86-567d-a70c-65e26fd13495 |  | note | Frequency: Prior to commencing any piling works.
label | 26503e5a-3f0c-53f6-9312-61822c8435c6 |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | 473e4161-71a8-5fb9-ae41-ec574ba60557 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.8 - Pile Preparation
label | 1f33f2c9-ef6f-5066-876c-66aab2269637 |  | note | Activity Task: Pile preparation prior to driving including pile set-out survey.
label | e75cbb0f-9e57-5732-943e-f29041fb5947 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 8f360776-75aa-5a79-808b-6d0d01c77cde |  | note | Frequency: Prior to driving piles.
label | bc7a5fbb-740b-56d8-9ac8-23984592906e |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | 0c8a783e-5380-5804-8370-31c73d6aba16 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.9 - On the Completion of the Installation of Each Pile
label | ad22c04c-eebb-55ea-9e76-58038aa3de5d |  | note | Activity Task: Provide records of the following for each pile containing information required in 12.5.1(f) in the Project Specification.
label | 76d5b260-4481-58f1-b086-7f553f1a4288 |  | note | Acceptance Criteria: Records completed and accepted by Engineer.
label | fab80f30-9706-56c0-ad94-802a4cc27426 |  | note | Frequency: On the completion of piling works.
label | 148b6f1b-7eae-5dbc-84f7-c8330621622f |  | note | Certifying Documentation, Record or Checksheet Complete piling records for each pile constructed. ITP signoff.
label | f458676a-d178-5d75-b3f0-448cc3636e50 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing - Piles
label | 175def24-2ac1-5110-947a-9ed0cf6554ca |  | note | Activity Task: All reinforcing prior to pouring concrete for the piles.
label | 119d7eb5-e382-5cdf-bf3c-d3dce95180d1 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 4448f95e-a544-543b-96fb-88295632cec2 |  | note | Frequency: Prior to pouring concrete.
label | 4f9b9d01-ec43-5667-bc4c-651d0762e9d2 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 82deb796-6761-5d87-8b34-5b1bf386b26f |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing - Abutment Beam and Wingwalls (Precast Components)
label | 3df7499d-e45a-56e9-b994-4df706dae93b |  | note | Activity Task: All reinforcing prior to pouring concrete for the precast components of the abutment beam and wingwalls.
label | 8583da8a-04a7-5858-8192-3283a1eea400 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 01743ffc-306c-527f-a927-9885352856a7 |  | note | Frequency: Prior to pouring concrete.
label | a4e053f9-3600-5330-b56f-fa8a9f474efd |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | b7fac549-99fd-5697-8a41-c5949ca329c3 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing - Abutment Beam and Wingwalls (to Bottom of Upstand)
label | ab29d64c-23d8-550b-839f-d172653e90ab |  | note | Activity Task: All reinforcing prior to pouring concrete for the abutment beam and wingwalls.
label | 993f3fdd-e660-5439-9c01-cfe953113b40 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 863ef745-04c2-5777-8272-8e8d36d8f15c |  | note | Frequency: Prior to pouring concrete.
label | 4d6efcec-fd51-5c06-ad08-99345073bca0 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | ee0243ab-4907-5268-b3a7-4dcd200539de |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing - Upstand and Wingwalls
label | 590c5730-69ae-5dfd-a05a-fb616550bda0 |  | note | Activity Task: All reinforcing prior to pouring concrete for the Abutment A upstand and top of wingwalls.
label | 7006dd6e-23e9-5d50-b68a-331d618e3e65 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 1c7c0415-58b8-5a97-affb-8b83e117e8fe |  | note | Frequency: Prior to pouring concrete.
label | aaf0583a-a5ee-56a2-b738-7752ccf3cdf2 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 9189713d-e58a-5457-b4be-cfd450ad07ff |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.11 - Pre-Pour Inspections for Each Pile Casing
label | ed78c8be-ed7e-5f96-9f1f-f137b4a96904 |  | note | Activity Task: Pre-pour inspection for each pile casing.
label | 28d3d954-1d8f-5c89-94c0-851cb558e7d1 |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | 7c2673e3-1017-5626-8a8d-b525d2a841f9 |  | note | Frequency: Prior to pouring concrete.
label | ed85c7e0-43c1-5627-b6d1-80ad826e171a |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 67276a7b-47cc-5c70-ae15-83d4271aadf3 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Abutment Beam and Wingwalls (Precast Components)
label | e2416486-59b6-510a-b29b-463f5caaeadc |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 2621c88b-cfd9-5437-a7dd-e0543354e6ac |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 9587b846-f9a7-539b-af69-ca2eae3fc348 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | e17433a9-76bb-5e71-b511-b4d07d836322 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | add873ff-658d-59a9-a6a8-eff5ca58ee15 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Abutment Beam and Wingwalls (to Bottom of Upstand)
label | 6893d9d0-d8d3-54eb-b04f-caba74e68a97 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 607533bb-d7e3-541d-9b94-0984a36c7537 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | c3272797-de02-5451-b2f4-036a8458b783 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 89d58526-80e0-50b3-9331-a33f3d380deb |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | d2e9bfa7-eba4-5ff0-90c4-10b1686daf51 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Upstand and Top of Wingwalls
label | 079c2d27-9335-575a-9baa-c344f48a4473 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | a343eda8-e7d3-56c6-8050-c0ce101aae1b |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 5fd4c473-d23b-57ae-84a1-39e7028a29cc |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 323699c5-8f4e-5023-aa93-4cbaea45c9f4 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 623cef70-e488-5ae1-929b-4049481f7cd7 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.1 - Abutment Beam
label | 000ab504-2f3c-5ad2-a00d-c7f41040c17d |  | note | Activity Task: Pre-pour inspection for each abutment beam.
label | 431e7e29-bc0b-5849-9870-a9b29d96bb13 |  | note | Acceptance Criteria: Abutment beam installation shall be within the tolerances set out in T-CES 102. Visual inspection and acceptance by Engineer.
label | f88f37a7-5390-5ee1-aa79-585919a594c1 |  | note | Frequency: Prior to pouring concrete.
label | 3b2e0b5f-797e-5671-8809-dfad9740acaa |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 899bf289-6737-57e6-8df0-9e009bed64ef |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.11 - Filler Board
label | ee96aa68-90ae-5ff9-a817-1b01c3e8c2a7 |  | note | Activity Task: All compressible filler board prior to covering over or pouring concrete.
label | 68aa4f81-13af-5dad-8fcd-e6959f20625d |  | note | Acceptance Criteria: Engineer to be given the opportunity to inspect filler board prior to covering or pouring concrete.
label | 708058a4-dc81-55f5-95a5-daab50b4be03 |  | note | Frequency: Prior to covering or pouring concrete.
label | 046b4406-3a12-5cb8-9782-ac6a2feef774 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | bbf7c4c2-457a-5890-9669-d82e0c048819 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.12 - Upstand and Top of Wingwalls
label | 2f9dcd45-d718-53c8-a54e-46d578e026fd |  | note | Activity Task: Pre-pour inspection for each upstand.
label | ac78dae0-c6ae-55ce-99eb-d19a43dfd06f |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 99904cd8-2b74-59f7-8c9b-0a1283df9af0 |  | note | Frequency: Prior to pouring concrete.
label | e266b2b0-9dbc-5639-81ad-9796516425e6 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 00bcd97d-7f91-5059-882b-48e139f45da6 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.3 - Granular Backfill
label | d383b9ad-5690-5894-ac24-89186c68c6be |  | note | Activity Task: Prior to backfilling to any part of the abutment or any abutment drainage. (Note: Existing drainage to systems behind abutments shall be protected during backfilling operations).
label | 3a107f83-0572-5e8b-8dd0-dcdf017eedf5 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | a0f1c0f3-4e1a-50b7-b438-40a85bbe2bb5 |  | note | Frequency: Prior to backfilling.
label | fb60608a-337c-58d5-95b2-c1b05e4a7ab3 |  | note | Certifying Documentation, Record or Checksheet Photos. ITP signoff.
label | f49f7215-d63d-5d05-8a3f-997241205f6f |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | PIER B
checkpoint-status |  |  | checkpoint | 1.3 - Proving Bores
label | b586e6a8-5057-5e95-9707-7ac88cb4d07e |  | note | Activity Task: Proving bores.
label | 6eef728a-c35a-543d-b068-53131963017f |  | note | Acceptance Criteria: Bore logs signed off by Engineer.
label | 29f92a26-bd43-5b8e-af2c-632a99c35909 |  | note | Frequency: Boreholes completed at the pier and eastern abutment.
label | 61c770d1-5a2b-5812-969a-cb4b91586060 |  | note | Certifying Documentation, Record or Checksheet Bore logs. ITP signoff.
label | 0df65e7b-8931-5e97-9e9c-08032e88fd2c |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Piles
label | 16164d55-5298-5fad-ab8e-4e395fa7a0b8 |  | note | Activity Task: Concrete mix design for the pier piles
label | cebf3e37-4f7a-564a-ae8b-806769f0369b |  | note | Acceptance Criteria: Signoff by Engineer.
label | 7f591045-55d5-529d-b338-74c9050c06ab |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 255c5dba-842b-5a7f-b911-59605807a974 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 34b13156-ab72-54a0-b6de-96e2b8edb318 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Pier Capping Beam
label | da1bdee9-38c1-5e66-a53b-f53bc93e042c |  | note | Activity Task: Concrete mix design for the pier capping beam.
label | 9f864d97-c64c-5124-bcd9-b3dd9e63de12 |  | note | Acceptance Criteria: Signoff by Engineer.
label | f930f5c3-fd01-559b-b70d-0e8ba42c631c |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | c2e9800d-84b2-5a27-9eaa-ef2baaf12a23 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 46913e8e-4663-504a-9bb8-2229af795b06 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.7 - Pile Setout
label | 25e23ed2-a4de-5ae0-8730-b3bfd475de32 |  | note | Activity Task: Set out of each pile
label | 18605743-6044-5e93-a8bf-a9f4c84332ce |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | 9de41725-32c6-59fc-b3bd-e4dd296be3ff |  | note | Frequency: Prior to commencing any piling works.
label | f18712eb-acac-51a1-a6c4-340ab0311e25 |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | 2c6d08e4-a6bb-57a5-b49e-e0036b3c6dca |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.8 - Pile Preparation
label | 717ac242-f9d0-5797-9fe9-6c93a6e1cd7c |  | note | Activity Task: Pile preparation prior to driving including pile set-out survey.
label | 0b4f8436-ab33-5020-bdbf-3b207c301aec |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 53c0175a-4553-5691-b2c6-4a87a63edc0d |  | note | Frequency: Prior to driving piles.
label | fa31eb91-baf9-5c97-b503-246bd734ecf3 |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | a981912f-7f45-5378-9c9b-19e9bec6ab43 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.9 - On the Completion of the Installation of Each Pile
label | 15dc2755-3f20-5a46-8ec8-872c1fcfd6a6 |  | note | Activity Task: Provide records of the following for each pile containing information required in 12.5.1(f) in the Project Specification.
label | 4125f26a-0387-56cd-8e3b-30155fc78fbf |  | note | Acceptance Criteria: Records completed and accepted by Engineer.
label | 809a2578-fdab-5faf-92e6-88bcb39651e7 |  | note | Frequency: On the completion of piling works.
label | eb093b2b-e72f-5ff8-877a-e885e55fe72a |  | note | Certifying Documentation, Record or Checksheet Complete piling records for each pile constructed. ITP signoff.
label | fb74950f-0fa3-55f6-9649-cce520d71339 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Piles
label | 6f5c6afa-4bbf-53ff-8424-35ed525ad914 |  | note | Activity Task: All reinforcing prior to concrete pours, including pre-fabricated elements.
label | fce3aa63-5c5a-50ea-a718-63f3ce09a840 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 0685e5d0-a6c3-53df-b1f7-ef62c7dc0371 |  | note | Frequency: Prior to pouring concrete.
label | af3e9c34-5e38-53e5-b4ff-338f8f34b258 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | a9844816-a202-58ef-93e6-9ef17e94674b |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Pier Capping Beam (to Bottom of Upstand)
label | 1348d314-94c6-5a48-8f38-221236f764db |  | note | Activity Task: All reinforcing prior to concrete pours, including pre-fabricated elements.
label | 5f06cbc7-48a2-5e4b-8196-8869c5c2deee |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 2fd80a24-c595-5935-bfe7-bc339324b6e1 |  | note | Frequency: Prior to pouring concrete.
label | d93e877b-e20b-5803-ab23-c1bdb44aa7ba |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 1c21655a-e158-514d-b72f-2ffdcd983d92 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcing - Pier Capping Beam Upstand
label | 86d23963-d704-5549-9c54-95587be093df |  | note | Activity Task: All reinforcing prior to concrete pours, including pre-fabricated elements.
label | ca7263c8-c79a-5ebf-b00b-0b28b0891405 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | b4a560a5-a1e1-51ce-9582-b3a8b74fd7f1 |  | note | Frequency: Prior to pouring concrete.
label | eaf6addc-c625-5dc4-8177-34207383911e |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | ec67ed6a-ec50-5870-88fc-7e3e8c59c9ee |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.11 - Pre-Pour Inspections for Each Pile Casing
label | 81996ffa-7630-5ca7-a3be-40b6a6253ee6 |  | note | Activity Task: Pre-pour inspection for each pile casing.
label | f872966b-ed45-55e8-94c7-87fa40f06ecf |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | 156ce216-6c07-55ef-bbb6-514a8e251aa1 |  | note | Frequency: Prior to pouring concrete.
label | 38b26628-dc2f-599b-bbab-7b9f4a707d17 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 178f318f-46c4-50b5-af87-27f928227e3c |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Pier Capping Beam (up to Bottom of Upstand)
label | f3662173-e660-54ce-9657-f38c26e2b2b9 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 2ca9647c-5909-504b-9a0b-75271b9855b7 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 8080844d-8a76-5017-939d-96f9fb9488af |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | cff3edc3-092e-5031-a370-b4d6ef8aea99 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | f03cbd92-e4c5-5fd4-b386-2ac3785d69c0 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Upstand
label | d7965166-d0cf-531a-8d35-d5c852ab3799 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 1096d82e-2892-5858-aa94-2ad7caaeb1f9 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 64e87d14-3fb5-5d08-84f7-8c463abe7c43 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 78e90635-b00e-5d4f-b83f-3b784e76ee38 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | b2fbaee2-a859-56eb-a4ee-7bbfb12f2b37 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.1 - Pier Capping Beam
label | 16faeb12-c3d0-5a57-bfce-9f06a185e6a7 |  | note | Activity Task: Pre-pour inspection for each abutment beam.
label | 80e2eabf-cde2-5ced-ae69-44c3db95c093 |  | note | Acceptance Criteria: Pier capping beam installation shall be within the tolerances set out in T-CES 102. Visual inspection and acceptance by Engineer.
label | c56402e2-d901-5231-81c5-12d846813977 |  | note | Frequency: Prior to pouring concrete.
label | d4d01d46-42ca-5b7f-91ba-f32494011ada |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | d655ec35-9e05-5a22-8510-2147dfde3404 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.12 - Upstand
label | f7eb4030-1d55-5344-b7a0-ee1d06a694cd |  | note | Activity Task: Pre-pour inspection for each backwall.
label | 9d07ae2e-23e4-51e0-ba49-2339e028ae9a |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 37c77c83-b71e-5f6c-ae15-bae17a61f21f |  | note | Frequency: Prior to pouring concrete.
label | 878b6561-b83b-509f-bd89-b07f9a8fa474 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | ce27f9fa-38a9-5a6e-a591-80d6242ca907 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | ABUTMENT C
checkpoint-status |  |  | checkpoint | 1.7 - Confirmation of Ground Conditions
label | c1faae98-6602-5a2d-9f55-c2abda8aa326 |  | note | Activity Task: Confirmation of ground conditions.
label | 1d34514e-7197-558f-b9da-3c8f250b8110 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 84b0938a-bc46-5d0d-9184-4061fe92bf95 |  | note | Frequency: After excavation and prior to any construction, installation or backfilling.
label | 1166f189-e9c8-5317-af1c-bc2ae9b67111 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 8ab0136d-8859-5660-988b-6d4c273ad5dd |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.13 - On the Completion of the Installation of Each Timber Pile
label | b4008aeb-2d00-5ea7-adbc-74ec381f02e1 |  | note | Activity Task: Provide records of the installation of each timber pile.
label | 7108b20d-77ac-5833-8eae-0884e36e850c |  | note | Acceptance Criteria: Records completed and accepted by the Engineer.
label | 9c6cef22-0b13-5156-bd1c-70b701f9bc4d |  | note | Frequency: At the completion of timber piling works.
label | d4b76e1d-7aca-5588-aa38-7617dd7ff9bf |  | note | Certifying Documentation, Record or Checksheet Completed pile card for each pile installed.
checkpoint-status |  |  | checkpoint | 2.13 - Additional Timber Piles - On the Completion of the Installation of Each Timber Pile
label | dab9c841-d04c-5fa5-b7a9-e4aae3808350 |  | note | Activity Task: Provide records of the installation of each timber pile.
label | 5d703936-e5cf-5233-b0dc-1f75724cb16f |  | note | Acceptance Criteria: Records completed and accepted by the Engineer.
label | b7665b04-0ad9-5d89-b197-126f7e898caf |  | note | Frequency: At the completion of timber piling works.
label | f894d88b-4b4f-53ad-b0a2-b175cacf0112 |  | note | Certifying Documentation, Record or Checksheet Completed pile card for each pile installed.
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Piles
label | 9444ed72-4a73-537e-8875-75a61155de1d |  | note | Activity Task: Concrete mix design for abutment A piles.
label | 9ee6fa17-e59d-5686-9895-4612218e0fac |  | note | Acceptance Criteria: Signoff by Engineer.
label | ad71cbc2-bf52-5595-8f85-3f953d0a9add |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 301934a9-6675-55e4-912a-55ce38d4c27e |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 7bb264ec-5570-5fec-8541-546e303b8594 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Abutment Beam and Wingwalls
label | b3026a29-105f-5d2b-925a-9abd0697a84e |  | note | Activity Task: Concrete mix design for abutment A beam and wingwalls.
label | 212a27d7-592c-5761-81b9-1bfa64c4e6f3 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 01044d53-3d49-5089-8345-ea530152b7a7 |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | e0667c0b-8d00-5216-873a-ed3183b89152 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | c8c5198c-db37-5a98-ac5c-37f7545d7df6 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Design - Settlement Slab
label | 8a442138-d9ab-549b-97c7-ca8a2c4d6aa8 |  | note | Activity Task: Concrete mix design for the settlement slab.
label | 8582936c-8c2b-5d0a-8deb-80c9a5a3b3f4 |  | note | Acceptance Criteria: Signoff by Engineer.
label | fa311223-a6f3-58a7-be4e-64624bcb0587 |  | note | Frequency: Mix design must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | de470102-233b-51e8-8ae4-9dd274db5c60 |  | note | Certifying Documentation, Record or Checksheet Concrete mix design.
label | 21adbb53-54c8-50a4-9b62-6dfa9010b3a5 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.4 - Sheet Pile Setout
label | e792257b-7a96-59fd-8488-e2e5d27985fe |  | note | Activity Task: Set out of line of front sheet piles. Set out of line of side sheet piles.
label | 7be1471d-6c7c-50df-a81b-33da7ac7f062 |  | note | Acceptance Criteria: Line of front sheet piles set out as per design. Line of side sheet piles set out as per design.
label | 500d2a10-a98e-5dfe-8bd1-22eb5cdf5476 |  | note | Frequency: Prior to driving sheet piles.
label | 275930c3-4012-5681-879e-51972914d2e6 |  | note | Certifying Documentation, Record or Checksheet Sheet pile set out confirmed by surveyor.
checkpoint-status |  |  | checkpoint | 2.5 - On the completion of the installation of front sheet piles
label | 5d138759-cfba-5f65-b166-aa5eaf55f2da |  | note | Activity Task: Provide as-built records of the installation of the front sheet piles.
label | 41c045f0-ffe3-5a51-8f17-3a7d7b19e342 |  | note | Acceptance Criteria: Front sheet piles are within tolerance, +/-75mm to design line. Height within +/-40mm.
label | 7f2a374d-537b-5256-b5f8-d985e40df5fa |  | note | Frequency: On the completion of the installation of the front sheet piles.
label | 7408e3ee-1cb8-5557-8924-d091254f6fea |  | note | Certifying Documentation, Record or Checksheet As-built records completed. ITP signoff.
checkpoint-status |  |  | checkpoint | 2.6 - On the completion of the installation of side sheet piles
label | b21e70b1-7180-5d8b-a305-637076cc37d7 |  | note | Activity Task: Provide as-built records of the installation of the side sheet piles.
label | a9f811f9-2e7b-5b44-9857-326686a13112 |  | note | Acceptance Criteria: Side sheet piles are within tolerance, +0mm/-150mm to design line. Height within +/-40mm.
label | 01adf80f-b2d9-5454-8a31-f83ed180def3 |  | note | Frequency: On the completion of the installation of the side sheet piles.
label | befc3338-1192-54be-bef2-04497aabc677 |  | note | Certifying Documentation, Record or Checksheet As-built records completed. ITP signoff.
checkpoint-status |  |  | checkpoint | 2.7 - Pile Setout
label | 3c79f830-c4c1-516c-8fcc-3fe467fbff94 |  | note | Activity Task: Set out of each pile
label | 2364f1f3-27c6-5775-9db0-9af85dc134f8 |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | b9f7e041-fc62-592b-aea0-312176522d00 |  | note | Frequency: Prior to commencing any piling works.
label | 2940df2e-bdb9-5bed-a9cf-e4a65a026035 |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | 20b17988-29d9-5454-9d43-a72f2b0d8790 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.8 - Pile Preparation
label | b076c4bd-634d-5264-992b-5b0a9431a33e |  | note | Activity Task: Pile preparation prior to driving including pile set-out survey.
label | 6c6e700d-1063-5915-a83a-16b6adfc1826 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 33b1ffc6-41b5-57b4-85fd-fe5282306ff0 |  | note | Frequency: Prior to driving piles.
label | c457930a-9b63-58e8-bf70-fca8a0e7892c |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | 83dcb3ed-346a-5693-806f-d407a0eedfd4 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.9 - On the Completion of the Installation of Each Pile
label | 934c4c10-e295-5191-88d0-db4e66bf5204 |  | note | Activity Task: Provide records of the following for each pile containing information required in 12.5.1(f) in the Project Specification.
label | 0b22f390-84c6-55be-bc63-5dd1ab3ef084 |  | note | Acceptance Criteria: Records completed and accepted by Engineer.
label | e9a64a0a-3671-572b-891e-db78cb42be1b |  | note | Frequency: On the completion of piling works.
label | a5ec814d-dae1-5e14-b896-cdf27d1f004c |  | note | Certifying Documentation, Record or Checksheet Complete piling records for each pile constructed. ITP signoff.
label | 5bb14adf-88f2-53f3-8791-6294d3e9f1b7 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Piles
label | 5e0be66a-6808-5582-b2b5-7b9428b547b9 |  | note | Activity Task: All reinforcing prior to pouring concrete for the piles.
label | f038c592-f786-5bd0-a0ee-8626e8a541bb |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | b6eebc22-32e5-596b-8e12-d73c96a55b93 |  | note | Frequency: Prior to pouring concrete.
label | c8f5f990-8f39-5718-8a50-f033934a713f |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 8e99ce7d-8ece-51b4-ad8b-eb53d39ace9c |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Abutment Beam and Wingwalls (Precast Components)
label | e684fdcd-53d2-573c-8d8f-7526dabe2d3f |  | note | Activity Task: All reinforcing prior to pouring concrete for the precast components of the abutment beam and wingwalls.
label | 6c61f421-6c74-5d3e-bb93-13e1687ad1cc |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 4ba66f47-480a-5113-8a68-a7a6523dfff7 |  | note | Frequency: Prior to pouring concrete.
label | 66d0a6b1-d47c-5a89-b6aa-6a217dae5795 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | f1885059-b7e9-5fb9-a35c-adc1dd09bd96 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Abutment Beam and Wingwalls (to Bottom of Upstand)
label | 430849f3-45b3-5060-b206-88fb2313851f |  | note | Activity Task: All reinforcing prior to pouring concrete for the abutment beam and wingwalls.
label | 612faad8-6c48-5265-9ac3-7d44e0f0abdd |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 13e809c6-6bd9-56e4-b90f-adb05bb57387 |  | note | Frequency: Prior to pouring concrete.
label | 5fb70cad-c80f-5c37-a05f-02f976e4f7a7 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 15674040-7003-5e46-ac6e-a16d4e256756 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.10 - Reinforcing - Abutment Beam and Wingwalls (Precast Components)
label | d4d02e76-71d5-549a-ba85-85be48599879 |  | note | Activity Task: All reinforcing prior to pouring concrete for the Abutment C upstand and top of wingwalls.
label | 9d46ace7-aab5-50f0-b1c0-e97a1124cc3c |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | d4899ee9-2784-54ed-ab49-78d084e95fd4 |  | note | Frequency: Prior to pouring concrete.
label | 44cbf844-6d3e-57dc-b031-012c61615bc9 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 0a4013c5-18f2-5d77-81ac-dbd9dc75b8d6 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.11 - Pre-Pour Inspections for Each Pile Casing
label | c2b44ef1-bad1-500d-9c02-34466cd457f0 |  | note | Activity Task: Pre-pour inspection for each pile casing.
label | 3c077dc6-fbdf-50bf-bc14-52540e6cbc4c |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | 89ac4fb6-cdea-5ede-8f3e-220d73e161dd |  | note | Frequency: Prior to pouring concrete.
label | ea8fada7-b7ec-53b4-b579-b03f952b0662 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 3c3ce792-26ed-583b-844c-a24fe6e17ee2 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Abutment Beam and Wingwalls
label | 9ccdb942-6dfc-5887-aa23-9315b0055f5c |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 2f97e54c-e097-52c7-985f-339cc9a3df3e |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 2e399812-e613-5215-8295-e8189e6e41d4 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | b14d8029-158b-58d8-9dd5-6d38777d1c31 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | fc8793b1-d285-50c0-a246-5d6dd84c8bef |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Abutment Beam and Wingwalls (to Bottom of Upstand)
label | db9160d9-732c-5167-959e-f93830a283fe |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 8169392a-340f-505d-9fac-ad73e36b6adc |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 7404b615-f0ef-5667-b762-b0cfe5754ef2 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 0b9dbdfc-7e55-5f59-892b-a8c4b998f081 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 3075962f-7b84-58de-aa4e-257c7f1c2d2e |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 2.12 - Formwork - Upstand and Top of Wingwalls
label | df90dc64-04a7-5c45-a4d0-ab81622697b9 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 29feef20-08e8-5dc2-b3ed-a61f5f097d3d |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 6f89b1ce-2d4d-55a8-b0c4-00e9614a1891 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | e5f9579a-7b1d-51cf-817a-8b871e4fe476 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | ef74eca5-f801-5549-a21b-fd798d9e7b7b |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.1 - Abutment Beam
label | 829ce12b-b6a2-59d1-8be2-adc9b2823359 |  | note | Activity Task: Pre-pour inspection for each abutment beam.
label | 36ba7c99-0ba1-5696-8fd6-7b5c155612c6 |  | note | Acceptance Criteria: Abutment beam installation shall be within the tolerances set out in T-CES 102. Visual inspection and acceptance by Engineer.
label | 532385d2-effb-5d41-a77f-bd2a445a0ad4 |  | note | Frequency: Prior to pouring concrete.
label | 4aed432a-e2b2-52a0-bb46-91e9b4777342 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 37fa526b-bcaf-58dd-87fa-fe45bed2918b |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.11 - Filler Board
label | fd0d60a3-0f19-59d9-bdb3-7924d4345731 |  | note | Activity Task: All compressible filler board prior to covering over or pouring concrete.
label | e4875eae-3dc7-5183-b849-22638fac7b1b |  | note | Acceptance Criteria: Engineer to be given the opportunity to inspect filler board prior to covering or pouring concrete.
label | 2e507519-4cee-5d6b-a77b-22e880263ae5 |  | note | Frequency: Prior to covering or pouring concrete.
label | 07794ed2-4276-5e9c-8fe6-44bc7f50ddc7 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | ebaa821e-c0ef-55a5-bdf4-dc885f2f0280 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.12 - Upstand and Top of Wingwalls
label | 574ed202-7dd7-5328-ae9d-355d35a581d5 |  | note | Activity Task: Pre-pour inspection for backwall.
label | ba4ece0d-f4d7-5f6f-9040-0187c6cd2663 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 304dde11-e715-568c-bd40-161b48200c14 |  | note | Frequency: Prior to pouring concrete.
label | 666dc960-e700-5008-83a0-e976bf3b8fdb |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | a8de88f8-79b8-51fa-8329-cea39a7742ce |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.3 - Granular Backfill
label | 8e72d10c-6011-5fe1-adb6-fed9d9e6369f |  | note | Activity Task: Prior to backfilling to any part of the abutment or any abutment drainage. (Note: Existing drainage to systems behind abutments shall be protected during backfilling operations).
label | c507debc-5622-573d-a690-208717f7eb3f |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 14b0bf60-7320-553d-b2fc-c859e5f71da5 |  | note | Frequency: Prior to backfilling.
label | 0db6f693-536b-5a8c-8b20-4704e962dd49 |  | note | Certifying Documentation, Record or Checksheet Photos. ITP signoff.
label | 24182850-33af-51f7-b2ee-8194e4fa4fad |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-group |  |  | section | SUPERSTRUCTURE
checkpoint-status |  |  | checkpoint | 3.2 - Shop/ Fabrication Drawing
label | dc652e6e-eda1-57bb-a247-6b68d477b375 |  | note | Activity Task: Shop/fabrication drawing review.
label | 9c1c9c03-2a9a-51e2-870f-37660737c589 |  | note | Acceptance Criteria: Shop drawings for all precast elements provided to the Engineer for review at least 10 days prior to casting. Shop drawings to include all geometry and details as set out in Clause 27.7.8.1 in the specification. Acceptance of shop drawings required by Engineer prior to the units being cast.
label | 7751baa7-2529-54dd-9e06-4b05e2678510 |  | note | Frequency: Drawings provided to Engineer for acceptance at least 10 days prior to any units being cast.
label | e7d87d8c-076b-5c27-a28a-883a2296dc33 |  | note | Certifying Documentation, Record or Checksheet Shop/fabrication drawings. ITP signoff.
label | 78a3f736-e3a9-5b54-8917-5db23dc8f769 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.3 - Casting of Precast Beams
label | 27f9b62e-035e-5f91-bb09-bf030bfe5050 |  | note | Activity Task: Casting of precast beams.
label | 27eef1c5-a2da-5768-9567-187bb1be8d48 |  | note | Acceptance Criteria: Manufacture of the precast beam units shall comply with T-CES 221. Concrete shall comply with T-CES 102. Beam drawings and specifications to be signed off by Engineer.
label | 328874c6-66c7-584b-988d-60a870cc7f84 |  | note | Frequency: Prior to the casting of the precast beam units.
label | fc95edf8-f1c5-5f24-998d-5a7f376b6cda |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 705854a5-c71e-5200-9b3d-04011b75fdc2 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.4 - Set-Out Survey
label | dbfa5102-93d9-55bb-b4f2-dfd524d0bbcb |  | note | Activity Task: Survey set-out of precast beams.
label | 24e375e0-4e83-58b4-b5b2-eccdbb429a8e |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 34ae53cc-285c-5d06-af2e-e2d641730a29 |  | note | Frequency: Prior to commencing any work on site.
label | 18fcb6ff-2851-5359-9194-6810fd4cba49 |  | note | Certifying Documentation, Record or Checksheet Survey records and photos. ITP signoff.
label | dd03c568-6260-550b-9e09-9c0ec1fcbd00 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.5 - Concrete Mix Design - Precast Bridge Beams
label | 66cb14df-094d-57f6-8010-a90a1bbe5930 |  | note | Activity Task: Concrete mix design required for the precast bridge beams
label | 0fc35c68-7f63-557c-8f38-6d97be87f6d5 |  | note | Acceptance Criteria: Signoff by Engineer.
label | 00e81389-db32-5b80-bab9-08c60476cc28 |  | note | Frequency: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 7d4c1e91-2339-5b7f-9422-fe090c52ce8f |  | note | Certifying Documentation, Record or Checksheet Concrete mix designs.
label | 597f80dd-92f4-5803-b00a-c14683e79581 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.5 - Concrete Mix Design - Beam Infill Concrete
label | 65b87606-88ca-5e5c-87ee-32eed0788123 |  | note | Activity Task: Concrete mix design required for the beam infill concrete
label | db4c0b21-515a-53a4-8ea7-3c92a093e18d |  | note | Acceptance Criteria: Signoff by Engineer.
label | f54b372a-7a68-52f6-bc79-bc4c66e2b5db |  | note | Frequency: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 7fb78bfe-5551-514d-9534-dc744bf1c9a4 |  | note | Certifying Documentation, Record or Checksheet Concrete mix designs.
label | 3ed2246e-319b-58d8-81cd-0f220a947120 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.5 - Concrete Mix Design - Settlement Slabs
label | 2509bdf6-b5a1-5eec-983f-427bad2e1321 |  | note | Activity Task: Concrete mix design required for the settlement slabs
label | db7e379b-fe9b-5519-ab9c-d86b325e5971 |  | note | Acceptance Criteria: Signoff by Engineer.
label | c05ad5c9-4eea-5e52-92fa-695e0f260104 |  | note | Frequency: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 45dbf48a-2a92-586a-855a-7923629fffdf |  | note | Certifying Documentation, Record or Checksheet Concrete mix designs.
label | a1535824-e34b-56e3-82fa-1ffa016e876f |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.5 - Concrete Mix Design - Shared User Path
label | 43040f06-f2d6-52df-a4dc-71b2bfd89d05 |  | note | Activity Task: Concrete mix design required for the shared user path
label | de332f1e-d9ef-5183-8025-0673deb66baf |  | note | Acceptance Criteria: Signoff by Engineer.
label | fceb5372-6236-5bf5-b69e-b77d091ac64c |  | note | Frequency: Mix designs must be submitted to Engineer for review at least 14 days prior to the concrete being required on site.
label | 146726d3-7a5f-5e8c-a5af-69eb0672241f |  | note | Certifying Documentation, Record or Checksheet Concrete mix designs.
label | 9c441358-35f3-5d18-a04f-115fcf05865e |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.6 - Reinforcing - Precast Bridge Beams
label | 8f4b6f05-1b17-5536-a692-fadd0d553fab |  | note | Activity Task: All reinforcing prior to concrete pours for the precast bridge beams.
label | af5a0ccf-84ab-5588-a088-ad103ddcaddc |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | f313179c-6429-5ee3-83cf-d2624bb887c8 |  | note | Frequency: Prior to pouring concrete.
label | d2a4dc06-f79b-5e04-b721-222032f50a20 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | 4d496e27-fabc-531b-8241-6938799b9ac7 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.6 - Reinforcing - Settlement Slabs
label | 14260336-8000-5314-b207-b2e7528a8329 |  | note | Activity Task: All reinforcing prior to concrete pours for the settlement slabs.
label | 1e326217-013a-51c8-8a6d-50d55d7b51d5 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | bb8302a9-f82b-5979-befd-5dda6de9c226 |  | note | Frequency: Prior to pouring concrete.
label | ab27dac2-7414-50a9-84a8-328cc55251bd |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | d7f0b454-fa47-5759-a076-97ec955bb8ff |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.6 - Reinforcing Shared User Path
label | 5b61d4dc-c08e-549c-90b2-2112b0918152 |  | note | Activity Task: All reinforcing prior to concrete pours for the shared user path.
label | 5caa4dfe-6b27-529f-af1a-56f8ccb580de |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 8971752d-6451-56fe-9cd6-0e3fe24be56e |  | note | Frequency: Prior to pouring concrete.
label | 6b7a7fd2-f08e-5ff9-bd95-7ed7d776fb02 |  | note | Certifying Documentation, Record or Checksheet Mill certificates for all reinforcing steel, prestressing strands, and structural steel. ITP signoff.
label | ec284341-4deb-58fc-9764-018488c22a76 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.7 - Prepour Inspection - Beam Infill Concrete
label | f3d3fe63-c0e3-516a-b766-4b86cc8a3db7 |  | note | Activity Task: Pre-pour inspection for the beam infill concrete.
label | e4831c9e-3e82-5731-96f7-9384bdb257b1 |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | f4f4c60e-b722-5a02-a54e-7d70a358baa9 |  | note | Frequency: Prior to pouring concrete.
label | a528a12e-b57a-5b3e-a14d-f5e063a4ae84 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 8b14729a-e1d7-5bfc-b8d3-2bc238308ac3 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.7 - Prepour Inspection - Shared User Path
label | 61278e1b-5c8b-5293-adec-bd15bd8bca36 |  | note | Activity Task: Pre-pour inspection for the shared user path.
label | 434be4b8-b622-5e7c-88f7-1c2d27b9ca01 |  | note | Acceptance Criteria: Pile installation tolerances shall be in accordance with Clause 6.1 of T-CES-403. Visual inspection and acceptance by Engineer.
label | e2e07d50-73b1-5c1c-adb0-d233498591b7 |  | note | Frequency: Prior to pouring concrete.
label | 6e53999f-d1af-50f0-90d3-917994ac1033 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 9997e90c-58bc-5ecf-b9d8-17030857aa01 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.8 - Formwork - Beam Infill Concrete
label | ecc883c1-d880-5f33-963a-5be68f2a8299 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 5afa975a-d43c-5c86-b2ce-7de957b73557 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 755d58f2-fe70-51d8-a6f9-54b789e4a1bc |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 84a3aa13-5fc7-563f-8e3f-69d5397d9cba |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | e5687cf3-fd43-5a9b-8937-edb8a7235c90 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.8 - Formwork - Settlement Slab A
label | 926539ff-daaf-5a6b-9774-bbc103bce4c6 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 7be6455f-497e-53d0-8aff-11015efece27 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | b0cf6513-e3fb-5412-8929-3ca927d4027d |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 74b2a303-bb55-5ed7-a6ad-ef0887e4dcc7 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 755c33e7-90c7-5d36-95ab-1079deab9f7c |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.8 - Formwork - Settlement Slab C
label | a30a80a1-7570-587e-938c-f3828db0d5bc |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 560b5245-d01a-5583-9081-24db89adbeb6 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 1ac2588f-dd03-5634-9095-b253e5bae1e1 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 4095172f-de2f-5a79-ac24-520b35b19439 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | ce49eac6-25c9-542e-b173-a0ed81a92a90 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.8 - Formwork - Upstand and Wingwalls
label | 15f3bab5-66e6-57c4-8eb2-1a7de7e33d33 |  | note | Activity Task: All formwork prior to placement of reinforcing and/or concrete.
label | 1bc8d41b-d8cb-5e6e-a1bc-51718c8a58c9 |  | note | Acceptance Criteria: Engineer to be given opportunity to inspect formwork prior to placement of reinforcing and/or concrete.
label | 4b663e17-3552-52b2-a373-a7ba48a27597 |  | note | Frequency: Prior to placement of reinforcing and/or concrete.
label | 889bb343-610f-5787-840e-d71812035bad |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | e8ddf564-adbf-5086-a35d-3931ae5a6ec4 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.11 - Filler Board
label | 3a9cbdff-bdfe-58f1-a500-f1710188cc41 |  | note | Activity Task: All compressible filler board prior to covering over or pouring concrete.
label | ef004707-e529-5260-9996-665c42f40461 |  | note | Acceptance Criteria: Engineer to be given the opportunity to inspect filler board prior to covering or pouring concrete.
label | 1a8119d3-2e82-5290-985f-5b444f35b2b9 |  | note | Frequency: Prior to covering or pouring concrete.
label | d6b3379a-ee4d-590d-80fc-42c733992859 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 8fdfb40b-0f87-5be8-b18d-52f9bdd9dda6 |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.14 - Lifting in of the Precast Bridge Beams
label | 7e26417c-1968-5b9d-82d9-bbc0854694d8 |  | note | Activity Task: Prior to cranage and lifting in of the precast bridge beams. See clause ‘27.11.1.10.3 - Placement’ in specification.
label | dea70981-1403-5f6b-911c-7ea12b3027ac |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | d48aed9b-ecd5-516f-bdac-f96a1ec26e7d |  | note | Frequency: Prior to lifting and placement of the bridge beams. (Note: methodology to be provided to the Engineer for the lifting and placement of the beams).
label | a9adf15e-78a0-5749-9278-e80b556f5433 |  | note | Certifying Documentation, Record or Checksheet Methodology accepted. ITP signoff.
label | 091915a9-3cf5-5367-b463-aae689a5c836 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.15 - Installation of Precast Bridge Beams
label | db3def34-1e15-5acb-8595-0a73a3f76aee |  | note | Activity Task: Engineer given the opportunity to witness the installation of the precast beams.
label | 7ff69c67-c1b1-5322-a8e9-d3c118c580d9 |  | note | Acceptance Criteria: Visual inspection by Engineer.
label | 9b9b3451-75d0-5514-9396-b46d8e141a5d |  | note | Frequency: Provide 24 hours’ notice to Engineer.
label | f024f464-b124-5d6d-ab08-197a2285fd87 |  | note | Certifying Documentation, Record or Checksheet Visual inspection.
label | d8980d2a-6993-5720-81f6-76bf17dcb59b |  | note | Critical Hold Point Authority: WITNESS POINT
checkpoint-status |  |  | checkpoint | 3.16 - Installation of the Precast Bridge Beams
label | d4acfa15-d14f-55e0-bdbc-b58947561f90 |  | note | Activity Task: After the installation of the precast bridge beams.
label | 7658af01-84a8-59cb-a622-f64a421522c9 |  | note | Acceptance Criteria: Beams shall be placed in position and levelled and aligned to the satisfaction of the Engineer.
label | 1a091e6d-bb01-528f-82f7-eed8f3b2ef90 |  | note | Frequency: After the installation of the precast bridge beams.
label | a6707a2a-447d-52ee-98ab-3feaa21936cb |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 4cf2bff8-aa3e-55ca-9bb4-22a9f099be0a |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.17 - Deck Infill Concrete
label | 0721f3a8-35d4-5abe-934d-9a4e6cbe47aa |  | note | Activity Task: Pre pour inspection for the deck infill concrete.
label | dd1ac735-d36a-5ccd-951b-6ab84c49dfe1 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 40846ac6-1a5f-5ba4-95a8-053fd90353b8 |  | note | Frequency: Prior to pouring infill concrete.
label | 3522c7f8-37c2-559b-8eb9-1c87e2d7d7a5 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 79dff0cf-b48d-5a10-9aac-6445b96cf966 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.18 - Transverse Deck Stressing
label | 51b38f5f-a2fc-50fd-845a-c7cc5728751c |  | note | Activity Task: Prior to transverse deck stressing. Stressing carried out in accordance with Section 8, NZS 3109:1997. Post tensioning anchorages to comply with BS EN 13391.
label | 635ae5b1-e0bc-5068-9316-775453233e2d |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | f12682f9-5954-5d2e-b907-ad290824dd7d |  | note | Frequency: Prior to transverse stressing.
label | 344b27a5-ac43-596a-9c18-88a9f9d5b95e |  | note | Certifying Documentation, Record or Checksheet Methodology accepted. Post tensioning records as per Clause 12.5.1g in specification. ITP signoff.
label | 7a49aa15-8fbc-59ec-b3f7-c97e4f7837fe |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.19 - Granular Backfill
label | 13c892e5-311d-5a4d-b886-130825692ae2 |  | note | Activity Task: Test sample to be used to determine maximum dry density and optimum moisture content (NZS 4402:1986 Test 2.8.2).
label | f5ac36d4-ac5c-5526-99fd-b23bdfd7b223 |  | note | Acceptance Criteria: Acceptance by Engineer.
label | ddc0496e-da97-52c0-bf95-fa4133891138 |  | note | Frequency: Prior to commencement of works.
label | c7005cee-e676-5f62-907b-2135938e17d1 |  | note | Certifying Documentation, Record or Checksheet
label | 6d1f272f-a791-584e-9b29-55b068a4e839 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.20 - Granular Backfill
label | ecbccc66-a922-5824-954a-6edd9648dc64 |  | note | Activity Task: Prior to backfilling to any part of the abutment or any abutment drainage. (Note: Existing drainage to systems behind abutments shall be protected during backfilling operations).
label | 168ec2f4-f765-5985-91c7-3d2a0348cdb0 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 25ed724c-74d7-50f6-828c-6532759e74ef |  | note | Frequency: Prior to backfilling.
label | ebe332f3-db33-530c-bfa9-55898a32e4cd |  | note | Certifying Documentation, Record or Checksheet Photos. ITP signoff.
label | 2ff810e4-73f1-5501-9b33-f3cfd6b70eb7 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.21 - Settlement Slab A
label | d44b91d1-a2f1-5329-987e-b36d6e8c6d3b |  | note | Activity Task: Pre-pour inspection for each settlement slab.
label | 5a79bf50-5fe8-5026-a9ac-841995388987 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | ab136c20-dcc8-5903-a37e-41e60a326a6b |  | note | Frequency: Prior to pouring concrete.
label | b6d002f4-b23e-59c3-8187-d362a034840a |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 5bfb34a8-3947-5094-9a81-34c38f9c83ff |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.21 - Settlement Slab B
label | 0be3dec0-67aa-5184-af4d-707fdd6839ac |  | note | Activity Task: Pre-pour inspection for each settlement slab.
label | e22a0cb9-4317-5c63-86c0-69aabe20ee5e |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 9e9b6726-c7a4-5985-85c4-877ba52ebc63 |  | note | Frequency: Prior to pouring concrete.
label | 32fabfbd-d82f-55f0-92bf-f15f0f4c5c05 |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos and ITP signoff.
label | 6ad82ab7-cefc-5d29-986f-d482516fedee |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.22 - Bridge Abutments - Interconnection
label | 2a925959-b7bf-5098-b82e-a6ddf3300727 |  | note | Activity Task: Prior to any interconnection between the new and existing bridge abutments.
label | 3385af08-abaa-59f0-aa6d-4701b4ff527b |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 89e36d4e-69df-5950-907b-048110aa99da |  | note | Frequency: Prior to connecting.
label | 9950ec18-2e94-5f93-ade0-54b14fae05c0 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 49f1d98d-a6b8-5535-81d5-bd1288bee441 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.23 - Bridge Footpath
label | 2885a466-2466-5bed-babc-e0aa8cfba539 |  | note | Activity Task: Pre pour inspection for the bridge footpath.
label | 656e51a7-e9b5-56e6-9758-efc3e7844498 |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | c6a342bc-38f7-5e6c-872e-70383531ef04 |  | note | Frequency: Prior to pouring footpath concrete.
label | 0561a84c-7e8c-5506-b49b-9d695a1762de |  | note | Certifying Documentation, Record or Checksheet Mix design accepted. Photos. ITP signoff.
label | 8fe9cb5b-d980-55ad-973b-8011b78595ce |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4.1 - Barrier Rail Fabrication
label | 2507f348-f06b-5edb-acf8-cece28e3dc36 |  | note | Activity Task: Barrier rail fabrication.
label | bf4f529b-fc10-5c5c-bead-ade497ec63ff |  | note | Acceptance Criteria: Barrier rails match drawings and comply with NZTA M/23 and TNZ M/17P. Construction of the new barrier is not to proceed before the set out has been checked and approved by the Engineer.
label | 163e323b-756c-591c-9bbc-4d886855ad75 |  | note | Frequency: Prior to installation of the barrier rails.
label | 20647f32-9769-5638-b35a-ecf570059e6e |  | note | Certifying Documentation, Record or Checksheet Barrier rail specifications. ITP signoff.
label | 25778fce-3dac-5f1d-8687-20f3f11707cc |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 4.2 - New Handrail
label | d00ce71a-4279-5fbf-a3fc-51f18d5d8f16 |  | note | Activity Task: Prior to the installation of the new handrail.
label | 170092f0-b438-58c0-b437-b1b09fc7314c |  | note | Acceptance Criteria: Visual inspection and acceptance by Engineer.
label | 3e77048c-ebb0-5cc8-bde1-f16985b3e749 |  | note | Frequency: Prior to the installation of the new handrail.
label | 08a492fc-d221-5c92-ab75-2124d2bf4bbd |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 921aa6bf-964e-5d4d-8aa6-f077221f0708 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 6.4 - On Completion of the Rip Rap
label | 201448cf-fb07-577b-bc06-363bce69d629 |  | note | Activity Task: On completion of the rip rap protection to the banks adjacent to the abutments. Note: Placement of rip rap shall not commence without Engineer’s approval.
label | fc115d45-acca-581d-a193-0ecc8cf13ebe |  | note | Acceptance Criteria: Placement within tolerances set out in clause 27.13.7.3 in specification. Visual inspection and acceptance by Engineer.
label | 00126298-f2f7-5c85-990d-934622653cc3 |  | note | Frequency: On completion of rip rap protection.
label | 00262b8d-8a7b-5b0b-9c5c-705d1294e5b6 |  | note | Certifying Documentation, Record or Checksheet ITP signoff.
label | 90d24eb2-0a2e-507e-a896-f35917035bc9 |  | note | Critical Hold Point Authority: HOLD POINT
holdpoint |  |  | signoff | CRITICAL HOLD POINT AUTHORITY