## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 3 - Pipeline, manhole installation and backfill | itp |  |  |  | Yes | ITP 3 - Pipeline, manhole installation and backfill | 0df084cb-ef5b-4bd3-abbd-cbe7aa33a436
checkpoint-status |  |  | checkpoint | 1 - Service Location
label | ec32f41e-5b0f-5fc7-b1b1-5a7d32514a73 |  | note | ACTIVITY TASK - Trenched excavations
label | d8752dc1-6c4e-5b94-9324-36879b78b3a7 |  | note | ACCEPTANCE CRITERIA - All utilities shown to be within 1m of the extent of any excavation to be fully exposed at regular intervals.
label | 453ee47c-2119-5a12-a7c3-bd53ce0e3ae1 |  | note | Any expected services not to be reported to the Engineer.
label | b999e849-bd0c-50cf-b140-0646b2b5edb2 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos.
label | 16a6138c-e807-56d5-9a0a-5ea38bc6369a |  | note | Supervisor, Foreman or Subcontractor - P
label | d0c166a2-3266-52d8-b4ff-93372da1205f |  | note | Project Manager or Delegated Person - W
label | 8ef03303-a004-54d9-a649-bab791dcb46a |  | note | Engineer’s Representative - R
text | c5e90e07-c35d-58ba-84ad-17d9f238f0a9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Survey & Setting Out
label | 4069881f-4e8f-5af6-88b1-847504595b5f |  | note | ACTIVITY TASK - Set out of the Works
label | 9d3e88f8-b436-55fe-abed-be4f91b626ac |  | note | ACCEPTANCE CRITERIA - Shall be certified by a Licenced Cadastral Surveyor, or surveyor approved by the Engineer. Any discrepancy in levels or dimensions from the specified in the design shall be brought to the attention of the Engineer.
label | 4f7bc617-a91e-5888-a820-ec9963fb2b19 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Specifications, photos.
label | 8e7b3f69-1fab-542f-97c5-60f27c59ccd6 |  | note | Supervisor, Foreman or Subcontractor - P
label | 71e67f64-fa88-537a-bbf4-77a944e40eb1 |  | note | Project Manager or Delegated Person - R
label | 59ea0098-65bf-53f9-91d3-eea2b7a4ac18 |  | note | Engineer’s Representative - R
text | 2de16741-346f-5d65-aac4-0de61d9c8d92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Installation of 1050mm, 1200mm, and 1500mm manholes
label | e7010404-c24e-5bf2-966b-0dbd7e69c34b |  | note | ACTIVITY TASK - Material supply
label | 0b443b41-2b15-59e7-a36a-a5ba78502ec2 |  | note | ACCEPTANCE CRITERIA - As per drawing 301 To be compliant with AS/NZS 4058 and NZS 3109
label | e6f6effb-df62-547f-a7bf-39c927c5d1aa |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | fc0e2f49-59e7-5091-bc36-fbabe41796c5 |  | note | Supervisor, Foreman or Subcontractor - P
label | 4b4ce4dd-c06b-5e80-b7fc-49e1c1168b02 |  | note | Project Manager or Delegated Person - R
label | d0ec2482-440f-5ba9-81a3-b09758eeadc8 |  | note | Engineer’s Representative - R
text | f62891f2-9854-5945-8350-bb56c60115bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Installation of 1050mm, 1200mm, and 1500mm manholes
label | f07b4b6a-d1d6-5ea1-8a77-960a19f26789 |  | note | ACTIVITY TASK - Construction
label | 2b125ffc-832f-5982-b858-87ead439168f |  | note | ACCEPTANCE CRITERIA - Where connecting to existing system, maintain performance of existing system.
label | a4edb1ca-d451-5a7e-8ace-b89989b25430 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos.
label | b1512890-c702-5cfa-a65b-378e4da04b64 |  | note | Supervisor, Foreman or Subcontractor - P
label | a707dcd7-b2e4-5e8c-a9e3-09be2052526c |  | note | Project Manager or Delegated Person - W
label | 482e1fc1-aeb8-55a2-9e2b-006019bb2d15 |  | note | Engineer’s Representative - R
text | 4875c456-7ee2-5567-b28e-e60946300ac3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Installation of PE pipe
label | dcdb8c3b-d60b-537e-a688-83612fe52c23 |  | note | ACTIVITY TASK - Material
label | 4f331edb-d832-5365-aa6d-cc9ec3021311 |  | note | ACCEPTANCE CRITERIA - Must comply with AS/NZS 5065 and have maximum SDR of 17.
label | 3bf3d7ac-fef3-5a50-af48-d8b7ddb5f40c |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Delivery dockets
text | 8404a32b-569c-5577-afa5-a52c96ff04b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Installation of PE pipe
label | 8b76bd86-2c23-5a66-9717-545c96ce216e |  | note | ACTIVITY TASK - Construction
label | 627d176d-e4cd-51b4-b274-f19da7b5e123 |  | note | ACCEPTANCE CRITERIA - Shall be in accordance with Worksafe NZ. Trench shall not be opened more than 30m ahead of completely backfilled trench. Shall be of sufficient width and depth to permit bedding, jointing, and compaction of backfill.
label | a8a9b12d-a092-5ee6-a4dd-78df6eeceb45 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos.
label | cb830bd8-6b77-5162-8d96-d7162b7b6d67 |  | note | Supervisor, Foreman or Subcontractor - P
label | 790dbd6b-1fed-558e-a473-3dad8b735f0a |  | note | Project Manager or Delegated Person - W
label | f57f95f4-6582-56e3-84ed-d08a7b03c48d |  | note | Engineer’s Representative - R
text | 4ff4ee67-c7a4-5230-83b1-e565735d60e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Installation of GRP pipe
label | 4f3176e0-a2b3-5978-bd13-2454d8816403 |  | note | ACTIVITY TASK - Material
label | d8d7f766-877e-579a-865d-3baa82d60f43 |  | note | ACCEPTANCE CRITERIA - Must comply with AWAA C 950. Shall be a minimum SN10000 and have a minimum Pressure Class of PN6
label | 0fa213c7-30d5-507e-853a-3462794d1c34 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Delivery dockets
text | 83581991-df35-50aa-98b8-58ddc7754100 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Installation of GRP pipe
label | f9f82582-33c8-5826-a69b-89e6c2fd29e9 |  | note | ACTIVITY TASK - Construction
label | 495e9552-8fa7-5c64-bdfc-10d0c6c18615 |  | note | ACCEPTANCE CRITERIA - Shall be in accordance with Worksafe NZ. Excavations shall not commence until sufficient supplies of pipes are available. Shall be of sufficient width and depth to permit bedding, jointing, and compaction of backfill.
label | d2ebc56a-5f6c-5451-a626-c6ced2344a21 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual Inspection, photos.
text | 276a5099-f9a0-53b0-b679-43d87b8df78f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Installation of uPVC pipe
label | 0d707e5e-43e2-51e3-9af7-8ac1918a1e9a |  | note | ACTIVITY TASK - Material
label | 0f63769d-0c24-5497-96a1-573bb7140b5f |  | note | ACCEPTANCE CRITERIA - Must comply with AS/NZS 1260, pipe class to be a minimum of SN16.
label | 444e1dcc-8c31-5e53-8ca2-f95b1f65cd6e |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Delivery dockets
text | b2d66466-f79e-59db-9edf-7174a8d0781a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Installation of uPVC pipe
label | d18b22dc-081f-562d-b4c2-a28269c9edb1 |  | note | ACTIVITY TASK - Construction
label | ccd0478d-4860-5f79-a4d6-89ff32db5fef |  | note | ACCEPTANCE CRITERIA - Shall be in accordance with Worksafe NZ. Trench shall not be opened more than 30m ahead of completely backfilled trench. Shall be of sufficient width and depth to permit bedding, jointing, and compaction of backfill.
text | 46c9e97a-6b4f-559e-b570-62e5a677923f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Lateral connections.
label | c62c9125-ecaf-5bd4-a063-cd15f8ac1fff |  | note | ACTIVITY TASK - Material
label | 9e33ad16-70c0-5edd-9b85-cef6f6ae2b0e |  | note | ACCEPTANCE CRITERIA - For pipes less than 300mm, sealed Y junctions to NZS4404 will be provided. For pipes greater than 300mm, saddle connections bonded to the exterior of the main pipe shall be provided.
label | 0de20a1c-1350-532f-8364-b9404c5e1973 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Delivery Dockets
text | a44c376f-ed91-5973-b763-b5e8915a9d7a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Lateral connections.
label | 65461a1c-42e6-5676-8cca-c1d0cc50f5d7 |  | note | ACTIVITY TASK - Construction
label | 4ef3e655-887d-5ac1-9df7-7d077be9c3c1 |  | note | ACCEPTANCE CRITERIA - AC pipe connections completed in accordance with details provided in Contract Drawings.
label | bc8ed4a2-0c26-5537-ac43-bb621cdbb69b |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos.
label | 255cf9f3-312b-5585-b0f2-f84e52c9a2f1 |  | note | Supervisor, Foreman or Subcontractor - P
label | 1df21dcd-273c-5e90-8755-8b496e5a2609 |  | note | Project Manager or Delegated Person - W
label | 1adf6bc1-0cdf-5f28-a419-dc84d8ad004c |  | note | Engineer’s Representative - R
text | d112ec79-638f-5816-8c24-b3b5c9919285 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Backfill
label | 50a75ff9-81b0-53b2-a30c-1a7d7cd41ad2 |  | note | ACTIVITY TASK - Construction
label | 2c9ebcf4-e0a9-5d4a-8fcd-237d50e19e53 |  | note | ACCEPTANCE CRITERIA - Backfill material shall be in accordance with relevant NZS standards for the pipe material being installed. Backfill for excavations shall be in accordance with drawing S25 of KDC Engineering Standards 2009. Backfilled layers to record a minimum CIV reading of 15 on each lift (every 20m), with a surface CIV reading of 45 or more.
label | 2f73cd29-7fec-5aad-91ca-53933d82f790 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, CIV results.
label | 37d5edc2-1abb-591a-ac58-cebb3d7dbb1d |  | note | Supervisor, Foreman or Subcontractor - P
label | 6925c262-242d-560d-82d1-183293d0883d |  | note | Project Manager or Delegated Person - R
label | 3d971a26-5e21-538e-ac62-bb7df5a0ce36 |  | note | Engineer’s Representative - R
text | 1d998e5c-a9d1-5eb2-9049-a8a4f8f59713 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Reinstatement
label | d8290d35-8bb4-57a4-a366-42fe8f1b6b53 |  | note | ACTIVITY TASK - Construction, roads
label | 40404b2c-a96e-5cff-8c45-c8fa95406f66 |  | note | ACCEPTANCE CRITERIA - All surfaces shall be reinstated as soon as possible. Surfaces shall be reinstated to at least the same standard that pertained prior to construction of the work.
label | ea017758-35a9-5cd6-92c2-31f37a2fc3d3 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos
label | 86747147-1c7b-559a-b9c9-2a0679e769da |  | note | Supervisor, Foreman or Subcontractor - P
label | 3450ef28-dc3d-529a-b13b-4b91c042eb3c |  | note | Project Manager or Delegated Person - R
label | ab783cfe-192a-59f1-8e8c-2786a26e877c |  | note | Engineer’s Representative - R
text | 740e705b-104b-51d0-8385-3ccf86c67670 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Reinstatement
label | cfe41bd9-38b4-5620-8d5e-b901221daf10 |  | note | ACTIVITY TASK - Construction, berm
label | 98c9ee4e-4c66-5571-a3c8-eaa5c665a7ea |  | note | ACCEPTANCE CRITERIA - Reinstatement of topsoil and other materials shall match adjoining surfaces and be finished off to the satisfaction of the owner or Engineer. All disturbed areas shall be filled with material at least equal in thickness and all other ways to that existing at the start of contract.
label | 97322eb3-059e-51eb-8084-e07d1ed05136 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Visual inspection, photos
label | 3715ae0e-3d3a-5185-8303-41951cb6cdcc |  | note | Supervisor, Foreman or Subcontractor - P
label | 6fc414f2-5803-591d-8bed-32a1d0f07b83 |  | note | Project Manager or Delegated Person - R
label | 1492d2e4-36be-5b77-ae6b-a5e9c512f64b |  | note | Engineer’s Representative - R
text | cf927a14-6d27-5608-b664-a577234bd7de |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - As-built documents
label | de277ed5-87c3-5695-8504-3a0d3e78215a |  | note | ACTIVITY TASK - AS-built drawings
label | 03fe9eb6-53d2-550c-88d7-de8aee005735 |  | note | ACCEPTANCE CRITERIA - Record details of: Length, diameter, type and class of pipe, pipe grade and flow direction. Manhole lid level and invert levels of all incoming and outgoing pipes. Invert levels of all drop connections at pipe grade line. Distance in meters from downstream manhole to all pipe junctions. Horizontal coordinates of all manholes and pipe terminations in terms of NZTM. Vertical levels in terms of NZVD 2016.
label | 25e099f5-7f4e-5166-9b9b-89a97aabc95b |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Compile all documentation in accordance with KDCES Section 3.6.
label | 3fa44397-035a-5c4e-bd74-112ef2f5fc0d |  | note | Supervisor, Foreman or Subcontractor - W
label | 8c31d1fa-3b5e-5072-ad94-80cbcf17a7e9 |  | note | Project Manager or Delegated Person - P
label | fd7f4059-66be-550d-852c-c9713b92c657 |  | note | Engineer’s Representative - H
text | bc9ff42c-31cb-59d6-b9d1-209462c7c60f |  | textbox | Date Completed:
checklist-flat |  |  | checklist | ITP 1 - Establishment and Initial Set Out | itp |  |  |  | Yes | ITP 1 - Establishment and Initial Set Out | cace3e3e-ac0c-4c27-a2af-6daa65e7e3b6
checkpoint-status |  |  | checkpoint | 1 - Award of Contract
label | e12545b5-81db-5760-a4fa-9888f8c15902 |  | note | ACTIVITY TASK - Award of Contract
label | ac7546df-bba2-5c69-b28d-e3c83df27159 |  | note | ACCEPTANCE CRITERIA - Letter of Award
label | b6cad589-003c-5b04-b671-aa14e30a6362 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Letter of Award
label | bb338f71-4919-53c8-8d16-a208efb41c52 |  | note | Project Manager or Delegated Person - R
text | e05cea30-f799-525e-b982-d0a4df87a21e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Management Plans
label | 02a2810b-f797-53f6-9033-505be9a03fe9 |  | note | ACTIVITY TASK - Project Commencement
label | e6e567a1-cc5f-5df2-9772-31ef9a0c23de |  | note | ACCEPTANCE CRITERIA - Submission to engineer to the contract
label | 14de61ad-02fc-57d6-964f-5cd5a9469481 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - ‘SSSP, EMP, QCP, TMP, JSA
label | c845e0ea-bd5d-54a8-81f8-e0cfe0d2b8fc |  | note | Project Manager or Delegated Person - P
label | 99113c22-5038-56b3-8369-ba4ac491e316 |  | note | Engineer’s Representative - R
text | 9fc63e78-aacf-51c6-ace2-2cf6dc117fcd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Insurances
label | 1d179038-f5b9-5088-b0b1-c7e3c4640126 |  | note | ACTIVITY TASK - Project Commencement
label | 7a5b8d33-d56c-5579-b65b-3dfd48978d4b |  | note | ACCEPTANCE CRITERIA - Current certificate
label | cded8d27-2c91-5540-bbe9-2a193bef1379 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Current certificate
label | bdedb704-8244-56c7-bf20-766fc1f11fad |  | note | Project Manager or Delegated Person - P
label | 24344617-674c-5d0d-b122-612ab98a20b9 |  | note | Engineer’s Representative - R
text | d5a0025e-631d-58e0-8d30-789fdc805efb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Dilapidation Survey
label | eab0785d-4c3f-511d-84a3-bbb619166b9f |  | note | ACTIVITY TASK - Project Commencement
label | ceb1bd37-a5fa-5988-88fd-a459e87277da |  | note | ACCEPTANCE CRITERIA - Photos and description of scope of work prior to commencement of physical works.
label | d6ff6e85-2c1b-5eef-810d-d69c4d5ff310 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Photos of footpath, Berm, pavement and individual properties.
label | ee748ba9-9702-5578-984a-a551093f3544 |  | note | Supervisor, Foreman or Subcontractor - P
label | bd839f00-7a90-58d8-8406-f94f78f4d88c |  | note | Project Manager or Delegated Person - R
text | 8eb87a79-39fa-5504-afbe-a62429ce8684 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Initial Set out
label | a7d66e2b-2589-59e0-8250-040c30eb22ae |  | note | ACTIVITY TASK - Set out of manhole positions and alignment of new line, etc
label | b9fae936-9490-5698-9889-fcbf17e7bb89 |  | note | ACCEPTANCE CRITERIA - As per drawings
label | 19bff0c7-0453-5470-b1a1-626ba63b2cf2 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Surveyor to set out
label | 3e157542-57ec-5173-9d36-289c7f67b241 |  | note | Supervisor, Foreman or Subcontractor - R
label | f15bee7e-e509-5952-96c0-eafcc4572b59 |  | note | Project Manager or Delegated Person - R
label | 4f093291-5aed-566a-bb65-1530568e8b97 |  | note | Engineer’s Representative - W
text | b2527cd2-3742-5164-b110-c833da3d632d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Notification to Residents
label | ce6f117a-71f5-5e0a-af62-5f07cd7de459 |  | note | ACTIVITY TASK - Project Commencement, Notification
label | af2eb5e2-8721-5c17-8817-22e19465ee96 |  | note | ACCEPTANCE CRITERIA - Letter to be distributed to affected residents prior to commencement of work.
label | d60f04fb-e956-53fc-9f71-41f1b578db63 |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - Letter to residents
label | bfc78b5b-3da2-56a0-ac77-455e77c5b289 |  | note | Project Manager or Delegated Person - P
label | b6c84419-9b44-5ac0-963b-bef58e368a41 |  | note | Engineer’s Representative - R
text | 7b06b3d7-fccc-5520-96dc-1f0bd2995d7e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - B4UDig
label | 54c2933f-b378-5c5e-88be-9f34537fef1d |  | note | ACTIVITY TASK - Submit B4UDig Notification
label | eddb14ce-b739-50a9-a06e-6ffad04c9c3f |  | note | ACCEPTANCE CRITERIA - B4UDig Submission confirmation
label | 1f89d01b-fe6f-5917-b28c-e44468b7497c |  | note | CERTIFYING DOCUMENTATION AND FREQUENCY - B4UDig Plans and sequence numbers
label | 5ef0d7b0-6460-58b4-83ac-4d68cd0c68bd |  | note | Project Manager or Delegated Person - P
label | 9b24ca88-ddd1-543f-ab82-8419e9cab89f |  | note | Engineer’s Representative - R
text | 77db6a65-f486-5840-a8b1-ad8c627733e4 |  | textbox | Date Completed:
checklist-flat |  |  | checklist | ITP 2 - Testing of PE, uPVC and Manholes | itp |  |  |  | Yes | ITP 2 - Testing of PE, uPVC and Manholes | ebccf4ff-e7ce-486b-8857-58a33cd79f5f
checkpoint-status |  |  | checkpoint | 1 - Material DN375 uPVC SN16, DN560 PE100 SDR17, DN525 SN1000 GRP
label | ab77b638-f078-53a7-a2f9-a84d4e10b567 |  | note | Activity TASK - Construction
label | 13d708ee-d278-515c-92c6-7199fcb74e97 |  | note | Acceptance Criteria - Leakage tests to be compliant with AS/NZS 2566.2.
label | e65793a0-749a-5404-ab59-9f9527ebc1a4 |  | note | Pipes to be jointed in accordance with PIPA POP001 for EF methods and POP003 for butt fusion methods.
label | 6aba9c8c-4dcc-5097-9bfd-bf5322e1d21d |  | note | Either low pressure air or hydrostatic testing
label | ed82a0e4-29ed-5a53-aaab-767949f4a8d4 |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection, photos of air tests
label | 1c6af1c8-133b-5a5b-9ab4-360c472eee82 |  | note | Supervisor, Foreman or Subcontractor - P
label | 2213a219-5e97-5d14-983f-c6ddb58dd66f |  | note | Project Manager or Delegated Person - W
label | 69d4d127-81ac-51fc-a1cb-2b770b720dbe |  | note | Engineer’s Representative - R
text | cbe49fe4-24ea-5817-a577-7ccada645fcb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Manholes, EF fittings
label | 9c6d4313-b052-5f86-82e1-3fb786b30629 |  | note | Activity TASK - Construction
label | 0fda699e-8c9a-5ec4-bea7-fd63d2d6bde6 |  | note | Acceptance Criteria - Leakage tests
label | 610e11e3-c829-5153-919d-5570b8b3061c |  | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspections, photos of air tests
label | fed264d2-cd05-5faa-b241-569d643d2f52 |  | note | Supervisor, Foreman or Subcontractor - P
label | 0ee9b6b3-9598-5d49-9724-c8e18465979b |  | note | Project Manager or Delegated Person - W
label | adf58fac-020b-57b8-aefc-a4bae8cc27d2 |  | note | Engineer’s Representative - R
text | 746d7938-ea83-5648-9c78-c3a4a0cf6d74 |  | textbox | Date Completed: