## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Piling | itp |  |  |  |  | ITP - Piling
section | 1.0 - Preliminary Inspections and Tests
checkpoint | 1.1 - Design and Drawings are of 100% Detail Design Status
label | Responsibility: Spiral Drillers Engineer
label | Spec Reference: N.A
label | Conformance Criteria summary: Latest Issue Design Drawings issued via email
label | Method: Document review/document control
label | Frequency: Prior to Start of work
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: IP
label | Records or Checklist Reference: SD Quality Control Checklist
holdpoint | HOLD POINT
checkpoint | 1.1.1b - Submittal of construction methodology
label | Responsibility: Spiral Drillers
label | Spec Reference: Project Memo Section 2.1.iii
label | Conformance Criteria summary: Include: Equipment, Pile construction methodology, delivery and storage of material, safe work area, pile concrete & sand placement.
label | Method: Document review
label | Frequency: Prior to Start of work
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: HP
label | Records or Checklist Reference: Approved ITP
holdpoint | HOLD POINT
section | 2.0 - Approved Materials
checkpoint | 2.1 - Reinforcing Cages
label | Responsibility: Spiral Drillers
label | Conformance Criteria summary: Mill Certifications
label | • Send notice in advance request for inspections
label | • 7.8.3 Micro-Alloying MA 300E or Grade 500E steel
label | • Reinforcing as per approved detail sheets.
label | • Reinforcing to comply with AS/NZS 4671 & NZS3109. Any cutting, bending or welding of reinforcing on site to be approved in writing by the design engineer.
label | Method: Detail Sheets approved by structural engineer prior to manufacture Mill certificates for reinforcing cages used. Engineer to inspect constructed cages.
label | Frequency: Per pile type intended to be constructed, Prior to manufacture, Once arrived on site
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: RR
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Delivery Dockets SD, Pile cards, Reinforcing Mill cert testing
holdpoint | HOLD POINT
checkpoint | 2.2 - Steel Pile Casing
label | Responsibility: Spiral Drillers
label | Spec Reference: SESOC Section 2.2.4
label | Conformance Criteria summary: Sizing to be 762mm x 16mm WT
label | • Pile casing to comply with the requirements in the project drawings.
label | • Deviation from straightness shall not be greater than 1/600 longitudinally.
label | Method: Steel casing mill certs, heat no. and material testing.
label | Frequency: Tests/certs for steel casings rolled from different steel coils.
label | Hold/Witness Requirements - C: RR
label | Hold/Witness Requirements - UCC: RR
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Delivery Dockets, Heat Number and Mill certs.
checkpoint | 2.3 - Concrete mix design
label | Responsibility: Spiral Drillers
label | Conformance Criteria summary: Submit proposed concrete mix design in advance of concrete been placed on site
label | • Concrete batching plant will keep records to prove ongoing suitability of plant and mix design, production tests and delivery.
label | • Concrete mix design to comply with NZS3104.
label | • Maximum permittable aggregate size to be 19mm.
label | • Mixing design intended strength to be XXMPa and meeting the requirements for exposure classification XX.
label | Method: Concrete mix design, Submitted to the engineer prior to concrete being placed.
label | Frequency: Prior to concrete being placed
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Written confirmation for acceptance of mix deisng. SDC QA - Concrete pile schedule Certificates, testing records
holdpoint | HOLD POINT
checkpoint | 2.4 - Welding on site
label | Responsibility: Spiral Drillers
label | Spec Reference: AS/NZS 1554.1. NZS 4781.
label | Conformance Criteria summary: Welders WPS form in AS/NZS 1554.1 Individual welders qualified to the WPS, AS/NZS 2980 Welder Certificate
label | Method: Welding WPS Certification of each welder
label | Frequency: Prior to Start of work
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Welding records and certificates, Current welding qualification
holdpoint | HOLD POINT
checkpoint | 2.5 - Piling Hammer & Equipment
label | Responsibility: Spiral Drillers
label | Conformance Criteria summary: Weigh bridge docket to verify the weight of the piling helmet.
label | • Driveability analysis to determine the drop height, Set and temporary compression requirements.
label | Method: Weigh bridge dockets, Driveability analysis document
label | Frequency: Prior to start of work
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Driveability analysis
holdpoint | HOLD POINT
section | 3.0 - Setting Out
checkpoint | 3.1 - Set out and survey
label | Responsibility: United Civil Construction
label | Spec Reference: Project drawings ASG Piling Specification Rev G – Section 1.13
label | Conformance Criteria summary: UCC to set out pile centre lines on guide frames installed by SDC. Set out requirements will vary from location but will be required on multiple occasions.
label | • Setout gridlines to be within +- 3mm of design position.
label | • UCC to provide several benchmark pegs along the alignment that are checked frequently to ensure accuracy.
label | • SDC will be responsible for offsets taken from the pile set out location.
label | Method: Registered surveyor Inspection and Set out
label | Frequency: Each Pile position.
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: IP
label | Hold/Witness Requirements - N P: IP
label | Records or Checklist Reference: SD Quality Control Checklist, Set out report for tolerance, As-built Survey, Monitoring of benchmarks.
holdpoint | HOLD POINT
section | 4.0 - Construction stage
checkpoint | 4.1 - Reinforcing Cages
label | Responsibility: Spiral Drillers
label | Spec Reference: SESOC Section 1.10
label | Conformance Criteria summary: Stack reinforcing cages on suitable supports on firm ground, in a manner to eliminate excessive handling stresses or other damage.
label | • Reject and replace reinforcing cages that are not as per the detail sheets.
label | • Compile delivery dockets for reference to mill certs.
label | Method: Each delivery
label | Frequency: Each delivery
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: IP
label | Hold/Witness Requirements - N P: IP
label | Records or Checklist Reference: Structural engineer inspection of reinforcing cages, SD Pile QA sheet Delivery dockets.
holdpoint | HOLD POINT
checkpoint | 4.2 - Concrete Dockets
label | Responsibility: Spiral Drillers
label | Spec Reference: Approved Mix design document.
label | Conformance Criteria summary: Mix design on delivery docket matches the approved mix design.
label | • On site material testing to confirm mix design characteristics are achieved.
label | Method: Slump Tests & Concrete dockets.
label | Frequency: Each Concrete truck.
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: RR
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: SD Concrete pour QA Sheet, Concrete testing report.
holdpoint | HOLD POINT
checkpoint | 4.3 - Bottom Driving Plug Material
label | Responsibility: Spiral Drillers
label | Spec Reference: SESOC Section 4.12.1
label | Conformance Criteria summary: Aggregate to conform to table 4.12-1 of SESOC Rev I (Sealing Chip).
label | • Plug Length shall not be less than 1.5x casing diameter at commencement of piling and shall not exceed 4.0m unless approved by the Engineer.
label | Method: Material grading cert. Pile measurements.
label | Frequency: Daily
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: RR
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: SD Polymer Checklist.
holdpoint | HOLD POINT
checkpoint | 4.4 - Pile installation/founding level.
label | Responsibility: Spiral Drillers/UCC
label | Conformance Criteria summary: Tolerances:
label | • The centre of the pile head at the design level of the head shall be within 75mm of its lateral position and 25mm of its vertical position.
label | • The pile shall be within 1:75 of its design. Do not force incorrectly placed piles into their correct position after they have been placed.
label | • Pile as built survey to be completed by United Civil Construction
label | ○ Founding Capacity:
label | • Pile locations to be driven to their required founding capacity verified using either Hiley or PDA.
label | ○ Driving Records:
label | • All Piles will have the drop height & no. of drops recorded at the following intervals.
label | • 1.0m -> Up to 20m deep.
label | • 0.5m -> To founding depth.
label | • Set/temporary compression recorded over 10 No. consecutive blows using either a manual set card or a Pile Driving Monitor.
label | Method: Position of pile: 75mm horizontal, 25mm vertical and 1:75 of its design
label | • Piles shall achieve a minimum founding resistance Outlined in IFC Drawings Cut off level to be +25, -25mm
label | Frequency: Each pile
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: SD Pile Card Geotechnical Engineer inspection record. PDA Record review
holdpoint | HOLD POINT
checkpoint | 4.5 - Welding process
label | Responsibility: Spiral Drillers
label | Spec Reference: AS/NZS 1554.1 NZS 3404.1 and AS/NZS 5131. AS/NZS 1554.1, clause 1.8.2. SESOC Section 2.2.6
label | Conformance Criteria summary: Welds to be carried out to the WPS form in AS/NZS 1554.1 Splicing will be a single bevel full strength butt weld, Flux-cored arc, self-shielded, welded one side with backing strip
label | • Weld testings: 10% Ultrasonic testing completed on Pile casing welds.
label | Method: Document review and on-site inspections (Radiograp hy or ultrasonic) Independent testing report.
label | Frequency: Weld testings: 10% non destruction examination testing (UT testing)
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: RR
label | Hold/Witness Requirements - N P: RR
label | Records or Checklist Reference: Independent test report
holdpoint | HOLD POINT
checkpoint | 4.6 - Concrete placing
label | Responsibility: Spiral Drillers
label | Conformance Criteria summary: Each pile is to be checked before each pour for any groundwater or contaminates in the pile
label | • Daily concrete pour record to approved checklist
label | • Concrete docket to be submitted each pour
label | ○ Testing
label | • Carry out 7 and 28 days testing
label | • Standard cylinders for each 50m3. 1 at 7 days, 2 at 28 days.
label | • 1 slump test per load
label | • Concrete to be poured in a manner that avoids hitting the reinforcing cage. Poured central down the pile hole. Concrete to be tested in an IANZ Accredited lab.
label | • Depth to top of concrete, placement time and method to be recorded for each truck.
label | Method: Concrete dockets, Test results And Pile cards
label | Frequency: Every 50m3 or minimum of 1 per day, Each pile to be inspected before pouring concrete
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: IP/RR
label | Hold/Witness Requirements - N P: IP/RR
label | Records or Checklist Reference: Concrete dockets and laboratory test results, SD Concrete QA Card.
holdpoint | HOLD POINT
section | 5.0 - Completion
checkpoint | 5.1 - As- built pile survey
label | Responsibility: United Civil/Spiral Drillers
label | Conformance Criteria summary: All piles installed are within the required tolerances as shown in the construction specification and drawings.
label | • +-75mm horizontal tolerance
label | • +- 25mm vertical tolerance
label | Method: As-built survey completed by a registered surveyor
label | Frequency: Upon completion of pile installation
label | Records or Checklist Reference: Complete As-built document referring position to design positions.
checkpoint | 5.2 - Warranty and code of compliance
label | Responsibility: Spiral Drillers
label | Conformance Criteria summary: Documented evidence Certificate, warranty or Producers statement
label | • Warranty meets spec requirements
label | • Commence warranty from date of practical completion
label | • Spiral Drillers will issue a Producer Statement for the entirety of their contracted works upon completion.
label | Method: Record review
label | Frequency: once
label | Hold/Witness Requirements - C: HP
label | Hold/Witness Requirements - UCC: HP
label | Hold/Witness Requirements - N P: RR/RR
holdpoint | HOLD POINT
checkpoint | Sign Off
textbox | Comments:
textbox | Work Completed:
label | The above items have been inspected and are in accordance with the drawings and specifications. All documentation as required by Specification is included in this Lot.
label | Contractor
textbox | Name:
textbox | Position Title:
textbox | Company
textbox | Date:
label | Ormat/Delegate
textbox | Name:
textbox | Position Title:
textbox | Company
textbox | Date: