## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Structural Steel Fabrication | itp |  |  |  |  | ITP - Structural Steel Fabrication
section | 1.1 - Preliminaries: Method & Documentation
checkpoint | 1.1.1 - Shop Drawings
label | RI: PM
label | Acceptance Criteria: Submit electronic copies of shop drawings, providing complete details of each assembley with respect to the steelwork fabrication, surface treatment and erection.
label | Method: Review
label | Frequency: Per Assembly
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Notice to Contractor: Permission to Fabricate
holdpoint | HOLD POINT
checkpoint | 1.1.2 - Independent Welding Inspector
label | RI: PM
label | Acceptance Criteria: Submit Third Party welding inspection entity, appropriately qualified in the welding inspection required by the Project.
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Approved Independent Welding Inspector
holdpoint | HOLD POINT
section | 1.2 - Preliminaries: Material Compliance
checkpoint | 1.2.1 - Structural Steel Grades
label | RI: PM
label | Acceptance Criteria: Project Specification
label | Applicable Standard and/or Technical Requirement: AS/NZS 3678, AS/NZS 3679.1
label | Method: Review
label | Frequency: Per Material Order
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: R
label | Verifying Record: Shop Drawings & Mill Certificates
holdpoint | HOLD POINT
checkpoint | 1.2.2 - Structural Bolts
label | RI: PM
label | Acceptance Criteria: Bolts will be sourced in accordance with NZS 1252:2016, All bolts are to be high strength steel bolts of grade 8.8 or higher, uno.
label | Applicable Standard and/or Technical Requirement: NZS 1252:1996
label | Method: Review
label | Frequency: Per Material Order
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: R
label | Verifying Record: Material Conformance Certificates
holdpoint | HOLD POINT
checkpoint | 1.2.3 - Shear Studs
label | RI: PM
label | Acceptance Criteria: All shear studs be produced in accordance with AS/NZS 1554.2:2003, with the relevant mill certificates and testing records, including mill certificates to which they will be connected proving prequalification of welds.
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | Method: Review
label | Frequency: Per Material Order
checkpoint | 1.2.4 - Structural Steel Supply Traceability
label | RI: PM
label | Acceptance Criteria: Refer Project Specification, All Plates are to be produced in accordance with NZS 5131 will mill certificates meeting the relevant grades given in 1.2.1.
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131
label | Method: Review
label | Frequency: Per Material Order
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: ACRS or JAS-ANZ Mill Certificatoin Certificates
holdpoint | HOLD POINT
checkpoint | 1.2.5 - Verified Mill Certificates
label | RI: PM
label | Applicable Standard and/or Technical Requirement: Project Specification
label | Method: Review
label | Frequency: Per Mill Certificate
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: ILAC Endorsment
holdpoint | HOLD POINT
checkpoint | 1.2.6 - Structural Steel & Bolt Third Party Testing
label | RI: PM
label | Acceptance Criteria: 3 No. samples from each batch of structural steel tested for mechanical and chemical properties at a certified IANZ lab in NZ, and the results submitted to the Engineer
label | Applicable Standard and/or Technical Requirement: Project Specification
label | Method: Material Test
label | Frequency: Per Batch
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: IANZ Laboratory Test Report
holdpoint | HOLD POINT
section | 1.3 - Preliminaries: Welding Procedures & Certification
checkpoint | 1.3.1 - Welding Personnel Qualifications
label | RI: PM
label | Acceptance Criteria: Review of proposed welders and their welding certificates and qualifications
label | Applicable Standard and/or Technical Requirement: AS/NZS ISO9606.1:2017
label | Method: Review
label | Frequency: Per Welder
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Personnel Welding Qualification Certificates
holdpoint | HOLD POINT
checkpoint | 1.3.2 - Welding Procedure Specification (WPS)
label | RI: PM
label | Acceptance Criteria: Pre-qualified to AS/NZS 1554.1:2014 as a minimum.
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014:2014
label | Method: PQR
label | Frequency: Per WPS
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: H
label | Verifying Record: Procedure Qualification Record
holdpoint | HOLD POINT
checkpoint | 1.3.3 - Independent Review of WPS
label | RI: PM
label | Acceptance Criteria: Review by nominated IWI of WPS and PQR
label | Method: Review
label | Frequency: Per WPS
label | Verification Activity By - Eastbridge: R
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Independent Review Record
section | 1.4 - Preliminaries: Corrosion Protection System
checkpoint | 1.4.1 - Coating Applicator
label | RI: PM
label | Acceptance Criteria: Contractors are required to be accredited under the Australian Paint Contractors Certification Program (PCCP)
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Coating Applicators Accreditation Certificate
holdpoint | HOLD POINT
checkpoint | 1.4.2 - Coating Specifier
label | RI: PM
label | Acceptance Criteria: Qualification to one of the following:
label | • NACE Protective Coating Specialist
label | • Australasian Corrosion Association
label | • (ACA) Technician or Technologist with successful completion of the ACA's Coating Selection and Specification Course and/or certified to NAC Coating Inspection Program (CIP) Level 2
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Coating Specifier Qualification Certificate
holdpoint | HOLD POINT
checkpoint | 1.4.3 - Coating Specification
label | RI: PM
label | Acceptance Criteria: Painting specification approved by an independent paint inspector. Note, only coatings approved by an independent body such as APAS, NEPCOAT or NORSOK shall be used.
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Approved Paint Specification from Independent Paint
holdpoint | HOLD POINT
section | 2 - Receiving & Storage of Parent Metals
checkpoint | 2.1 - Material Receiving into Store
label | RI: PM
label | Acceptance Criteria: All incoming mateials shall be inspected for conformance to the requirements of the Project and heat numbers checked against mill certificates
label | Applicable Standard and/or Technical Requirement: PQP "Material Receiving" NZS3404.2:2009, 2.2.2
label | Method: Inspection
label | Frequency: Per Material Order
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Material Receipt Certification
checkpoint | 2.2 - Storage
label | RI: PM
label | Acceptance Criteria: Materials shall be kept free from dirt, grease and other foreign matter and protected from corrosion as far as possible and shall be stored above ground on platforms, skids or other supports.
section | 3 - Fabrication: Cutting, Holing & Bending
checkpoint | 3.1 - Sharp Edges
label | RI: FSUP
label | Acceptance Criteria: Rounded to a 2 mm radius by grinding after fabrication to ensure that a protective coating of normal thickness will adhere to the edges
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.4
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint | 3.2 - As-Cut Surfaces
label | RI: FSUP
label | Acceptance Criteria: Australian Welding Research Association Class 2 surface
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.2 Table 6.5
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint | 3.3 - Re-Entrant Corners
label | RI: FSUP
label | Acceptance Criteria: Shaped notch free to a minimum radius of 10 mm unless specifically indicated otherwise by geometry detail or as indicated on the drawings
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.5.3
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastrbidge Standard Fabrication Checksheet
checkpoint | 3.4 - Holing
label | RI: FSUP
label | Acceptance Criteria: Standard holes for bolts shall be D+2mm unless otherwise noted. Slotted holes shall be D=2mm wide and 2.5D long unless otherwise noted.
label | • Standard holes for pins shall be D+1mm unless otherwise noted.
label | • In the event of misalignment of bolt holes at any joint, reaming or drilling to more than 1.5mm larger than the bolt diameter will not be permitted unless specifically approved by the Engineer
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.7
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Fabrication Checksheet
checkpoint | 3.5 - Shaping
label | RI: FSUP
label | Applicable Standard and/or Technical Requirement: AS/NZS 5131:2016 - Sect 6.6
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Welding Checksheet
checkpoint | 3.6 - Markings & Identification
label | RI: FSUP
label | Acceptance Criteria: Steelwork markings and indentification is correct as per shop drawings
label | Applicable Standard and/or Technical Requirement: NZS 3404.1
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Fabrication Checksheet
section | 4 - Welding
checkpoint | 4.1 - Check Welding Consumables
label | RI: EBWI
label | Acceptance Criteria: Consumables to be stored in accordance with the manufacturers specification
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect 7.5.2
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: W
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Approved Weld Testing Regime
checkpoint | 4.2 - Welding Plan
label | RI: EBWI
label | Acceptance Criteria: Considerations for all welding to made in respect to Section 7.2.2 for all welding related matters
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect 7.2
label | Method: Inspection
label | Frequency: Once
label | Verification Activity By - Eastbridge: R
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Visual Scanning Weld Report
checkpoint | 4.3 - Allocate welders to specific welds
label | RI: EBWI
label | Acceptance Criteria: Welders to be qualified in accordance with AS/NZS ISO9606.1:2017
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS ISO9606.1:2017
label | Method: Inspection
label | Frequency: 100%
label | Verification Activity By - Eastbridge: R
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Visual Examination Weld Report
checkpoint | 4.4 - Pre-weld inspections
label | RI: IWCI
label | Acceptance Criteria: Pre-weld inspections shall be made in accordance with Section 7.5.4
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS 5131:2016 Sect. 7.5.4
label | Method: Inspection
label | Frequency: 100%
label | Verification Activity By - Eastbridge: R
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Non-Destructive Testing Weld Report
checkpoint | 4.5 - Welder traceability
label | RI: IWCI
label | Acceptance Criteria: Welders to be traceable in accordance with Table 7.4 - CC4
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS/NZS5131:2016 Sect 7.4.3 Table 7.4
label | Method: Review
label | Frequency: 100%
label | Verification Activity By - Eastbridge: S
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Ultrasonic Weld Report
checkpoint | 4.6 - Stud Welding
label | RI: EBWI
label | Acceptance Criteria: Welders to be selected in accordance with AS/NZS 1554.2:2003
label | Applicable Standard and/or Technical Requirement: AS/NZS, AS/NZS 1554.2:2003 5131:2016 Sect. 5.6 & 7.5.11
label | Method: Review
label | Frequency: 100%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint | HOLD POINT
section | 5 - Welding Inspection & NDT
checkpoint | 5.1 - Weld Testing Regime
label | RI: PM
label | Acceptance Criteria: Generally, spread across all weld types, all welders and multiple welds of the same type.
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | Method: Review
label | Frequency: Once
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Approved Weld Testing Regime
holdpoint | HOLD POINT
checkpoint | 5.2 - Weld Integrity: Visual Scanning
label | RI: EBWI
label | Acceptance Criteria: Weld location is as per shop drawing for each section
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | Method: Inspection
label | Frequency: 100%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Visual Scanning Weld Report
holdpoint | HOLD POINT
checkpoint | 5.3 - Weld Integrity: Visual Examination
label | RI: EBWI
label | Acceptance Criteria: Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | Method: Inspection
label | Frequency: 100%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Visual Examination Weld Report
holdpoint | HOLD POINT
checkpoint | 5.4 - Weld Integrity: Magnetic Particle Inspection
label | RI: IWCI
label | Acceptance Criteria: Structural fillet welds only
label | • Table 6.2.2: Permissible levels of imperfections in butt and fillet welds as determined by visual, magenetic particle and liquid penetrant examination of the weld zone
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | Method: MPI
label | Frequency: 25%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Non-Destructive Testing Weld Report
holdpoint | HOLD POINT
checkpoint | 5.5 - Weld Integrity: Ultrasonic Testing
label | RI: IWCI
label | Acceptance Criteria: Structural butt welds only
label | • Table 6.2.1: Permissible levels of imperfections as determined by radiograpic or ultrasonic examination for welds of category SP
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014, AS 2207
label | Method: UT
label | Frequency: 25%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Ultrasonic Weld Report
holdpoint | HOLD POINT
checkpoint | 5.6 - Stud Welds: Ring Testing
label | RI: EBWI
label | Acceptance Criteria: "Ring" sound of stud when tapped with a 3kg hammer in the direction of the beam.
label | • If stud gives a "'dead' sound, the test is failed.
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | Method: Ring Test
label | Frequency: 100%
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint | HOLD POINT
checkpoint | 5.7 - Stud Welds: Bend Testing
label | RI: EBWI
label | Acceptance Criteria: No evidence of fracture under bending 15 degrees from original axis
label | • First and second for each production weld set-up followed by specified frequency
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.2:2003
label | Method: Bend Test
label | Frequency: 1 in 50
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Welding Checksheet
holdpoint | HOLD POINT
checkpoint | 5.8 - Fabricated Condition
label | RI: EBWI
label | Acceptance Criteria: Ensure slag, spatter, scale and flux has been removed and general appearance is acceptable
label | Applicable Standard and/or Technical Requirement: AS/NZS 1554.1:2014
label | Method: Inspection
label | Frequency: Per Section
label | Verification Activity By - Eastbridge: I
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Eastbridge Standard Fabrication Checksheet
section | 6 - Post Fabrication
checkpoint | 6.1 - Final Inspection
label | RI: PM
label | Acceptance Criteria: Ensure all inspections and tests are completed, all reports and documentation are available and all results comply with the requirements
label | Applicable Standard and/or Technical Requirement: –
label | Method: Review
label | Frequency: Per Dispatch
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: H
label | Verification Activity By - Client Rep: H
label | Verifying Record: Final Inspection Checksheet
holdpoint | HOLD POINT
checkpoint | 6.2 - Dispatch
label | RI: PM
label | Acceptance Criteria: Inspect delivery dockets and ensure that each item on packing list has been packed and in the correct quantity inclusive of weights
label | Applicable Standard and/or Technical Requirement: –
label | Method: Review
label | Frequency: Per Dispatcj
label | Verification Activity By - Eastbridge: H
label | Verification Activity By - Contractor: R
label | Verification Activity By - Client Rep: R
label | Verifying Record: Dispatch Docket
section | Sign Off
checkpoint | ITP Sign Off for Construction
textbox | Project Engineer:
textbox | Date:
checkpoint | All works completed, records attached and work conforming
textbox | Site Engineer:
textbox | Date:
textbox | Project Engineer:
textbox | Date:
textbox | Quality Manager:
textbox | Date: