## Project Checklist Templates
Type | Name | Values
checklist | *1 - Pre-Commencement Activities
section | Details
checkpoint | Project Self-Assessment Tool- BU Project Audits -
checkpoint | 1.1 - Submission of Waterproofing System products
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of Waterproofing System - confirmation of compatibility with substrate and follow-on trade requirements
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.2 - Submission of Waterproofing System Warranties
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Warranty is for required duration and relevant party
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.3 - Submission of Manufacturer's Application Method Statement (MAMS)
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of MAMS by Waterproofing Consultant
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.4 - Submission of AMS and WRA Content - including Safety Data Sheets for chemicals
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of AMSs and WRAs
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.5 - Waterproofing company to demonstrate Competency of Applicators
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Competency scheme document, register of applicators
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.6 - Detailed design complete - including shop details
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of shop drawings
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.7 - Testing equipment details - and calibration records (if electronic leak detection specified)
note | Specification Reference - AS3740 App C3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - In calibration
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.8 - First of Type Inspection -joint witness and sign-off on Prototype or First Install with membrane system representative (as below)
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Joint acceptance of the First of Type and close-out of any agreed issues
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Inspection: Nominated Authority - WC (H)
signoff | AUTHORITY HOLDPOINT
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter [Vulkem 350R/951NF datasheet]
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply Anti Rock Primer Primer in line with MAMS - take photograph of primer container with technical details and photo/video of application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Anti Rock Primer applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | 350R/951NF layer minimum curing/drying times:
note | 5C - 12C ¦¦ 24 - 72 Hours
note | 12C - 18C ¦¦ 6 - 24 Hours
note | 18C - 29C ¦¦ 4 - 6 Hours
note | 29C ¦¦ 4 Hours
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
note | Test/ Inspection - Test
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
note | Inspection: Site Manager - DC (W)
note | Records & Comments - Pass or Fail
textbox | Observed setting time:
checkpoint | 2.13 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure protection has been applied to membrane.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.
checklist | Apply 2 coats Vulkem NEM 150mm upstands
checkpoint | Apply 2 coats Vulkem NEM 150mm upstands
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Below ground tremco system
checkpoint | Tremco Paraseal system installed.
checkpoint | Pressure strip install
checkpoint | Install Versidrain 8 geo
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Car Park Sealer
checkpoint | Apply Carpark sealer P4 rating
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Courtyards under paving
checkpoint | Apply primer
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Coving
checkpoint | Install coving (40mm radius) vinyl flake 150mm high.
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Epoxy screeds to fall wet area setdowns
checkpoint | Install screed to fall using Hychem GP epoxy/sand mortar.
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Epoxy wall coating to ensuites 74 @ 23sqm per cell
checkpoint | Mechanical sand walls
checkpoint | Prime with Hychem GP epoxy resin
checkpoint | Apply 2 coats Hychem SF 20v epoxy
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | FLGE 505.1 - Topel Sealer
section | Details
checkpoint | Concrete moisture content check – measure moisture content of concrete substrate.
checkpoint | Substrate condition inspection.
checkpoint | Apply clear sealer (Topel Sealer) in line with MAMS.
checklist | FLGE 505.2 - Deckshield ID at 1.5mm
section | Details
checkpoint | Concrete moisture content check – measure moisture content of concrete substrate.
checkpoint | Substrate condition inspection.
checkpoint | Prime Flowprime in line with MAMS.
checkpoint | Apply seal coat (Flowcoat OP) in line with MAMS.
checkpoint | Apply topcoat (Deckshield UV) in line with MAMS.
checklist | FLGE 505.2 Deckshield ID 1.5mm
checkpoint | Apply flowcrete flowprime and broadcast aggregate
checkpoint | Apply seal coat of Flowcoat OP
checkpoint | Apply top coat of Deckshield UV
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | FLGE 505.3 Dark grey Deckshield ID 2mm
checkpoint | Apply 2 coats Flowprime and broadcast with aggregate
checkpoint | Apply 1 coat Flowcoat OP
checkpoint | Apply1 coat Deckshield UV
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | FLGE.3 - Deckshield ID at 2mm
section | Details
checkpoint | Concrete moisture content check – measure moisture content of concrete substrate.
checkpoint | Substrate condition inspection.
checkpoint | Prime Flowprime in line with MAMS.
checkpoint | Apply seal coat (Flowcoat OP) in line with MAMS.
checkpoint | Apply topcoat (Deckshield UV) in line with MAMS.
checklist | ILD
checkpoint | ILD testing
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | International Leak Detection (ILD Australia) Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | L.L Roof plant
checkpoint | Apply Tremproof 200EC primer
checkpoint | Apply Vulkem 360 base coat
checkpoint | Apply 951 top coat 150mm upstands
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Level 1 plant room/L.L roof plant room
checkpoint | Apply tremproof 200EC primer
checkpoint | Apply Vulkem 360 base coat
checkpoint | Apply Vulkem 951 top coat
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Protection
checkpoint | Install protection to horizontal surfaces
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Protection to BOH
checkpoint | Install protection to horizontal surfaces
checkpoint | Remove Protection
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Remove protection
checkpoint | Remove protection
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Roof Areas
checkpoint | Apply Primer
checkpoint | Apply base layer 3mm
checkpoint | Apply top layer 4mm mineral finish
checkpoint | Pressure strip termination at 150mm
checkpoint | ILD testing
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Sealing of Pour Joints
checkpoint | Supply and install Enviro joint band
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Stairs/BOH/Dryers
checkpoint | Apply 2 coats Flowcoat OP light grey to 0.35 DFT
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Standard ITP - Aus Standards - Wet Area Waterproofing
section | 1 - Pre-Commencement Activities
checkpoint | Project Self-Assessment Tool- BU Project Audits -
checkpoint | 1.1 - Submission of Waterproofing System products
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of Waterproofing System - confirmation of compatibility with substrate and follow-on trade requirements
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.2 - Submission of Waterproofing System Warranties
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Warranty is for required duration and relevant party
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.3 - Submission of Manufacturer's Application Method Statement (MAMS)
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of MAMS by Waterproofing Consultant
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.4 - Submission of AMS and WRA Content - including Safety Data Sheets for chemicals
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of AMSs and WRAs
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.5 - Waterproofing company to demonstrate Competency of Applicators
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Competency scheme document, register of applicators
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.6 - Detailed design complete - including shop details
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Approval of shop drawings
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.7 - Testing equipment details - and calibration records (if electronic leak detection specified)
note | Specification Reference - AS3740 App C3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - In calibration
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (R)
note | Inspection: Nominated Authority - WC (R)
checkpoint | 1.8 - First of Type Inspection -joint witness and sign-off on Prototype or First Install with membrane system representative (as below)
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Joint acceptance of the First of Type and close-out of any agreed issues
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - One-off prior to commencement
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Inspection: Nominated Authority - WC (H)
signoff | AUTHORITY HOLDPOINT
section | 2 - Construction Inspections
checkpoint | 2.1 - Install Concrete substrate and wall system
note | Specification Reference - AS3600 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Project specification criteria
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - SS (I)
note | Inspection: John Holland - PE (S)
note | Records & Comments - Project Self-Assessment Tool- BU Project Audits
checkpoint | 2.2 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Slabs require a relative humidity of less than 75%
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.6 - Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
checkpoint | 2.7 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.8 - Subcontractor Pre-placement Check: Confirm equipment, personnel and temperature is acceptable for membrane installation - note equipment ref, name of applicators and temperature on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Required size:
textbox | Measured size:
checkpoint | 2.9 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
textbox | Records & Comments - Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1 - 100% Witness Point: Watch the Subcontractor apply primer in line with MAMS - take photograph of primer container with technical details and photo/video of application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Correct primer applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - 100% Witness Point: Watch the Subcontractor apply membrane layers in line with MAMS and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements, timing between layers in line with the MAMS
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.12 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
textbox | Records & Comments - Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.13 - Membrane compound setting time - note planned and actual setting time on checklist
note | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.14 - HOLD POINT: Confirm that setting time for membrane has been complied with
note | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
textbox | Records & Comments - Planned setting time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.15 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
note | Test/ Inspection - Test
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
note | Inspection: Nominated Authority - DC (W)
textbox | Records & Comments - Observed setting time:
checkpoint | 2.16 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure that they do not damage the membrane system.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - All records loaded into the Work Lot System and Verified.
checklist | Trims to ensuite doorways
checkpoint | Supply and install trims to doorways
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Under wet area screeds (50mm Set Downs)
checkpoint | Caulk to junctions
checkpoint | Apply 2 coats Hyclad E
checkpoint | Return 150mm above screed
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Vinyl flake epoxy system wet area setdowns
checkpoint | Prime screeds
checkpoint | Apply 2 coats Hychem SF20 epoxy
checkpoint | Apply vinyl flakes
checkpoint | Apply 2 coats Hychem PA sealer includes 150mm upstands
checkpoint-no-value | Danlaid Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checkpoint-no-value | John Holland Group Sign Off Required
signoff | HOLDPOINT - Request Sign Off / Add Signature
checklist | Ω (DEPRECATED) *Standard ITP - Aus Standards - Wet Area Waterproofing (version 0)
section | 2 - Construction Inspections
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Slabs require a relative humidity of less than 75%
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Required size:
textbox | Measured size:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
textbox | Records & Comments - Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply primer in line with MAMS - take photograph of primer container with technical details and photo/video of application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Correct primer applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply membrane layers in line with MAMS and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements, timing between layers in line with the MAMS
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
textbox | Records & Comments - Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
note | Test/ Inspection - Test
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
note | Inspection: Nominated Authority - DC (W)
textbox | Records & Comments - Observed setting time:
checkpoint | 2.13 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure protection has been applied to membrane.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - All records loaded into the Work Lot System and Verified.