## ITP Cover Page
Signage Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 135 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 135
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Signage |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-2800 to 146000-002A-2851
Client: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 4.2.25 |  | Zion Nordstrom |  | Minor comments |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | [8 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Signage Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 135 - Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | ITP to be submitted to the Engineer. | Downer | Construction Pack | Prior to Works | H | SE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version AND THAT THE NOTES OF THE PLANS ARE BEING FOLLOWED | Downer | IFC Drawings | Prior to works start | H | PE
3.01.04 | Site Inspection | Site Inspection of Marked Out Sign Locations prior to any works to ensure no clashes and appropriate location for signs. | Refer to NZTA Traffic Control Device and MOTSAM |  | Prior to Works | HP
3.01.05 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.06 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.07 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.08 | Subcontractors | Ensure that subcontract and supplier agreements have been completed. All subcontractors have been inducted. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Materials
4.01.01 | Concrete | 20MPa grout mix to be used for signage footings. | Designer | Dockets | At delivery | H | SE
4.01.02 | Steelworks | Any steelwork shall be in accordance with NZS 3404: 1997. Structural steel plate shall comply with AS 3678 – 250. Steel posts shall be grade ASTM 106, Grade B or AP15L, Grade B. Steel RHS posts shall comply with AS 1163: 1981 Grade 350. All steelwork shall be hot dip galvanised after manufacturer in accordance with AS 1650 unless otherwise stated. | NZS 3404: 1997 | Dockets | Prior to Delivery | H | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Signage
5.01.01 | Signage Location | Prefered method of installation will be sockets Signage in Concrete Islands These footings will be installed after kerbs have been poured and before the islands are poured. Socket installed into raised islands will be dug out and installed level with the kerbs. Signage in Berms Excavate footings to minimum size of 300x300x600mm. Install sockets and pour concrete to finish level. | Refer to NZTA Traffic Control Device and MOTSAM | Photos | Each Sign | HP | SE
5.01.02 | Footings (Sockets) | Prefered method of installation will be sockets Signage in Concrete Islands These footings will be installed after kerbs have been poured and before the islands are poured. Socket installed into raised islands will be dug out and installed level with the kerbs. Signage in Berms Excavate footings to minimum size of 300x300x600mm. Install sockets and pour concrete to finish level. | As shown in RITS | Photos | Each Sign | H | SE
5.01.03 | Sign Installation | Check signs and pole sizing against drawings. Ensure sign is plumb, orientated correctly, correct height to underside of sign, correct offset from kerb, ID sticker is attached to back of the sign, correct bracket and channels used, all brackets secured tightly. | Designer | Sign Installation Record | Each Sign | H | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Red-line Markup | Provide red-line markups for items that have been moved, modified, etc. | Downer | Red-line Markup | Upon Completion | H | SE