## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 135 - Signage | itp |  |  |  |  | ITP - 135 - Signage Rev A
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer.
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version AND THAT THE NOTES OF THE PLANS ARE BEING FOLLOWED
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.04 - Site Inspection
label | Acceptance / Conformance Criteria - Site Inspection of Marked Out Sign Locations prior to any works to ensure no clashes and appropriate location for signs.
label | Standard / Specification - Refer to NZTA Traffic Control Device and MOTSAM
label | Verifying Document -
label | Frequency - Prior to Works
label | Verification Activity: Activity - HP
label | Verification Activity: By -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.05 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.06 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.07 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.08 - Subcontractors
label | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
label | ○ All subcontractors have been inducted.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Concrete
label | Acceptance / Conformance Criteria - 20MPa grout mix to be used for signage footings.
label | Standard / Specification - Designer
label | Verifying Document - Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Steelworks
label | Acceptance / Conformance Criteria - Any steelwork shall be in accordance with NZS 3404: 1997. Structural steel plate shall comply with AS 3678 – 250.
label | ○ Steel posts shall be grade ASTM 106, Grade B or AP15L, Grade B. Steel RHS posts shall comply with AS 1163: 1981 Grade 350. All steelwork shall be hot dip galvanised after manufacturer in accordance with AS 1650 unless otherwise stated.
label | Standard / Specification - NZS 3404: 1997
label | Verifying Document - Dockets
label | Frequency - Prior to Delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Signage Location
label | Acceptance / Conformance Criteria - Prefered method of installation will be sockets
label | ○ Signage in Concrete Islands
label | — These footings will be installed after kerbs have been poured and before the islands are poured.
label | — Socket installed into raised islands will be dug out and installed level with the kerbs.
label | ○ Signage in Berms
label | — Excavate footings to minimum size of 300x300x600mm.
label | — Install sockets and pour concrete to finish level.
label | Standard / Specification - Refer to NZTA Traffic Control Device and MOTSAM
label | Verifying Document - Photos
label | Frequency - Each Sign
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Footings (Sockets)
label | Acceptance / Conformance Criteria - Prefered method of installation will be sockets
label | ○ Signage in Concrete Islands
label | — These footings will be installed after kerbs have been poured and before the islands are poured.
label | — Socket installed into raised islands will be dug out and installed level with the kerbs.
label | ○ Signage in Berms
label | — Excavate footings to minimum size of 300x300x600mm.
label | — Install sockets and pour concrete to finish level.
label | Standard / Specification - As shown in RITS
label | Verifying Document - Photos
label | Frequency - Each Sign
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Sign Installation
label | Acceptance / Conformance Criteria - Check signs and pole sizing against drawings.
label | ○ Ensure sign is plumb, orientated correctly, correct height to underside of sign, correct offset from kerb, ID sticker is attached to back of the sign, correct bracket and channels used, all brackets secured tightly.
label | Standard / Specification - Designer
label | Verifying Document - Sign Installation Record
label | Frequency - Each Sign
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Red-line Markup
label | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
label | Standard / Specification - Downer
label | Verifying Document - Red-line Markup
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature