## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-199-CIV-SSB-Type A fill-LTP Construction | itp |  |  |  |  | ITP-199-CIV-SSB-Type A fill-LTP Construction Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-199-CIV-SSB-Type A Fill - LTP Construction
label | ITP Description: SSB-Type A Fill - LTP Construction
label | Discipline (e.g. CIV/STR/RAIL): 199-CIV
label | Revision Number: 0
label | Revision Date: 19/09/2024
label | ITP created by: VM
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: IFC Drawings VR 204, VR 210
section | Preliminaries-Materials
checkpoint | 2.1 Material Conformance-Fill Material
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fill materials used for the load transform platform shall be approved by the design Geotechnical Engineer.
textbox | Reference: Material approval/RFI in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each material type
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Design Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder RFI or MA
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Geotextile
label | REFERENCE: IFC Drawings VR 210
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Geotextile BIDIM A 29 or equivalent to be used
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Geogrid
label | REFERENCE: IFC Drawings VR 210
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Geogrid Working Load is to be 60 kN/m
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentations
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: VR 204.10 (b), VR 204.11 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
textbox | Reference: Previous layer Lot Number if applicable:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of fill works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY:
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS:
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set Out
label | REFERENCE: Design Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot prior to commencement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Signed ITP, Lot Map
date | Date Completed:
section | Type A Fill/Verge Activities
checkpoint | 5.1 Placing of Fill
label | REFERENCE: IFC Drawings VR 204.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm and according to IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.2 Test Roll
label | REFERENCE: VR 173.03, VR 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test Roll as per 173.03
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot/Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Compaction Testing
label | REFERENCE: Table 204.131, VR 204.14 c) Table 204.142
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
label | ○ Standard Compactive Effort
label | – For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | ○ Compaction and Moisture content
label | – Scale A: Characteristic Density Ratio 99%.
label | – Scale B: Characteristic Density Ratio 98%.
label | – Scale C: Mean Value of Density Ratio: 100%
label | – Lot size - the leser of one day's production or 5,000sqm
label | ATTACH: COMPACTION TEST RESULTS
label | – – – – – – – – – – – – – – – – –
label | METHOD: Review Document
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
date | Date Completed:
checkpoint | 5.4 Geogrid installation
label | REFERENCE: IFC Drawings, MRP-087-C-ACD-DRG-09-BFD-CBR-3385
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Geogrid should be installed with 2m overlap in principal strength direction and 0.5m on other directions.
label | ○ Geogrid shall be placed without punctures or tears.
label | ○ Geogrid shall b e covered by fill material within 48 hours of placement
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Geogrid installation-Overlaps
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Overlaps in Principal direction shall be 2m and key to top of the next layer
label | ○ Overlaps in other directions shall be 0.5m to the same layer
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.2 Survey Conformance andPreparation of final surface
label | REFERENCE: VR 204.15, VR 204.03f,g and h
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | ○ The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Attach: Survey results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Top of Type A/Verge
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP