## ITP Cover Page
[16 empty] | NZTA Unbound Pavement Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Tuvalu Safe and Resilient Aviation Project (TuSRAP)
Number and Revision: 300208 - 04 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tuvalu Safe and Resilient Aviation Project (TuSRAP) |  |  |  |  | ITP Number: |  |  | 04 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | 300208 |  |  |  |  | ITP Status: |  |  | For Approval
ITP Description: |  |  | Runway Pavement Pre-Works and Remediation |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | 161840 |  |  |  |  | Drawing Sets: |  |  | 12506660-ISSUE FOR CONSTRUCTION_20240802
Customer: |  |  | Tuvalu Ministry of Transport Energy, Communications and Innovation (MTECI) |  |  |  |  | Specification: |  |  | Funafuti Airport Technical Specification_Rev A_Aug 2024_Final
Quality Specified:
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Review | 2024-09-12 |  | Stuat McCarron/Ross Eden |  | NZTA Unbound Pavement ITP |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | For Approval | 2024-09-17 |  | Ross Eden |  | For Engineer's Approval & Acceptance |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
C | For Approval | 2024-09-28 |  | Ross Eden |  | For Engineer's Approval & Acceptance |  |  |  | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Doug Forsyth |  |  | #VALUE! |  | 2024-09-28 | Downer PM
Downer QM |  | Ross Eden |  |  | #VALUE! |  | 2024-09-28 | Downer QM
Client (If Applicable) |  | Nick Hansen | [5 empty] | Client (If Applicable)

## TuSRAP Pre-Works ITP
NZTA Unbound Pavement Inspection and Test Plan
Project: Tuvalu Safe and Resilient Aviation Project (TuSRAP)
Number and Revision: 300208 - 04 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JESA to the Engineer before works | Downer | Construction Pack | Submit 10 days prior to commencement of works | H | PE
3.02.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.02 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.02.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.03 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.02.04 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | TNZ M/4 - AP40 Material Approval
4.01.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | TNZ M/4: 2024 - 4 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG
4.1.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | TNZ M/4: 2024 - 5 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG
4.0103 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE |  |  | 5000m3 is typically used where source is consistent
4.02 | TNZ M/3 Notes - AP65 Subbase Material Approval
4.02.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG |  |  | M/3 is a guide not a specification. Refer to Contract Specification
4.02.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG |  |  | M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy
4.02.03 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE |  |  | 5000m3 is typically used where source is consistent
SECTION 5 – CONSTRUCTION ACTIVITY – TNZ F/01:1997 SPECIFICATION FOR EARTHWORKS CONSTRUCTION
5.01 | Testing of Subgrade Suitability
5.01.01 | Subgrade CBR Testing | DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level. | NZS 4402:1986 - 6.5.2 | DCP Report | min 2 tests per lot | R | PE |  |  | CBR=5 OK CBR>3 excavate 200mm and place geogrid CBR<3 notify Eng or as directed by Eng
5.01.02 | Subgrade Compaction & Trimming | Neatly trim and compact subgrade with appropriate equipment | TNZ F/01: 1997 11.0 | DCP Report | min 2 tests per lot | HP | ENG |  |  | Or as directed by Eng
SECTION 6 – CONSTRUCTION ACTIVITY – TNZ B/02:2005 SPECIFICATION FOR CONSTRUCTION OF UNBOUND GRANULAR PAVEMENT LAYERS
6.01 | Construction Of Unbound Granular Pavement Layers
6.01.01 | Material Placement | The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. | I | SV / PE
6.01.02 | Greenfield Sites Plateau Density Tests | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. | TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 | HP | ENG
6.01.03 | Overlay Sites Plateau Density Tests | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 | HP | ENG
6.01.04 | Sub-basecourse Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG |  |  | Or as directed by Eng
6.01.05 | Sub-basecourse Layer thickness. | The Sub-basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE
6.01.06 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG |  |  | Or as directed by Eng
6.01.07 | Basecourse Layer thickness. | The Basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE
6.01.08 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing | I | SV / PE
6.01.09 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing | I | SV / PE
6.01.10 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | TNZ B/02: 2005 - 7.8 | Photos | Prior to sealing | R | PE
6.01.11 | Pre-surfacing Requirements | Surface to be dry and clean | QPR2000 Manufacturer's Requirements | Photos | Prior to sealing | R | PE
6.01.12 | Surfacing | Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment | QPR2000 Manufacturer's Requirements | Photos | Post Sealing | R | PE
SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.01 | Site Post Construction Activities
7.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | R | SE
7.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | R | SV
7.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | R | PE
7.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | R | PE

## Construction ITP
NZTA Unbound Pavement Inspection and Test Plan
Project: Tuvalu Safe and Resilient Aviation Project (TuSRAP)
Number and Revision: 300208 - 04 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – TNZ F/01:1997 SPECIFICATION FOR EARTHWORKS CONSTRUCTION
5.01 | Testing of Subgrade Suitability
5.01.01 | Subgrade CBR Testing | DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level. | NZS 4402:1986 - 6.5.2 | DCP Report | min 2 tests per lot | R | PE |  |  | CBR=5 OK CBR>3 excavate 200mm and place geogrid CBR<3 notify Eng or as directed by Eng
5.01.02 | Subgrade Compaction & Trimming | Neatly trim and compact subgrade with appropriate equipment | TNZ F/01: 1997 11.0 | DCP Report | min 2 tests per lot | HP | ENG |  |  | Or as directed by Eng
SECTION 6 – CONSTRUCTION ACTIVITY – TNZ B/02:2005 SPECIFICATION FOR CONSTRUCTION OF UNBOUND GRANULAR PAVEMENT LAYERS
6.01 | Construction Of Unbound Granular Pavement Layers
6.01.01 | Material Placement | The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. | I | SV / PE
6.01.02 | Sub-basecourse Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG |  |  | Or as directed by Eng
6.01.03 | Sub-basecourse Layer thickness. | The Sub-basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE
6.01.04 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG |  |  | Or as directed by Eng
6.01.05 | Basecourse Layer thickness. | The Basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE
6.01.06 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing | I | SV / PE
6.01.07 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing | I | SV / PE
6.01.08 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | TNZ B/02: 2005 - 7.8 | Photos | Prior to sealing | R | PE
6.01.09 | Pre-surfacing Requirements | Surface to be dry and clean | QPR2000 Manufacturer's Requirements | Photos | Prior to sealing | R | PE
6.01.10 | Surfacing | Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment | QPR2000 Manufacturer's Requirements | Photos | Post Sealing | R | PE

## Material Tests ITP
NZTA Unbound Pavement Inspection and Test Plan
Project: Tuvalu Safe and Resilient Aviation Project (TuSRAP)
Number and Revision: 300208 - 04 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | TNZ M/4 - AP40 Material Approval
4.01.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | TNZ M/4: 2024 - 4 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG
4.1.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | TNZ M/4: 2024 - 5 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG
4.0103 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE |  |  | 5000m3 is typically used where source is consistent
4.02 | TNZ M/3 Notes - AP65 Subbase Material Approval
4.02.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG |  |  | M/3 is a guide not a specification. Refer to Contract Specification
4.02.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG |  |  | M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy
4.02.03 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE |  |  | 5000m3 is typically used where source is consistent

## Post Construction ITP
NZTA Unbound Pavement Inspection and Test Plan
Project: Tuvalu Safe and Resilient Aviation Project (TuSRAP)
Number and Revision: 300208 - 04 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.01 | Site Post Construction Activities
7.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | R | SE
7.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | R | SV
7.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | R | PE
7.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | R | PE