## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | TuSRAP Runway Pre-works ITP - Construction - 04 - REV C | itp |  |  |  |  | TuSRAP Runway Pre-works ITP - Construction - 04 - REV C
section | SECTION 5 – CONSTRUCTION ACTIVITY – TNZ F/01:1997 SPECIFICATION FOR EARTHWORKS CONSTRUCTION
checkpoint | 5.01.01 - Subgrade CBR Testing
label | Acceptance / Conformance Criteria - DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level.
label | Standard / Specification - NZS 4402:1986 - 6.5.2
label | Verifying Document - DCP Report
label | Frequency - min 2 tests per lot
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
label | Comments / Closeout Details - CBR=5 OK
label | ○ CBR>3 excavate 200mm and place geogrid
label | ○ CBR<3 notify Eng or as directed by Eng
checkpoint | 5.01.02 - Subgrade Compaction & Trimming
label | Acceptance / Conformance Criteria - Neatly trim and compact subgrade with appropriate equipment
label | Standard / Specification - TNZ F/01: 1997 11.0
label | Verifying Document - DCP Report
label | Frequency - min 2 tests per lot
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - Or as directed by Eng
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – CONSTRUCTION ACTIVITY – TNZ B/02:2005 SPECIFICATION FOR CONSTRUCTION OF UNBOUND GRANULAR PAVEMENT LAYERS
checkpoint | 6.01.01 - Material Placement
label | Acceptance / Conformance Criteria - The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 6.01.02 - Sub-basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | Standard / Specification - TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 2 Tests per lot
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - Or as directed by Eng
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.03 - Sub-basecourse Layer thickness.
label | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitured for Layer thickness.
label | Standard / Specification - TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 6.01.04 - Basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
label | Standard / Specification - TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 2 Tests per lot
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - Or as directed by Eng
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.05 - Basecourse Layer thickness.
label | Acceptance / Conformance Criteria - The Basecourse shall be monitured for Layer thickness.
label | Standard / Specification - TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 6.01.06 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 6.01.07 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 6.01.08 - Surface Finish post sweeping
label | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Standard / Specification - TNZ B/02: 2005 - 7.8
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 6.01.09 - Pre-surfacing Requirements
label | Acceptance / Conformance Criteria - Surface to be dry and clean
label | Standard / Specification - QPR2000 Manufacturer's Requirements
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 6.01.10 - Surfacing
label | Acceptance / Conformance Criteria - Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment
label | Standard / Specification - QPR2000 Manufacturer's Requirements
label | Verifying Document - Photos
label | Frequency - Post Sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checklist | TuSRAP Runway Pre-works ITP - Material Tests - 04 - REV C | itp |  |  |  |  | TuSRAP Runway Pre-works ITP - Material Tests - 04 - REV C
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - TNZ M/4: 2024 - 4, NZS 4407 : 1991, NZS 4402 : 1986
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.02 - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Standard / Specification - TNZ M/4: 2024 - 5, NZS 4407 : 1991
label | Verifying Document - IANZ Lab Reports
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
label | Comments / Closeout Details - 5000m3 is typically used where source is consistent
checkpoint | 4.02.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2024, NZS 4407 : 1991, NZS 4402 : 1986
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.02 - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2024, NZS 4407 : 1991
label | Verifying Document - IANZ Lab Reports
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.03 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
label | Comments / Closeout Details - 5000m3 is typically used where source is consistent
checklist | TuSRAP Runway Pre-works ITP - Post Construction - 04 - REV C | itp |  |  |  |  | TuSRAP Runway Pre-works ITP - Post Construction - 04 - REV C
section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 7.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 7.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 7.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - R
label | Verification Activity: By - PE