## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Switchboards
| Scope |  |  | Site QA | Switchboards
Rows
|  | Exterior | dynamic | Exterior | Switchboards | Site QA
|  | Block 2 | dynamic | Block 2 | Switchboards | Site QA
|  | Block 3 | dynamic | Block 3 | Switchboards | Site QA
Columns
|  | Spatial certificate signed if required |  | Spatial certificate signed if required
|  | Fixings installed in wall correctly if board is wall mounted |  | Fixings installed in wall correctly if board is wall mounted
|  | All clearances sighted to ensure location is compliant |  | All clearances sighted to ensure location is compliant
|  | All cables correctly installed in protection device & earth & neutral bars & fully secured |  | All cables correctly installed in protection device and earth and neutral bars and fully secured
|  | Cables neatly dressed |  | Cables neatly dressed
|  | Phase tabs on chassy covered |  | Phase tabs on chassy covered
|  | All earths & neutrals labelled to match phase numbers |  | All earths and neutrals labelled to match phase numbers
|  | Switchboard is clean on the inside & outside |  | Switchboard is clean on the inside and outside
|  | Masking blanks installed |  | Masking blanks installed
|  | DB legend installed |  | DB legend installed
|  | Feisst label on the door installed |  | Feisst label on the door installed
First Fix
| Scope |  |  | Site QA | First Fix
Rows
|  | Block 2 | dynamic | Block 2 | First Fix | Site QA
|  | Block 3 | dynamic | Block 3 | First Fix | Site QA
|  | Exterior | dynamic | Exterior | First Fix | Site QA
Columns
|  | Flush Boxes - Fire Rated or Acoustic |  | Fire Rated or Acoustic | Flush Boxes
|  | Flush Boxes - Height as per plan |  | Height as per plan | Flush Boxes
|  | Flush Boxes - Location as per plan |  | Location as per plan | Flush Boxes
|  | Flush Boxes - Intumescent Pad In Place |  | Intumescent Pad In Place | Flush Boxes
|  | Cabling - Power cables installed correctly |  | Power cables installed correctly | Cabling
|  | Cabling - Lighting cables installed correctly |  | Lighting cables installed correctly | Cabling
|  | Cabling - Equipment cables installed correctly |  | Equipment cables installed correctly | Cabling
|  | Cabling - Circuits clearly labelled |  | Circuits clearly labelled | Cabling
|  | Cabling - Separation between Data & Power at 300mm or as specified |  | Separation between Data and Power at 300mm or as specified | Cabling
|  | Cabling - All cables secured via cable ties with ends cut |  | All cables secured via cable ties with ends cut | Cabling
|  | Cable Ladder - Minimum 25% spare capacity left on cable tray |  | Minimum 25% spare capacity left on cable tray | Cable Ladder
|  | QA - Lights - Setout Correct |  | Setout Correct | QA - Lights
|  | QA - Lights - Cabling in correct location |  | Cabling in correct location | QA - Lights
|  | QA - Lights - Emergency/ Exit Lighting |  | Emergency/ Exit Lighting | QA - Lights
|  | QA - Lights - Nogging installed for Electrical Services |  | Nogging installed for Electrical Services | QA - Lights
|  | Seismic Bracing - For Lighting |  | For Lighting | Seismic Bracing
|  | Seismic Bracing - Cable Tray |  | Cable Tray | Seismic Bracing
|  | Seismic Bracing - Switchboard |  | Switchboard | Seismic Bracing
|  | Conduits - Correct size installed |  | Correct size installed | Conduits
|  | Conduits - Location as per plan |  | Location as per plan | Conduits
|  | Conduits - All conduits glued & watertight |  | All conduits glued & watertight | Conduits
|  | Conduits - Clean inside & in good condition |  | Clean inside and in good condition | Conduits
|  | Conduits - Stainless screws used |  | Stainless screws used | Conduits
Second Fix
| Scope |  |  | Site QA | Second Fix
Rows
|  | Block 2 | dynamic | Block 2 | Second Fix | Site QA
|  | Block 3 | dynamic | Block 3 | Second Fix | Site QA
|  | Exterior | dynamic | Exterior | Second Fix | Site QA
Columns
|  | Power Outlets - Correct type installed |  | Correct type installed | Power Outlets
|  | Power Outlets - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Power Outlets
|  | Power Outlets - Outlet Installed level |  | Outlet Installed level | Power Outlets
|  | Power Outlets - Circuit Tested & results recorded |  | Circuit Tested and results recorded | Power Outlets
|  | Power Outlets - Description Labelled on the outlet face with vivid & with dymo labeller on cover plate & ensure label is level |  | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level | Power Outlets
|  | Light Switches - Correct type installed |  | Correct type installed | Light Switches
|  | Light Switches - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Light Switches
|  | Light Switches - Light switch Installed level |  | Light switch Installed level | Light Switches
|  | Light Switches - Circuit Tested & results recorded |  | Circuit Tested and results recorded | Light Switches
|  | Light Switches - Description Labelled on the outlet face with vivid & with dymo labeller on cover plate & ensure label is level |  | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level | Light Switches
|  | Light Fixtures - Correct type installed |  | Correct type installed | Light Fixtures
|  | Light Fixtures - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Light Fixtures
|  | Light Fixtures - Tested for operation |  | Tested for operation | Light Fixtures
|  | Light Fixtures - Correctly installed with stainless screws & 90 / 45 angle |  | Correctly installed with stainless screws & 90 / 45 angle | Light Fixtures
FEL SM Weekly Site Progress
| Scope |  |  | FEL SM Weekly Site Checklist
Rows
|  | FEL SM Weekly Site Checklist | dynamic | FEL SM Weekly Site Checklist
Columns
|  | Prestart Meeting with Team |  | Prestart Meeting with Team
|  | Review Tasks for the week |  | Review Tasks for the week
|  | Identify Targets Including Hours |  | Identify Targets Including Hours
|  | Approve hours by 9AM for previous week |  | Approve hours by 9AM for previous week
|  | Review SWMS |  | Review SWMS
|  | Site Toolbox Meeting |  | Site Toolbox Meeting
|  | SSSP in Order |  | SSSP in Order
|  | Materials organized for week ahead |  | Materials organized for week ahead
|  | Plans printed with any relevant notes added |  | Plans printed with any relevant notes added
|  | Submit Toolbox minutes to main contractor and FEL office |  | Submit Toolbox minutes to main contractor and FEL office
|  | Job Cards up to date and submitted |  | Job Cards up to date and submitted
|  | Team tasks for week ahead filled out on whiteboard |  | Team tasks for week ahead filled out on whiteboard