## Master List Templates
Id | Type | Name | Values | Prompting Name
850ee71d-d2df-5dad-a93c-b836182b2248 | checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
26d5d62f-8773-5d6d-81f7-d3753ca4498e | checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
4977d416-cdc2-5db9-a0a9-9fa87c56ca6a | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
258a39b8-19ff-5418-829d-82c7f06ce5e9 | checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3d8767f9-be0b-5aac-8f8d-8d8d30576afc | checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
d22d01c7-b271-511d-bf41-2fff8ae5a522 | checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
6661068e-fea7-5cf6-8f24-87de51d674b3 | checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: SWA Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
34e18449-c3fd-51e1-b56f-ccf521a5d073 | signoff | AUTHORITY HOLDPOINT
6011a022-02be-59a2-94b2-a549f045b1b4 | checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
df52cdfd-6140-55da-9bdb-919ccff3ef0e | checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
c2ae29b9-5806-569e-9a2b-c426503dac7f | checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
36fd9b7a-b6e8-5247-b9fc-beb7b3b74a89 | checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
7b5f6175-7f46-5e8e-9ee6-408a701b92a1 | checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
10f33595-9d77-50f4-8495-2fa4d6875210 | checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
d4973271-760f-5b31-af74-2ebb3b7ab3b1 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
26d72225-2718-546d-bfad-44cc023633ba | checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
d7d138dc-b209-5f3f-9e52-54a34e093893 | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
6a8c7900-a2b5-5b4c-a9f2-c7a3c37ec233 | checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
cbc56fa7-00d7-56ad-8ff1-adc73e4f310b | checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
1da3da15-df67-53b8-8391-08ce244460db | checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
5cef2364-fc9a-55b3-897e-5719fb07fa24 | checkpoint | 1.1 - Line marking Conformance
6decc52f-f238-5406-ab45-b16481be0a0b | note | FREQUENCY: Prior to commencing any activity
7c288dfd-04f6-552e-b391-cad67fc8e389 | note | SPECIFICATION REFERENCE: 721.A05
0eed24db-71c4-56d9-8c7a-215ae2ec8619 | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
fa4c2060-243b-501c-8e2f-27a76b3071ef | note | METHOD: Record Review
6433e9d9-b4ff-5fb3-90fa-e39d594a5687 | note | RECORDS: Material sheet
abe5d130-c2eb-59cf-932e-10707b24b6f6 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
a6bb2cbf-0d23-52b0-b090-753f9c10c343 | date | Date Completed:
c5e3f47c-1aa8-52ad-8554-cf927bf34df6 | checkpoint | 1.2 - Site preparation
d18fc51f-9df8-57ee-b89e-384f6558a56e | note | FREQUENCY: Prior to commencing any activity
d66cd9af-99fe-503e-b88f-bec56f029177 | note | SPECIFICATION REFERENCE: 721.A06
c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd | note | METHOD: Visual and photos
b39132fc-055b-52d3-8708-1e0fd0fa57a5 | note | RECORDS: Photos
c9307376-374c-5ff1-b4c2-6f24de01fc24 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c | date | Date Completed:
10e8df30-8e3b-5e45-9098-f3d33006ff0a | checkpoint | 1.3 - Set-out of Pavement Markings
7bde258e-74c2-5c81-bf6b-35ad7ddc6081 | note | FREQUENCY: Prior to commencing any activity
de495b17-2a23-56c0-ad33-f7afc9581f62 | note | SPECIFICATION REFERENCE: 721.A09
6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 | note | METHOD: Visual and photos
c558960a-0248-57f7-90b1-384e21ba49ad | note | RECORDS: Photos
f1b399a1-dea7-51e6-87f2-19eb06a93111 | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
08893043-6dba-527a-9b46-af7ef49a05f5 | date | Date Completed:
42ac8a73-53d5-50a4-af62-d62c56b9c160 | signoff | AUTHORITY HOLDPOINT
4d771e39-83c7-5f41-a79c-a877901269cc | section | 2 - Installation
53d345a3-b074-53be-9960-4c84b68ad956 | checkpoint | 2.1 - Line marking Installation
c216f09e-e64f-5289-90ff-ea17db6088ce | note | FREQUENCY: During Construction
7b41ef96-e45e-5b58-8eba-c45bf7e440a0 | note | SPECIFICATION REFERENCE: 721.E01
1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
c7f74a36-d531-5906-8184-1de2656be786 | note | METHOD: Visual and photos
2de447ee-5a6f-56df-822b-09690da6d889 | note | RECORDS: Photos
83888801-2031-57f3-9d6e-cf2df5ddddfa | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
ecf7e8c7-cd15-594e-b258-61d9a4262581 | date | Date Completed:
d7536392-f7f1-5cf6-a9e1-10ecb3aafac4 | checkpoint | 2.2 - Glass bead Install
5455461d-d578-5fef-9098-a807025a435f | note | FREQUENCY: During line marking works
129c5718-be6b-5fc0-91c6-c9e6c29be098 | note | SPECIFICATION REFERENCE: 721.E01
ce56130a-5110-595a-aec7-42c6ca9abcef | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
351b2f21-f74a-5d7f-b7a2-9715036c0f93 | note | METHOD: Visual and photos
e9e028e9-191f-54b7-80e9-a5bf175842e5 | note | RECORDS: Photos
6d897b20-0225-53cb-9378-5dd5cfdc8b15 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
66e6e253-8acf-59ac-ae0d-5e39d27d0b8f | date | Date Completed:
92b4b64a-0442-5ccf-809c-1df2c0c9fc2b | section | 3 - Compliance
2e11042d-a62c-5dff-b90b-fcb515194edd | checkpoint | 3.1 - Completion Inspection
a78cba1d-391d-5576-b565-d7c818c9ae63 | note | FREQUENCY: Upon Construction
eca57be0-f036-5a9c-bdf8-e25656d8747b | note | SPECIFICATION REFERENCE: 721.E01
c016ebed-7ed6-50d5-901b-0940617d2880 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
89a29f29-226a-5cf8-a981-41a43db99235 | note | METHOD: Visual and photos
e7353a58-a06a-51aa-8a5e-2b88791f02b0 | note | RECORDS: Photos
2139db14-7aa0-5b72-8de0-a3783d940be8 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
453e1ff4-6428-5952-a42b-9d525c515a66 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
5d9c743b-b1d0-566a-9dda-72569b99b130 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2275156b-b27e-564c-83c7-e53642e4cd9e | textbox | Print Name:
6b1dd9bd-aca6-522f-9252-6caa596d6f13 | textbox | Position:
3320fbd0-ce9f-544f-b805-702c0f697824 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
346e49e8-47bc-4749-a343-58c3eff9d7ff | checklist | Concrete Pour Record |  | Concrete Pour Record
decc4ae7-db80-4b2e-9c80-491b697b9bd9 | section | Preliminaries
6e950b39-a789-4a0b-ba42-dc989a63186c | checkpoint | Survey (1)
a114b964-e012-58fb-8340-55a850003857 | note | ACCEPTANCE CRITERIA: Sufficient survey set out information is available.
474cdf33-f47e-52b0-84e6-29403e6bd4d3 | date | Date Completed:
82f9ca9a-9501-4382-b55b-810793d47c6c | checkpoint | Survey (2)
85db5add-8502-5029-b2ec-ae09d1faa949 | note | ACCEPTANCE CRITERIA: Correct line and level for placement of concrete
285592e8-42c0-5dc6-87a1-273e1883a1b1 | date | Date Completed:
034faf9a-6a66-4786-89d8-40d3397f1f07 | checkpoint | Material Delivery (1)
9dbb26a4-74e8-55b8-ad79-3342a3d953a8 | note | ACCEPTANCE CRITERIA: Items conform with the applicable Australian Standard/s
2a663534-a869-564b-a1d3-c75332b03fa1 | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
9c3afd1a-26b1-5adf-9da2-7dc563393a42 | date | Date Completed:
8aaff2a1-7e1f-4989-b52e-7c945da54714 | checkpoint | Material Delivery (2)
4bc8b152-1424-5b11-9cc3-4bf43c217e16 | note | ACCEPTANCE CRITERIA: Items delivered with no visible signs of damage
b99e1221-caae-5d4c-9147-5e452db78b5a | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
968fee1d-b0d7-58c5-920f-1907084d08e1 | date | Date Completed:
d2f998cd-73eb-43c3-bf78-6dcca650d515 | section | Pre-Pour Check (to be completed by Engineer or Supervisor)
3d48c77e-4c03-4047-b2ef-854a4568a7c9 | checkpoint | Confirm Dimensions
03f8e694-66c7-5ce3-8f49-358df6ac7235 | note | ACCEPTANCE CRITERIA: Visual Check and Measure dimensions are correct for trench width or Thrust Block dimensions
a035709c-8844-5a32-89c5-81642f7fb875 | date | Date Completed:
d6a0cde7-a8d1-4f05-a053-a3e953512410 | checkpoint | Initial pour against ground (1)
ec31f62c-c010-5018-8503-ff962a5ec8de | note | ACCEPTANCE CRITERIA: Surface free of water and soft spots
0a38ec50-ace2-54d5-89b5-f632576bd5d7 | date | Date Completed:
72f7bbb4-0fb0-4cd5-a883-b9793b55368e | checkpoint | Initial pour against ground (2)
c4e99a11-9f3e-5e7a-b700-bfe3736dca78 | note | ACCEPTANCE CRITERIA: Hardstand/ ground suitable for concrete pump location
8763fea4-0af4-526c-8607-0b43ac3382fb | date | Date Completed:
df69d467-c00f-456c-b3b7-07ec65493b63 | checkpoint | Initial pour against ground (3)
4815e622-24a3-51a7-8bdc-c1d1c8812ddf | note | ACCEPTANCE CRITERIA: 50mm blinding UNO
3adbb4d9-d41e-5ebc-9864-a6529bf134a2 | date | Date Completed:
0720518c-3fce-49b2-bb20-ee47ee93791b | checkpoint | Initial pour against ground (4)
1eef74ae-9b2c-567c-840f-5c415e67da25 | note | ACCEPTANCE CRITERIA: If for Thrust Block no loose Material
7203128f-e7c3-5fe7-aaf0-c9581bcae687 | date | Date Completed:
4d7f6957-b9e3-42eb-b13a-af7159f88f8d | checkpoint | Construction joints & surfaces
9f08a4d0-929e-5db5-8f8e-1924e83978f3 | note | ACCEPTANCE CRITERIA: Clean and free of laitance, scabble where required.
a4dc1e1f-575f-5bf5-94a9-ba2609840e02 | date | Date Completed:
23ef06e0-b7bf-495c-8ca0-5ac8058e4b7e | checkpoint | Reinforcement
4248ec4c-9262-5269-96fb-3b0e7dd17fba | note | ACCEPTANCE CRITERIA: Installed as per IFC drawings
41120141-3825-5274-a47a-93fa08f18e0d | note | ○ Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified
29f194f3-f336-5401-a06b-dd5d6174ed8d | note | ○ Extra tie wire on splice bars around construction joints and wedges fixed to support splice bars in stop end formwork
08361996-3304-51d8-a416-e774593941f9 | note | COMMENTS / RECORDS:
baac8399-01fb-56bb-9ab1-9426475d0780 | note | Cover (mm):
f88a314e-48fb-5ca6-a7e8-7c1ff5016e94 | tickbox | 50mm above obvert
327bd230-15e6-513e-a677-f96e126870e2 | tickbox | 75mm ground clearance
b970f5d1-15ec-57ce-bfdd-30e2e1b8bcaa | note | Reo Count:
b73e1354-4e60-54c5-bd59-b2c3ebcf9bfe | tickbox | Reo Count
c4ce3874-e841-554a-beb3-c4237202c3d7 | date | Date Completed:
740bc3c3-cc8e-475d-a527-7d075b4af213 | checkpoint | Cast-in items, block outs and hold down bolts
7864c898-f51b-5f4a-9699-eed662aee989 | note | ACCEPTANCE CRITERIA: Type, quantity and location as per design.
b3d27ff4-4e2c-5b11-adf1-8211568b8fba | date | Date Completed:
8a872082-341e-4ed7-81a0-d0fc075e8cbd | checkpoint | Final inspection (1)
dd142f68-b156-54f2-89ed-a8a02158097e | note | ACCEPTANCE CRITERIA: Pour arrangements agreed and equipment adequate
6c821076-40ab-592a-a64b-af72e3167ff9 | date | Date Completed:
00bfd1a0-4d52-4679-89da-342b1ec84756 | checkpoint | Final inspection (2)
7b0c96fe-19fa-5239-be3d-ac8c7bff5203 | note | ACCEPTANCE CRITERIA: Surface free of water, dust, debris and stains.
512f9628-b920-50ad-adb8-4a6fc1e47372 | date | Date Completed:
c2e6ef42-4272-4bb3-a25c-bab3b75d1a68 | section | Concrete Pour (to be completed by Engineer or Supervisor)
01d832be-7b8e-415d-8e5f-7a2411b6552f | checkpoint | Correct Batch / Grade of Concrete
fba7b12e-6163-5715-9268-b3bdbf481736 | note | ACCEPTANCE CRITERIA: Visual Acceptance of the docket prior to pouring
352ac658-1e55-535c-9c17-163c1f4dd291 | date | Date Completed:
c79fec9a-7d09-49fb-96ae-39bf42c253c8 | checkpoint | Concrete quality
981abd6b-3662-51d7-be6b-99638520e738 | note | ACCEPTANCE CRITERIA: Visual assessment of quality - note details of any loads rejected
38b1a9f5-3a07-5556-b84e-7c2a144c78fe | date | Date Completed:
b3468d4a-6dc3-48a3-9ece-2f4591d422ef | checkpoint | Concrete Testing (Vertical Crest Thrust Block)
e35a273e-aa90-5bce-8168-2e217760ca82 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
f6675274-38c0-5bfe-8d55-28c89f1db898 | date | Date Completed:
e44c8bd4-231f-448e-8d29-daa2b12d1964 | checkpoint | Concrete Testing (All Other Concrete Pours)
1d5e1b6e-5a98-5b75-a165-8d228e158bb1 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
58b7d6d1-48fe-5423-a467-d3692d14415a | date | Date Completed:
4c66d260-243b-41e2-8953-d645341b917e | checkpoint | Compaction Method
41dd52de-885f-5885-9de5-fa662439db3d | note | ACCEPTANCE CRITERIA:
895441a0-5808-5a83-840a-0b1d70a487cc | tickbox | Pencil vibrators
3c7d4070-81c6-52e5-b46f-93b7156ac22b | textbox | ____No
18408afc-737d-5d08-a20d-410df604ae23 | date | Date Completed:
a2fff851-145a-5612-8ba5-dba6a106c273 | textbox | Signed:
f2154298-e766-5972-9282-3dca100e366d | note | Engineer (initial & date)
6cc2f104-bd57-5b69-b029-19d0b56e0be3 | textbox | Engineer - Initials:
66d9882e-6202-55d8-84fe-d1564f13127e | date | Engineer - Date:
16d7dfa5-957f-5236-9457-494209a670b3 | note | Supervisor (initial & date)
b7c4edba-9f75-53af-904a-4094072b890a | textbox | Supervisor - Initials:
4691252d-5de4-59cc-a63b-2711103ff57d | date | Supervisor - Date:
68224f10-8759-4236-8874-5632ed536fd8 | section | Post Pour Check (to be completed by Engineer or Supervisor)
9d7d7ab9-b41e-4fc9-9c1c-fb5274178168 | checkpoint | Curing of exposed surfaces
810d7661-c45a-58d5-9056-e92a37b33c7e | note | ACCEPTANCE CRITERIA: Exposed surfaces cured
695f7040-2d56-5d6b-8ed5-1925048a1a9f | tickbox | Polyethylene sheeting (edges / laps sealed, 300mm min laps)
0f764953-e7a3-5488-8c6c-0b97ba962a58 | tickbox | Curing compound
94bd2c9d-f0e0-55d0-b48b-f976111dadc9 | tickbox | Water curing (continuous spraying, ponding, wet Hessian)
a7fbe6bb-16ba-5669-82cf-c858ac2bfaa0 | date | Date Completed:
5adaa3d2-86e0-4aa8-9b63-05c0841af3ba | checkpoint-no-value | Location of embedment, hold down bolts and penetrations
3f001e90-eaf7-5acd-8a54-e35cb9665764 | note | ACCEPTANCE CRITERIA: All embedded items, hold down bolts and penetration located in accordance with drawings
0c1ee87d-e0e7-5e2d-abf8-15d5615cd58a | note | Refer defects list below
5ce42010-82fd-5992-9218-27d2b36cc1cb | date | Date Completed:
a2d76aaf-179f-4c02-93d6-caeac17676b8 | checkpoint | Details of defects – cracking in slab pours and Inspection of repairs.
9b872936-2b65-59ec-b422-b6dcaecc3d9b | note | ACCEPTANCE CRITERIA: Finish concrete surfaces inspected by Supervisor. Within specification tolerances (≤ 0.2mm)
f2f8830a-7f46-5633-a117-bb42f8b492e0 | note | ○ All defects repaired
f7c0e7d7-f120-54c7-8a86-747a264c440a | tickbox | Cracks requiring repairs observed
3696c69f-4807-5d18-9987-ae3c98f774ed | tickbox | Refer to attached location plan
f8646abb-b6ff-5be6-ada7-86d282f3631f | textbox | RFI
17b5c1bb-fd76-51be-ab19-b6df65cb6bd5 | tickbox | Repairs in accordance with approved specification.
d0e1305f-deab-5434-ae78-96cd570aaa49 | note | COMMENTS / RECORDS:
896ae33c-4c17-58a4-8e9f-cbcaf97a05be | textbox | Type of surface finish:
7a510f27-dc30-51a7-8a95-605ecc952634 | date | Date Completed:
2a0f2917-4d5d-4207-ad23-08c5caa415b1 | section | Final inspection
46e83414-5521-40ad-a330-342f5ca61e0a | checkpoint | Witness Point
795ae5a8-f08d-5a00-8a40-6ca6167546b4 | note | Engineer (initial & date)
93e5323b-4739-55ed-a797-1377245aac9e | textbox | Engineer - Name:
a8006b88-b4b3-5238-835c-5f5e874fd2fc | date | Engineer - Date:
7ea072b4-ebcd-5529-b506-56cfda3153a1 | note | Supervisor (initial & date)
d61d0af2-03b4-5807-b251-0471abe253e4 | textbox | Supervisor - Name:
bec9f298-d258-5126-8453-d304a57cd661 | date | Supervisor - Date:
2dedd558-a4a8-4b40-ae58-6fcbef100903 | signoff | Signatures
ed109a49-6696-48fe-80fd-76697dccd6ba | checkpoint | Details of other defects
797c68be-ddfe-5b6b-b1d0-b3e407f4347b | button | Defects listed and NCR raised (Y/N) | Yes,No
2eeae433-ef6a-57a2-bfca-1af92cef8424 | textbox | NCR #
44490003-4a69-40c4-bd75-b550f3f07db7 | checkpoint | As Built survey complete
df0f97ac-1a28-4cac-8e86-8a8e850388a4 | checkpoint | Close out
7c59119c-22a3-56ba-8246-28b3c6af462b | note | Final inspection: All work completed accordance with applicable procedures, drawings, specifications and approved changes
70e1cc3e-2e8b-5302-8287-12d0db41692c | note | Engineer (Name, Sign & Date)
f77088a2-379c-51ee-8612-ed2eb88eb4ac | textbox | Name:
1d642801-a9d3-5046-94f6-e0eea2272e21 | date | Date:
522d8b50-41c3-423e-b541-dd53a93435bc | signoff | Sign ITP
f9f3ce1a-52b6-42e7-8ebc-5f8f5dfa08d2 | checkpoint | Final Inspection
294182eb-db36-5a4a-877f-6128166bbc91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
154d2203-e473-5f8b-94ed-928fca373454 | textbox | Print Name:
91ffa316-85cf-58cc-bd53-6295a9ec1c04 | textbox | Position:
d2eb4d9f-27a7-5568-b75a-b5e7f47d26d9 | date | Date:
1ae80cc1-2a01-4060-9790-f68c05a67a73 | checklist | ITP No. 1 - Bridge Rail Installation | itp | ITP No. 1 - Bridge Rail Installation
e1664d1c-6e0d-43b6-8a7f-2ad517a7b0ee | section | Details
53b6390d-169a-4b06-9281-6802cb722a89 | checkpoint | 1 - Receive Materials
6cfda95e-3bc1-5821-b78c-f49640d441ba | note | FREQUENCY: Inspection prior to receiving
f555b790-e421-5c68-a25e-36a7ac72c27c | note | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
92772672-a62f-50ed-85ec-dd018c8f334e | note | REFERENCE DOCUMENTS: AS5131
955f8c3e-e08e-5d6f-8ca5-679fbeb9b22b | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
04afd706-d82f-5b98-b047-100cf827370d | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
012c83c7-6ad8-54d1-8b70-af1bb900b345 | note | HP, AP
4cb2a58c-055e-5d57-96c0-b6d4a924b75f | note | RESPONSIBILITY: Project Manager, Clients Superintendent
960e9cb4-d25e-5039-89a4-f08ac34c06b0 | date | Date Completed:
3a9af799-7408-4113-8974-1fc1afd375e1 | signoff | AUTHORITY HOLDPOINT
ad063ec7-f1cc-4ba8-9bf8-5f9510c60bde | checkpoint | 2 - Material Testing
aa9f3dd9-6811-5a62-94ac-7422c45ae4d8 | note | FREQUENCY: Each Lot and as required
2e3581eb-4cac-5b4b-9b56-5e99bc85c0ef | note | ACCEPTANCE CRITERIA: All materials to comply with IFC drawings
77627463-c200-574f-99dd-211abd546d85 | note | REFERENCE DOCUMENTS: Drawings
e5750e6c-d8d1-5e74-9c56-fcb52856179e | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
694ef867-3d34-53cd-b9ea-700a0d94afba | note | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
9ba89753-ca73-59d6-9a02-6043309c0005 | note | HP AP
8d5bbb85-9082-5bda-abf0-662d4f0985dd | note | RESPONSIBILITY: Project Manager, Clients Superintendent
1c2dae39-5a16-5f10-8d1c-8a9ef426fef3 | date | Date Completed:
5db9681e-47e0-4b0d-a128-8232d599f954 | signoff | AUTHORITY HOLDPOINT
15e8cbbf-8b9a-4ec5-a1ea-54461711deb8 | checkpoint | 3 - Welding
8b7e8bb2-613e-58b5-b1f4-638ae84d50ec | note | FREQUENCY: Visual Inspection
dcdc7bb6-f3c5-5b63-923d-f68e185729de | note | ACCEPTANCE CRITERIA: All welds to comply with IFC drawings
16950f38-6e12-5338-9696-27b8780f0efb | note | REFERENCE DOCUMENTS: AS5131
a7ead46b-b170-5ef9-83c7-9766ede6a68a | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
cbd44ed9-483d-5500-8215-4a9131d8edf1 | note | RECORD OF CONFORMITY: Qualified Welder Certification Reports
927bab02-20d3-5ed9-a950-7933bcc0b997 | note | HP, AP
163c2b91-bed7-5e23-9929-01bc22530997 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
9d1a39d1-dbdf-53cc-81b7-08a8d4a838e3 | date | Date Completed:
3ad61cbc-e43a-4612-85a2-d8e49e6cc60d | signoff | AUTHORITY HOLDPOINT
29a84c9c-4f8a-4121-9c3e-8d2cd67f7ec0 | checkpoint | 4 - Dimensional Inspection
dc24788e-b079-5f2c-9bdb-6146e3f4bf71 | note | FREQUENCY: Tolerance as per design
246ee90a-aa25-5f33-bb4e-e8c54248183e | note | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
b877852f-a749-54da-b861-fcab96d24190 | note | REFERENCE DOCUMENTS: Drawings
c4c97c92-1d57-539d-b3e9-50b698c093d8 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
2a2d6140-ab18-5ac2-ab44-40617783b262 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
c25d6dbd-02a1-5353-b229-16bb09c2cc05 | note | IP, IP
0cac953f-1410-5dce-8087-f3f0c3110182 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
e57019dd-a209-5eea-9f55-6947fc7829fa | date | Date Completed:
4616bacb-ee86-4e64-abcb-ec9d99dc4e28 | checkpoint | 5 - Surface Treatments
65e2461d-ace4-5ab8-abbb-94e605caaaa2 | note | FREQUENCY: Inspection prior to receiving
aa3c12b6-88f8-5bb9-aaae-622d27d07f3b | note | ACCEPTANCE CRITERIA: Superintendent shall confirm the quality of rail surface before the erection of rails commence.
2d6a0987-ffb7-583c-8d87-c269a2dd31d2 | note | REFERENCE DOCUMENTS: Drawings
4fa2179e-723b-5d80-a07f-ceb887a7a896 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
3ec01b32-b156-5f9a-b536-4aab617ddfc1 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
f824b24b-f491-5c87-938a-dd2ca7b4bf5e | note | IP, IP
6ae78cc8-47ad-50e6-bea9-13e2f17f1a36 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8de18812-189f-5dd7-a6d9-88368a78bd68 | date | Date Completed:
91268f55-c149-4a7f-beee-eeb0fe31cc42 | checkpoint | 6 - Fixtures
4abbd69f-1cd2-5a74-889f-d1187db0c345 | note | FREQUENCY: Visual inspection
bb4cb3fd-74ee-50a2-8a6b-9db23dd6ffc7 | note | ACCEPTANCE CRITERIA: Superintendent shall confirm the positioning/number of bolted connections.
d4d865ad-83fe-52ba-be4e-eabe3a1528d3 | note | REFERENCE DOCUMENTS: -
7b18ae47-9f75-5e8a-8b07-6878c6d6ce88 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
74c084f5-12dc-556d-857e-ae91dadba3e8 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
9c8720bb-a0eb-545f-91b7-d86fff8aac0e | note | IP, IP
00f88805-10fc-56d4-b338-a04feac75797 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8be56d19-5ae0-5a5c-b147-26d774e55245 | date | Date Completed:
abc6fb4d-4ddb-4b9c-ab50-b1338ff3408a | checkpoint | 7 - Concrete Infills
9e8aa6c7-feec-55f4-abd8-56960fda2d73 | note | FREQUENCY: Visual inspection prior to pour
8cecc8c9-cc89-5603-8875-631368138bd9 | note | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the positioning of bolted connections before the installation of the concrete infill commence.
59df7b80-cd25-54ef-80bd-c5cab8155fa6 | note | REFERENCE DOCUMENTS: -
5d951d03-9c4d-5371-92a1-247a90d4a9c1 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
e10760e6-d3bd-5ef7-9ee3-73603d34c0b7 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
17f9468c-b2d4-5267-97e2-08b1613e8b48 | note | HP, WP
42efda9f-f465-52bd-9a6b-d22d8d22c9b2 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
e0a03363-2ba0-5de8-b1dc-066ac726eebb | date | Date Completed:
64ba0693-3cb0-4193-b998-86e7070115f2 | signoff | AUTHORITY HOLDPOINT
645ffd5a-e010-4052-994b-7288b386e12a | checkpoint | 8 - Finishings
0e486dea-25c2-569f-86a7-16142bf3e6ae | note | FREQUENCY: Visual inspection upon completion
2d06bd82-9d88-5d82-a812-63922d2d347a | note | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the finished bridge rail in accordance to the design drawings.
fc4ce7dc-fc6f-5971-8ae8-ce7bb9668c78 | note | REFERENCE DOCUMENTS: -
aa36b0ec-c8e5-5ff8-bdc0-423028ee3177 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
678128bb-d616-5edf-a204-4a81c0917cfc | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
750c1919-15c1-54f5-899f-479f289fc6cb | note | IP, IP
f84548a2-78f5-5295-99e1-75cab5d5fe74 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
d8289a72-018b-5063-aae0-9f7cb8b8affb | date | Date Completed:
3dfbfff0-b483-4dd5-8d0b-f41900c8e8ef | checkpoint | Final Inspection
456b3b71-098d-5cf4-93cf-1414a9f664dd | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
572b658b-8558-5a48-abe3-56a4b223366b | textbox | Print Name:
9f5fe989-38c4-5765-a746-9a269e5b326c | textbox | Position:
9095111b-3fc0-55d9-8c39-fd6a17cf2aa5 | date | Date:
2c1d99ea-7385-4669-ae2c-48b0be7a0157 | signoff | Sign ITP
58a3711a-4ce9-46f0-bab9-ae400aae9946 | checklist | ITP No. 2 - Bored Pile Installation | itp | ITP No. 2 - Bored Pile Installation
ccbdda98-f163-4cf0-83e7-1d6b48fc3bb7 | section | Details
0e904d62-dada-47c3-bf12-c5584b9cad72 | checkpoint | 1 - Survey Setout
1fbf4a83-4896-53d4-92fe-9496d3a59dc4 | note | FREQUENCY: Inspection all new Setout
b516ec90-0128-5129-8fdf-fd8717be6b2b | note | ACCEPTANCE CRITERIA: Site inspection and client witness point
735cc604-6d7a-567d-8208-2aaa07a3ba55 | note | REFERENCE DOCUMENTS: Section 204
2c52ee11-78a0-5c3a-89b4-8cd90764927e | note | INSPECTION / TEST METHOD: Inspection
a3ef43bb-85c5-5e68-b94d-1a71062618f7 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d2ad6378-ac91-56e9-8ccb-0a28d5a0704a | note | HP, WP
cd3b2509-846d-559f-8673-81669a4bbff8 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
4e6afd8d-3e30-5bb0-9497-677a0289efac | date | Date Completed:
706057d1-2216-4f04-9cfe-1f30d1f67956 | signoff | AUTHORITY HOLDPOINT
fd088394-4e6d-4e25-af9d-b8a724a5c78f | checkpoint | 2 - Clearing and stripping of topsoil
b7073e76-3ed3-53a1-bcd4-e265f6c5f3ce | note | FREQUENCY: Clearing and stripping lot 1 of site
59eb685a-ea5c-5a8c-af05-247b92028ea7 | note | ACCEPTANCE CRITERIA: Compliance with drawings
e1048678-f677-5dd1-bf04-631134e7c51c | note | REFERENCE DOCUMENTS: Section 204
ef83a318-b00a-5a27-b45e-9082a18b7a17 | note | INSPECTION / TEST METHOD: Inspection
8c29ca65-e226-5486-9c83-f01640ea02b9 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d4c35abb-5dec-5326-a898-9dbbbef5cf16 | note | IP, IP
89d7f748-b8ec-5df5-bd77-8b3da4ed3302 | note | RESPONSIBILITY:
0519b884-8929-59ad-a8c3-82572243e7d3 | date | Date Completed:
7747ac9c-3967-43cc-b9aa-6fd6bacae01d | checkpoint | 3 - Supply & install of bored piles
9ffcb84b-cd53-5164-b881-3a2ef42b52d3 | note | FREQUENCY: Each bored Pile
60fd874c-d8bd-512f-81c4-dceeec70b149 | note | ACCEPTANCE CRITERIA: Compliance with drawings through completion of pile which includes:
27ffe0e6-a137-5aec-9393-c32ce74280e0 | note | ○ Material conformance checks
35420002-d4a5-59e2-bf99-4fe84365b662 | note | ○ Line, level, cover, and angle checks
2b8e9acf-26f0-5b7d-a3a4-9954867966b1 | note | REFERENCE DOCUMENTS: Section 606
a7508b70-ac9a-5f7a-9fbc-ad3ab38ad43e | note | INSPECTION / TEST METHOD: Pre-pour inspection, Delivery dockets
da1bfe8e-56dd-5c95-b3a0-e4c50d1675cc | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
27f37392-0b4b-53c4-9037-12cb5f75b1d0 | note | HP, WP
bbbec084-7f87-5e30-af30-bd09f0be73be | note | RESPONSIBILITY: Project Manager, Clients Superintendent
1aae1dea-b990-5d96-9935-85e58b4f216c | date | Date Completed:
839b1af8-7f2c-40da-9ae9-5c9ce671b92b | signoff | AUTHORITY HOLDPOINT
c7e43732-cc5e-4461-a79a-89d741ee0d57 | checkpoint | 4 - Earthwork reinstatement
c8cb109a-9a02-5d07-ac8d-134b542a7d4d | note | FREQUENCY: Each lot where 1 lot is 1 site
d3b3a854-e53e-5542-9c55-91b9368bc070 | note | ACCEPTANCE CRITERIA: Compliance with drawings. checks for line, length and level
b638e125-ee06-5eb7-8647-1b4ca3d3d131 | note | REFERENCE DOCUMENTS: Section 201
59457830-a407-56b7-95db-c3eece8dd0be | note | INSPECTION / TEST METHOD: Inspection
33794a4e-a923-5fc5-a166-6208082deb52 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
7f68fd04-196c-54eb-bd02-898a48223a33 | note | HP, WP
2ea6fa4c-eba8-50c4-a323-185432abd354 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
9ab5602f-efa7-528a-bf1d-de5c82bf42e7 | date | Date Completed:
f21868cc-3241-4842-913b-d3e2ac72bccf | signoff | AUTHORITY HOLDPOINT
8e334325-12a8-41a6-a189-e836f1c18bd0 | checkpoint | 5 - Practical Completion submission and acceptance
746e85c2-1f9c-50ef-b831-4636b6f4d097 | note | FREQUENCY: Each lot where 1 lot is 1 site
c0f50cc8-4234-592f-8e9b-0806266015bc | note | ACCEPTANCE CRITERIA: Project completion achieved in accordance with subcontract agreement.
df8783d9-b4de-5aa1-927e-a28758ad7d6d | note | REFERENCE DOCUMENTS: N/A
7338177b-1df9-5074-a74b-6e64366acd51 | note | INSPECTION / TEST METHOD: Inspection
ce9b3b16-f1c4-52f6-ae0a-1031cbaf7010 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
29fed374-e90f-5409-8906-e58ed3631f8a | note | HP, WP
ab25c10c-6b84-5765-a545-f884728211f1 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
c8be335d-2c9e-5798-80b7-6b60070253ff | date | Date Completed:
9d1e8a5b-8183-4025-b3c1-12275a9b3590 | signoff | AUTHORITY HOLDPOINT
ed794521-d298-425a-a77a-179eed0ab265 | checkpoint | Requirement to undertake Pile Integrity Testing
994a812f-2559-4adc-9d76-753b012edbae | checkpoint | Final Inspection
e48ca631-d6f8-5fb2-b710-2c8107c88ba9 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
00627329-6fd9-5a3d-baf1-00adcbe4a097 | textbox | Print Name:
5893bc27-234a-50fe-99b9-40771e471a80 | textbox | Position:
8cef173c-5c84-5013-b4d1-3a1dddf4d816 | date | Date:
887e6413-fe16-41a2-aba4-f60685ade924 | signoff | Sign ITP
b832ded7-1923-4a16-ba6f-761184a900ed | checklist | ITP No. 3 - Guardrail Installation | itp | ITP No. 3 - Guardrail Installation
824b1b18-3358-43ed-a633-8398cd0f3119 | section | Details
6fd1cf18-b472-4719-8a06-016c1917f5f8 | checkpoint | 1 - Setout
1c0adc80-f7f1-5abc-9def-1aa029c09918 | note | FREQUENCY: Prior to commencing any activity
2d16519b-1eeb-50f9-92cd-aed99b3ab00f | note | ACCEPTANCE CRITERIA: Chainage locations clearly identified for extent
74640689-ed2f-5aad-a020-7b58668c857e | note | REFERENCE DOCUMENTS: Design drawings Section 708
b2905f43-0053-5b6f-a727-4ef23e5a463a | note | INSPECTION / TEST METHOD: Inspection
85ddbf7c-73cc-58c1-83fc-7de2f2597764 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
5c763457-92e4-5e6d-ba9a-bf1ff09b34f5 | note | HP, AP
7ab1e8de-9c98-518a-92a9-c138d5c0c84e | note | RESPONSIBILITY: Project Manager, Clients Superintendent
89d47a7b-2a64-5017-b4e5-ac7c6b0dae74 | date | Date Completed:
16862089-07f9-45bd-89bf-836da7be3f6a | signoff | AUTHORITY HOLDPOINT
7d29dc54-79c1-4009-a4d2-e91b80cfda80 | checkpoint | 2 - Supply of materials
ad883418-1f28-56ae-9354-1c6c282db6f9 | note | FREQUENCY: Each delivery
16569a61-7449-5f0b-acf9-7a78b0875080 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
36f7cbad-1f6f-5016-aeac-09f6a66d82df | note | REFERENCE DOCUMENTS: Design drawings Section 708
3e66aa30-0d9c-5006-8c06-0ad815085450 | note | INSPECTION / TEST METHOD: Inspection, Certificate of materials
ef16625b-057d-5259-83ea-26e3cbd38739 | note | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
132f73f0-3f7f-59a7-a757-6b85d7908d3d | note | HP AP
5c980973-f8ca-5aca-ba97-51b014c0e029 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
bdc22abd-fd67-5c39-afc9-da2d454c771a | date | Date Completed:
9a9e4bb4-d68d-4bc2-8624-5e74fb2d258a | signoff | AUTHORITY HOLDPOINT
701dda6b-049c-4a8e-bdbc-a5e5bee6737b | checkpoint | 3 - Installation
e11e6b6f-92e9-5761-a5e7-ce28f4c9a8e9 | note | FREQUENCY: Each lot as required
ff78ae02-dbb5-50a0-b82b-17eccfd9d8e9 | note | ACCEPTANCE CRITERIA: The offset, height and post spacing is to conform with VicRoads specifications and the detailed design
d978bb43-3e35-5db8-ad54-5b0f2f941345 | note | REFERENCE DOCUMENTS: Design drawings Section 708
d15d4928-a218-5f5a-983b-99bf84a5ab04 | note | INSPECTION / TEST METHOD: Inspection
c3062974-c1c9-598b-825a-290fd33fa436 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
797f9361-6664-5aea-be16-3df430340317 | note | HP, AP
4b90c5c3-c7f5-514a-98fe-b9b2817be8f4 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8eeda902-70fa-5c5c-80eb-553f74a2f56e | date | Date Completed:
e62b0143-d7bc-46ee-86cf-f36cb3732b5e | signoff | AUTHORITY HOLDPOINT
9eaa4758-68af-4b56-8991-a6299ccf168e | checkpoint | 4 - End Treatments
0207bff1-43f1-5acd-887d-b7d316d8442e | note | FREQUENCY: Each lot as required
45c9732b-733c-571a-9843-f45dfb1d3ed3 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads specifications
2cc7317c-ffd5-52cb-aa94-084d6e51d052 | note | REFERENCE DOCUMENTS: Design drawings Section 708
83ba2ab4-db18-5ab2-8ec3-ca9aeba93eac | note | INSPECTION / TEST METHOD: Inspection
a0832483-9ae8-5119-8147-79b5844dcef5 | note | RECORD OF CONFORMITY: Qualified Welder Certification Reports
c32401ae-e81b-50fc-88b3-0ccd8d1a4e4e | note | IP, IP
9d50696c-3ce7-5910-a5b9-ef9e6ee50150 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
71db2813-96d3-5637-9b35-2b6c1accebe5 | date | Date Completed:
813b4352-c4e9-44c1-bb48-122dfd487fed | checkpoint | 5 - Motorcycle rub rail
de3e21ce-fa2f-57dd-b8f2-7ff271f61c7b | note | FREQUENCY: Each lot as required
b47e90da-b6be-5b92-ae2b-f13e7a62ca0c | note | ACCEPTANCE CRITERIA: Where specified, motorcycle rub rail is to be installed on the new length of guardrail
e3082cde-9ca8-586a-af29-29444d985f05 | note | REFERENCE DOCUMENTS: Design drawings Section 708
a79320c6-af1f-560e-880f-9447afb132b5 | note | INSPECTION / TEST METHOD: Inspection
4762d785-e27d-5761-973a-3377f2e4eb23 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
31663dd6-bf14-5a31-afa9-481363d8f027 | note | IP, IP
d887b7a1-f9cc-5c24-867a-1ba296a98176 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
b3e4a56e-69bb-57a3-b17a-02fc26aaf3b5 | date | Date Completed:
2b7530ad-f2c1-4cb0-b52f-b2ecac30960d | checkpoint | Final Inspection
88d6140f-d62c-581a-a4e5-112238177352 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
3b7bb401-83e3-5902-9d43-b99bd2c30c0c | textbox | Print Name:
758ee2a4-ca83-506f-947d-5227d7bfe9ae | textbox | Position:
319f045b-33e8-5ff9-8fb9-3506e8e9838f | date | Date:
2ab2f725-eed2-40f5-aff4-8fc9e09055cb | signoff | Sign ITP