## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Hydrant ITP | [5 empty] | Hydrant ITP (Specific Levels)
section | First Fix - Floor Hydrant
checkpoint | Pipework Fabrication
label | Delivery inspection
label | Fittings to Spec
label | Pipe and weld quality
label | Cut sheets and plans align with pipe delivered to site
checkpoint | Installation Inspection
label | Installed to approved drawing
label | Compliance with AS2419
checkpoint | Check Hydrant Landing Valves
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
checkpoint | Check Hose Reel
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
checkpoint | Isolation Valve installation
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
label | Valve numbering
checkpoint | Valves Set Installation
label | – Type and material
label | – Finish
label | – Make and model no.
label | – Capacity/output
label | – Joints and connections
label | – Supports
label | – Position
label | – Accessories
label | – Controls and electrical services
label | – Signage, Labeling, Locks and Straps
checkpoint | Compliance Check
label | 100mm around valve Handle
label | Hydrant on 45 degree
label | Couplin Bolts not impeding operation
checkpoint | Council Inspection Rough In
section | Second Fix - Zone Pressure Test at top of zone
checkpoint | Pipework Fabrication
label | Delivery inspection
label | Fittings to Spec
label | Pipe and weld quality
label | Cut sheets and plans align with pipe delivered to site
checkpoint | Hydraulic Pressure Test AS2419
label | Hydrostatic pressure testing of 1700KPA for a 2 hour period as required in AS2419,S10.2.2. Oniste testing installation @ 1700KPA
label | Add photos
holdpoint | SIGN OFF
section | Third Fix - Final Sign Off
checkpoint | Signage, Locks and Straps
checkpoint | Asset register and Test Tag NO.
checkpoint | Block Plan Installation
checkpoint | Commissioning
checkpoint | As Built Complete
checklist | Hydrant ITP | [5 empty] | Hydrant ITP
section | First Fix - Floor Hydrant
checkpoint | Pipework Fabrication
label | Delivery inspection
label | Fittings to Spec
label | Pipe and weld quality
label | Cut sheets and plans align with pipe delivered to site
checkpoint | Installation Inspection
label | Installed to approved drawing
label | Compliance with AS2419
checkpoint | Check Hydrant Landing Valves
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
checkpoint | Check Hose Reel
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
checkpoint | Isolation Valve installation
label | – Type and material
label | – Joints and connections
label | – Position and spacing / obstruction
label | – Fixing and supports in accordance with AS2419
label | Note number of units per floor attach photo
label | Valve numbering
checkpoint | Valves Set Installation
label | – Type and material
label | – Finish
label | – Make and model no.
label | – Capacity/output
label | – Joints and connections
label | – Supports
label | – Position
label | – Accessories
label | – Controls and electrical services
label | – Signage, Labeling, Locks and Straps
checkpoint | Compliance Check
label | 100mm around valve Handle
label | Hydrant on 45 degree
label | Couplin Bolts not impeding operation
checkpoint | Council Inspection Rough In
section | Second Fix - Final Sign Off
checkpoint | Signage, Locks and Straps
checkpoint | Asset register and Test Tag NO.
checkpoint | Block Plan Installation
checkpoint | Commissioning
checkpoint | As Built Complete