## Sheet1
5.01.01 | Subgrade CBR Testing | DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level. | NZS 4402:1986 - 6.5.2 | DCP Report | min 2 tests per lot | R | PE | CBR=5 OK CBR>3 excavate 200mm and place geogrid CBRCHAR(LESS)3 notify Eng or as directed by Eng | 5.01.01 - Subgrade CBR Testing | Acceptance / Conformance Criteria - DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level. | Standard / Specification - NZS 4402:1986 - 6.5.2 | Verifying Document - DCP Report | Frequency - min 2 tests per lot | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - CBR=5 OK CBR>3 excavate 200mm and place geogrid CBRCHAR(LESS)3 notify Eng or as directed by Eng | 7.01.01 - Construction Record Compilation
5.01.02 | Subgrade Compaction CHAR(AMP) Trimming | Neatly trim and compact subgrade with appropriate equipment | TNZ F/01: 1997 11.0 | DCP Report | min 2 tests per lot | HP | ENG | Or as directed by Eng | 5.01.02 - Subgrade Compaction CHAR(AMP) Trimming | Acceptance / Conformance Criteria - Neatly trim and compact subgrade with appropriate equipment | Standard / Specification - TNZ F/01: 1997 11.0 | Verifying Document - DCP Report | Frequency - min 2 tests per lot | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - Or as directed by Eng | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
6.01.01 | Material Placement | The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. | I | SV / PE |  | 6.01.01 - Material Placement | Acceptance / Conformance Criteria - The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout | Standard / Specification - TNZ B/02: 2005 - 5.1 | Verifying Document - Survey / Level Checks | Frequency - Continuous monitoring. | Verification Activity: Activity - I | Verification Activity: By - SV / PE | Comments / Closeout Details - | Standard / Specification - Downer
6.01.02 | Sub-basecourse Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG | Or as directed by Eng | 6.01.02 - Sub-basecourse Pavement Layer Compaction | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92 | Standard / Specification - TNZ B/02: 2005 - 7.6 | Verifying Document - NDM Report | Frequency - Min 2 Tests per lot | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - Or as directed by Eng | Verifying Document - Records
6.01.03 | Sub-basecourse Layer thickness. | The Sub-basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE |  | 6.01.03 - Sub-basecourse Layer thickness. | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitured for Layer thickness. | Standard / Specification - TNZ B/02: 2005 - 7.5 | Verifying Document - Survey / Level Checks | Frequency - Continuous monitoring. | Verification Activity: Activity - W | Verification Activity: By - SV / PE | Comments / Closeout Details - | Frequency - Post construction
6.01.04 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95 | TNZ B/02: 2005 - 7.6 | NDM Report | Min 2 Tests per lot | HP | ENG | Or as directed by Eng | 6.01.04 - Basecourse Pavement Layer Compaction | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95 | Standard / Specification - TNZ B/02: 2005 - 7.6 | Verifying Document - NDM Report | Frequency - Min 2 Tests per lot | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - Or as directed by Eng | Verification Activity: Activity - R
6.01.05 | Basecourse Layer thickness. | The Basecourse shall be monitured for Layer thickness. | TNZ B/02: 2005 - 7.5 | Survey / Level Checks | Continuous monitoring. | W | SV / PE |  | 6.01.05 - Basecourse Layer thickness. | Acceptance / Conformance Criteria - The Basecourse shall be monitured for Layer thickness. | Standard / Specification - TNZ B/02: 2005 - 7.5 | Verifying Document - Survey / Level Checks | Frequency - Continuous monitoring. | Verification Activity: Activity - W | Verification Activity: By - SV / PE | Comments / Closeout Details - | Verification Activity: By - SE
6.01.06 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing | I | SV / PE |  | 6.01.06 - Surface Shape | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | Standard / Specification - TNZ B/02: 2005 - 7.7 | Verifying Document - Survey / Straight edge Report | Frequency - Prior to sealing | Verification Activity: Activity - I | Verification Activity: By - SV / PE | Comments / Closeout Details - | Comments / Closeout Details -
6.01.07 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing | I | SV / PE |  | 6.01.07 - Holding Water | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | Standard / Specification - TNZ B/02: 2005 - 7.7 | Verifying Document - Survey | Frequency - Prior to sealing | Verification Activity: Activity - I | Verification Activity: By - SV / PE | Comments / Closeout Details - | 7.01.02 - Survey Records
6.01.08 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | TNZ B/02: 2005 - 7.8 | Photos | Prior to sealing | R | PE |  | 6.01.08 - Surface Finish post sweeping | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | Standard / Specification - TNZ B/02: 2005 - 7.8 | Verifying Document - Photos | Frequency - Prior to sealing | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
6.01.09 | Pre-surfacing Requirements | Surface to be dry and clean | QPR2000 Manufacturer's Requirements | Photos | Prior to sealing | R | PE |  | 6.01.09 - Pre-surfacing Requirements | Acceptance / Conformance Criteria - Surface to be dry and clean | Standard / Specification - QPR2000 Manufacturer's Requirements | Verifying Document - Photos | Frequency - Prior to sealing | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - | Standard / Specification - Downer
6.01.10 | Surfacing | Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment | QPR2000 Manufacturer's Requirements | Photos | Post Sealing | R | PE |  | 6.01.10 - Surfacing | Acceptance / Conformance Criteria - Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment | Standard / Specification - QPR2000 Manufacturer's Requirements | Verifying Document - Photos | Frequency - Post Sealing | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - | Verifying Document - Records
Frequency - Post construction
4.01.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | TNZ M/4: 2024 - 4 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG |  | 4.01.01 - Source Property Tests and Sampling | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | Standard / Specification - TNZ M/4: 2024 - 4 NZS 4407 : 1991 NZS 4402 : 1986 | Verifying Document - IANZ Lab Reports | Frequency - 10,000m3 | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - | Verification Activity: Activity - R
4.1.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | TNZ M/4: 2024 - 5 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG |  | 4.1.02 - Production Property Test Sampling | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | Standard / Specification - TNZ M/4: 2024 - 5 NZS 4407 : 1991 | Verifying Document - IANZ Lab Reports | Frequency - | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - | Verification Activity: By - SV
4.01 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE | 5000m3 is typically used where source is consistent | 4.01 - Testing for Layer Compaction - MDD | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | Verifying Document - IANZ Lab Reports | Frequency - 5,000m2 | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - 5000m3 is typically used where source is consistent | Comments / Closeout Details -
4.02.01 | Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | 10,000m3 | HP | ENG | M/3 is a guide not a specification. Refer to Contract Specification | 4.02.01 - Source Property Tests and Sampling | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | Standard / Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 NZS 4402 : 1986 | Verifying Document - IANZ Lab Reports | Frequency - 10,000m3 | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification | 7.01.03 - Redline Drawings
4.02.02 | Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 | IANZ Lab Reports |  | HP | ENG | M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy | 4.02.02 - Production Property Test Sampling | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | Standard / Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2024 NZS 4407 : 1991 | Verifying Document - IANZ Lab Reports | Frequency - | Verification Activity: Activity - HP | Verification Activity: By - ENG | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
4.02.03 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 | R | PE | 5000m3 is typically used where source is consistent | 4.02.03 - Testing for Layer Compaction - MDD | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | Verifying Document - IANZ Lab Reports | Frequency - 5,000m2 | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - 5000m3 is typically used where source is consistent | Standard / Specification - Downer
Verifying Document - Redlines
7.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | R | SE |  | 7.01.01 - Construction Record Compilation | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Standard / Specification - Downer | Verifying Document - Records | Frequency - Post construction | Verification Activity: Activity - R | Verification Activity: By - SE | Comments / Closeout Details - | Frequency - Post construction
7.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | R | SV |  | 7.01.02 - Survey Records | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting | Standard / Specification - Downer | Verifying Document - Records | Frequency - Post construction | Verification Activity: Activity - R | Verification Activity: By - SV | Comments / Closeout Details - | Verification Activity: Activity - R
7.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | R | PE |  | 7.01.03 - Redline Drawings | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Standard / Specification - Downer | Verifying Document - Redlines | Frequency - Post construction | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - | Verification Activity: By - PE
7.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | R | PE |  | 7.01.04 - Defect, Snag and Punch List | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register | Standard / Specification - Downer | Verifying Document - Register | Frequency - Post construction | Verification Activity: Activity - R | Verification Activity: By - PE | Comments / Closeout Details - | Comments / Closeout Details -
7.01.04 - Defect, Snag and Punch List
Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
Standard / Specification - Downer
Verifying Document - Register
Frequency - Post construction
Verification Activity: Activity - R
Verification Activity: By - PE
Comments / Closeout Details -