## AC-14
Inspection Test Plan - ITP Action Plan
Project |  | B1001F - Devil's Elbow Culvert |  |  | CPS Approver | Signature | Project Manager | Tony King
ITP Name |  | Asphalt - Surfacing |  |  |  |  | Project Engineer | Arvinder Singh
ITP Document No |  | B1001-02-608-00000-CO-IT-TREC-0F0003 |  |  |  | Name & Date | Site Engineer | Jamie Anderson
CWP Document No |  | B1001-02-608-00000-CO-WP-TREC-0F0001 |  |  | Quality Approver | Signature | Quality Engineer | Subash KC
Status |  | Approved |  | 2024-07-24 |  |  | CPS Engineer | Greg Bailey
Revision | [5 empty] | J Addis 24/7/24 | CPS Manager | Dave Hooker
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Conformance Criteria | Inspection / Test Method (submission, visual inspection, testing, measure, review) | Records | Construction Assignee | CPS Assignee | Date(s)
1 | Pre-Construction
1.1 | Survey Setout - Milling | WITNESS | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report | Prior to commencement | Mark out on site, confirmed by CPS Engineer | Visual inspection, Survey | Survey, Photos, COR | Site Engineer
1.2 | Milling Existing AC | MONITOR | Milling undertaken to correct depth of nominal thickness | During operation | Design Report, depth of milling confirmed by CPS | Visual Inspection | COR | Site Engineer
2 | Material Compliance
2.1 | Binder Penetration Grade | WITNESS | To comply with NZTA M01: 2020 - Table 6.1 | Prior to commencement | Property Test | NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements | Lab Report | Site Engineer
2.2 | Coarse Aggregate Source | WITNESS | To comply with NZTA M10 - Refer to Section 2 | Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates. | Table 2.1 in NZTA M10 | Property Test | IANZ Report | Site Engineer
2.3 | Fine Aggregate Sources | WITNESS | To comply with NZTA M10 - Refer to Section 2 | Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates. | Table 2.2 in NZTA M10 | Property Test | IANZ Report | Site Engineer
2.4 | Quality Plan | WITNESS | Includes the following : Mix Design Sampling and Testing Manufacturing and Storage Placement Paving Plan Random Sampling Locations | 10 days minimum prior to paving | Testing | Refer to Section 8 of NZTA M10 | Mix design | Site Engineer | CPS Engineer
3 | Asphalt - Surfacing
3.1 | Survey Setout - Paving | WITNESS | Determine paving run start/stop locations | Prior to commencement | Survey, Visual Inspection | Ensure accurate survey setting out is in place. | Subconctractor QA | Site Engineer | CPS Engineer
3.2 | Weather Check | WITNESS | Ensure weather conditions are acceptable for work to proceed | Prior to commencement | Weather Forecast | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C | Subcontractor QA | Site Engineer
3.3 | Surface Preparation | WITNESS | Ensure previous layer is broomed clean. | Prior to commencement | Truck broom to have been used and surface approved by CPS Engineer | Visual inspection | Photos | Site Engineer | CPS Engineer
3.4 | Membrane seal | WITNESS | Application as per Design Requirements (Chip size / binder application rate) | Prior to asphalt Spray sheet for everyday. | Spray sheet, QA records | Application as per Design Requirements (Chip size / binder application rate) | Spray sheet, QA records | Site Engineer
3.5 | Temperature of Asphalt for paving | WITNESS | The tempreature of the asphalt shall enable compaction required to achieve air voids %.. | 1 test per 20m of a | Temperature Check | The asphalt shall have a minimum tempreature of 80 degrees celcius on completion of compaction. | Subcontractor QA | Site Engineer
3.6 | Thickness (Cores) | HOLD | Layer thickness measured from core samples. | Each core taken for density | Core Test | ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications | Lab test report | Site Engineer | CPS Engineer
3.7 | Compaction and airvoids | HOLD | To comply with NZTA M10: or project specification | AS per specification | NDM for Quality Control Only | NZTA M/10:Section 9.9.3 | IANZ Report, QA Records | Site Engineer | CPS Engineer
3.8 | Surface Finish and Roughness | HOLD | No vissible cracks, defects related to poorly constructed joints, water ponding, | Post Construction Site walkover. | Visual inspection. | No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality. | COR | Site Engineer | CPS Engineer
4 | Post-Construction Closeout | [6 empty] | Construction Assignee(s) | Construction Assignee(s) | CPS Assignee
4.1 | Final Walkover (Snags) | HOLD | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Completed report | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Snag List signed by attendees | Quality Manager
4.2 | Survey As-builts | HOLD | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | All RFI, NCRs and site changes must be recorded. Signed and dated | Drawings Survey as-built | As-built Drawings. Redline Markups | Site Engineer
4.3 | Quality Assurance Deliverables | WITNESS | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Ensure all QA is uploaded into ConQA / Procore | Document Review | As-builts, NCR's and RFI's | Quality Manager
4.4 | Final Approvals | HOLD | Signoffs by Project Manager, Quality Manager and CPS Manager | At the completion of the CWP | Ensure all parties have signed and approved ITP | Document Review | Signatures | Project Manager | Quality Manager | CPS Manager
Note on D3: e.g. B1004A - White Pines Bush North

## Drop Down Lists
ACTION | Construction Assignee | CPS Assignee
HOLD | Site Engineer | CPS Engineer
WITNESS | Project Engineer | Geotechnical Engineer
MONITOR | Project Manager | Specialist
| Sub-Contractor | Designer
| Third-Party | Third-Party