## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1001F - Devil's Elbow Culvert - A/C | itp |  |  |  |  | ITP - B1001F - Devil's Elbow Culvert - A/C
section | 1 - Pre-Construction
checkpoint | CPS Approver
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
checkpoint | Quality Approver
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Survey Setout - Milling
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | Frequency - Prior to commencement
label | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection, Survey
label | Records - Survey, Photos, COR
checkpoint | 1.2 - Milling Existing AC
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Milling undertaken to correct depth of nominal thickness
label | Frequency - During operation
label | Conformance Criteria - Design Report, depth of milling confirmed by CPS
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Records - COR
section | 2 - Material Compliance
checkpoint | 2.1 - Binder Penetration Grade
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M01: 2020 - Table 6.1
label | Frequency - Prior to commencement
label | Conformance Criteria - Property Test
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Records - Lab Report
checkpoint | 2.2 - Coarse Aggregate Source
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M10 - Refer to Section 2
label | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
label | Conformance Criteria - Table 2.1 in NZTA M10
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Property Test
label | Records - IANZ Report
checkpoint | 2.3 - Fine Aggregate Sources
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M10 - Refer to Section 2
label | Frequency - Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates.
label | Conformance Criteria - Table 2.2 in NZTA M10
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Property Test
label | Records - IANZ Report
checkpoint | 2.4 - Quality Plan
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Includes the following:
label | ○ Mix Design
label | ○ Sampling and Testing
label | ○ Manufacturing and Storage
label | ○ Placement
label | ○ Paving Plan
label | ○ Random Sampling Locations
label | Frequency - 10 days minimum prior to paving
label | Conformance Criteria - Testing
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Refer to Section 8 of NZTA M10
label | Records - Mix design
section | 3 - Asphalt - Surfacing
checkpoint | 3.1 - Survey Setout - Paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Conformance Criteria - Survey, Visual Inspection
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Ensure accurate survey setting out is in place.
label | Records - Subconctractor QA
checkpoint | 3.2 - Weather Check
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure weather conditions are acceptable for work to proceed
label | Frequency - Prior to commencement
label | Conformance Criteria - Weather Forecast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C
label | Records - Subcontractor QA
checkpoint | 3.3 - Surface Preparation
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure previous layer is broomed clean.
label | Frequency - Prior to commencement
label | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection
label | Records - Photos
checkpoint | 3.4 - Membrane seal
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Application as per Design Requirements (Chip size / binder application rate)
label | Frequency - Prior to asphalt Spray sheet for everyday.
label | Conformance Criteria - Spray sheet, QA records
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Application as per Design Requirements (Chip size / binder application rate)
label | Records - Spray sheet, QA records
checkpoint | 3.5 - Temperature of Asphalt for paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - The tempreature of the asphalt shall enable compaction required to achieve air voids %.
label | Frequency - 1 test per 20m of a
label | Conformance Criteria - Temperature Check
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - The asphalt shall have a minimum tempreature of 80 degrees celcius on completion of compaction.
label | Records - Subcontractor QA
checkpoint | 3.6 - Thickness (Cores)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Layer thickness measured from core samples.
label | Frequency - Each core taken for density
label | Conformance Criteria - Core Test
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Records - Lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Compaction and airvoids
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - To comply with NZTA M10: or project specification
label | Frequency - AS per specification
label | Conformance Criteria - NDM for Quality Control Only
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - NZTA M/10:Section 9.9.3
label | Records - IANZ Report, QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Surface Finish and Roughness
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - No vissible cracks, defects related to poorly constructed joints, water ponding,
label | Frequency - Post Construction Site walkover.
label | Conformance Criteria - Visual inspection.
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality.
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Conformance Criteria - Completed report
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT