## Guardrail & Wire Rope
Inspection Test Plan - ITP Action Plan
Project |  | B11010A - Te Ngarue Culvert |  |  | CPS Approver | Signature | Project Manager | Eben van Niekerk
ITP Name |  | Retrofit Guardrail |  |  |  |  | Project Engineer | Maurice Talbot
ITP Document No |  | B1101-02-626-00000-CO-IT-TREC-0A0005 |  |  |  | Name & Date | Site Engineer | Craig Lindsey
CWP Document No |  | B1101-02-626-00000-CO-WP-TREC-0A0001 |  |  | Quality Approver | #VALUE! | Quality Engineer | Eddy Mardle
Status |  | Approved |  | 2024-08-15 |  |  | CPS Engineer | Greg Bailey
Revision |  | B - Replacing previous version approved 26 Oct |  | 2024-08-15 |  | J Addis 15/08/24 | CPS Manager | David Hooker
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Conformance Criteria | Inspection / Test Method (submission, visual inspection, testing, measure, review) | Records | Construction Assignee | CPS Assignee | Date(s)
1 | Setout & Checks
1.1 | Design Check | M | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | National Standard for Traffic Signal | Document review | COR, Photos | Site Engineer
1.2 | Safety Barrier | W | Contractor to mark out location of safety barrier to be reinstated. | Prior to commencement | Visual inspection by CPS to agree with the set out. | Survey | COR, Photos | Site Engineer | CPS Engineer
2 | Material Compliance
2.1 | Barrier Compliance | H | All roadside barriers shall comply with TNZ M/23 for NCHRP Report 350 Test Level 4 | Prior to commencement | TNZ M/23 | Visual inspection/ Document review | Manufacturing certificates and delivery dockets | Site Engineer | CPS Engineer
3 | Guardrail Installation
3.1 | W-Beam Guardrail Installation | M | W-Beam Guardrail on ductile steel shall be reinstated in accordance to Installation Manual and Specifications. | During installation and on completion | TNZ M/23 | Visual inspection, measurement | Installation Checklist | Site Engineer
3.2 | Leading & Trailing End Terminal Installation | W | Leading & Trailing End Terminal shall be reinstated in accordance to Installation Manual and Specifications | During installation and on completion | TNZ M/23 | Visual inspection, measurement | Installation Checklist | Site Engineer
3.3 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person. System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM | Post-construction, ideally before TTM removed | Pass inspection RSHDS 4 | Visual inspection: Kurt Samson | Confirmation from inspector | Site Engineer | CPS Engineer
4 | Post-Construction Closeout | [6 empty] | Construction Assignee(s) | Construction Assignee(s) | CPS Assignee
4.1 | Final Walkover (Snags) | HOLD | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Completed report | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Snag List signed by attendees | Quality Manager
4.2 | Survey As-builts | HOLD | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | All RFI, NCRs and site changes must be recorded. Signed and dated | Drawings Survey as-built | As-built Drawings. Redline Markups | Site Engineer
4.3 | Quality Assurance Deliverables | WITNESS | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Ensure all QA is uploaded into ConQA / Procore | Document Review | As-builts, NCR's and RFI's | Quality Manager
4.4 | Final Approvals | HOLD | Signoffs by Project Manager, Quality Manager and CPS Manager | At the completion of the CWP | Ensure all parties have signed and approved ITP | Document Review | Signatures | Project Manager | Quality Manager | CPS Manager
Note on D3: e.g. B1004A - White Pines Bush North
Note on D4: e.g. Basecourse, Retaining wall etc
Note on K10: CPS Engineer must always be assigned to Hold Points