## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1101A - Te Ngarue - Guardrail | itp |  |  |  |  | ITP - B1101A - Te Ngarue - Guardrail
section | 1 - Setout & Checks
checkpoint | CPS Approver
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
checkpoint | Quality Approver
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Design Check
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Conformance Criteria - National Standard for Traffic Signal
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document review
label | Records - COR, Photos
checkpoint | 1.2 - Safety Barrier
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Contractor to mark out location of safety barrier to be reinstated.
label | Frequency - Prior to commencement
label | Conformance Criteria - Visual inspection by CPS to agree with the set out.
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Survey
label | Records - COR, Photos
section | 2 - Material Compliance
checkpoint | 2.1 - Barrier Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection/ Document review
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Guardrail Installation
checkpoint | 3.1 - W-Beam Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - W-Beam Guardrail on ductile steel shall be reinstated in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection, measurement
label | Records - Installation Checklist
checkpoint | 3.2 - Leading & Trailing End Terminal Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be reinstated in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection, measurement
label | Records - Installation Checklist
checkpoint | 3.3 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person.
label | ○ System checklists to be completed and co signed by contractor and CPS.
label | ○ All faults to be rectified before acceptance into network maintenance and RAMM
label | Frequency - Post-construction, ideally before TTM removed
label | Conformance Criteria - Pass inspection RSHDS 4
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual inspection: Kurt Samson
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Conformance Criteria - Completed report
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT