## Digout
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
By (Role Key)
1 | Service Locates |  | Services located by Chorus and Delta prior to works commencing. | Photos | Once for each work location | Hold Point | Alliance
2 | AP40 Material Quality | Record M4 Test Document | Confirm material meets M4 Spec | Photos | Once for each work location | Verification | Alliance
3 | Scala Penetrometer | Scala on fault to determine digout depth |  | Photos, Field testing document | One set of tests for each patch | Hold Point | Alliance
4 | Digout | Digout complete to required depth. Stability of subgrade assessed | No soft spots, uneven areas or potential issues affecting roads foundations | Visual, Photo |  | Verification | Alliance
5 | AP65 Backfill | Clegg testing to be done on backfill | Clegg Impact Value to be greater than 25 | Photos, Field testing document | Every 150mm lift, Minimum 1 per 20m2 | Hold Point | Alliance
6 | AP40 Backfill | Clegg testing to be done on backfill | Clegg Impact Value to be greater than 35 | Photos, Field testing document | Every 150mm lift, Minimum 1 per 20m2 | Hold Point | Alliance
7 | Ready for sealing |  |  | Photo |  | Verification | Alliance

## Stabi
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
By (Role Key)
1 | Cement | Cement added and raked evenly | 1 Bag per 10 m2, raked evenly | Visual, photo | Once per patch | Verification | Alliance
2 | Emulsion Mill | Litres of Emulsion used per m2 | Aim 8L per m2 | Add comment of Litres used | Once per patch | Verification | Alliance
3 | Pavement Stength | Clegg testing to be done | Clegg Impact Value to be greater than 35 | Photos, Field testing document | Minimum 1 per 20m2 | Hold Point | Alliance
4 | Ready for Sealing |  |  | Photo |  | Verification | Alliance