## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Sealed Pavement Maintenance - Digouts all depths | itp |  |  |  |  | Sealed Pavement Maintenance - Digouts all depths
section | Details
checkpoint | 1 - Service Locates
label | Acceptance Criteria - Services located by Chorus and Delta prior to works commencing.
label | Verifying Document - Photos
label | Frequency - Once for each work location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - AP40 Material Quality
label | Inspection Point: Quality Control Activity - Record M4 Test Document
label | Acceptance Criteria - Confirm material meets M4 Spec
label | Verifying Document - Photos
label | Frequency - Once for each work location
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance
checkpoint | 3 - Scala Penetrometer
label | Inspection Point: Quality Control Activity - Scala on fault to determine digout depth
label | Verifying Document - Photos, Field testing document
label | Frequency - One set of tests for each patch
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Digout
label | Inspection Point: Quality Control Activity - Digout complete to required depth. Stability of subgrade assessed
label | Acceptance Criteria - No soft spots, uneven areas or potential issues affecting roads foundations
label | Verifying Document - Visual, Photo
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance
checkpoint | 5 - AP65 Backfill
label | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | Acceptance Criteria - Clegg Impact Value to be greater than 25
label | Verifying Document - Photos, Field testing document
label | Frequency - Every 150mm lift, Minimum 1 per 20m2
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - AP40 Backfill
label | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | Verifying Document - Photos, Field testing document
label | Frequency - Every 150mm lift, Minimum 1 per 20m2
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Ready for sealing
label | Verifying Document - Photo
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance
checklist | Sealed Pavement Maintenance - Stabilise (emulsion) | itp |  |  |  |  | Sealed Pavement Maintenance - Stabilise (emulsion)
section | Details
checkpoint | 1 - Cement
label | Inspection Point: Quality Control Activity - Cement added and raked evenly
label | Acceptance Criteria - 1 Bag per 10 m2, raked evenly
label | Verifying Document - Visual, photo
label | Frequency - Once per patch
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance
checkpoint | 2 - Emulsion Mill
label | Inspection Point: Quality Control Activity - Litres of Emulsion used per m2
label | Acceptance Criteria - Aim 8L per m2
label | Verifying Document - Add comment of Litres used
label | Frequency - Once per patch
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance
checkpoint | 3 - Pavement Stength
label | Inspection Point: Quality Control Activity - Clegg testing to be done
label | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | Verifying Document - Photos, Field testing document
label | Frequency - Minimum 1 per 20m2
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By - Alliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Ready for Sealing
label | Verifying Document - Photo
label | Inspection Type (Visual, other) - Verification
label | Inspection: By - Alliance