## ITP - 112
MSE Wall Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0112 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 12 – CONSTRUCTION ACTIVITY – MSE WALL
12.01 | MSE Wall Foundation
12.01.01 | Compaction Acceptance | NDM test results provided to Engineer, min compaction 95% Surface is flat and even | PS 15.5.2 | Compaction Results, Photos | Prior to starting MSE Wall | HP | ENG - AOS
12.02 | Cirtex Induction
12.02.01 | Onsite Induction | Induction completed with all construction crew regarding constructing the MSE Wall | PS 15.5.2 | Photos | Prior to starting MSE Wall | HP | Cirtex
12.03 | Structural Fill
12.03.01 | Structural Fill Plateau Testing | The Contractor shall undertake 'plateau' trial compaction tests to confirm the methodology of constructing the fill. This should be carried out according to TNZ F/1: 1997. The plateau density tests shall be undertaken on 20m test strips with the compaction plant that will be used on site. | PS 15.5.4 PS 15.5.5 | Site Notes | Three tests per stockpile per piece of Compaction Plant | HP | ENG - WSP
12.03.02 | Structural Fill Installation | Compacted Layer thicknesses for MSE Wall shall be limited to no greater than 150mm. | PS 15.5.4 PS 15.5.6 | Photos | Every lift | V | SE
12.03.03 | Compaction Acceptance | The Contractor shall supply copies of test results, certificates, etc. to the Engineer to confirm that materials or works comply with the specified requirements. 5 NDM tests per lift, min 95% | PS 15.5.4 PS 15.5.7 | Comopaction results | 5 tests per lift | HP | ENG - AOS
12.03.04 | Final Slope | Final layer to be graded back away from the southwall for drainage | PS 15.5.4 PS 15.5.8 | Photos | At completion of the MSE wall | HP | ENG - AOS
12.04 | Duramesh Panels
12.04.01 | Duramesh Panels | Panels set at 1:10 with 5 long and 5 short braces at equal spacing Duramesh panels connected together in the horizontal direction not the vertical | PS 15.5.2 | Photos | During Construction | V | SE
12.04.02 | Geofabric and Geogrid installation | Geofabric and Geogrid right against the panel face with both right in the corner of the panel Geogrid cut in non-structural direction to get around bracing | PS 15.5.2 | Photos | During Construction | V | SE
12.04.03 | Compaction Acceptance | Light compaction (Vibrating plate/roller with a mass per m less than 1300kg and a total mass of less than 1000kg) within 1.2m of the panel face | PS 15.5.3 | Photos | During Construction | H | SE
12.05 | Geogrid
12.05.01 | Geogrid layer | Photos/measurements of overlaps, min 300mm Grid tight with no sagging/bulging | PS 15.5.5 | Photos/measurements | During Construction | V | SE
12.05.02 | Grid Tail | 2m tail for the first 2.4m, increases to 4m after 2.4m high Tail burried into structural fill, 100mm cover | PS 15.5.6 | Photos/measurements | During Construction | V | SE