## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0112-MSE-Wall-Earthworks | itp |  |  |  | Yes | DS2676-DOW-ITP-CV-0112-MSE-Wall-Earthworks Rev 0
section | 12.01 MSE Wall Foundation
checkpoint | 12.01.01 - Compaction Acceptance
label | Acceptance / Conformance Criteria - NDM test results provided to Engineer, min compaction 95%
label | ○ Surface is flat and even
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Compaction Results, Photos
label | Frequency - Prior to starting MSE Wall
label | Activity - HP
label | By - ENG - AOS
holdpoint | AUTHORITY HOLDPOINT
section | 12.02 Cirtex Induction
checkpoint | 12.02.01 - Onsite Induction
label | Acceptance / Conformance Criteria - Induction completed with all construction crew regarding constructing the MSE Wall
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Photos
label | Frequency - Prior to starting MSE Wall
label | Activity - HP
label | By - Cirtex
holdpoint | AUTHORITY HOLDPOINT
section | 12.03 Structural Fill
checkpoint | 12.03.01 - Structural Fill Plateau Testing
label | Acceptance / Conformance Criteria - The Contractor shall undertake 'plateau' trial compaction tests to confirm the methodology of constructing the fill. This should be carried out according to TNZ F/1: 1997. The plateau density tests shall be undertaken on 20m test strips with the compaction plant that will be used on site.
label | Standard / Specification - PS 15.5.4, PS 15.5.5
label | Verifying Document - Site Notes
label | Frequency - Three tests per stockpile per piece of Compaction Plant
label | Activity - HP
label | By - ENG - WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.03.02 - Structural Fill Installation
label | Acceptance / Conformance Criteria - Compacted Layer thicknesses for MSE Wall shall be limited to no greater than 150mm.
label | Standard / Specification - PS 15.5.4, PS 15.5.6
label | Verifying Document - Photos
label | Frequency - Every lift
label | Activity - V
label | By - SE
checkpoint | 12.03.03 - Compaction Acceptance
label | Acceptance / Conformance Criteria - The Contractor shall supply copies of test results, certificates, etc. to the Engineer to confirm that materials or works comply with the specified requirements. 5 NDM tests per lift, min 95%
label | Standard / Specification - PS 15.5.4, PS 15.5.7
label | Verifying Document - Comopaction results
label | Frequency - 5 tests per lift
label | Activity - HP
label | By - ENG - AOS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12.03.04 - Final Slope
label | Acceptance / Conformance Criteria - Final layer to be graded back away from the southwall for drainage
label | Standard / Specification - PS 15.5.4 PS 15.5.8
label | Verifying Document - Photos
label | Frequency - At completion of the MSE wall
label | Activity - HP
label | By - ENG - AOS
holdpoint | AUTHORITY HOLDPOINT
section | 12.04 Duramesh Panels
checkpoint | 12.04.01 - Duramesh Panels
label | Acceptance / Conformance Criteria - Panels set at 1:10 with 5 long and 5 short braces at equal spacing
label | ○ Duramesh panels connected together in the horizontal direction not the vertical
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Photos
label | Frequency - During Construction
label | Activity - V
label | By - SE
checkpoint | 12.04.02 - Geofabric and Geogrid installation
label | Acceptance / Conformance Criteria - Geofabric and Geogrid right against the panel face with both right in the corner of the panel
label | ○ Geogrid cut in non-structural direction to get around bracing
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Photos
label | Frequency - During Construction
label | Activity - V
label | By - SE
checkpoint | 12.04.03 - Compaction Acceptance
label | Acceptance / Conformance Criteria - Light compaction (Vibrating plate/roller with a mass per m less than 1300kg and a total mass of less than 1000kg) within 1.2m of the panel face
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Photos
label | Frequency - During Construction
label | Activity - H
label | By - SE
section | 12.05 Geogrid
checkpoint | 12.05.01 - Geogrid layer
label | Acceptance / Conformance Criteria - Photos/measurements of overlaps, min 300mm
label | ○ Grid tight with no sagging/bulging
label | Standard / Specification - PS 15.5.5
label | Verifying Document - Photos/measurements
label | Frequency - During Construction
label | Activity - V
label | By - SE
checkpoint | 12.05.02 - Grid Tail
label | Acceptance / Conformance Criteria - 2m tail for the first 2.4m, increases to 4m after 2.4m high
label | ○ Tail burried into structural fill, 100mm cover
label | Standard / Specification - PS 15.5.6
label | Verifying Document - Photos/measurements
label | Frequency - During Construction
label | Activity - V
label | By - SE